## Project_Work_Order6385864530533
Project Work Order
From 01 Jul 2020 To 08 Aug 2024
Page 1 of 1
Total Records: 8152 Records 1 To 8152
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
EAST POINT MARKET | 1 | 1 | 09 Nov 2021 | SAHARA ENGINEERING | KEP- Openable Window reshuffle for Sinages | Lumpsum work- DCW | No. | 0 | 7500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 24 Nov 2021 |  | DEV. Compound Wall | Cancelled | Avinash Padmanabha | 27 Nov 2021
EAST POINT MARKET | 1 | 1 | 09 Nov 2021 | SAHARA ENGINEERING | KEP- Openable Window reshuffle for Sinages | Lumpsum work- DCW | No. | 6 | 7500 | 45000 | 8100 | 53100 | 2.5 | 6 | 45000 | 8100 | 53100 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 24 Nov 2021 |  | DEV. Compound Wall | Approved | skmishra
EAST POINT MARKET | 1 | 2 | 09 Nov 2021 | SAHARA ENGINEERING | KEP- Openable Window reshuffle for Sinages | Lumpsum work- DCW | No. | 6 | 7500 | 45000 | 8100 | 53100 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 1 | 0 | 09 Nov 2021 | SAHARA ENGINEERING | ACP Work-1st,3rd,4th,5th Fl-Water Leakage Prevention | ACP Work (M+L) | Sq.Ft | 256 | 45 | 11520 | 2073.6 | 13593.6 | 2.5 | 256 | 11520 | 2073.6 | 13593.6 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 1 | 0 | 09 Nov 2021 | SAHARA ENGINEERING | ACP Work-1st,3rd,4th,5th Fl-Water Leakage Prevention | ACP Work (M+L) | Sq.Ft | 1696 | 215 | 364640 | 65635.2 | 430275.2 | 2.5 | 1696 | 364640 | 65635.2 | 430275.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 1 | 0 | 09 Nov 2021 | SAHARA ENGINEERING | ACP Work-1st,3rd,4th,5th Fl-Water Leakage Prevention | ACP Work (M+L) | Sq.Ft | 632 | 140 | 88480 | 15926.4 | 104406.4 | 2.5 | 632 | 88480 | 15926.4 | 104406.4 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 1 | 1 | 09 Nov 2021 | SAHARA ENGINEERING | KEP-Team for Removing of Ext Glass | Glass removing -Mkt | Sq.Ft | 2000 | 35 | 70000 | 12600 | 82600 | 2.5 | 1856 | 64960 | 11692.8 | 76652.8 | 144 | 5947.2 |  | 92.8 |  | Avinash Padmanabha | skmishra | construction open | 24 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | skmishra
EAST POINT MARKET | 1 | 2 | 09 Nov 2021 | SAHARA ENGINEERING | External Facade Glass Changing - 1 No. | Glass removing -Mkt | Sq.Ft | 288 | 35 | 10080 | 1814.4 | 11894.4 | 0 | 288 | 10080 | 1814.4 | 11894.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 1 | 1 | 09 Nov 2021 | SAHARA ENGINEERING | KEP- ACP Fixing where Glass Removing | ACP Work (M+L) | Sq.Ft | 2000 | 250 | 500000 | 90000 | 590000 | 2.5 | 1904 | 476000 | 85680 | 561680 | 96 | 28320 |  | 95.2 |  | Avinash Padmanabha | skmishra | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 2 | 0 | 09 Nov 2021 | SAHARA ENGINEERING | Scaffolding Work for ODU Platform | Scaffolding Work (M+L) | Sq.Ft | 900 | 22 | 19800 | 3564 | 23364 | 2.5 | 900 | 19800 | 3564 | 23364 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 3 | 1 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | 5th Fl OHWT Waterproffing | PU Injection grouting treatment | No. | 5 | 360 | 1800 | 324 | 2124 | 10 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 3 | 1 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | 5th Fl OHWT Waterproffing | Waterproofing wok (L)-BC | Sq.Ft | 1400 | 27 | 37800 | 6804 | 44604 | 10 | 0 | 0 | 0 | 0 | 1400 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 3 | 1 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | 5th Fl OHWT Waterproffing | Breaking Of Plaster- BRE | Sq.Ft | 1400 | 27 | 37800 | 6804 | 44604 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 3 | 1 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | 5th Fl OHWT Waterproffing | Chemical Coating- DPo | Sq.Ft | 1700 | 9 | 15300 | 2754 | 18054 | 10 | 0 | 0 | 0 | 0 | 1700 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | DEV. Podium | Approved | Swapnil Erande
EAST POINT MARKET | 3 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | Basement Fl -Retaining Wall WP Work | Rough Shahabad W/P | Sq.Ft | 5004.01 | 45 | 225180.45 | 40532.48 | 265712.93 | 2.5 | 4208.5186 | 189383.34 | 34089 | 223472.34 | 795.4914 | 42240.59 |  | 84.1029 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 4 | 0 | 09 Nov 2021 | MD JAFAR IMAM | Basement Fl Retaining Wall-RCC Breaking Work | Lumpsum work- DCW | No. | 1 | 200000 | 200000 | 0 | 200000 | 2.5 | 1 | 200000 | 0 | 200000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | DEV. Compound Wall | Approved | skmishra
EAST POINT MARKET | 4 | 1 | 09 Nov 2021 | MD JAFAR IMAM | KEP-Basement Fl Core Cutting in Basement Retaining Wall | Core Cutting - BCo | No. | 31 | 1100 | 34100 | 0 | 34100 | 2.5 | 29 | 31900 | 0 | 31900 | 2 | 2200 |  | 93.5484 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Shut off Nozzle (M+L) | No. | 4 | 220 | 880 | 158.4 | 1038.4 | 2.5 | 4 | 880 | 158.4 | 1038.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Starter (M+L) | No. | 2 | 2700 | 5400 | 972 | 6372 | 2.5 | 2 | 5400 | 972 | 6372 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Electrical Cabling (L) | Mtrs | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 2 Core 1.5Sq.mm Cable(M+L) | Mtrs | 60 | 120 | 7200 | 1296 | 8496 | 2.5 | 60 | 7200 | 1296 | 8496 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Smoke Detector (M+L) | No. | 5 | 2592 | 12960 | 2332.8 | 15292.8 | 2.5 | 5 | 12960 | 2332.8 | 15292.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Starter (M+L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 150NB Butterfly Valve (M+L) | No. | 2 | 9000 | 18000 | 3240 | 21240 | 2.5 | 2 | 18000 | 3240 | 21240 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Butterfly Valve 100mm (M+L) | No. | 1 | 7000 | 7000 | 1260 | 8260 | 2.5 | 1 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 25mm Ball Valve (M+L) | No. | 50 | 600 | 30000 | 5400 | 35400 | 2.5 | 50 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Pendent Sprinkler (M+L) | No. | 150 | 320 | 48000 | 8640 | 56640 | 2.5 | 150 | 48000 | 8640 | 56640 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Ball Valve 20mm (M+L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Hose Reel Set (M+L) | set | 48 | 6000 | 288000 | 51840 | 339840 | 2.5 | 48 | 288000 | 51840 | 339840 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 3 Core 4sq.mm Cable(M+L) | Mtrs | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Pressure Switch (M+L) | No. | 2 | 3000 | 6000 | 1080 | 7080 | 2.5 | 2 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Electrical Cabling (L) | Mtrs | 114 | 50 | 5700 | 1026 | 6726 | 2.5 | 114 | 5700 | 1026 | 6726 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Fire Hose Cabinet (M+L)- No. | No. | 28 | 2400 | 67200 | 12096 | 79296 | 2.5 | 28 | 67200 | 12096 | 79296 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Ball Valve 20mm (M+L) | No. | 0 | 600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Sprinkler Redcer (M+L) - No. - No. | No. | 40 | 150 | 6000 | 1080 | 7080 | 2.5 | 40 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Sprinkler Redcer (M+L) - No. - No. | No. | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Butterfly Valve 80mm (M+L) | No. | 0 | 8000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | SS Single Hydrant Outlet (M+L) | No. | 52 | 4500 | 234000 | 42120 | 276120 | 2.5 | 52 | 234000 | 42120 | 276120 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Pendent Sprinkler (M+L) | No. | 0 | 320 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Smoke Detector (M+L) | No. | 0 | 2880 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | No category | Cancelled | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 2 Core 1.5Sq.mm Cable(M+L) | Mtrs | 0 | 130 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Manual Call Point (M+L) | No. | 0 | 2200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Butterfly Valve 100mm (M+L) | No. | 0 | 9000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT GORE | 20 Mar 2023
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 25mm Ball Valve (M+L) | No. | 4 | 600 | 2400 | 432 | 2832 | 2.5 | 4 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Pendent Sprinkler (M+L) | No. | 122 | 280 | 34160 | 6148.8 | 40308.8 | 2.5 | 121.9999 | 34159.97 | 6148.8 | 40308.77 | 0.0001 | 0.03 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Hose Clip with Gasket (M+L) | No. | 4 | 450 | 1800 | 324 | 2124 | 2.5 | 4 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Pressure Switch (M+L) | No. | 2 | 3000 | 6000 | 1080 | 7080 | 2.5 | 2 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Manual Call Point (M+L) | No. | 52 | 2000 | 104000 | 18720 | 122720 | 2.5 | 52 | 104000 | 18720 | 122720 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | S.S. Branch Pipe (M+L) | No. | 28 | 1672 | 46816 | 8426.88 | 55242.88 | 2.5 | 28 | 46816 | 8426.88 | 55242.88 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Main Pump Servicing (M+L) | No. | 4 | 10000 | 40000 | 7200 | 47200 | 2.5 | 4 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Alarm System Servcing (M+L) | set | 4 | 40000 | 160000 | 28800 | 188800 | 2.5 | 4 | 160000 | 28800 | 188800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Shut off Nozzle (M+L) | No. | 48 | 220 | 10560 | 1900.8 | 12460.8 | 2.5 | 48 | 10560 | 1900.8 | 12460.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Butterfly Valve 80mm (M+L) | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Hose Clip with Gasket (M+L) | No. | 48 | 450 | 21600 | 3888 | 25488 | 2.5 | 48 | 21600 | 3888 | 25488 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Canvas Hose Pipe (M+L) | No. | 28 | 5000 | 140000 | 25200 | 165200 | 2.5 | 28 | 140000 | 25200 | 165200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 1 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | 3 Core 4sq.mm Cable(M+L) | Mtrs | 70 | 160 | 11200 | 2016 | 13216 | 2.5 | 70 | 11200 | 2016 | 13216 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Pressure Gauge (M+L) | set | 13 | 1250 | 16250 | 2925 | 19175 | 2.5 | 13 | 16250 | 2925 | 19175 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Main Panel Servicing (M+L) | No. | 1 | 15000 | 15000 | 2700 | 17700 | 2.5 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | ABC Type Fire Extinguisher 4 kg (M+L) | No. | 8 | 1500 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Booster Pump Servicing (L) | No. | 4 | 3000 | 12000 | 2160 | 14160 | 2.5 | 4 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 5 | 0 | 09 Nov 2021 | KAMAL FIRE FIGHTING SYSTEM | SRA Bldg Fire Fighting Maintenance Work | Servicing of Starter (M+L) | No. | 4 | 625 | 2500 | 450 | 2950 | 2.5 | 4 | 2500 | 450 | 2950 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 31 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA CHOUGULE | 27 Sep 2022
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 89.45 | 1.25 | 111.81 | 0 | 111.81 | 2.5 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (Light Grey) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1160.61 | 1.25 | 1450.76 | 0 | 1450.76 | 2.5 | 0 | 0 | 0 | 0 | 1160.61 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 250.03 | 1.25 | 312.54 | 0 | 312.54 | 2.5 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 165.34 | 1.25 | 206.68 | 0 | 206.68 | 2.5 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 206.02 | 1.25 | 257.53 | 0 | 257.53 | 2.5 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (Light Grey) | Scrapping with 2nd Coat Putty | Sq.Ft | 1160.61 | 1.25 | 1450.76 | 0 | 1450.76 | 2.5 | 0 | 0 | 0 | 0 | 1160.61 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | Scrapping with 1st Coat Putty | Sq.Ft | 250.03 | 1.25 | 312.54 | 0 | 312.54 | 2.5 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | 1 Coat Primer (Water Base) (L) | Sq.Ft | 46.59 | 1.25 | 58.24 | 0 | 58.24 | 2.5 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 206.02 | 1.25 | 257.53 | 0 | 257.53 | 2.5 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 46.59 | 1.25 | 58.24 | 0 | 58.24 | 2.5 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ceiling&Beam Premium Emulsion (L) (White) | Scrapping with 1st Coat Putty | Sq.Ft | 31345.85 | 1.25 | 39182.31 | 0 | 39182.31 | 2.5 | 0 | 0 | 0 | 0 | 31345.85 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Retaining Wall Acrylic Paint Exterior Paint(L)-( | 1st Coat Acrylic Paint (L) | Sq.Ft | 4943 | 1.25 | 6178.75 | 0 | 6178.75 | 2.5 | 0 | 0 | 0 | 0 | 4943 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Retaining Wall Acrylic Paint Exterior Paint(L)-( | 1 Coat Primer (External) (L) - | Sq.Ft | 4943 | 1.25 | 6178.75 | 0 | 6178.75 | 2.5 | 0 | 0 | 0 | 0 | 4943 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (Light Grey) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1160.61 | 1.25 | 1450.76 | 0 | 1450.76 | 2.5 | 0 | 0 | 0 | 0 | 1160.61 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (Light Grey) | Scrapping with 1st Coat Putty | Sq.Ft | 1160.61 | 1.25 | 1450.76 | 0 | 1450.76 | 2.5 | 0 | 0 | 0 | 0 | 1160.61 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Premium Emulsion (L) (White) | Scrapping with 2nd Coat Putty | Sq.Ft | 2353.58 | 1.25 | 2941.98 | 0 | 2941.98 | 2.5 | 0 | 0 | 0 | 0 | 2353.58 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 61.31 | 1.25 | 76.64 | 0 | 76.64 | 2.5 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 206.02 | 1.25 | 257.53 | 0 | 257.53 | 2.5 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ceiling&Beam Premium Emulsion (L) (White) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 31345.85 | 1.25 | 39182.31 | 0 | 39182.31 | 2.5 | 31345.85 | 39182.31 | 0 | 39182.31 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | Scrapping with 1st Coat Putty | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | Scrapping with 2nd Coat Putty | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | Scrapping with 1st Coat Putty | Sq.Ft | 165.34 | 1.25 | 206.68 | 0 | 206.68 | 2.5 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | Scrapping with 1st Coat Putty | Sq.Ft | 206.02 | 1.25 | 257.53 | 0 | 257.53 | 2.5 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (White) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1212.37 | 1.25 | 1515.46 | 0 | 1515.46 | 2.5 | 0 | 0 | 0 | 0 | 1212.37 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Premium Emulsion (L) (White) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 2353.58 | 1.25 | 2941.98 | 0 | 2941.98 | 2.5 | 0 | 0 | 0 | 0 | 2353.58 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | 2nd Coat Satin Matt Paint (L) | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | Scrapping with 2nd Coat Putty | Sq.Ft | 61.31 | 1.25 | 76.64 | 0 | 76.64 | 2.5 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | Scrapping with 2nd Coat Putty | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Premium Emulsion (L) (White) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 2353.58 | 1.25 | 2941.98 | 0 | 2941.98 | 2.5 | 0 | 0 | 0 | 0 | 2353.58 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | Scrapping with 1st Coat Putty | Sq.Ft | 46.59 | 1.25 | 58.24 | 0 | 58.24 | 2.5 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 165.34 | 1.25 | 206.68 | 0 | 206.68 | 2.5 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Acrylic Paint Exterior Paint(L) | 1st Coat Acrylic Paint (L) | Sq.Ft | 1283.54 | 1.25 | 1604.43 | 0 | 1604.43 | 2.5 | 0 | 0 | 0 | 0 | 1283.54 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Acrylic Paint Exterior Paint(L) | 1 Coat Primer (External) (L) - | Sq.Ft | 1283.54 | 1.25 | 1604.43 | 0 | 1604.43 | 2.5 | 0 | 0 | 0 | 0 | 1283.54 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | 1st Coat Satin Matt Paint (L) | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Satin Matt Paint Base Grey (L) | 2nd Coat Satin Matt Paint (L) | Sq.Ft | 1396.79 | 1.25 | 1745.99 | 0 | 1745.99 | 2.5 | 0 | 0 | 0 | 0 | 1396.79 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | Scrapping with 2nd Coat Putty | Sq.Ft | 89.45 | 1.25 | 111.81 | 0 | 111.81 | 2.5 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (White) | Scrapping with 1st Coat Putty | Sq.Ft | 1212.37 | 1.25 | 1515.46 | 0 | 1515.46 | 2.5 | 0 | 0 | 0 | 0 | 1212.37 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | Scrapping with 1st Coat Putty | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Satin Matt Paint Base Grey (L) | 1st Coat Satin Matt Paint (L) | Sq.Ft | 1396.79 | 1.25 | 1745.99 | 0 | 1745.99 | 2.5 | 0 | 0 | 0 | 0 | 1396.79 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Retaining Wall Acrylic Paint Exterior Paint(L)-( | 2nd Coat Acrylic Paint (L) | Sq.Ft | 4943 | 1.25 | 6178.75 | 0 | 6178.75 | 2.5 | 0 | 0 | 0 | 0 | 4943 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ceiling&Beam Premium Emulsion (L) (White) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 31345.85 | 1.25 | 39182.31 | 0 | 39182.31 | 2.5 | 0 | 0 | 0 | 0 | 31345.85 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | Oil Base Primer (L) | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | 2nd Coat Satin Matt Paint (L) | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 250.03 | 1.25 | 312.54 | 0 | 312.54 | 2.5 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (Light Grey) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1160.61 | 1.25 | 1450.76 | 0 | 1450.76 | 2.5 | 0 | 0 | 0 | 0 | 1160.61 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 89.45 | 1.25 | 111.81 | 0 | 111.81 | 2.5 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Acrylic Paint Exterior Paint(L) | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1283.54 | 1.25 | 1604.43 | 0 | 1604.43 | 2.5 | 0 | 0 | 0 | 0 | 1283.54 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 165.34 | 1.25 | 206.68 | 0 | 206.68 | 2.5 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | Scrapping with 2nd Coat Putty | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | Scrapping with 1st Coat Putty | Sq.Ft | 61.31 | 1.25 | 76.64 | 0 | 76.64 | 2.5 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (White) | Scrapping with 2nd Coat Putty | Sq.Ft | 1212.37 | 1.25 | 1515.46 | 0 | 1515.46 | 2.5 | 0 | 0 | 0 | 0 | 1212.37 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (White) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1212.37 | 1.25 | 1515.46 | 0 | 1515.46 | 2.5 | 0 | 0 | 0 | 0 | 1212.37 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Satin Matt Paint Base Grey (L) | Scrapping with 2nd Coat Putty | Sq.Ft | 1396.79 | 1.25 | 1745.99 | 0 | 1745.99 | 2.5 | 0 | 0 | 0 | 0 | 1396.79 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | Scrapping with 2nd Coat Putty | Sq.Ft | 165.34 | 1.25 | 206.68 | 0 | 206.68 | 2.5 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | Scrapping with 2nd Coat Putty | Sq.Ft | 206.02 | 1.25 | 257.53 | 0 | 257.53 | 2.5 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ceiling&Beam Premium Emulsion (L) (White) | Scrapping with 2nd Coat Putty | Sq.Ft | 31345.85 | 1.25 | 39182.31 | 0 | 39182.31 | 2.5 | 0 | 0 | 0 | 0 | 31345.85 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Premium Emulsion (L) (White) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 2353.58 | 1.25 | 2941.98 | 0 | 2941.98 | 2.5 | 0 | 0 | 0 | 0 | 2353.58 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 61.31 | 1.25 | 76.64 | 0 | 76.64 | 2.5 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 46.59 | 1.25 | 58.24 | 0 | 58.24 | 2.5 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ceiling&Beam Premium Emulsion (L) (White) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 31345.85 | 1.25 | 39182.31 | 0 | 39182.31 | 2.5 | 0 | 0 | 0 | 0 | 31345.85 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | 1st Coat Satin Matt Paint (L) | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | Scrapping with 1st Coat Putty | Sq.Ft | 89.45 | 1.25 | 111.81 | 0 | 111.81 | 2.5 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | Oil Base Primer (L) | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 250.03 | 1.25 | 312.54 | 0 | 312.54 | 2.5 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | Scrapping with 1st Coat Putty | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | Scrapping with 2nd Coat Putty | Sq.Ft | 250.03 | 1.25 | 312.54 | 0 | 312.54 | 2.5 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (L) (White) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1212.37 | 1.25 | 1515.46 | 0 | 1515.46 | 2.5 | 0 | 0 | 0 | 0 | 1212.37 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | Scrapping with 1st Coat Putty | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 89.45 | 1.25 | 111.81 | 0 | 111.81 | 2.5 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 43.49 | 1.25 | 54.36 | 0 | 54.36 | 2.5 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Satin Matt Paint Base Grey (L) | Scrapping with 1st Coat Putty | Sq.Ft | 1396.79 | 1.25 | 1745.99 | 0 | 1745.99 | 2.5 | 0 | 0 | 0 | 0 | 1396.79 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 61.31 | 1.25 | 76.64 | 0 | 76.64 | 2.5 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Premium Emulsion (L) (White) | Scrapping with 1st Coat Putty | Sq.Ft | 2353.58 | 1.25 | 2941.98 | 0 | 2941.98 | 2.5 | 0 | 0 | 0 | 0 | 2353.58 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Satin Matt Paint Base Grey (L) | Oil base Primer-BC | Sq.Ft | 1396.79 | 1.25 | 1745.99 | 0 | 1745.99 | 2.5 | 0 | 0 | 0 | 0 | 1396.79 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | Scrapping with 2nd Coat Putty | Sq.Ft | 46.59 | 1.25 | 58.24 | 0 | 58.24 | 2.5 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 6 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | Scrapping with 2nd Coat Putty | Sq.Ft | 388.95 | 1.25 | 486.19 | 0 | 486.19 | 2.5 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 7 | 0 | 09 Nov 2021 | JOHNSON LIFTS PRIVATE LIMITED | Society Lift Maintenance(Lift Tray Maintenance) | Lift Repair & Maintenance | No. | 1 | 14695 | 14695 | 2645.1 | 17340.1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 7 | 1 | 09 Nov 2021 | JOHNSON LIFTS PRIVATE LIMITED | Society Lift Maintenance(Lift Tray Maintenance) | Lift Repair & Maintenance | No. | 1 | 995762.71 | 995762.71 | 179237.28 | 1174999.99 | 0 | 0.3 | 298728.81 | 53771.18 | 352499.99 | 0.7 | 822500 |  | 30 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 8 | 1 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-2nd Floor Passage & Shops area Base Coat waterproofing | Base Coat -cc | Sq.Ft | 17849 | 20 | 356980 | 64256.4 | 421236.4 | 10 | 8131.6474 | 162632.95 | 29273.94 | 191906.89 | 9717.3526 | 229329.51 |  | 45.558 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Community Hall&Refuse Area Floor Base Coat Waterproo | Base Coat -cc | Sq.Ft | 3413.8 | 20 | 68276 | 12289.68 | 80565.68 | 10 | 3033.4347 | 60668.69 | 10920.36 | 71589.05 | 380.3653 | 8976.63 |  | 88.858 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Fl Community Hall&Refuse Area Chemical Waterproofing | Chemical W/P (L+M) | Sq.Ft | 1315.43 | 22 | 28939.46 | 5209.1 | 34148.56 | 10 | 372.97 | 8205.34 | 689.2 | 8894.54 | 942.46 | 25254.02 |  | 28.3535 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-3rd Floor Passage&Shop area Base Coat Waterproofing | Base Coat -cc | Sq.Ft | 18025.48 | 20 | 360509.6 | 64891.72 | 425401.32 | 10 | 18024.2206 | 360484.41 | 64887.2 | 425371.61 | 1.2594 | 29.71 | 3rd Floor: Base Coat: Cement & Sand provided by GGG. (1:4 Single Coat ) rate 20 rupees/sqft. Chemical in the scope of Contractor. | 99.993 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Fl Community Hall&Refuse Area Chemical Waterproofing | Chemical W/P (L+M) | Sq.Ft | 3413.8 | 22 | 75103.6 | 13518.64 | 88622.24 | 10 | 3413.8 | 75103.6 | 13518.64 | 88622.24 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Community Hall&Refuse Area Floor Base Coat Waterproo | Base Coat -cc | Sq.Ft | 2023.73 | 20 | 40474.6 | 7285.42 | 47760.02 | 10 | 2023.73 | 40474.6 | 7285.42 | 47760.02 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 1 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-2nd Floor Passage & Shops area Chemical coat waterproofi | Chemical Waterproofing-cc | Sq.Ft | 17849 | 20 | 356980 | 64256.4 | 421236.4 | 10 | 8131.6474 | 162632.95 | 29273.94 | 191906.89 | 9717.3526 | 229329.51 |  | 45.558 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Community Hall&Refuse Area Floor Base Coat Waterproo | Base Coat -cc | Sq.Ft | 1057.99 | 20 | 21159.8 | 3808.76 | 24968.56 | 10 | 1057.99 | 21159.8 | 3808.76 | 24968.56 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Fl Community Hall&Refuse Area Chemical Waterproofing | Chemical W/P (L+M) | Sq.Ft | 1057.99 | 22 | 23275.78 | 4189.64 | 27465.42 | 10 | 0 | 0 | 0 | 0 | 1057.99 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 8 | 0 | 09 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-3rd Floor Passage&Shop area Chemical Waterproofing-(Sq.F | Chemical W/P (L+M) | Sq.Ft | 16366.09 | 22 | 360053.98 | 64809.72 | 424863.7 | 10 | 16353.9444 | 359786.78 | 53493.46 | 413280.24 | 12.1456 | 11583.46 | Chemical Waterproofing with Testing Certificate. Area 100% (-) work done passage work. Rate without Cement, Water. Chemical two coat. Chemical in the scope of Contractor. | 99.9258 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | 1st Coat Satin Matt Paint (M) | Sq.Ft | 388.95 | 2 | 777.9 | 0 | 777.9 | 0 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 250.03 | 2 | 500.06 | 0 | 500.06 | 0 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 43.49 | 2 | 86.98 | 0 | 86.98 | 0 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | 1st Coat Satin Matt Paint (M) | Sq.Ft | 388.95 | 2 | 777.9 | 0 | 777.9 | 0 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 165.34 | 2 | 330.68 | 0 | 330.68 | 0 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 206.02 | 2 | 412.04 | 0 | 412.04 | 0 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | 2nd Coat Satin Matt Paint (M) | Sq.Ft | 388.95 | 2 | 777.9 | 0 | 777.9 | 0 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 43.49 | 2 | 86.98 | 0 | 86.98 | 0 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | 1 Coat Primer (Water Base) (M) | Sq.Ft | 46.59 | 2 | 93.18 | 0 | 93.18 | 0 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 250.03 | 2 | 500.06 | 0 | 500.06 | 0 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 206.02 | 2 | 412.04 | 0 | 412.04 | 0 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 89.45 | 2 | 178.9 | 0 | 178.9 | 0 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 165.34 | 2 | 330.68 | 0 | 330.68 | 0 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Orange) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 43.49 | 2 | 86.98 | 0 | 86.98 | 0 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | 2nd Coat Satin Matt Paint (M) | Sq.Ft | 388.95 | 2 | 777.9 | 0 | 777.9 | 0 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Light Blue) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 206.02 | 2 | 412.04 | 0 | 412.04 | 0 | 0 | 0 | 0 | 0 | 206.02 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Yellow ) (M+L) | Oil Base Primer (M) | Sq.Ft | 388.95 | 2 | 777.9 | 0 | 777.9 | 0 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 61.31 | 2 | 122.62 | 0 | 122.62 | 0 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 46.59 | 2 | 93.18 | 0 | 93.18 | 0 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Yellow) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 250.03 | 2 | 500.06 | 0 | 500.06 | 0 | 0 | 0 | 0 | 0 | 250.03 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 43.49 | 2 | 86.98 | 0 | 86.98 | 0 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 89.45 | 2 | 178.9 | 0 | 178.9 | 0 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Ramp Wall Satin Matt Paint (Dark Grey)(M+L) | Oil Base Primer (M) | Sq.Ft | 388.95 | 2 | 777.9 | 0 | 777.9 | 0 | 0 | 0 | 0 | 0 | 388.95 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Pink) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 89.45 | 2 | 178.9 | 0 | 178.9 | 0 | 0 | 0 | 0 | 0 | 89.45 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Purple) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 165.34 | 2 | 330.68 | 0 | 330.68 | 0 | 0 | 0 | 0 | 0 | 165.34 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 43.49 | 2 | 86.98 | 0 | 86.98 | 0 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | 1st Coat Premium Emulsion Paint (M) | Sq.Ft | 61.31 | 2 | 122.62 | 0 | 122.62 | 0 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Blue) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 61.31 | 2 | 122.62 | 0 | 122.62 | 0 | 0 | 0 | 0 | 0 | 61.31 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Green) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 43.49 | 2 | 86.98 | 0 | 86.98 | 0 | 0 | 0 | 0 | 0 | 43.49 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 9 | 0 | 09 Nov 2021 | AZAM KHAN | Basement Fl Column Premium Emulsion (M+L)(Red) - 46.59 Sq | 2nd Coat Premium Emulsion Paint (M) | Sq.Ft | 46.59 | 2 | 93.18 | 0 | 93.18 | 0 | 0 | 0 | 0 | 0 | 46.59 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Watchman Cabin Top Slab/Shade - 1 No. | Wastage & Profite Cont. - USL | No. | 1 | 7000 | 7000 | 0 | 7000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Society Sign Board | Wastage & Profite Cont. - USL | No. | 1 | 8000 | 8000 | 0 | 8000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Top Terrace Door | Wastage & Profite Cont. - USL | No. | 4 | 3000 | 12000 | 0 | 12000 | 2.5 | 4 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Terrace Duct Top Jali In Plastic - 1 No. | Jali fixing | Sq.Ft | 530 | 30 | 15900 | 0 | 15900 | 2.5 | 0 | 0 | 0 | 0 | 530 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab MS Work(A | Wastage & Profite Cont. - USL | No. | 16 | 3000 | 48000 | 0 | 48000 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Chamber Cover | Wastage & Profite Cont. - USL | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab(A1) | Wastage & Profite Cont. - USL | No. | 16 | 3000 | 48000 | 0 | 48000 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Man Hole Cover(D1) - 1 No. | Wastage & Profite Cont. - USL | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | UGWT MS Staircase | Wastage & Profite Cont. - USL | No. | 4 | 1500 | 6000 | 0 | 6000 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 10 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Manhole Cover | Wastage & Profite Cont. - USL | No. | 2 | 2000 | 4000 | 0 | 4000 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Society Sign Board | Base Plate (M+L) | No. | 3 | 200 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Manhole Cover | Fabrication work (M) | Kgs | 41.4 | 55 | 2277 | 0 | 2277 | 0 | 0 | 0 | 0 | 0 | 41.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Society Sign Board | Fabrication work (M) | Kgs | 64 | 75 | 4800 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 64 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab(A1) | Fabrication work (M) | Kgs | 842.4 | 60 | 50544 | 0 | 50544 | 0 | 0 | 0 | 0 | 0 | 842.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Watchman Cabin Top Slab/Shade - 1 No. | Fabrication work (M) | Kgs | 130.8 | 55 | 7194 | 0 | 7194 | 0 | 0 | 0 | 0 | 0 | 130.8 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab MS Work(A | Fabrication work (M) | Kgs | 1152 | 55 | 63360 | 0 | 63360 | 0 | 0 | 0 | 0 | 0 | 1152 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Manhole Cover | Fabrication work (M) | Kgs | 93.62 | 60 | 5617.2 | 0 | 5617.2 | 0 | 0 | 0 | 0 | 0 | 93.62 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab(A1) | Fastner (M) - SOSB | No. | 256 | 16 | 4096 | 0 | 4096 | 0 | 0 | 0 | 0 | 0 | 256 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab MS Work(A | Fabrication work (M) | Kgs | 936 | 60 | 56160 | 0 | 56160 | 0 | 0 | 0 | 0 | 0 | 936 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab(A1) | Fabrication work (M) | Kgs | 1056 | 55 | 58080 | 0 | 58080 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Man Hole Cover(D1) - 1 No. | Fabrication work (M) | Kgs | 19.5 | 60 | 1170 | 0 | 1170 | 0 | 0 | 0 | 0 | 0 | 19.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Man Hole Cover(D1) - 1 No. | Fabrication work (M) | Kgs | 12.6 | 55 | 693 | 0 | 693 | 0 | 0 | 0 | 0 | 0 | 12.6 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Chamber Cover | Fabrication work (M) | Kgs | 13.5 | 55 | 742.5 | 0 | 742.5 | 0 | 0 | 0 | 0 | 0 | 13.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Chamber Cover | Fabrication work (M) | Kgs | 6.75 | 55 | 371.25 | 0 | 371.25 | 0 | 0 | 0 | 0 | 0 | 6.75 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Chamber Cover | Fabrication work (M) | Kgs | 48.75 | 60 | 2925 | 0 | 2925 | 0 | 24.375 | 1462.5 | 0 | 1462.5 | 24.375 | 1462.5 |  | 50 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Society Sign Board | Fabrication work (M) | Kgs | 224 | 65 | 14560 | 0 | 14560 | 0 | 0 | 0 | 0 | 0 | 224 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab MS Work(A | Base Plate (M+L) | No. | 64 | 200 | 12800 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 64 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Society Sign Board | Anchor Fastener (M) | No. | 12 | 25 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Top Terrace Door | Fabrication work (M) | Kgs | 104 | 75 | 7800 | 0 | 7800 | 0 | 104 | 7800 | 0 | 7800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Chamber Cover | Fabrication work (M) | Kgs | 21 | 55 | 1155 | 0 | 1155 | 0 | 21 | 1155 | 0 | 1155 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Manhole Cover | Fabrication work (M) | Kgs | 39.2 | 55 | 2156 | 0 | 2156 | 0 | 0 | 0 | 0 | 0 | 39.2 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Top Terrace Door | Fabrication work (M) | Kgs | 117.6 | 55 | 6468 | 0 | 6468 | 0 | 117.6 | 6468 | 0 | 6468 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Watchman Cabin Top Slab/Shade - 1 No. | Base Plate (M+L) | No. | 6 | 200 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab(A1) | Base Plate (M+L) | No. | 64 | 200 | 12800 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 64 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | SRA Electric Duct Service Slab MS Work(A | Fastner (M) - SOSB | No. | 256 | 16 | 4096 | 0 | 4096 | 0 | 0 | 0 | 0 | 0 | 256 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Watchman Cabin Top Slab/Shade - 1 No. | Rough Shahabad W/P | Sq.Ft | 40 | 50 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Society Sign Board | Fabrication work (M) | Kgs | 44 | 65 | 2860 | 0 | 2860 | 0 | 0 | 0 | 0 | 0 | 44 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | UGWT MS Staircase | Fabrication work (M) | Kgs | 282.84 | 65 | 18384.6 | 0 | 18384.6 | 0 | 0 | 0 | 0 | 0 | 282.84 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Top Terrace Door | Aldrop SOS | No. | 8 | 170 | 1360 | 0 | 1360 | 0 | 8 | 1360 | 0 | 1360 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Top Terrace Door | Hinges- SOS | No. | 12 | 50 | 600 | 0 | 600 | 0 | 12 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Top Terrace Door | Fabrication work (M) | Kgs | 126 | 55 | 6930 | 0 | 6930 | 0 | 126 | 6930 | 0 | 6930 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 11 | 0 | 09 Nov 2021 | ABDUL SATTAR SHAIKH | Man Hole Cover(D1) - 1 No. | Fabrication work (M) | Kgs | 11.7 | 55 | 643.5 | 0 | 643.5 | 0 | 0 | 0 | 0 | 0 | 11.7 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 2 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor refuge wall Single coat sand faced plaster | Sand Face Plaster | Sq.Ft | 2406.399 | 20 | 48127.98 | 0 | 48127.98 | 2.5 | 1080.7138 | 21614.28 | 0 | 21614.28 | 1325.6852 | 26513.7 |  | 44.91 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of Cement | Bags | 65 | 10 | 650 | 0 | 650 | 0 | 65 | 650 | 0 | 650 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | SRA-12th Floor WP Top Breaking&Debris Shifting | Debris Removing & Shifting Work | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Front Panel Shifting +Cleaning Front area | Lumpsum work- DCW | No. | 1 | 800 | 800 | 0 | 800 | 2.5 | 1 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Subhsagar Side Railway Side Chember Raised | PCC Work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | 02 RCC WORK | Cancelled | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Railway Side 4th Fl Refuse Old PCC Breaking | Lumpsum work- DCW | No. | 1 | 6500 | 6500 | 0 | 6500 | 2.5 | 1 | 6500 | 0 | 6500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Steps Work in front of KFC Shops Ent Plaza | Brick Pillar- Dld | R.Ft | 21 | 100 | 2100 | 0 | 2100 | 2.5 | 21 | 2100 | 0 | 2100 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of Cement | Bags | 65 | 10 | 650 | 0 | 650 | 0 | 65 | 650 | 0 | 650 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 2 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Panel Shifting - UTI | No. | 110 | 160 | 17600 | 0 | 17600 | 0 | 110 | 17600 | 0 | 17600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Steps Work in front of KFC Shops Ent Plaza | Brick Pillar- Dld | R.Ft | 21 | 60 | 1260 | 0 | 1260 | 2.5 | 21 | 1260 | 0 | 1260 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ent Plaza Chamber Excavation &Drain Line Excavation | Chamber Rate Diff. - UTR | No. | 2 | 3500 | 7000 | 0 | 7000 | 2.5 | 2 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | UTI. Rainwater harvesting | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- New Chamber Excavation in plaza - 1 No. | Debris Removing & Shifting Work | No. | 5 | 1300 | 6500 | 0 | 6500 | 2.5 | 5 | 6500 | 0 | 6500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Breaking the beam plaster for ODU Platform Work | Department Labour - Day | Day | 10 | 1300 | 13000 | 0 | 13000 | 0 | 10 | 13000 | 0 | 13000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Subhsagar Side Railway Side Chember Raised | Breaking Of Tile - Mkt | Sq.Ft | 100 | 15 | 1500 | 0 | 1500 | 2.5 | 100 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | MKT. Marketing Infrastructure | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Railway side MACD Excavation&chamber making | Lumpsum work- DCW | No. | 1 | 8500 | 8500 | 0 | 8500 | 2.5 | 1 | 8500 | 0 | 8500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Shop.No.G Godown Shifting - 1 No. | Lumpsum work- DCW | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-3rd Floor -Front Side Bund Wall making - 1 No. | Blockwork -SOS | Sq.Ft | 100 | 16 | 1600 | 0 | 1600 | 2.5 | 100 | 1600 | 0 | 1600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Refuse Area Side Fatima Side Wall Plaster Chi | Breaking & Shifting- BRE | Sq.Ft | 395.14 | 15 | 5927.1 | 0 | 5927.1 | 2.5 | 395.14 | 5927.1 | 0 | 5927.1 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. BBM, Plaster, POP | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Railway Side 4th Fl Refuse Slab Ghadai | Ghadai work- BCP | Sq.Ft | 816 | 5 | 4080 | 0 | 4080 | 2.5 | 816 | 4080 | 0 | 4080 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Steps Work in front of KFC Shops Ent Plaza | Brick Pillar- Dld | R.Ft | 21 | 80 | 1680 | 0 | 1680 | 2.5 | 21 | 1680 | 0 | 1680 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Breaker for Chamber Raising | Breaker | Day | 0.5 | 650 | 325 | 0 | 325 | 2.5 | 0.5 | 325 | 0 | 325 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Department Labour for Site Petty Work | Departmental Labour | No. | 10 | 500 | 5000 | 0 | 5000 | 0 | 10 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement RCC Retaining Wall Plaster Removal Work | Debris Removing & Shifting Work | No. | 1 | 8000 | 8000 | 0 | 8000 | 2.5 | 0.6625 | 5300 | 0 | 5300 | 0.3375 | 2700 |  | 66.25 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Subhsagar Side Railway Side Chember Raised | PCC Work | Sq.Ft | 100 | 6 | 600 | 0 | 600 | 2.5 | 100 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 02 RCC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 2 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Labour Lumsum | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-1st Floor 1st Fl Firoz Bhai Shop Old Flooring Dem | Granite Flooring Rate Diff. | Sq.Ft | 222.81 | 5 | 1114.05 | 0 | 1114.05 | 2.5 | 222.81 | 1114.05 | 0 | 1114.05 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Steps Work in front of KFC Shops Ent Plaza | Soling & PCC | Sq.Ft | 168 | 20 | 3360 | 0 | 3360 | 2.5 | 168 | 3360 | 0 | 3360 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 02 RCC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Refuse Area Side Fatima Side Wall Plaster Chi | Plaster Work -Dld | Sq.Ft | 395.14 | 20 | 7902.8 | 0 | 7902.8 | 2.5 | 395.14 | 7902.8 | 0 | 7902.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl Retaining Wall Hacking | Hacking Work | Sq.Ft | 585 | 3 | 1755 | 0 | 1755 | 2.5 | 585 | 1755 | 0 | 1755 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 02 RCC WORK | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Mobile Toilet Shifting Removal Temporary | Toilet shifting Work-SO | No. | 2 | 1500 | 3000 | 0 | 3000 | 2.5 | 2 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Rabit Shifting of Nali area 1st ,5th to 4th to Gr Floor | Department Labour- BC | No. | 7 | 500 | 3500 | 0 | 3500 | 0 | 7 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Lumpsum work- DCW | No. | 1 | 2700 | 2700 | 0 | 2700 | 0 | 1 | 2700 | 0 | 2700 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-1st Floor Firoz Bhai Shop.No.10 1st Fl-Blockwork | Sand Face Plaster | Sq.Ft | 863.6 | 20 | 17272 | 0 | 17272 | 2.5 | 500.2835 | 10005.67 | 0 | 10005.67 | 363.3165 | 7266.33 |  | 57.93 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of AAC Blocks | No. | 640 | 3 | 1920 | 0 | 1920 | 0 | 640 | 1920 | 0 | 1920 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Window&Door RCC Linttle Making | RCC Lintel BC | No. | 10 | 200 | 2000 | 0 | 2000 | 2.5 | 10 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Superstructure | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-5th Floor Top Terrace Gutter Nali Breaking | Department Labour - Day | Day | 3 | 1300 | 3900 | 0 | 3900 | 0 | 3 | 3900 | 0 | 3900 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | SOC. M. Civil Work Maintenace | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Railway Side 4th Fl Refuse Old PCC Breaking | Breaker | Day | 3 | 1300 | 3900 | 0 | 3900 | 2.5 | 3 | 3900 | 0 | 3900 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of Cement | Bags | 65 | 10 | 650 | 0 | 650 | 0 | 65 | 650 | 0 | 650 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-1st Floor 1st Fl Firoz Bhai Shop Plaster Work | Rate Differ.For Internal Plaster - DCH | Sq.Ft | 774.15 | 3 | 2322.45 | 0 | 2322.45 | 2.5 | 774.15 | 2322.45 | 0 | 2322.45 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Club House | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement RCC Retaining Wall Plaster Removal Work | Breaker | Day | 15 | 1300 | 19500 | 0 | 19500 | 2.5 | 10 | 13000 | 0 | 13000 | 5 | 6500 |  | 66.6667 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 2 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Gypsum Unloading work | Bags | 1120 | 4 | 4480 | 0 | 4480 | 0 | 1120 | 4480 | 0 | 4480 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Ramp Area Ramp Front Portion Work(Civil Work)-(No.) | Excavation | Cu.Ft | 412.77 | 6.5 | 2683.01 | 0 | 2683.01 | 0 | 412.77 | 2683.01 | 0 | 2683.01 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 2 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Jointing Mortar Unloading | Bags | 50 | 5 | 250 | 0 | 250 | 0 | 50 | 250 | 0 | 250 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Steps Work in front of KFC Shops Ent Plaza | Brick Pillar- Dld | R.Ft | 21 | 40 | 840 | 0 | 840 | 2.5 | 21 | 840 | 0 | 840 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Ramp Area Ramp Front Portion Work(Civil Work)-(No.) | Lumpsum work- DCW | No. | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 1 | 1900 | 0 | 1900 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 1 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Ramp Area Ramp Front Portion Work(Civil Work)-(No.) | Soling 9" Rate Diffe.-DCW | Sq.Ft | 279.76 | 1.5 | 419.64 | 0 | 419.64 | 2.5 | 279.76 | 419.64 | 0 | 419.64 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Floor Subhsagar Front Side PCC For Opening Purpose | Lumpsum work- DCW | No. | 1 | 2200 | 2200 | 0 | 2200 | 2.5 | 1 | 2200 | 0 | 2200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl Cleaning +Tile Shifting | Lumpsum work- DCW | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of Tiles | Box | 65 | 10 | 650 | 0 | 650 | 0 | 65 | 650 | 0 | 650 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | SRA-12th Floor WP Top Breaking&Debris Shifting | Breaker | Day | 4 | 1300 | 5200 | 0 | 5200 | 2.5 | 4 | 5200 | 0 | 5200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 12 | 0 | 10 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-1st Floor Firoz Bhai Shop.No.10 1st Fl-Blockwork | Blockwork 5" - BC - | Sq.Ft | 431.8 | 16 | 6908.8 | 0 | 6908.8 | 2.5 | 431.8 | 6908.8 | 0 | 6908.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. BBM, Plaster, POP | Approved | Avinash Padmanabha | 19 Nov 2021
EAST POINT MARKET | 13 | 2 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-4th Fl Toilet (Gents+Ladies) Plumbing Work(L) | Urinal Fixing | No. | 4 | 2800 | 11200 | 0 | 11200 | 2.5 | 4 | 11200 | 0 | 11200 | 0 | 0 | (Gents Toilet-4) | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 4000 | 4000 | 0 | 4000 | 2.5 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | 4th Floor Utility line ball valve fixing - 1 No. | Ball Valve Fixing | No. | 7 | 200 | 1400 | 0 | 1400 | 2.5 | 7 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | KEP- 4th Fl-Community Hall Toilet,Nahani Trap,Downtake Line | Plumbing Work -Mkt | No. | 2 | 6800 | 13600 | 0 | 13600 | 2.5 | 2 | 13600 | 0 | 13600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 3200 | 3200 | 0 | 3200 | 2.5 | 1 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 2 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-4th Fl Toilet (Gents+Ladies) Plumbing Work(L) | Basin Fixing-cc | No. | 9 | 1800 | 16200 | 0 | 16200 | 2.5 | 9 | 16200 | 0 | 16200 | 0 | 0 | (Gents Toilet-4 & Ladies Toilet-5) | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 2 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-Gr Floor Gr Fl,4th Fl,OHWT Plumbing Work | Transport Charges | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 | (Pune-Kurla & Return) | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | Fatima Side 4th Floor SRA line WC line repairing work | Lumpsum work- DCW | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 3200 | 3200 | 0 | 3200 | 2.5 | 1 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Inlet & Outlet provision -cc | No. | 2 | 7000 | 14000 | 0 | 14000 | 2.5 | 1 | 7000 | 0 | 7000 | 1 | 7000 |  | 50 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Inlet & Outlet provision -cc | No. | 2 | 1600 | 3200 | 0 | 3200 | 2.5 | 1 | 1600 | 0 | 1600 | 1 | 1600 |  | 50 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 8000 | 8000 | 0 | 8000 | 2.5 | 1 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | Plumbing Work 3rd Fl&2nd Fl ShopWater Meter Installation | Water Meter Fixing Work - UWR | No. | 40 | 500 | 20000 | 0 | 20000 | 2.5 | 29 | 14500 | 0 | 14500 | 11 | 5500 |  | 72.5 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | UTI. Water Supply | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 3200 | 3200 | 0 | 3200 | 0 | 1 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | Community hall pipe laying below flooring for drain water. | 2" PVC Pipe Laying-UTI | R.Ft | 220 | 10 | 2200 | 0 | 2200 | 2.5 | 220 | 2200 | 0 | 2200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | UTI. Electricity Infrastructur | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-Plumbing Pipe Damage due to Fire Old Pipe | Plumbing work lumpsum- | No. | 1 | 110000 | 110000 | 0 | 110000 | 2.5 | 1 | 110000 | 0 | 110000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Inlet & Outlet provision -cc | No. | 0 | 14000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Cancelled | Dushant Gore | 28 Sep 2022
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Inlet & Outlet provision -cc | No. | 0 | 7000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Cancelled | Dushant Gore | 28 Sep 2022
EAST POINT MARKET | 13 | 1 | 16 Nov 2021 | TUKARAM B KATAKE | KEP- New ,Old, Repairing Plumbing Work | Plumbing Lumpsum - SO | No. | 1 | 170200 | 170200 | 0 | 170200 | 2.5 | 0.8061 | 137198.22 | 0 | 137198.22 | 0.1939 | 33001.78 | 4th floor toilet fixing FRP cabin,SRA all plumbing duct line repairing from 5th to12th floor,Ground to old toilet CP/Sanitary/flush valve/urinal/WC/wash basin removing and shifting to 4th floor,2nd and 3rd floor,4th floor inlet and outlet work | 80.61 |  | Avinash Padmanabha | skmishra | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | skmishra
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 1600 | 1600 | 0 | 1600 | 2.5 | 1 | 1600 | 0 | 1600 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | 4th floor mobile toilet for labour use | Lumpsum work- DCW | No. | 1 | 4000 | 4000 | 0 | 4000 | 2.5 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 2 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-4th Fl Toilet (Gents+Ladies) Plumbing Work(L) | Commode fixing cc | No. | 8 | 5000 | 40000 | 0 | 40000 | 2.5 | 8 | 40000 | 0 | 40000 | 0 | 0 | (Gents Toilet-4 & Ladies Toilet-4) | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 0 | 4800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 28 Sep 2022
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-Basement Fl Verticlal & Horizontal Line for Water Drain | Pipe Laying -AIE | R.Ft | 100 | 20 | 2000 | 0 | 2000 | 2.5 | 100 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 1600 | 1600 | 0 | 1600 | 2.5 | 1 | 1600 | 0 | 1600 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 2 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-Gr Floor Gr Fl,4th Fl,OHWT Plumbing Work | Food Allowance | No. | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 24 Nov 2021 |  | 14 MISC WORK | Cancelled | Avinash Padmanabha | 01 Dec 2021
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 3200 | 3200 | 0 | 3200 | 2.5 | 1 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 4800 | 4800 | 0 | 4800 | 2.5 | 1 | 4800 | 0 | 4800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | KEP- UGWT To 12th Fl New OHWT Connection | Plumbing work lumpsum- | No. | 1 | 30000 | 30000 | 0 | 30000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 15000 | 15000 | 0 | 15000 | 2.5 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Inlet & Outlet provision -cc | No. | 1 | 4800 | 4800 | 0 | 4800 | 2.5 | 1 | 4800 | 0 | 4800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-Basement Fl KFC Line Drain Work Hanging Work | Pipe Laying -AIE | R.Ft | 90 | 50 | 4500 | 0 | 4500 | 2.5 | 90 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | Basement BMC line hanging for waterproofing work | Lumpsum work- DCW | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 2 | 16 Nov 2021 | TUKARAM B KATAKE | KEP-Gr Floor Gr Fl,4th Fl,OHWT Plumbing Work | Food Allowance | No. | 0.2 | 15000 | 3000 | 0 | 3000 | 0 | 0.2 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | KEP Plaza 4" Pipe Line Fitting in Greese Chamber for MACD | Pipe Laying -AIE | R.Ft | 150 | 20 | 3000 | 0 | 3000 | 2.5 | 150 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 800 | 800 | 0 | 800 | 2.5 | 1 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 2500 | 2500 | 0 | 2500 | 2.5 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | 1st Floor Tem. water tank shifting for checkerd plate work | Labour Lumpsum - Dld | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 13 | 3 | 16 Nov 2021 | TUKARAM B KATAKE | Misc. plumbing works | Plumbing work lumpsum- | No. | 1 | 6400 | 6400 | 0 | 6400 | 2.5 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 13 | 0 | 16 Nov 2021 | TUKARAM B KATAKE | Society Drainage chamber extension work | Chamber work - cc | No. | 5 | 1500 | 7500 | 0 | 7500 | 2.5 | 5 | 7500 | 0 | 7500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 1932 | 84 | 162288 | 29211.84 | 191499.84 | 0 | 1932 | 162288 | 29211.84 | 191499.84 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 3240 | 84 | 272160 | 48988.8 | 321148.8 | 0 | 3240 | 272160 | 48988.8 | 321148.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Masa & Lord Forklore Checkered Plate Work | Anchor Bolt-MWB | No. | 220 | 40 | 8800 | 1584 | 10384 | 0 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (M) | Kgs | 287.25 | 112 | 32172 | 5790.96 | 37962.96 | 0 | 287.25 | 32172 | 5790.96 | 37962.96 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Masa & Lord Forklore Checkered Plate Work | Fabrication work (M) | Kgs | 1885 | 80 | 150800 | 27144 | 177944 | 0 | 1778.7991 | 142303.93 | 25614.7 | 167918.63 | 106.2009 | 10025.37 |  | 94.366 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Atrium Lobby Beam Fabrication | Anchor Fastener (M) | No. | 520 | 50 | 26000 | 4680 | 30680 | 0 | 304 | 15200 | 2736 | 17936 | 216 | 12744 |  | 58.4615 |  | Dushant Gore | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 1848 | 84 | 155232 | 27941.76 | 183173.76 | 0 | 1680.02 | 141121.68 | 25401.9 | 166523.58 | 167.98 | 16650.18 |  | 90.9102 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Atrium Lobby Beam Fabrication | Base Plate (M). | Kgs | 317.47 | 84 | 26667.48 | 4800.14 | 31467.62 | 0 | 184.68 | 15513.12 | 2792.36 | 18305.48 | 132.79 | 13162.14 |  | 58.1724 |  | Dushant Gore | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | Admin. Direct Expenses | Cancelled | skmishra | 17 Nov 2021
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 2640 | 84 | 221760 | 39916.8 | 261676.8 | 0 | 2640 | 221760 | 39916.8 | 261676.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 1488 | 84 | 124992 | 22498.56 | 147490.56 | 0 | 1488 | 124992 | 22498.56 | 147490.56 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Atrium Lobby Beam Fabrication | MS Square Pipe (M) | Kgs | 1050 | 84 | 88200 | 15876 | 104076 | 0 | 1050 | 88200 | 15876 | 104076 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (M) | Kgs | 282 | 92 | 25944 | 4669.92 | 30613.92 | 0 | 282 | 25944 | 4669.92 | 30613.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work (M) | Sq.Ft | 42419.84 | 55 | 2333091.2 | 419956.42 | 2753047.62 | 0 | 0 | 0 | 0 | 0 | 42419.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Anchor Bolt-MWB | No. | 60 | 70 | 4200 | 756 | 4956 | 0 | 34.998 | 2449.86 | 440.98 | 2890.84 | 25.002 | 2065.16 |  | 58.33 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fastner (M+L) | No. | 720 | 360 | 259200 | 46656 | 305856 | 0 | 704.16 | 253497.6 | 45629.56 | 299127.16 | 15.84 | 6728.84 |  | 97.8 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 1480 | 84 | 124320 | 22377.6 | 146697.6 | 0 | 1480 | 124320 | 22377.6 | 146697.6 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (M) | Kgs | 135.4 | 84 | 11373.6 | 2047.24 | 13420.84 | 0 | 135.4 | 11373.6 | 2047.24 | 13420.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 6820 | 84 | 572880 | 103118.4 | 675998.4 | 0 | 6819.996 | 572879.66 | 103118.34 | 675998 | 0.004 | 0.4 |  | 99.9999 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 14 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (M) | Kgs | 4048 | 84 | 340032 | 61205.76 | 401237.76 | 0 | 4047.998 | 340031.83 | 61205.72 | 401237.55 | 0.002 | 0.21 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 4048 | 21 | 85008 | 15301.44 | 100309.44 | 2.5 | 4048 | 85008 | 15301.44 | 100309.44 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 1488 | 21 | 31248 | 5624.64 | 36872.64 | 2.5 | 1488 | 31248 | 5624.64 | 36872.64 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 2640 | 21 | 55440 | 9979.2 | 65419.2 | 2.5 | 2640 | 55440 | 9979.2 | 65419.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (L) | Kgs | 287.25 | 28 | 8043 | 1447.74 | 9490.74 | 2.5 | 287.25 | 8043 | 1447.74 | 9490.74 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Departmental Work - DPo | Day | 6 | 2000 | 12000 | 2160 | 14160 | 0 | 6 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Podium | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Lumpsum - Dld | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Lumpsum - Dld | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (L) | Kgs | 135.4 | 21 | 2843.4 | 511.82 | 3355.22 | 2.5 | 135.4 | 2843.4 | 511.82 | 3355.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 6820 | 21 | 143220 | 25779.6 | 168999.6 | 2.5 | 6816.59 | 143148.39 | 25766.72 | 168915.11 | 3.41 | 84.49 |  | 99.95 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 3240 | 21 | 68040 | 12247.2 | 80287.2 | 2.5 | 3240 | 68040 | 12247.2 | 80287.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Atrium Lobby Beam Fabrication | Base Plate (L) | Kgs | 317.47 | 21 | 6666.87 | 1200.04 | 7866.91 | 2.5 | 184.68 | 3878.28 | 698.1 | 4576.38 | 132.79 | 3290.53 |  | 58.1724 |  | Dushant Gore | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Transport Charges | No. | 1 | 23000 | 23000 | 4140 | 27140 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Atrium Lobby Beam Fabrication | MS Square Pipe (L) | Kgs | 1050 | 21 | 22050 | 3969 | 26019 | 2.5 | 1049.4999 | 22039.5 | 3967.12 | 26006.62 | 0.5001 | 12.38 |  | 99.9524 |  | Dushant Gore | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Masa & Lord Forklore Checkered Plate Work | Fabrication work (L) | Kgs | 1885 | 21 | 39585 | 7125.3 | 46710.3 | 2.5 | 1781.2857 | 37407 | 6733.26 | 44140.26 | 103.7143 | 2570.04 |  | 94.4979 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 1932 | 21 | 40572 | 7302.96 | 47874.96 | 2.5 | 1932 | 40572 | 7302.96 | 47874.96 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Flex Framing. | No. | 15 | 900 | 13500 | 2430 | 15930 | 2.5 | 15 | 13500 | 2430 | 15930 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work (L) | Sq.Ft | 42419.84 | 20 | 848396.8 | 152711.42 | 1001108.22 | 2.5 | 0 | 0 | 0 | 0 | 42419.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 1480 | 21 | 31080 | 5594.4 | 36674.4 | 2.5 | 0 | 0 | 0 | 0 | 1480 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (L) | Kgs | 282 | 28 | 7896 | 1421.28 | 9317.28 | 2.5 | 282 | 7896 | 1421.28 | 9317.28 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP 6th Slab Fabrication Repainting Work | Fabrication work (L) | Kgs | 1848 | 21 | 38808 | 6985.44 | 45793.44 | 2.5 | 1679.832 | 35276.47 | 6349.76 | 41626.23 | 168.168 | 4167.21 |  | 90.9 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Lumpsum - Dld | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 15 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Transport Charges | No. | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Window Grill (L) | Sq.Ft | 52.5 | 180 | 9450 | 1701 | 11151 | 2.5 | 52.5 | 9450 | 1701 | 11151 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | 4th Floor sample office fabrication & KFC front flex removin | Flex Removing | No. | 1 | 3500 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 18 Nov 2021 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (L) | Kgs | 455.4 | 21 | 9563.4 | 1721.42 | 11284.82 | 2.5 | 455.4 | 9563.4 | 1721.42 | 11284.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Mechanical Fastner (M+L) - No. | No. | 2106 | 45 | 94770 | 17058.6 | 111828.6 | 2.5 | 963.9985 | 43379.93 | 7808.38 | 51188.31 | 1142.0015 | 60640.29 |  | 45.7739 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Rolling Shutter (L) | Sq.Ft | 140.25 | 70 | 9817.5 | 1767.16 | 11584.66 | 2.5 | 140.25 | 9817.5 | 1767.16 | 11584.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Basement Fl Guttter Jali & Sump Well Covering Work | Fabrication work (L) | Kgs | 337 | 21 | 7077 | 1273.86 | 8350.86 | 2.5 | 337 | 7077 | 1273.86 | 8350.86 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 16 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | 4th Floor sample office fabrication & KFC front flex removin | MS Channel. (L) | Kgs | 641 | 21 | 13461 | 2422.98 | 15883.98 | 2.5 | 641 | 13461 | 2422.98 | 15883.98 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 18 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Base Plate (L) | Kgs | 2275 | 25 | 56875 | 10237.5 | 67112.5 | 2.5 | 1026.616 | 25665.4 | 4619.78 | 30285.18 | 1248.384 | 36827.32 |  | 45.126 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Channel. (L) | Kgs | 11917.43 | 25 | 297935.75 | 53628.44 | 351564.19 | 2.5 | 5511.442 | 137786.05 | 24801.5 | 162587.55 | 6405.988 | 188976.64 |  | 46.2469 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 12 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Basement Fl Guttter Jali & Sump Well Covering Work | Fabrication work (L) | Kgs | 2508 | 21 | 52668 | 9480.24 | 62148.24 | 2.5 | 2508 | 52668 | 9480.24 | 62148.24 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 16 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | 4th Floor sample office fabrication & KFC front flex removin | MS Square Pipe (L) | Kgs | 200 | 21 | 4200 | 756 | 4956 | 2.5 | 200 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Basement Fl Guttter Jali & Sump Well Covering Work | Fabrication work (L) | Kgs | 51.6 | 21 | 1083.6 | 195.04 | 1278.64 | 2.5 | 51.6 | 1083.6 | 195.04 | 1278.64 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (L) | No. | 16 | 200 | 3200 | 576 | 3776 | 2.5 | 16 | 3200 | 576 | 3776 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | 4th Floor sample office fabrication & KFC front flex removin | MS Square Pipe (L) | Kgs | 1450 | 21 | 30450 | 5481 | 35931 | 2.5 | 1450 | 30450 | 5481 | 35931 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work. | No. | 7 | 1500 | 10500 | 1890 | 12390 | 2.5 | 7 | 10500 | 1890 | 12390 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Gas Cutting & Welding | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 18 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 39 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 35 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 79 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 115 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Angle fixing- SOS.. | Kgs | 103.2 | 30 | 3096 | 557.28 | 3653.28 | 2.5 | 103.2 | 3096 | 557.28 | 3653.28 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 27 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication Work (L) | Kgs | 128 | 21 | 2688 | 483.84 | 3171.84 | 2.5 | 128 | 2688 | 483.84 | 3171.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | M.S. Door fixing-Dld. | No. | 1 | 12000 | 12000 | 2160 | 14160 | 2.5 | 1 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Angle. (L) | Kgs | 2709.72 | 25 | 67743 | 12193.74 | 79936.74 | 2.5 | 2084 | 52100 | 9378 | 61478 | 625.72 | 18458.74 |  | 76.9083 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Bolt (L) | No. | 60 | 20 | 1200 | 216 | 1416 | 2.5 | 60 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | M.S.Structure removing | Kgs | 4977.81 | 10 | 49778.1 | 8960.06 | 58738.16 | 2.5 | 4977.81 | 49778.1 | 8960.06 | 58738.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT GORE | 07 Apr 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 108 Rolling Shutter - 82.856 Sq.Ft | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Name Board fixing-BC | No. | 3 | 1600 | 4800 | 864 | 5664 | 2.5 | 3 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Flex fixing work- BC | Sq.Ft | 900 | 5 | 4500 | 810 | 5310 | 2.5 | 900 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 112 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 22 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Base Plate (L) | Kgs | 337.5 | 21 | 7087.5 | 1275.76 | 8363.26 | 2.5 | 337.5 | 7087.5 | 1275.76 | 8363.26 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Base Plate (L) | Kgs | 8.5 | 21 | 178.5 | 32.14 | 210.64 | 2.5 | 8.5 | 178.5 | 32.14 | 210.64 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Removing | Kgs | 9429 | 10 | 94290 | 16972.2 | 111262.2 | 0 | 9429 | 94290 | 16972.2 | 111262.2 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 64 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (L) | No. | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 15 Apr 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 33 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 34 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 37 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 114 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 25 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Base Plate (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 21 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Fastner (M+L) | No. | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 26 Jul 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 20 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Mechanical Fastner (M+L) - No. | No. | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (L) | No. | 24 | 60 | 1440 | 259.2 | 1699.2 | 2.5 | 24 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 80 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Channel. (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | No category | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 26 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 61 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Angle fixing- SOS.. | Kgs | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | S OH Infrastructure | Cancelled | skmishra | 15 Apr 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Rolling Shutter (L) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 15 Apr 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 23 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 65 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 87 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 36 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (L) | No. | 32 | 20 | 640 | 115.2 | 755.2 | 2.5 | 32 | 640 | 115.2 | 755.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 28 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 85 Rolling Shutter - 86.123 Sq.Ft | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 29 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Angle. (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Name Board fixing-BC | No. | 0 | 1600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | B.C. Building Common Items | Cancelled | skmishra | 15 Apr 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 24 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Mechanical Fastner (M+L) - No. | No. | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 26 Jul 2022
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 111 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 16 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-4th Fl Atrium Lobby False Ceiling Work MS Support Work | Fabrication work (M) | Kgs | 3080 | 84 | 258720 | 46569.6 | 305289.6 | 0 | 3080 | 258720 | 46569.6 | 305289.6 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (M) | No. | 24 | 300 | 7200 | 1296 | 8496 | 0 | 24 | 7200 | 1296 | 8496 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (M) | No. | 32 | 20 | 640 | 115.2 | 755.2 | 0 | 32 | 640 | 115.2 | 755.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Base Plate (M). | Kgs | 2275 | 75 | 170625 | 30712.5 | 201337.5 | 0 | 1026.616 | 76996.2 | 13859.32 | 90855.52 | 1248.384 | 110481.98 |  | 45.126 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Bolt (M) | No. | 60 | 20 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | M.S. Ladder (m+l)-BC | No. | 4 | 11200 | 44800 | 8064 | 52864 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | B.C. Building Common Items | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Channel. (M) | Kgs | 11917.43 | 65 | 774632.95 | 139433.94 | 914066.89 | 0 | 7374.2071 | 479323.46 | 86278.22 | 565601.68 | 4543.2229 | 348465.21 |  | 61.8775 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Base Plate (M). | Kgs | 8.5 | 84 | 714 | 128.52 | 842.52 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 37 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Rolling Shutter (M) | Sq.Ft | 140.25 | 210 | 29452.5 | 5301.46 | 34753.96 | 0 | 140.25 | 29452.5 | 5301.46 | 34753.96 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 61 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Base Plate (M). | Kgs | 337.5 | 84 | 28350 | 5103 | 33453 | 0 | 337.5 | 28350 | 5103 | 33453 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 39 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 26 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 33 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 87 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | 4th Floor sample office fabrication & KFC front flex removin | MS Square Pipe (M) | Kgs | 1450 | 84 | 121800 | 21924 | 143724 | 0 | 1450 | 121800 | 21924 | 143724 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Angle. (M) | Kgs | 2709.72 | 65 | 176131.8 | 31703.72 | 207835.52 | 0 | 2189.988 | 142349.22 | 25622.86 | 167972.08 | 519.732 | 39863.44 |  | 80.8197 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 1 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Anchor Fastener (M) | No. | 16 | 800 | 12800 | 2304 | 15104 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Base Plate (M). | Kgs | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 26 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | Base Plate (M). | Kgs | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 114 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Angle. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 26 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 23 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 2 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | 4th Floor sample office fabrication & KFC front flex removin | Transport Charges | No. | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 18 Nov 2021 |  | S OH Infrastructure | Approved | aditya chougule | 14 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 28 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 12 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Angle. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 20 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 115 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 64 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 112 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 65 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 25 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 34 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | No category | Cancelled | skmishra | 06 Aug 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 108 Rolling Shutter - 82.856 Sq.Ft | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT GORE | 07 Apr 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 111 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 35 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 3 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work For 2nd Floor Rolling Shutter | MS Angle. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 26 Jul 2022
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 79 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 29 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 27 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 24 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 80 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 21 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 85 Rolling Shutter - 86.123 Sq.Ft | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 22 Jun 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 36 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Cancelled | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 17 | 4 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 22 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 18 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 05 Oct 2023
EAST POINT MARKET | 18 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-4th Fl Atrium Lobby False Ceiling Work MS Support Work | Fabrication work (L) | Kgs | 3080 | 21 | 64680 | 11642.4 | 76322.4 | 2.5 | 3080 | 64680 | 11642.4 | 76322.4 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 19 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Basement Fl Guttter Jali & Sump Well Covering Work | Fabrication work (M) | Kgs | 136.4 | 74 | 10093.6 | 1816.84 | 11910.44 | 0 | 136.4 | 10093.6 | 1816.84 | 11910.44 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 19 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Basement Fl Guttter Jali & Sump Well Covering Work | Fabrication work (M) | Kgs | 2508 | 74 | 185592 | 33406.56 | 218998.56 | 0 | 2508 | 185592 | 33406.56 | 218998.56 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 19 | 0 | 17 Nov 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Basement Fl Guttter Jali & Sump Well Covering Work | Fabrication work (M) | Kgs | 51.6 | 74 | 3818.4 | 687.32 | 4505.72 | 0 | 51.6 | 3818.4 | 687.32 | 4505.72 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 18 Nov 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 20 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Guest House-Gas Bill | Gas Charging | No. | 1 | 8902 | 8902 | 0 | 8902 | 0 | 1 | 8902 | 0 | 8902 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 20 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9983 | 19966 | 0 | 19966 | 0.0017 | 34 |  | 99.83 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 20 | 2 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Guest House-Gas Bill | Gas Charging | No. | 1 | 5760 | 5760 | 0 | 5760 | 0 | 1 | 5760 | 0 | 5760 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.3973 | 3973 | 0 | 3973 | 0.6027 | 6027 |  | 39.73 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9629 | 9629 | 0 | 9629 | 0.0371 | 371 |  | 96.29 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.1764 | 1764 | 0 | 1764 | 0.8236 | 8236 |  | 17.64 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9925 | 9925 | 0 | 9925 | 0.0075 | 75 |  | 99.25 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 21 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9906 | 9906 | 0 | 9906 | 0.0094 | 94 |  | 99.06 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9985 | 9985 | 0 | 9985 | 0.0015 | 15 |  | 99.85 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.1589 | 1589 | 0 | 1589 | 0.8411 | 8411 |  | 15.89 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 21 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.3315 | 3315 | 0 | 3315 | 0.6685 | 6685 |  | 33.15 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 21 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9392 | 9392 | 0 | 9392 | 0.0608 | 608 |  | 93.92 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 0.21 | 10000 | 2100 | 0 | 2100 | 0 | 0.21 | 2100 | 0 | 2100 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 21 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9441 | 9441 | 0 | 9441 | 0.0559 | 559 |  | 94.41 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 2 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 0 | 21087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Nov 2021 |  | S OH Expenses | Cancelled | Dushant Gore | 24 Jun 2022
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 21 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.4148 | 4148 | 0 | 4148 | 0.5852 | 5852 |  | 41.48 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.8024 | 8024 | 0 | 8024 | 0.1976 | 1976 |  | 80.24 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 2 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 21087 | 21087 | 0 | 21087 | 0 | 1 | 21087 | 0 | 21087 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9976 | 9976 | 0 | 9976 | 0.0024 | 24 |  | 99.76 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.3265 | 3265 | 0 | 3265 | 0.6735 | 6735 |  | 32.65 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9753 | 9753 | 0 | 9753 | 0.0247 | 247 |  | 97.53 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 21 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 21 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Expenses | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 22 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 22 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 2 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 8000 | 8000 | 0 | 8000 | 0 | 1 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 22 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 22 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 22 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 22 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Travelling Expenses | Travelling Allowance | Month | 1 | 11888 | 11888 | 0 | 11888 | 0 | 1 | 11888 | 0 | 11888 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Nov 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 2 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 23 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 23 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 23 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 0 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 18 Nov 2021
EAST POINT MARKET | 23 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 4 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 3 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 1 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 23 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 23 | 5 | 18 Nov 2021 | SATISH RAMCHANDRA JAGTAP | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Gas Meter (M) | No. | 38 | 6151.25 | 233747.5 | 42074.56 | 275822.06 | 0 | 0 | 0 | 0 | 0 | 38 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Paint Yellow | Ltrs | 15 | 209 | 3135 | 564.3 | 3699.3 | 0 | 8.0287 | 1678 | 302.04 | 1980.04 | 6.9713 | 1719.26 |  | 53.5247 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Ball valve 65 NB Brass Type (M) | No. | 8 | 2560.25 | 20482 | 3686.76 | 24168.76 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | SITC Ball Valve 25mm (M) | No. | 40 | 764.75 | 30590 | 5506.2 | 36096.2 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Clamp & Hardware | No. | 250 | 71.25 | 17812.5 | 3206.26 | 21018.76 | 0 | 50.007 | 3563 | 641.34 | 4204.34 | 199.993 | 16814.42 |  | 20.0028 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | ERW C Class Pipe 2.5" dia NB (M) | Mtrs | 170 | 748.13 | 127181.25 | 22892.62 | 150073.87 | 0 | 102.0003 | 76308.97 | 13735.62 | 90044.59 | 67.9997 | 60029.28 |  | 60.0002 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | ERW C Class Pipe 3/4" dia NB (M) | Mtrs | 42 | 266 | 11172 | 2010.96 | 13182.96 | 0 | 0 | 0 | 0 | 0 | 42 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Ball valve 40 NB Brass Type (M) | No. | 5 | 1030.75 | 5153.75 | 927.68 | 6081.43 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Filter 1" | No. | 44 | 2612.5 | 114950 | 20691 | 135641 | 0 | 0 | 0 | 0 | 0 | 44 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Consumable | No. | 1 | 14725 | 14725 | 2650.5 | 17375.5 | 0 | 0.2 | 2945 | 530.1 | 3475.1 | 0.8 | 13900.4 |  | 20 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | SITC Ball Valve 50mm (M) | No. | 4 | 2227.75 | 8911 | 1603.98 | 10514.98 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Ball valve 15 NB Brass Type (M) | No. | 40 | 299.25 | 11970 | 2154.6 | 14124.6 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | ERW C Class Pipe 2" dia NB (M) | Mtrs | 255 | 605.15 | 154313.25 | 27776.38 | 182089.63 | 0 | 0 | 0 | 0 | 0 | 255 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | M.S. Support Supply (M)- UDG | Kgs | 150 | 49.88 | 7481.25 | 1346.62 | 8827.87 | 0 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | UTI. D.G.Set | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Paint Black | Ltrs | 5 | 156.75 | 783.75 | 141.08 | 924.83 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Paint Primer | Ltrs | 15 | 209 | 3135 | 564.3 | 3699.3 | 0 | 10.0478 | 2099.99 | 378 | 2477.99 | 4.9522 | 1221.31 |  | 66.9853 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | 40 Seamless CS Pipe 1.5" NB (M) | Mtrs | 18 | 445.55 | 8019.9 | 1443.58 | 9463.48 | 0 | 7.0205 | 3127.98 | 563.04 | 3691.02 | 10.9795 | 5772.46 |  | 39.0028 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 24 | 0 | 18 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Gas Meter (M) | No. | 6 | 14962.5 | 89775 | 16159.5 | 105934.5 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | ERW C Class Pipe 2" dia NB (L) | Mtrs | 255 | 259.35 | 66134.25 | 11904.16 | 78038.41 | 2.5 | 0 | 0 | 0 | 0 | 255 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Ball valve 65 NB Brass Type (L) | No. | 8 | 1097.25 | 8778 | 1580.04 | 10358.04 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | ERW C Class Pipe 3/4" dia NB (L) | Mtrs | 42 | 114 | 4788 | 861.84 | 5649.84 | 2.5 | 0 | 0 | 0 | 0 | 42 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Gas Meter (L) | No. | 38 | 2636.25 | 100177.5 | 18031.96 | 118209.46 | 2.5 | 0 | 0 | 0 | 0 | 38 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Gas Meter (L) | No. | 6 | 6412.5 | 38475 | 6925.5 | 45400.5 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | SITC Ball Valve 50mm (L) | No. | 4 | 954.75 | 3819 | 687.42 | 4506.42 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Ball valve 40 NB Brass Type (L) | No. | 5 | 441.75 | 2208.75 | 397.58 | 2606.33 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | M.S. Support Erection (L)- UDG | Kgs | 150 | 21.38 | 3206.25 | 577.12 | 3783.37 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | UTI. D.G.Set | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | SITC Ball Valve 25mm (L) | No. | 40 | 327.75 | 13110 | 2359.8 | 15469.8 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | ERW C Class Pipe 2.5" dia NB (L) | Mtrs | 170 | 320.63 | 54506.25 | 9811.12 | 64317.37 | 2.5 | 102.0008 | 32704.01 | 5886.72 | 38590.73 | 67.9992 | 25726.64 |  | 60.0005 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | 40 Seamless CS Pipe 1.5" NB (L) | Mtrs | 18 | 190.95 | 3437.1 | 618.68 | 4055.78 | 2.5 | 7.0175 | 1339.99 | 241.2 | 1581.19 | 10.9825 | 2474.59 |  | 38.9861 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 25 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Ball valve 15 NB Brass Type (L) | No. | 40 | 128.25 | 5130 | 923.4 | 6053.4 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 26 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Consultancy Charges | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 24 Nov 2021 |  | Consultacy Architectural | Approved | chetan.jewalikar
EAST POINT MARKET | 26 | 0 | 19 Nov 2021 | PUNE PIPED GAS CO | Gas Piping System-(No.) | Inspection Charges | No. | 1 | 9975 | 9975 | 1795.5 | 11770.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA.CHOUGULE | 06 Jun 2023
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 0 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 27 | 1 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 27 | 3 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 27 | 2 | 19 Nov 2021 | VIJAYA PRABHU G | Guest House Rental Charges | Rental Charges. | Month | 1 | 37500 | 37500 | 0 | 37500 | 0 | 1 | 37500 | 0 | 37500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 28 | 0 | 20 Nov 2021 | COMFORT SALES AND SERVICES | Sales Office AC Repair&Service | A.C. Repair & maintenance.-SO | No. | 1 | 5700 | 5700 | 0 | 5700 | 0 | 1 | 5700 | 0 | 5700 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Repair & Maintenance | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of AAC Blocks | No. | 675 | 3 | 2025 | 0 | 2025 | 0 | 675 | 2025 | 0 | 2025 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl -Sump Well Slab,BBM,Plaster,Filling Work | Plaster Work - BRE | Sq.Ft | 50 | 16 | 800 | 0 | 800 | 2.5 | 50 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Escalator Front Champher Work | Departmental Labour | No. | 0.5 | 500 | 250 | 0 | 250 | 2.5 | 0.5 | 250 | 0 | 250 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Escalator Front Champher Work | Departmental Labour | No. | 0.5 | 800 | 400 | 0 | 400 | 2.5 | 0.5 | 400 | 0 | 400 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Tile Shifting 1st Fl to 2nd Fl | Material Shiftting - DER | No. | 167 | 10 | 1670 | 0 | 1670 | 0 | 167 | 1670 | 0 | 1670 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Extrawork/Rework | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 1 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Site Expences | No. | 1 | 10395 | 10395 | 0 | 10395 | 0 | 1 | 10395 | 0 | 10395 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-3rd Floor -Facade Side BBM Work - 1 No. | Department Labour- BC | No. | 1 | 800 | 800 | 0 | 800 | 2.5 | 1 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Aerocon Panel Shifting From 1st to Basement - 1 No. | Panel Shifting - UTI | No. | 159 | 160 | 25440 | 0 | 25440 | 0 | 159 | 25440 | 0 | 25440 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | UTI. Electricity Infrastructur | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-5th Floor -Breaking rabit shifting 5th to Gr Fl | Department Labour- BC | No. | 27 | 500 | 13500 | 0 | 13500 | 2.5 | 27 | 13500 | 0 | 13500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Lumpsum work- DCW | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 | (4ft x 3ft, 2ft x 3ft, 4ft x 2ft, 4ft x 1ft, 3ft x 3ft, 2ft x 2ft). | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl -Sump Well Slab,BBM,Plaster,Filling Work | Blockwork 5" - BC - | Sq.Ft | 37.5 | 16 | 600 | 0 | 600 | 2.5 | 37.5 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. BBM, Plaster, POP | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl -Sump Well Slab,BBM,Plaster,Filling Work | RCC Work - BC | Sq.Ft | 436.5 | 50 | 21825 | 0 | 21825 | 2.5 | 436.5 | 21825 | 0 | 21825 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Superstructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-3rd Floor -Common Passage Area Gypsum Chipping Work | Departmental Labour | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Fasade Side Wall Cement Ghotai - 1 No. | Department Labour- BC | No. | 2 | 800 | 1600 | 0 | 1600 | 2.5 | 2 | 1600 | 0 | 1600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Escalator Front Champher Work | Departmental Labour | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | B.C. Rework/Extrawork | Cancelled | Avinash Padmanabha | 22 Nov 2021
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-3rd Floor -Facade Side BBM Work - 1 No. | Department Labour- BC | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Escalator Front Champher Work | Departmental Labour | No. | 0 | 400 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | B.C. Rework/Extrawork | Cancelled | Avinash Padmanabha | 22 Nov 2021
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-5th Floor -SRA Bldg Flat Side leakage prevention - 1 | Department Labour- BC | No. | 4 | 500 | 2000 | 0 | 2000 | 2.5 | 4 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 1 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Site Expences | No. | 1 | 2500 | 2500 | 0 | 2500 | 0 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-1st Floor -Shop.No.12,11,9&10,7&8,6,5A Work - 1 No. | Department Labour- BC | No. | 15.5 | 500 | 7750 | 0 | 7750 | 2.5 | 15.5 | 7750 | 0 | 7750 | 0 | 0 | M/C = 04 Nos. (28/08/2021) M/C = 03 Nos. (30/08/2021) M/C = 02 Nos. (31/08/2021) M/C = 02 Nos. (02/09/2021) M/C = 03 Nos. (03/09/2021) M/C = 1.5 Nos. (04/09/2021) | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl -Sump Well Slab,BBM,Plaster,Filling Work | Filling Work -Dld | Cu.Ft | 56.25 | 3.5 | 196.88 | 0 | 196.88 | 2.5 | 56.25 | 196.88 | 0 | 196.88 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 1 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Site Expences | No. | 1 | 2100 | 2100 | 0 | 2100 | 0 | 1 | 2100 | 0 | 2100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Fasade Side Wall Cement Ghotai - 1 No. | Department Labour- BC | No. | 2.5 | 500 | 1250 | 0 | 1250 | 2.5 | 2.5 | 1250 | 0 | 1250 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Rough Shahabad Unloading | No. | 1749 | 3 | 5247 | 0 | 5247 | 0 | 1749 | 5247 | 0 | 5247 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-5th Floor -SRA Bldg Flat Side leakage prevention - 1 | Department Labour- BC | No. | 2 | 800 | 1600 | 0 | 1600 | 2.5 | 2 | 1600 | 0 | 1600 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 1 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Site Expences | No. | 1 | 2600 | 2600 | 0 | 2600 | 0 | 1 | 2600 | 0 | 2600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Unloading of Tiles | Box | 97 | 10 | 970 | 0 | 970 | 0 | 97 | 970 | 0 | 970 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 1 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | Site Expenses | Site Expences | No. | 1 | 4432.5 | 4432.5 | 0 | 4432.5 | 0 | 1 | 4432.5 | 0 | 4432.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor -Toilet filling for plumbing line&tiling - 1 | PCC | Sq.Ft | 203 | 15 | 3045 | 0 | 3045 | 2.5 | 203 | 3045 | 0 | 3045 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 29 | 0 | 20 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Common Activity Passage Flooring removing 1st&3rd fl | Granite Flooring removing-BCV | Sq.Ft | 536.6 | 15 | 8049 | 0 | 8049 | 2.5 | 536.6 | 8049 | 0 | 8049 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 30 | 0 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | KEP- Facade Cleaning System | Cleaning Work - SO | Sq.Ft | 15000 | 4 | 60000 | 10800 | 70800 | 2.5 | 15000 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 30 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 30 | 1 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | Glass Cleaning Work - 0 No. | Glass Cleaning work. | Sq.Ft | 2541 | 2 | 5082 | 914.76 | 5996.76 | 0 | 2541 | 5082 | 914.76 | 5996.76 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 30 | 1 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | Glass Cleaning Work - 0 No. | Glass Cleaning work. | Sq.Ft | 1088 | 2 | 2176 | 391.68 | 2567.68 | 0 | 1088 | 2176 | 391.68 | 2567.68 | 0 | 0 | 136 Sqft x 8 Nos. Escalatos. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 30 | 1 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | Glass Cleaning Work - 0 No. | Glass Cleaning work. | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Nov 2021 |  | No category | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 30 | 0 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | KEP- Facade Cleaning System | Lumpsum work- DCW | No. | 1 | 15000 | 15000 | 2700 | 17700 | 2.5 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 30 Nov 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 30 | 1 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | Glass Cleaning Work - 0 No. | Glass Cleaning work. | Sq.Ft | 24984 | 2 | 49968 | 8994.24 | 58962.24 | 0 | 12492 | 24984 | 4497.12 | 29481.12 | 12492 | 29481.12 |  | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 30 | 1 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | Glass Cleaning Work - 0 No. | Glass Cleaning work. | Sq.Ft | 6246 | 2 | 12492 | 2248.56 | 14740.56 | 0 | 6246 | 12492 | 2248.56 | 14740.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 30 | 0 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | KEP- Facade Cleaning System | AMC Charges | No. | 4 | 30000 | 120000 | 21600 | 141600 | 0 | 3 | 90000 | 16200 | 106200 | 1 | 35400 |  | 75 |  | Runal Kindalkar | chetan.jewalikar | construction open | 30 Nov 2021 |  | SOC. M. Maintenace of Utilitie | Approved | chetan.jewalikar
EAST POINT MARKET | 30 | 0 | 22 Nov 2021 | MBG MAINTENANCE SERVICES PRIVATE LIMITED | KEP- Facade Cleaning System | Cleaning Work - SO | Sq.Ft | 15000 | 3.5 | 52500 | 9450 | 61950 | 2.5 | 15000 | 52500 | 9450 | 61950 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 30 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 0 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle Services | Transport charges-SOS | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 0 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle Services | Transport charges-SOS | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 2 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 2 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 2 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 2 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 16 Feb 2022
EAST POINT MARKET | 31 | 4 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Credle Shifting Charges Shifting for Sinage Work | Shifting Charges-SO | No. | 10 | 5000 | 50000 | 9000 | 59000 | 0 | 7 | 35000 | 6300 | 41300 | 3 | 17700 |  | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 31 | 0 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle Services | Dismentling & Installation work (L) | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Nov 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 0 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle Services | Rental Charges - So | Month | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 1 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Credle Shifting Charges Shifting for Sinage Work | Shifting Charges-SO | No. | 12 | 8000 | 96000 | 17280 | 113280 | 0 | 5 | 40000 | 7200 | 47200 | 7 | 66080 |  | 41.6667 |  | Dushant Gore | Swapnil Erande | construction open | 23 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 31 | 0 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle Services | Shifting Work BCE | No. | 1 | 9000 | 9000 | 1620 | 10620 | 0 | 1 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 0 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle Services | Shifting Work BCE | No. | 1 | 9000 | 9000 | 1620 | 10620 | 0 | 1 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 31 | 3 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 31 | 3 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 31 | 3 | 23 Nov 2021 | KAUSHAL CRADLE SERVICES | Cradle for Signages work at front side & railway side. | Rental Charges. | Month | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 0.5 | 15000 | 2700 | 17700 | 0.5 | 17700 |  | 50 |  | Dushant Gore | Swapnil Erande | construction open | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | 14'' Storage in 19 mm thk Comm. Ply | Sq.Ft | 33 | 1500 | 49500 | 8910 | 58410 | 0 | 33 | 49500 | 8910 | 58410 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | 16'' Storage in 19 mm thk Comm. Ply | Sq.Ft | 70 | 1500 | 105000 | 18900 | 123900 | 0 | 68 | 102000 | 18360 | 120360 | 2 | 3540 |  | 97.1429 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | 16'' Storage in 19 mm thk Comm. Ply | Sq.Ft | 77 | 1500 | 115500 | 20790 | 136290 | 0 | 77 | 115500 | 20790 | 136290 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Providing and removing of Storage Laminates | Sq.Ft | 56 | 350 | 19600 | 3528 | 23128 | 0 | 56 | 19600 | 3528 | 23128 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Cutting & Fixing old door | No. | 10 | 1200 | 12000 | 2160 | 14160 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | 14'' Storage in 19 mm thk Comm. Ply | Sq.Ft | 48.6 | 1500 | 72900 | 13122 | 86022 | 0 | 48.6 | 72900 | 13122 | 86022 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Reception Table (M+L) | No. | 1 | 24000 | 24000 | 4320 | 28320 | 0 | 1 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Pentry Shutter frame in 19 mm thk Comm. Ply | R.Ft | 12 | 7200 | 86400 | 15552 | 101952 | 0 | 12 | 86400 | 15552 | 101952 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Pedestal Single drawer in19 mm thk comm. Ply | No. | 2 | 11500 | 23000 | 4140 | 27140 | 0 | 2 | 23000 | 4140 | 27140 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Prov. & making Table with 25 mm thk Black Board | R.Ft | 18 | 3100 | 55800 | 10044 | 65844 | 0 | 16.0002 | 49600.62 | 8928.12 | 58528.74 | 1.9998 | 7315.26 |  | 88.89 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Seating with storage of 19 mm thk comm. Ply | R.Ft | 7 | 4300 | 30100 | 5418 | 35518 | 0 | 6 | 25800 | 4644 | 30444 | 1 | 5074 |  | 85.7143 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | 14'' Storage in 19 mm thk Comm. Ply | Sq.Ft | 30 | 1500 | 45000 | 8100 | 53100 | 0 | 30 | 45000 | 8100 | 53100 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Providing & Making Soft Board table | Sq.Ft | 41.4 | 170 | 7038 | 1266.84 | 8304.84 | 0 | 24.0037 | 4080.63 | 734.52 | 4815.15 | 17.3963 | 3489.69 |  | 57.98 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Sliding door in 35 mm thk board | Sq.Ft | 24.5 | 1400 | 34300 | 6174 | 40474 | 0 | 24.5 | 34300 | 6174 | 40474 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Providing and removing Work Station table laminates | No. | 2 | 10500 | 21000 | 3780 | 24780 | 0 | 2 | 21000 | 3780 | 24780 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 32 | 0 | 23 Nov 2021 | ANAND FURNITURE AND INTERIOR | KEP-Carpentry Work (M+L) | Providing and removing Table laminate | R.Ft | 15 | 1150 | 17250 | 3105 | 20355 | 0 | 15 | 17250 | 3105 | 20355 | 0 | 0 |  | 100 |  | runal kindalkar | skmishra | Construction | 23 Nov 2021 |  | 09 CARPENTRY WORK | Approved | skmishra
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.4278 | 6417 | 0 | 6417 | 0.5722 | 8583 |  | 42.78 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.4265 | 6397.5 | 0 | 6397.5 | 0.5735 | 8602.5 |  | 42.65 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.4989 | 7483.5 | 0 | 7483.5 | 0.5011 | 7516.5 |  | 49.89 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.4105 | 6157.5 | 0 | 6157.5 | 0.5895 | 8842.5 |  | 41.05 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.6173 | 9259.5 | 0 | 9259.5 | 0.3827 | 5740.5 |  | 61.73 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3033 | 4549.5 | 0 | 4549.5 | 0.6967 | 10450.5 |  | 30.33 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2618 | 3927 | 0 | 3927 | 0.7382 | 11073 |  | 26.18 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3234 | 4851 | 0 | 4851 | 0.6766 | 10149 |  | 32.34 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3325 | 4987.5 | 0 | 4987.5 | 0.6675 | 10012.5 |  | 33.25 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2866 | 4299 | 0 | 4299 | 0.7134 | 10701 |  | 28.66 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2066 | 3099 | 0 | 3099 | 0.7934 | 11901 |  | 20.66 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2305 | 3457.5 | 0 | 3457.5 | 0.7695 | 11542.5 |  | 23.05 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3612 | 5418 | 0 | 5418 | 0.6388 | 9582 |  | 36.12 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3983 | 5974.5 | 0 | 5974.5 | 0.6017 | 9025.5 |  | 39.83 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.6525 | 9787.5 | 0 | 9787.5 | 0.3475 | 5212.5 |  | 65.25 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.5 | 7500 | 0 | 7500 | 0.5 | 7500 |  | 50 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3966 | 5949 | 0 | 5949 | 0.6034 | 9051 |  | 39.66 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.5469 | 8203.5 | 0 | 8203.5 | 0.4531 | 6796.5 |  | 54.69 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3009 | 4513.5 | 0 | 4513.5 | 0.6991 | 10486.5 |  | 30.09 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.215 | 3225 | 0 | 3225 | 0.785 | 11775 |  | 21.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3317 | 4975.5 | 0 | 4975.5 | 0.6683 | 10024.5 |  | 33.17 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.5314 | 7971 | 0 | 7971 | 0.4686 | 7029 |  | 53.14 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3458 | 5187 | 0 | 5187 | 0.6542 | 9813 |  | 34.58 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 02 Mar 2024
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.6089 | 9133.5 | 0 | 9133.5 | 0.3911 | 5866.5 |  | 60.89 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2034 | 3051 | 0 | 3051 | 0.7966 | 11949 |  | 20.34 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.8114 | 12171 | 0 | 12171 | 0.1886 | 2829 |  | 81.14 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.4184 | 6276 | 0 | 6276 | 0.5816 | 8724 |  | 41.84 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2936 | 4404 | 0 | 4404 | 0.7064 | 10596 |  | 29.36 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.22 | 3300 | 0 | 3300 | 0.78 | 11700 |  | 22 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3298 | 4947 | 0 | 4947 | 0.6702 | 10053 |  | 32.98 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.5725 | 8587.5 | 0 | 8587.5 | 0.4275 | 6412.5 |  | 57.25 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.2538 | 3807 | 0 | 3807 | 0.7462 | 11193 |  | 25.38 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | Swapnil Erande
EAST POINT MARKET | 33 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 02 Mar 2024
EAST POINT MARKET | 33 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.3671 | 5506.5 | 0 | 5506.5 | 0.6329 | 9493.5 |  | 36.71 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.2605 | 5210 | 0 | 5210 | 0.7395 | 14790 |  | 26.05 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9004 | 18008 | 0 | 18008 | 0.0996 | 1992 |  | 90.04 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.3552 | 7104 | 0 | 7104 | 0.6448 | 12896 |  | 35.52 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.8561 | 8561 | 0 | 8561 | 0.1439 | 1439 |  | 85.61 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.821 | 16420 | 0 | 16420 | 0.179 | 3580 |  | 82.1 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9794 | 19588 | 0 | 19588 | 0.0206 | 412 |  | 97.94 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9802 | 19604 | 0 | 19604 | 0.0198 | 396 |  | 98.02 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.8168 | 16336 | 0 | 16336 | 0.1832 | 3664 |  | 81.68 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.2515 | 5030 | 0 | 5030 | 0.7485 | 14970 |  | 25.15 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.3335 | 6670 | 0 | 6670 | 0.6665 | 13330 |  | 33.35 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.2365 | 4730 | 0 | 4730 | 0.7635 | 15270 |  | 23.65 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9109 | 18218 | 0 | 18218 | 0.0891 | 1782 |  | 91.09 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9556 | 19112 | 0 | 19112 | 0.0444 | 888 |  | 95.56 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9984 | 9984 | 0 | 9984 | 0.0016 | 16 |  | 99.84 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Operating Expenses | Miscellaneous Expenses | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 0.9198 | 32193 | 0 | 32193 | 0.0802 | 2807 |  | 91.98 |  | chetan.jewalikar | chetan.jewalikar | construction open | 25 Nov 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9807 | 9807 | 0 | 9807 | 0.0193 | 193 |  | 98.07 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.5764 | 11528 | 0 | 11528 | 0.4236 | 8472 |  | 57.64 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.6284 | 12568 | 0 | 12568 | 0.3716 | 7432 |  | 62.84 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.2118 | 4236 | 0 | 4236 | 0.7882 | 15764 |  | 21.18 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.8803 | 8803 | 0 | 8803 | 0.1197 | 1197 |  | 88.03 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9883 | 19766 | 0 | 19766 | 0.0117 | 234 |  | 98.83 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.8592 | 17184 | 0 | 17184 | 0.1408 | 2816 |  | 85.92 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.8148 | 16296 | 0 | 16296 | 0.1852 | 3704 |  | 81.48 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.8379 | 16758 | 0 | 16758 | 0.1621 | 3242 |  | 83.79 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.2077 | 4154 | 0 | 4154 | 0.7923 | 15846 |  | 20.77 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9056 | 18112 | 0 | 18112 | 0.0944 | 1888 |  | 90.56 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 5 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.3954 | 7908 | 0 | 7908 | 0.6046 | 12092 |  | 39.54 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.1412 | 2824 | 0 | 2824 | 0.8588 | 17176 |  | 14.12 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 3 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.2362 | 4724 | 0 | 4724 | 0.7638 | 15276 |  | 23.62 |  | Aditya Chougule | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.9339 | 18678 | 0 | 18678 | 0.0661 | 1322 |  | 93.39 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 34 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 25 May 2022
EAST POINT MARKET | 34 | 4 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Marketing Infra Marketing Expenses/Misc | Marketing Operating Expenses | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.5552 | 11104 | 0 | 11104 | 0.4448 | 8896 |  | 55.52 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.655 | 6550 | 0 | 6550 | 0.345 | 3450 |  | 65.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.93 | 9300 | 0 | 9300 | 0.07 | 700 |  | 93 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.556 | 5560 | 0 | 5560 | 0.444 | 4440 |  | 55.6 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7 | 7000 | 0 | 7000 | 0.3 | 3000 |  | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.998 | 9980 | 0 | 9980 | 0.002 | 20 |  | 99.8 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 0 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.636 | 6360 | 0 | 6360 | 0.364 | 3640 |  | 63.6 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.2275 | 2275 | 0 | 2275 | 0.7725 | 7725 |  | 22.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7239 | 7239 | 0 | 7239 | 0.2761 | 2761 |  | 72.39 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9881 | 9881 | 0 | 9881 | 0.0119 | 119 |  | 98.81 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.164 | 1640 | 0 | 1640 | 0.836 | 8360 |  | 16.4 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.16 | 1600 | 0 | 1600 | 0.84 | 8400 |  | 16 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7591 | 7591 | 0 | 7591 | 0.2409 | 2409 |  | 75.91 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 1 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.75 | 7500 | 0 | 7500 | 0.25 | 2500 |  | 75 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 35 | 2 | 23 Nov 2021 | VIJAY KUMAR (STAFF) | Mall Maintenance Services | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.31 | 3100 | 0 | 3100 | 0.69 | 6900 |  | 31 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Nov 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 36 | 1 | 24 Nov 2021 | ANIL TRANSPORT SERVICE | Water Supply | Water Tanker | Trips | 120 | 1500 | 180000 | 0 | 180000 | 0 | 120 | 180000 | 0 | 180000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 29 Nov 2021 |  | UTI. Water Supply | Approved | chetan.jewalikar
EAST POINT MARKET | 36 | 2 | 24 Nov 2021 | ANIL TRANSPORT SERVICE | Water Supply | Water Tanker | Trips | 120 | 1500 | 180000 | 0 | 180000 | 0 | 120 | 180000 | 0 | 180000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Nov 2021 |  | UTI. Water Supply | Approved | Swapnil Erande
EAST POINT MARKET | 36 | 3 | 24 Nov 2021 | ANIL TRANSPORT SERVICE | Water Supply | Water Tanker | Trips | 120 | 1500 | 180000 | 0 | 180000 | 0 | 45 | 67500 | 0 | 67500 | 75 | 112500 |  | 37.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Nov 2021 |  | UTI. Water Supply | Approved | Swapnil Erande
EAST POINT MARKET | 36 | 0 | 24 Nov 2021 | ANIL TRANSPORT SERVICE | Water Supply | Water Tanker | Trips | 120 | 1500 | 180000 | 0 | 180000 | 0 | 119.9604 | 179940.6 | 0 | 179940.6 | 0.0396 | 59.4 |  | 99.967 |  | chetan.jewalikar | chetan.jewalikar | construction open | 29 Nov 2021 |  | UTI. Water Supply | Approved | chetan.jewalikar
EAST POINT MARKET | 37 | 0 | 26 Nov 2021 | SCHINDLER INDIA PVT. LTD. | KEP- Lift Maintenance | Lead Acid Battery 12V | No. | 2 | 2168.68 | 4337.36 | 780.72 | 5118.08 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 26 Nov 2021 |  | 18. Maintenance & Repair Work | Approved | skmishra
EAST POINT MARKET | 37 | 0 | 26 Nov 2021 | SCHINDLER INDIA PVT. LTD. | KEP- Lift Maintenance | Installation Charges | No. | 1 | 729.1 | 729.1 | 131.24 | 860.34 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 26 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 37 | 0 | 26 Nov 2021 | SCHINDLER INDIA PVT. LTD. | KEP- Lift Maintenance | Rope Pulley | No. | 1 | 13815.65 | 13815.65 | 2486.82 | 16302.47 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 26 Nov 2021 |  | 18. Maintenance & Repair Work | Approved | skmishra
EAST POINT MARKET | 37 | 0 | 26 Nov 2021 | SCHINDLER INDIA PVT. LTD. | KEP- Lift Maintenance | Safety Gear | No. | 1 | 4545 | 4545 | 818.1 | 5363.1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 26 Nov 2021 |  | 18. Maintenance & Repair Work | Approved | skmishra
EAST POINT MARKET | 37 | 0 | 26 Nov 2021 | SCHINDLER INDIA PVT. LTD. | KEP- Lift Maintenance | Wiring JHSG | No. | 1 | 1574.7 | 1574.7 | 283.44 | 1858.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 26 Nov 2021 |  | 18. Maintenance & Repair Work | Approved | skmishra
EAST POINT MARKET | 38 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Near Stair.No.1 Shubhsagar Storage WP Work-(No. | Brickbat W/P | Sq.Ft | 53.125 | 40 | 2125 | 382.5 | 2507.5 | 10 | 53.125 | 2125 | 382.5 | 2507.5 | 0 | 0 | Brick Bat Waterproofing work with red clay 4" thick bricks including base coat with C:M 1:4 proportion up to 15 mm thick, Laying red bricks above base coat with proper line level & slope of 100:1 to 120:1 then soaking for 24 hours to 36 hours, then final | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 38 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Near Stair.No.1 Shubhsagar Storage WP Work-(No. | Rough Shahabad W/P | Sq.Ft | 34.5 | 45 | 1552.5 | 279.46 | 1831.96 | 10 | 34.5 | 1552.5 | 279.46 | 1831.96 | 0 | 0 | Rough Shahabad Waterproofing with rough shahabad tile fixing with cement paste & packing inside at joint with 20mm metal & filling with cement paste with brush finish & after 24 hours filling/ pouring pure cement slurry inside, including proper cleaning, | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 06 WATERPROOFING WORK | Approved | skmishra
EAST POINT MARKET | 38 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Near Stair.No.1 Shubhsagar Storage WP Work-(No. | Lumpsum work- DCW | No. | 1 | 800 | 800 | 144 | 944 | 10 | 1 | 800 | 144 | 944 | 0 | 0 | Charges for inside tile breaking and cement grouting work, as per instructed by engineer Incharge. | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | DEV. Compound Wall | Approved | skmishra
EAST POINT MARKET | 38 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Near Stair.No.1 Shubhsagar Storage WP Work-(No. | Sand Face Plaster | Sq.Ft | 5 | 28 | 140 | 25.2 | 165.2 | 10 | 5 | 140 | 25.2 | 165.2 | 0 | 0 | Sand face plaster (Single Coat) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machin etc complete as per drawing. Loading, shi | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 05 GYPSUM & PLASTER | Approved | skmishra
EAST POINT MARKET | 38 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Near Stair.No.1 Shubhsagar Storage WP Work-(No. | IPS W/P | Sq.Ft | 50.625 | 25 | 1265.63 | 227.82 | 1493.45 | 10 | 50.625 | 1265.63 | 227.82 | 1493.45 | 0 | 0 | IPS Waterproofing with in situ concrete, including laying with proper line level & slope, ghotai with dry cement & broom/brush finish etc. Loading, shifting & unloading of estimated raw material from store to required place to be done by contractor. | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 06 WATERPROOFING WORK | Approved | skmishra
EAST POINT MARKET | 39 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP- Chequered Plate PCC,Base Coat,Bund Wall | PCC SOSt | Sq.Ft | 1779.66 | 25 | 44491.5 | 8008.48 | 52499.98 | 2.5 | 1661.804 | 41545.1 | 7478.14 | 49023.24 | 117.856 | 3476.74 |  | 93.3776 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Infrastructure | Approved | skmishra
EAST POINT MARKET | 40 | 1 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | 3rd Floor Misc work | Breaker-BC | No. | 15 | 1300 | 19500 | 0 | 19500 | 2.5 | 5.5 | 7150 | 0 | 7150 | 9.5 | 12350 |  | 36.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 40 | 0 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl Edge Trimix Breaking | Lumpsum work- DCW | No. | 1.475 | 1300 | 1917.5 | 0 | 1917.5 | 2.5 | 1.46 | 1898 | 0 | 1898 | 0.015 | 19.5 | Edge Trimix Breaking- 4" - 6" Deep and 6" - 8" wide along the periphery. ( 13 Days x 1300 Rs/Day ). | 98.9831 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 29 Nov 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 40 | 0 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Basement Fl Retaining Wall Plaster Breaking&Debris Shift | Breaking Of Plaster- BRE | Sq.Ft | 2937.13 | 10 | 29371.3 | 0 | 29371.3 | 2.5 | 1879.7632 | 18797.63 | 0 | 18797.63 | 1057.3668 | 10573.67 |  | 64 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 29 Nov 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 40 | 1 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | 3rd Floor Misc work | Mason - DCW | No. | 40 | 950 | 38000 | 0 | 38000 | 2.5 | 40 | 38000 | 0 | 38000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Nov 2021 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 40 | 1 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | 3rd Floor Misc work AAC Blockwork-(L) | Blockwork - USS | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 29 Nov 2021 |  | UTI. Solar System | Cancelled | DUSHANT.GORE | 17 Jul 2023
EAST POINT MARKET | 40 | 1 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | 3rd Floor Misc work | Helper - SM | No. | 40 | 600 | 24000 | 0 | 24000 | 2.5 | 40 | 24000 | 0 | 24000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Nov 2021 |  | UTI. Strom Line | Approved | Swapnil Erande
EAST POINT MARKET | 40 | 1 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | 3rd Floor Misc work 1st Floor Single Coat Plaster Work | Single Coat Plaster (L) | Sq.Ft | 1008.08 | 20 | 20161.6 | 0 | 20161.6 | 2.5 | 199.9999 | 4000 | 0 | 4000 | 808.0801 | 16161.6 |  | 19.8397 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Nov 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 40 | 1 | 26 Nov 2021 | SURESH KUMAR MURALIDHAR | 3rd Floor Misc work AAC Blockwork-(L) | Blockwork - USS | Sq.Ft | 544.54 | 20 | 10890.8 | 0 | 10890.8 | 2.5 | 0 | 0 | 0 | 0 | 544.54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Nov 2021 |  | UTI. Solar System | Approved | Swapnil Erande
EAST POINT MARKET | 41 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Terrace Floor Terrace Slope Provision on the existing Wa | Brickbat W/P | Sq.Ft | 280 | 40 | 11200 | 2016 | 13216 | 10 | 280 | 11200 | 2016 | 13216 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 41 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP- Sloping Roof Drain Channel(Gutters) | Waterproofing work- BCo | Sq.Ft | 230.4 | 25 | 5760 | 1036.8 | 6796.8 | 10 | 229.02 | 5725.5 | 1030.6 | 6756.1 | 1.38 | 40.7 |  | 99.401 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 41 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Terrace Floor Terrace Slope Provision on the existing Wa | Vata+BBM+Plaster Work | R.Ft | 27 | 60 | 1620 | 291.6 | 1911.6 | 10 | 26.64 | 1598.4 | 287.72 | 1886.12 | 0.36 | 25.48 |  | 98.6667 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 06 WATERPROOFING WORK | Approved | skmishra
EAST POINT MARKET | 41 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Terrace Floor Terrace New Waterproofing East&West Side a | Brickbat W/P | Sq.Ft | 120 | 40 | 4800 | 864 | 5664 | 10 | 120 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 41 | 0 | 26 Nov 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Basement Fl -Lift Pit Waterproofing | Incentive- | No. | 2 | 1100 | 2200 | 396 | 2596 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | DEV. Murum Filling | Approved | skmishra
EAST POINT MARKET | 42 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Misc Work Rework | Department Labour- BC | No. | 27 | 500 | 13500 | 0 | 13500 | 0 | 26.9988 | 13499.4 | 0 | 13499.4 | 0.0012 | 0.6 |  | 99.9956 |  | Avinash Padmanabha | skmishra | construction open |  |  | B.C. RCC Substructure | Approved | skmishra
EAST POINT MARKET | 42 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Misc Work Rework | Department Labour- BC | No. | 27 | 850 | 22950 | 0 | 22950 | 0 | 26.9988 | 22948.98 | 0 | 22948.98 | 0.0012 | 1.02 | Supply of Mason for Misc work on daily basis, as per approved attachted proposal. | 99.9956 |  | Avinash Padmanabha | skmishra | construction open |  |  | B.C. RCC Substructure | Approved | skmishra
EAST POINT MARKET | 42 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-1st&2nd Fl Granite Flooring Removing Work | Granite Flooring removing-BCV | Sq.Ft | 1120 | 15 | 16800 | 0 | 16800 | 2.5 | 1120 | 16800 | 0 | 16800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open |  |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 42 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- 1st&2nd Fl Granite Flooring Removing Work | Granite Flooring removing-BCV | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 27 Nov 2021
EAST POINT MARKET | 43 | 0 | 27 Nov 2021 | ABDUL SATTAR SHAIKH | Bldg SRA-OHWT&UGWT FRP Cover Fixing | Chamber Cover fixing-USL | No. | 26 | 800 | 20800 | 0 | 20800 | 2.5 | 26 | 20800 | 0 | 20800 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | UTI. Strom Line | Approved | skmishra
EAST POINT MARKET | 43 | 0 | 27 Nov 2021 | ABDUL SATTAR SHAIKH | Bldg SRA-OHWT&UGWT FRP Cover Fixing | Chamber Cover fixing-USL | No. | 15 | 800 | 12000 | 0 | 12000 | 2.5 | 15 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | UTI. Strom Line | Approved | skmishra
EAST POINT MARKET | 44 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | Damp Proof Course (L) | Sq.Ft | 12888.11 | 1.5 | 19332.17 | 0 | 19332.17 | 2.5 | 12888.1001 | 19332.15 | 0 | 19332.15 | 0.0099 | 0.01 |  | 99.9999 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 10 PAINTING WORK | Approved | skmishra
EAST POINT MARKET | 44 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | Apex Paint -1st Coat (L) | Sq.Ft | 12888.11 | 2 | 25776.22 | 0 | 25776.22 | 2.5 | 12888.1001 | 25776.2 | 0 | 25776.2 | 0.0099 | 0.02 |  | 99.9999 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 10 PAINTING WORK | Approved | skmishra
EAST POINT MARKET | 44 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | 1 Coat Primer (External) (L) - | Sq.Ft | 6444.05 | 1.5 | 9666.08 | 0 | 9666.08 | 2.5 | 6444.05 | 9666.08 | 0 | 9666.08 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 10 PAINTING WORK | Approved | skmishra
EAST POINT MARKET | 44 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | Apex Paint -2nd Coat (L) | Sq.Ft | 12888.11 | 2 | 25776.22 | 0 | 25776.22 | 2.5 | 12888.1001 | 25776.2 | 0 | 25776.2 | 0.0099 | 0.02 |  | 99.9999 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 10 PAINTING WORK | Approved | skmishra
EAST POINT MARKET | 45 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | Damp Proof Course (M) | Sq.Ft | 12888.11 | 1 | 12888.11 | 0 | 12888.11 | 0 | 12886.9552 | 12886.96 | 0 | 12886.96 | 1.1548 | 1.15 |  | 99.991 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 10 PAINTING WORK | Approved | skmishra
EAST POINT MARKET | 45 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | Crack Filling (M) | Sq.Ft | 12888.11 | 1 | 12888.11 | 0 | 12888.11 | 0 | 12886.9552 | 12886.96 | 0 | 12886.96 | 1.1548 | 1.15 |  | 99.991 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 12 MASONARY WORK | Approved | skmishra
EAST POINT MARKET | 45 | 0 | 27 Nov 2021 | AZAM KHAN | KEP- External Painting Work-(Sq.Ft) | 1 Coat Primer (External) (M) | Sq.Ft | 12888.11 | 1 | 12888.11 | 0 | 12888.11 | 0 | 12886.9552 | 12886.96 | 0 | 12886.96 | 1.1548 | 1.15 |  | 99.991 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 10 PAINTING WORK | Approved | skmishra
EAST POINT MARKET | 46 | 0 | 27 Nov 2021 | ABDUL KHALIQUE SHAIKH | KEP- Electrical&Plumbing Maintenance | Maintenance Work - SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Site Staff | Approved | skmishra
EAST POINT MARKET | 46 | 0 | 27 Nov 2021 | ABDUL KHALIQUE SHAIKH | KEP- Electrical&Plumbing Maintenance | Maintenance Work - SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Site Staff | Approved | skmishra
EAST POINT MARKET | 46 | 0 | 27 Nov 2021 | ABDUL KHALIQUE SHAIKH | KEP- Electrical&Plumbing Maintenance | Maintenance Work - SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Site Staff | Approved | skmishra
EAST POINT MARKET | 46 | 0 | 27 Nov 2021 | ABDUL KHALIQUE SHAIKH | KEP- Electrical&Plumbing Maintenance | Maintenance Work - SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Site Staff | Approved | skmishra
EAST POINT MARKET | 46 | 0 | 27 Nov 2021 | ABDUL KHALIQUE SHAIKH | KEP- Electrical&Plumbing Maintenance | Maintenance Work - SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Site Staff | Approved | skmishra
EAST POINT MARKET | 46 | 0 | 27 Nov 2021 | ABDUL KHALIQUE SHAIKH | KEP- Electrical&Plumbing Maintenance | Maintenance Work - SO | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | S OH Site Staff | Approved | skmishra
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Wall Premium Emulsion Pain | 1 Coat Primer (Water Base) (L) | Sq.Ft | 3580.74 | 1.25 | 4475.93 | 0 | 4475.93 | 2.5 | 3580.74 | 4475.93 | 0 | 4475.93 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Ceiling Premium Emulsion P | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 754.6 | 1.25 | 943.25 | 0 | 943.25 | 2.5 | 0 | 0 | 0 | 0 | 754.6 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Wall Premium Emulsion Pain | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 3580.74 | 1.25 | 4475.93 | 0 | 4475.93 | 2.5 | 2667.9478 | 3334.93 | 0 | 3334.93 | 912.7922 | 1140.99 |  | 74.5083 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Wall Premium Emulsion Pain | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 3580.74 | 1.25 | 4475.93 | 0 | 4475.93 | 2.5 | 0 | 0 | 0 | 0 | 3580.74 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Ceiling Premium Emulsion P | Scrapping with 1st Coat Putty | Sq.Ft | 754.6 | 1.25 | 943.25 | 0 | 943.25 | 2.5 | 754.6 | 943.25 | 0 | 943.25 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Wall Premium Emulsion Pain | Scrapping with 2nd Coat Putty | Sq.Ft | 3580.74 | 1.25 | 4475.93 | 0 | 4475.93 | 2.5 | 3580.74 | 4475.93 | 0 | 4475.93 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Wall Premium Emulsion Pain | Scrapping with 1st Coat Putty | Sq.Ft | 3580.74 | 1.25 | 4475.93 | 0 | 4475.93 | 2.5 | 3580.74 | 4475.93 | 0 | 4475.93 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Ceiling Premium Emulsion P | Scrapping with 2nd Coat Putty | Sq.Ft | 754.6 | 1.25 | 943.25 | 0 | 943.25 | 2.5 | 754.6 | 943.25 | 0 | 943.25 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Ceiling Premium Emulsion P | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 754.6 | 1.25 | 943.25 | 0 | 943.25 | 2.5 | 0 | 0 | 0 | 0 | 754.6 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 47 | 0 | 27 Nov 2021 | AZAM KHAN | KEP-3rd Fl Mall Management Office Ceiling Premium Emulsion P | 1 Coat Primer (Water Base) (L) | Sq.Ft | 754.6 | 1.25 | 943.25 | 0 | 943.25 | 2.5 | 754.6 | 943.25 | 0 | 943.25 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 48 | 0 | 27 Nov 2021 | SAHARA ENGINEERING | KEP-Aluminium Ventilators | Ventilator (M+L) | Sq.Ft | 450 | 450 | 202500 | 36450 | 238950 | 0 | 27 | 12150 | 2187 | 14337 | 423 | 224613 |  | 6 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | DEV. Landscape/Equipment | Approved | skmishra
EAST POINT MARKET | 49 | 0 | 27 Nov 2021 | SAI ENTERPRISES. | KEP- Escalators Area Light Fittings | LIGHTS | No. | 36 | 535 | 19260 | 3466.8 | 22726.8 | 0 | 36 | 19260 | 3466.8 | 22726.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | MKT. Media | Approved | skmishra
EAST POINT MARKET | 49 | 0 | 27 Nov 2021 | SAI ENTERPRISES. | KEP-Gr Fl Sample Lights | LIGHTS | No. | 1 | 3070 | 3070 | 552.6 | 3622.6 | 0 | 1 | 3070 | 552.6 | 3622.6 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | MKT. Media | Approved | skmishra
EAST POINT MARKET | 49 | 0 | 27 Nov 2021 | SAI ENTERPRISES. | KEP- Escalators Area Light Fittings | LIGHTS | No. | 2 | 677 | 1354 | 243.72 | 1597.72 | 0 | 2 | 1354 | 243.72 | 1597.72 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | MKT. Media | Approved | skmishra
EAST POINT MARKET | 49 | 0 | 27 Nov 2021 | SAI ENTERPRISES. | KEP-Gr Fl Sample Lights | LIGHTS | No. | 2 | 555 | 1110 | 199.8 | 1309.8 | 0 | 2 | 1110 | 199.8 | 1309.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | MKT. Media | Approved | skmishra
EAST POINT MARKET | 50 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Fl-Toilet Demolition Work | Rabit Shifting work | Sq.Ft | 2322.01 | 3 | 6966.03 | 0 | 6966.03 | 2.5 | 2322.01 | 6966.03 | 0 | 6966.03 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 50 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Fl-Toilet Demolition Work | Removing Dado glazed tiles | Sq.Ft | 2322.01 | 7 | 16254.07 | 0 | 16254.07 | 2.5 | 2322 | 16254 | 0 | 16254 | 0.01 | 0.07 |  | 99.9996 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | Admin. Indirect Expenses | Approved | skmishra
EAST POINT MARKET | 50 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP Gr Fl-Plaza FRP Chamber Fixing | Chamber Fixing - Mkt | No. | 4 | 800 | 3200 | 0 | 3200 | 2.5 | 3 | 2400 | 0 | 2400 | 1 | 800 |  | 75 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | skmishra
EAST POINT MARKET | 50 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Fl-Toilet Demolition Work | Rabit Shifting work | Sq.Ft | 736.68 | 3 | 2210.04 | 0 | 2210.04 | 2.5 | 729.3333 | 2188 | 0 | 2188 | 7.3467 | 22.04 |  | 99.0027 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 50 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Gr Fl-Toilet Demolition Work | Removing Tilling Work - DSP | Sq.Ft | 736.68 | 7 | 5156.76 | 0 | 5156.76 | 2.5 | 729.2857 | 5105 | 0 | 5105 | 7.3943 | 51.76 |  | 98.9963 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | DEV. Swimming Pool | Approved | skmishra
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | PCC | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | B.C. Building Common Items | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | Blockwork 5" - BC - | Sq.Ft | 154.08 | 11 | 1694.88 | 0 | 1694.88 | 2.5 | 0 | 0 | 0 | 0 | 154.08 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. BBM, Plaster, POP | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | Brickwork 9" - SO | Sq.Ft | 39.36 | 14 | 551.04 | 0 | 551.04 | 2.5 | 39.36 | 551.04 | 0 | 551.04 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | Trimix Work | Sq.Ft | 133 | 10 | 1330 | 0 | 1330 | 2.5 | 133 | 1330 | 0 | 1330 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | UTI. Drainage | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | PCC | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Laying of 3" to 6" thick PCC including Mixing by manual ,Concrete Mixer etc. with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting | 0 |  | Avinash Padmanabha |  | construction open |  |  | B.C. Building Common Items | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-Scaffolding Work | Scaffolding work | Sq.Ft | 1375 | 5 | 6875 | 0 | 6875 | 0 | 0 | 0 | 0 | 0 | 1375 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. RCC Superstructure | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | PCC | Sq.Ft | 47.5 | 6 | 285 | 0 | 285 | 2.5 | 47.5 | 285 | 0 | 285 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | Ramp Area Ramp Front Portion Work(Civil Work)-(No.) | Soling Work -SOSB | Sq.Ft | 279.76 | 5 | 1398.8 | 0 | 1398.8 | 0 | 279.76 | 1398.8 | 0 | 1398.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | Sand Face Plaster | Sq.Ft | 308 | 15 | 4620 | 0 | 4620 | 2.5 | 0 | 0 | 0 | 0 | 308 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- Ramp Front Portion Work(Civil Work)-(No.) | Cement Ghotai | Sq.Ft | 25.27 | 12 | 303.24 | 0 | 303.24 | 2.5 | 25.27 | 303.24 | 0 | 303.24 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 0 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP- 6th Slab Front Gutter Concreting Work | Concreting Work-Dld | Sq.Ft | 216 | 10 | 2160 | 0 | 2160 | 0 | 216 | 2160 | 0 | 2160 | 0 | 0 | Laying of Concrete and Shuttering work for 6th slab front side gutter of specified grade of concrete including compaction by vibrator, with proper line level and roughening them if special finish is to be provided (All raw material /RMC will be provided b | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 51 | 1 | 27 Nov 2021 | SURESH KUMAR MURALIDHAR | KEP-2nd Fl Blockwork-100mm | Blockwork 4" - BC | Sq.Ft | 17888.69 | 14 | 250441.66 | 0 | 250441.66 | 2.5 | 16289.3881 | 228051.43 | 0 | 228051.43 | 1599.3019 | 22390.23 |  | 91.0597 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 0 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.8854 | 4427 | 0 | 4427 | 0.1146 | 573 |  | 88.54 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.805 | 8050 | 0 | 8050 | 0.195 | 1950 |  | 80.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6886 | 6886 | 0 | 6886 | 0.3114 | 3114 |  | 68.86 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.578 | 5780 | 0 | 5780 | 0.422 | 4220 |  | 57.8 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6321 | 6321 | 0 | 6321 | 0.3679 | 3679 |  | 63.21 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6813 | 6813 | 0 | 6813 | 0.3187 | 3187 |  | 68.13 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9612 | 9612 | 0 | 9612 | 0.0388 | 388 |  | 96.12 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6964 | 6964 | 0 | 6964 | 0.3036 | 3036 |  | 69.64 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7365 | 7365 | 0 | 7365 | 0.2635 | 2635 |  | 73.65 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9112 | 9112 | 0 | 9112 | 0.0888 | 888 |  | 91.12 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 0 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.8874 | 4437 | 0 | 4437 | 0.1126 | 563 |  | 88.74 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.5546 | 5546 | 0 | 5546 | 0.4454 | 4454 |  | 55.46 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 0 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.8786 | 4393 | 0 | 4393 | 0.1214 | 607 |  | 87.86 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6768 | 6768 | 0 | 6768 | 0.3232 | 3232 |  | 67.68 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9883 | 9883 | 0 | 9883 | 0.0117 | 117 |  | 98.83 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7824 | 7824 | 0 | 7824 | 0.2176 | 2176 |  | 78.24 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6654 | 6654 | 0 | 6654 | 0.3346 | 3346 |  | 66.54 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 1 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.664 | 6640 | 0 | 6640 | 0.336 | 3360 |  | 66.4 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.3645 | 3645 | 0 | 3645 | 0.6355 | 6355 |  | 36.45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 3 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.411 | 4110 | 0 | 4110 | 0.589 | 5890 |  | 41.1 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 52 | 2 | 27 Nov 2021 | ZUBAIR AALAM MUSTAQUE AHMED ANSARI | Site Expenses Tea Expenses | Tea Expenses-SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7892 | 7892 | 0 | 7892 | 0.2108 | 2108 |  | 78.92 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 53 | 0 | 29 Nov 2021 | ABDUL SATTAR SHAIKH | KEP- Railay Side Debris Cleaning &Dry Material Shifting | DumperTrips | Trips | 3 | 6000 | 18000 | 0 | 18000 | 0 | 3 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | MKT. Marketing Infrastructure | Approved | skmishra
EAST POINT MARKET | 53 | 0 | 29 Nov 2021 | ABDUL SATTAR SHAIKH | KEP- Fatima Side Cleaning | Lumpsum work- DCW | No. | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | DEV. Compound Wall | Approved | skmishra
EAST POINT MARKET | 53 | 0 | 29 Nov 2021 | ABDUL SATTAR SHAIKH | KEP- Railay Side Debris Cleaning &Dry Material Shifting | JCB Charges.. | No. | 1 | 8000 | 8000 | 0 | 8000 | 0 | 1 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 01 EARTHWORK & ROADWORK | Approved | skmishra
EAST POINT MARKET | 54 | 0 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 0 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 2 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 3 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 0 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 4 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 3 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 2 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 0 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 0 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 2 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 4 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 2 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 4 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 3 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 3 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 4 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 4 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 2 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 0 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Staff Conveyance &Transport | Staff Conveyance - SO | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | S OH Conveyance & Transport | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 3 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 4 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 1 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | chetan.jewalikar
EAST POINT MARKET | 54 | 3 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 54 | 2 | 29 Nov 2021 | RAFIULLAH EHSANULLAH | Travelling Expenses | Travelling Allowance | Month | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | Mall Maintenance Departmetal work | Departmental Labour- Pair | Pair | 50 | 2200 | 110000 | 0 | 110000 | 0 | 28 | 61600 | 0 | 61600 | 22 | 48400 |  | 56 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 1 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | KEP-3rd Fl Mall Management Office Tiling work | Vitrified Skirting BC | R.Ft | 271.41 | 28 | 7599.48 | 0 | 7599.48 | 2.5 | 271.41 | 7599.48 | 0 | 7599.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Granite Door Frame- BCV | R.Ft | 81 | 60 | 4860 | 0 | 4860 | 2.5 | 75.4394 | 4526.36 | 0 | 4526.36 | 5.5606 | 333.64 |  | 93.1351 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Dado Fixing | Sq.Ft | 30 | 30 | 900 | 0 | 900 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Vitrified Flooring 800x800- BC | Sq.Ft | 596.056 | 28 | 16689.57 | 0 | 16689.57 | 2.5 | 596.056 | 16689.57 | 0 | 16689.57 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Dado Fixing | Sq.Ft | 273.83 | 30 | 8214.9 | 0 | 8214.9 | 2.5 | 213.7728 | 6413.18 | 0 | 6413.18 | 60.0572 | 1801.72 |  | 78.0677 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 1 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | KEP-3rd Fl Mall Management Office Tiling work | Dado BC | Sq.Ft | 34.04 | 28 | 953.12 | 0 | 953.12 | 2.5 | 34.04 | 953.12 | 0 | 953.12 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | Basement Storage Toilet Making | Ceramic Flooring 12"X12" - ULT | Sq.Ft | 60.39 | 28 | 1690.92 | 0 | 1690.92 | 2.5 | 60.39 | 1690.92 | 0 | 1690.92 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Granite Skirting | R.Ft | 9.5 | 50 | 475 | 0 | 475 | 2.5 | 9.5 | 475 | 0 | 475 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 0 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | KEP-4th Floor 4th Fl-Toilet Dado &Flooring (OC Purpose) | Ceramic Flooring BC | Sq.Ft | 438.53 | 28 | 12278.84 | 0 | 12278.84 | 2.5 | 219.27 | 6139.56 | 0 | 6139.56 | 219.26 | 6139.28 |  | 50.0011 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 55 | 0 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | KEP-4th Floor 4th Fl-Toilet Dado &Flooring (OC Purpose) | Dado BC | Sq.Ft | 1341.26 | 30 | 40237.8 | 0 | 40237.8 | 2.5 | 1005.92 | 30177.6 | 0 | 30177.6 | 335.34 | 10060.2 |  | 74.9981 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Granite Patta -H - BCo | R.Ft | 36.08 | 60 | 2164.8 | 0 | 2164.8 | 2.5 | 36.08 | 2164.8 | 0 | 2164.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 1 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | KEP-3rd Fl Mall Management Office Tiling work | Granite Kitchen Otta BC | R.Ft | 11.5 | 800 | 9200 | 0 | 9200 | 2.5 | 11.5 | 9200 | 0 | 9200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Dado Fixing | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Dec 2021 |  | 11 TILING WORK | Cancelled | Dushant Gore | 05 Aug 2022
EAST POINT MARKET | 55 | 1 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | KEP-3rd Fl Mall Management Office Tiling work | Vitrified Flooring -BC | Sq.Ft | 815.12 | 28 | 22823.36 | 0 | 22823.36 | 2.5 | 815.12 | 22823.36 | 0 | 22823.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Vitrified Flooring work | Sq.Ft | 127.87 | 28 | 3580.36 | 0 | 3580.36 | 2.5 | 85.6899 | 2399.32 | 0 | 2399.32 | 42.1801 | 1181.04 |  | 67.0133 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Granite Flooring | Sq.Ft | 142.08 | 60 | 8524.8 | 0 | 8524.8 | 2.5 | 142.08 | 8524.8 | 0 | 8524.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | Basement Storage Toilet Making | Granite Door Frame- BCV | R.Ft | 66.33 | 60 | 3979.8 | 0 | 3979.8 | 2.5 | 66.33 | 3979.8 | 0 | 3979.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Granite Kitchen Otta BC | R.Ft | 9 | 800 | 7200 | 0 | 7200 | 2.5 | 9 | 7200 | 0 | 7200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | Basement Storage Toilet Making | Dado Fixing | Sq.Ft | 315.17 | 30 | 9455.1 | 0 | 9455.1 | 2.5 | 315.1507 | 9454.52 | 0 | 9454.52 | 0.0193 | 0.58 |  | 99.9939 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 55 | 2 | 29 Nov 2021 | ATIULLAH SHAFI MOHD SIDDIQUI | 4th Floor Show office Flooring work | Vitrified Skirting BC | R.Ft | 68.28 | 28 | 1911.84 | 0 | 1911.84 | 2.5 | 68.28 | 1911.84 | 0 | 1911.84 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 56 | 5 | 29 Nov 2021 | SAHARA ENGINEERING | Main Entry Mini Gate Fin Type ACP Work - 1 Sq.Ft | ACP Work- (L) | Sq.Ft | 152 | 150 | 22800 | 4104 | 26904 | 2.5 | 106.4 | 15960 | 2872.8 | 18832.8 | 45.6 | 8071.2 |  | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 56 | 3 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby ACP Sheet Fixing work | False Ceiling (l) -BC | Sq.Ft | 899 | 73.5 | 66076.5 | 11893.78 | 77970.28 | 2.5 | 899 | 66076.5 | 11893.78 | 77970.28 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 56 | 3 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby ACP Sheet Fixing work | ACP False Ceiling (L) | Sq.Ft | 0 | 73.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Dec 2021 |  | No category | Cancelled | skmishra | 11 Apr 2022
EAST POINT MARKET | 56 | 3 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby ACP Sheet Fixing work | ACP Sheet (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Dec 2021 |  | B.C. Building Common Items | Cancelled | skmishra | 11 Apr 2022
EAST POINT MARKET | 56 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Periphery Area Wall | 12mm Toughned Glass work (L) | Sq.Ft | 1132.37 | 150 | 169855.5 | 30574 | 200429.5 | 2.5 | 1126.3571 | 168953.57 | 30411.64 | 199365.21 | 6.0129 | 1064.3 |  | 99.469 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 56 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (l) -BC | Sq.Ft | 1039.56 | 73.5 | 76407.66 | 13753.38 | 90161.04 | 2.5 | 1039.56 | 76407.66 | 13753.38 | 90161.04 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 56 | 5 | 29 Nov 2021 | SAHARA ENGINEERING | Main Entry Mini Gate Regular ACP Work - 1 Sq.Ft | ACP Work- (L) | Sq.Ft | 248 | 75 | 18600 | 3348 | 21948 | 2.5 | 173.6 | 13020 | 2343.6 | 15363.6 | 74.4 | 6584.4 |  | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 56 | 1 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling Rate Diff (M) | Sq.Ft | 1039.56 | 10 | 10395.6 | 1871.2 | 12266.8 | 0 | 1039.56 | 10395.6 | 1871.2 | 12266.8 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 02 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 56 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-3rd Fl Atrium Periphery Area Glass Wall | 12mm Toughned Glass work (L) | Sq.Ft | 1000.45 | 150 | 150067.5 | 27012.16 | 177079.66 | 2.5 | 1000.45 | 150067.5 | 27012.16 | 177079.66 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 56 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Cable Tray Covered By ACP Sheet | ACP Work- (L) | Sq.Ft | 1043.03 | 70 | 73012.1 | 13142.18 | 86154.28 | 2.5 | 0 | 0 | 0 | 0 | 1043.03 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 02 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 56 | 1 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (m) -BC | Sq.Ft | 2102.44 | 181.5 | 381592.86 | 68686.72 | 450279.58 | 0 | 2102.44 | 381592.86 | 68686.72 | 450279.58 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 02 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 56 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (L)-BCo | Sq.Ft | 2222.5 | 60 | 133350 | 24003 | 157353 | 2.5 | 2028.9958 | 121739.75 | 21913.16 | 143652.91 | 193.5042 | 13700.09 |  | 91.2934 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 56 | 2 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-3rd Fl Mall Management Office Door Work | Glass Door (M+L)- DEV | Sq.Ft | 127 | 720 | 91440 | 16459.2 | 107899.2 | 2.5 | 127 | 91440 | 16459.2 | 107899.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Dec 2021 |  | DEV. Club House | Approved | chetan.jewalikar
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Acrylic sheet (M+L) | Sq.Ft | 64 | 85 | 5440 | 979.2 | 6419.2 | 2.5 | 64 | 5440 | 979.2 | 6419.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | SS Angle (M+L) | Sq.Ft | 57.6 | 1200 | 69120 | 12441.6 | 81561.6 | 2.5 | 57.6 | 69120 | 12441.6 | 81561.6 | 0 | 0 | Structural work, ACP & CNC work to be done with specified angle, plumb, line level & proper Alignment. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 3 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (M)-BCo | Sq.Ft | 2222.5 | 195 | 433387.5 | 78009.76 | 511397.26 | 0 | 2029.0158 | 395658.08 | 71218.46 | 466876.54 | 193.4842 | 44520.72 |  | 91.2943 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Fitting & Removing | No. | 1 | 2500 | 2500 | 450 | 2950 | 0 | 1 | 2500 | 450 | 2950 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 5 | 29 Nov 2021 | SAHARA ENGINEERING | Main Entry Mini Gate Regular ACP Work - 1 Sq.Ft | ACP Work- (M) | Sq.Ft | 248 | 175 | 43400 | 7812 | 51212 | 0 | 173.6 | 30380 | 5468.4 | 35848.4 | 74.4 | 15363.6 |  | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 2 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby ACP Sheet Fixing work | False Ceiling (m) -BC | Sq.Ft | 899 | 181.5 | 163168.5 | 29370.34 | 192538.84 | 0 | 899 | 163168.5 | 29370.34 | 192538.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (m) -BC | Sq.Ft | 1039.56 | 171.5 | 178284.54 | 32091.22 | 210375.76 | 0 | 1039.56 | 178284.54 | 32091.22 | 210375.76 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Transportaion | No. | 1 | 3500 | 3500 | 630 | 4130 | 0 | 1 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Cutting CNC Sheet (L) - Sq.Ft | Sq.Ft | 300 | 48.33 | 14499 | 2609.82 | 17108.82 | 0 | 300 | 14499 | 2609.82 | 17108.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 1 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (l) -BC | Sq.Ft | 2102.44 | 73.5 | 154529.34 | 27815.28 | 182344.62 | 2.5 | 2102.44 | 154529.34 | 27815.28 | 182344.62 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 30 Nov 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 57 | 3 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Transportaion | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Transportaion | No. | 1 | 7500 | 7500 | 1350 | 8850 | 0 | 1 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 3 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | CNC Cut Jali (M+L) | Sq.Ft | 444.5 | 1200 | 533400 | 96012 | 629412 | 0 | 412.7698 | 495323.76 | 89158.28 | 584482.04 | 31.7302 | 44929.96 |  | 92.8616 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-3rd Fl Atrium Periphery Area Glass Wall | 12mm Toughned Glass work (M) | Sq.Ft | 1000.45 | 350 | 350157.5 | 63028.36 | 413185.86 | 0 | 1000.45 | 350157.5 | 63028.36 | 413185.86 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 57 | 4 | 29 Nov 2021 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Lumpsum work- DCW | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Nov 2021 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 2 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby ACP Sheet Fixing work | ACP False Ceiling (M) | Sq.Ft | 0 | 181.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Nov 2021 |  | No category | Cancelled | skmishra | 11 Apr 2022
EAST POINT MARKET | 57 | 5 | 29 Nov 2021 | SAHARA ENGINEERING | Main Entry Mini Gate Fin Type ACP Work - 1 Sq.Ft | ACP Work- (M) | Sq.Ft | 152 | 350 | 53200 | 9576 | 62776 | 0 | 106.4 | 37240 | 6703.2 | 43943.2 | 45.6 | 18832.8 |  | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 57 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Periphery Area Wall | 12mm Toughned Glass work (M) | Sq.Ft | 1132.37 | 350 | 396329.5 | 71339.32 | 467668.82 | 0 | 1126.3571 | 394224.99 | 70960.5 | 465185.49 | 6.0129 | 2483.34 |  | 99.469 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 57 | 0 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Cable Tray Covered By ACP Sheet | ACP Work- (M) | Sq.Ft | 1043.03 | 160 | 166884.8 | 30039.26 | 196924.06 | 0 | 0 | 0 | 0 | 0 | 1043.03 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 30 Nov 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | skmishra
EAST POINT MARKET | 57 | 2 | 29 Nov 2021 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby ACP Sheet Fixing work | ACP Sheet (M) | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Nov 2021 |  | B.C. Building Common Items | Cancelled | skmishra | 11 Apr 2022
EAST POINT MARKET | 58 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (M) - SOSB | No. | 231 | 300 | 69300 | 12474 | 81774 | 0 | 231 | 69300 | 12474 | 81774 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 58 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (M) - SOSB | No. | 61.6 | 800 | 49280 | 8870.4 | 58150.4 | 0 | 61.6 | 49280 | 8870.4 | 58150.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 58 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fabrication work (M) | Kgs | 0 | 84 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 01 Dec 2021 |  | Admin. Direct Expenses | Cancelled | Avinash Padmanabha | 01 Dec 2021
EAST POINT MARKET | 58 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (M) - SOSB | No. | 60 | 70 | 4200 | 756 | 4956 | 0 | 60 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 01 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 58 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Chequered Plate Fixing between Facade&Beam &escalator | Fastner (M) - SOSB | No. | 380 | 20 | 7600 | 1368 | 8968 | 0 | 0 | 0 | 0 | 0 | 380 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 01 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 58 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (M) - SOSB | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Dec 2021 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 11 Apr 2022
EAST POINT MARKET | 58 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Chequered Plate Fixing between Facade&Beam &escalator | Fastner (M) - SOSB | No. | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 01 Dec 2021 |  | S OH Infrastructure | Cancelled | Avinash Padmanabha | 01 Dec 2021
EAST POINT MARKET | 58 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (M) - SOSB | No. | 24 | 70 | 1680 | 302.4 | 1982.4 | 0 | 24 | 1680 | 302.4 | 1982.4 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 01 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 58 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fabrication work (M) | Kgs | 3650.9 | 84 | 306675.6 | 55201.6 | 361877.2 | 0 | 3650.9 | 306675.6 | 55201.6 | 361877.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Dec 2021 |  | Admin. Direct Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 58 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fabrication work (M) | Kgs | 4085 | 84 | 343140 | 61765.2 | 404905.2 | 0 | 4085 | 343140 | 61765.2 | 404905.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 01 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 58 | 2 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fabrication Work (M) (Rate Diff.) | Kgs | 7735.9 | 35 | 270756.5 | 48736.18 | 319492.68 | 0 | 7735.8992 | 270756.47 | 48736.16 | 319492.63 | 0.0008 | 0.05 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Dec 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 58 | 2 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl Ent Canopy at Gr Fl Railway Side (MS Work) | Fabrication Work (M) (Rate Diff.) | Kgs | 190 | 35 | 6650 | 1197 | 7847 | 0 | 190 | 6650 | 1197 | 7847 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Dec 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 58 | 2 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Rolling Shutter Rate Diff.(M) | Sq.Ft | 680 | 30 | 20400 | 3672 | 24072 | 0 | 680 | 20400 | 3672 | 24072 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 59 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fabrication work (L) | Kgs | 4085 | 21 | 85785 | 15441.3 | 101226.3 | 2.5 | 4085 | 85785 | 15441.3 | 101226.3 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 59 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Chequered Plate Fixing between Facade&Beam &escalator | Transport Charges | No. | 1 | 3500 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 59 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fabrication work (L) | Kgs | 3650.9 | 21 | 76668.9 | 13800.4 | 90469.3 | 2.5 | 3650.9 | 76668.9 | 13800.4 | 90469.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 59 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (L) - SOSB | No. | 231 | 60 | 13860 | 2494.8 | 16354.8 | 2.5 | 231 | 13860 | 2494.8 | 16354.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 59 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (L) - SOSB | No. | 60 | 20 | 1200 | 216 | 1416 | 2.5 | 60 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 59 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (L) - SOSB | No. | 61.6 | 200 | 12320 | 2217.6 | 14537.6 | 2.5 | 61.6 | 12320 | 2217.6 | 14537.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 59 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Chequered Plate Fixing between Facade&Beam &escalator | Fastner (L) - SOSB | No. | 492 | 20 | 9840 | 1771.2 | 11611.2 | 2.5 | 0 | 0 | 0 | 0 | 492 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 59 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Fastner (L) - SOSB | No. | 24 | 20 | 480 | 86.4 | 566.4 | 2.5 | 24 | 480 | 86.4 | 566.4 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 59 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Chequered Plate Fixing between Facade&Beam &escalator | Fabrication work (L) | Kgs | 3073.52 | 21 | 64543.92 | 11617.9 | 76161.82 | 2.5 | 0 | 0 | 0 | 0 | 3073.52 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 59 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Transport Charges | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 60 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | Fabrication Work (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | DEV. Ext Development | Cancelled | Avinash Padmanabha | 01 Dec 2021
EAST POINT MARKET | 60 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | Fastner (M) - SOSB | No. | 2304 | 20 | 46080 | 0 | 46080 | 0 | 0 | 0 | 0 | 0 | 2304 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 60 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | Deck Sheet (M) | Kgs | 806.4 | 65 | 52416 | 0 | 52416 | 0 | 0 | 0 | 0 | 0 | 806.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 60 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | Fabrication Work (M) | Kgs | 4234.94 | 52 | 220216.88 | 0 | 220216.88 | 0 | 0 | 0 | 0 | 0 | 4234.94 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Ext Development | Approved | chetan.jewalikar
EAST POINT MARKET | 61 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | RCC Work Lumpsum-BRE | No. | 142 | 1000 | 142000 | 0 | 142000 | 2.5 | 49.7 | 49700 | 0 | 49700 | 92.3 | 92300 |  | 35 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 61 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | Waterproofing work lumpsum- ARW | No. | 192 | 500 | 96000 | 0 | 96000 | 2.5 | 0 | 0 | 0 | 0 | 192 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 61 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | Bldg SRA Duct Closing Work | Fabrication work lumpsum -SOSB | No. | 167 | 2000 | 334000 | 0 | 334000 | 2.5 | 33 | 66000 | 0 | 66000 | 134 | 268000 |  | 19.7605 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 62 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | KEP- Plumbing &labour work for Handicap Ramp | Lumpsum work- DCW | No. | 1 | 3500 | 3500 | 0 | 3500 | 2.5 | 0.7142 | 2499.7 | 0 | 2499.7 | 0.2858 | 1000.3 |  | 71.42 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 01 Dec 2021
EAST POINT MARKET | 62 | 0 | 01 Dec 2021 | ABDUL SATTAR SHAIKH | KEP- Plumbing &labour work for Handicap Ramp | Lumpsum work- DCW | No. | 0.5 | 4000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 0.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | DEV. Compound Wall | Approved | Avinash Padmanabha | 01 Dec 2021
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Labour Lumsum | No. | 3 | 1000 | 3000 | 540 | 3540 | 2.5 | 3 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl-Staircase No.1 MS Door Cutting for WP | Lumpsum work- DCW | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Barricating Work (L) - SO | Kgs | 509.191 | 21 | 10693.01 | 1924.74 | 12617.75 | 2.5 | 509.191 | 10693.01 | 1924.74 | 12617.75 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Plumbing Line SRA Extra Support | Fabrication work (M) | Kgs | 450 | 84 | 37800 | 6804 | 44604 | 0 | 0 | 0 | 0 | 0 | 450 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Lumpsum - Dld | No. | 1 | 1000 | 1000 | 180 | 1180 | 0 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl-Staircase No.1 MS Door Cutting for WP | Lumpsum work- DCW | No. | 0 | 6000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open |  |  | DEV. Compound Wall | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Lumpsum - Dld | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | Plumbing Line SRA Extra Support | Fabrication work (L) | Kgs | 450 | 21 | 9450 | 1701 | 11151 | 2.5 | 0 | 0 | 0 | 0 | 450 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | M.S.Chain Fixing (M+L) | R.Ft | 20 | 80 | 1600 | 288 | 1888 | 2.5 | 20 | 1600 | 288 | 1888 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fastner (M+L) | No. | 80 | 45 | 3600 | 648 | 4248 | 2.5 | 80 | 3600 | 648 | 4248 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Fabrication work Removing | Kgs | 805.4 | 12 | 9664.8 | 1739.66 | 11404.46 | 0 | 805.4 | 9664.8 | 1739.66 | 11404.46 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 63 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Common Activity Standay Making MS Pipe | Fabrication work lumpsum -SOSB | No. | 20 | 550 | 11000 | 1980 | 12980 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 63 | 1 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP MS Work Fabrication work | Flex Framing | Sq.Ft | 954.83 | 6 | 5728.98 | 1031.22 | 6760.2 | 2.5 | 954.83 | 5728.98 | 1031.22 | 6760.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 64 | 0 | 01 Dec 2021 | MUNNA RABITWALA | KEP-Common Activity Debris Shifting From Site(Regular Basis) | Debris Shifting Work | Brass. | 68.47 | 1800 | 123246 | 22184.28 | 145430.28 | 0 | 57.1998 | 102959.64 | 0 | 102959.64 | 11.2702 | 42470.64 |  | 83.5399 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 64 | 1 | 01 Dec 2021 | MUNNA RABITWALA | KEP- Debris Shifting Work | Debris Shifting Work | Brass. | 100 | 1800 | 180000 | 32400 | 212400 | 0 | 70.5555 | 126999.9 | 0 | 126999.9 | 29.4445 | 85400.1 |  | 70.5555 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Dec 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 65 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-Gr Fl Wall Gypsum (Tikki Dhada) | Tikki Dhada (L) | Sq.Ft | 575.87 | 14 | 8062.18 | 0 | 8062.18 | 2.5 | 0 | 0 | 0 | 0 | 575.87 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | Gala Cutting | No. | 60 | 300 | 18000 | 0 | 18000 | 2.5 | 50 | 15000 | 0 | 15000 | 10 | 3000 |  | 83.3333 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | 3000mm Framing (L) | No. | 4 | 500 | 2000 | 0 | 2000 | 2.5 | 4 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | 1800mm Framing (L) | No. | 2 | 300 | 600 | 0 | 600 | 2.5 | 2 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 4 | 01 Dec 2021 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Labour Lumpsum - BC | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | Gala Cutting- BC | No. | 16 | 500 | 8000 | 0 | 8000 | 2.5 | 16 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 0 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-Common Area Gypsum Touchup Work | Department Labour- BC | Pair | 20 | 850 | 17000 | 0 | 17000 | 0 | 3 | 2550 | 0 | 2550 | 17 | 14450 |  | 15 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 65 | 2 | 01 Dec 2021 | KHAN KAMAR ALAM | 3rd floor New gardians office gypsum work | Labour lumpsum | No. | 1 | 18000 | 18000 | 0 | 18000 | 2.5 | 1 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | 1200mm Framing (L) | No. | 20 | 200 | 4000 | 0 | 4000 | 2.5 | 14 | 2800 | 0 | 2800 | 6 | 1200 |  | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-1st Fl Wall Gypsum (Tikki Dhada) | Tikki Dhada (L) | Sq.Ft | 1778.64 | 14 | 24900.96 | 0 | 24900.96 | 2.5 | 0 | 0 | 0 | 0 | 1778.64 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 65 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-4th Fl Community Hall&Society Office Gypsum Wall (Patra | Gypsum on Wall (L) | Sq.Ft | 1440.72 | 7 | 10085.04 | 0 | 10085.04 | 2.5 | 0 | 0 | 0 | 0 | 1440.72 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | Repairing Work Mkt | No. | 2 | 5000 | 10000 | 0 | 10000 | 2.5 | 2 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 4 | 01 Dec 2021 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Labour Lumpsum - BC | No. | 1 | 2500 | 2500 | 0 | 2500 | 2.5 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | Vertical Patta (L) | R.Ft | 2450 | 25 | 61250 | 0 | 61250 | 2.5 | 2450 | 61250 | 0 | 61250 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 4 | 01 Dec 2021 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Labour Lumpsum - BC | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 65 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-4th Fl Community Hall&Society Office Gypsum Ceiling(Patr | Gypsum on Ceiling (L) | Sq.Ft | 1806.57 | 7 | 12645.99 | 0 | 12645.99 | 2.5 | 0 | 0 | 0 | 0 | 1806.57 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 65 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Floor Food Court Ceiling Misc. Work - 1 No. | Vertical Patta (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Cancelled | DUSHANT GORE | 03 Apr 2023
EAST POINT MARKET | 65 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-4th Fl Community Hall&Society Office Gypsum Beam (Tikki | Tikki Dhada (L) | Sq.Ft | 1322.1 | 13 | 17187.3 | 0 | 17187.3 | 2.5 | 0 | 0 | 0 | 0 | 1322.1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 66 | 0 | 01 Dec 2021 | SURESH KUMAR MURALIDHAR | KEP-3rd Floor Sand Faced Plaster(Single Coat) | Sand Face Plaster | Sq.Ft | 3316.94 | 20 | 66338.8 | 0 | 66338.8 | 2.5 | 1725.62 | 34512.4 | 0 | 34512.4 | 1591.32 | 31826.4 | Sand face plaster (Single Coat) at 3rd floor Foodcourt area, Including Cement, crush sand mortar with specified proportion. with scaffolding (M+L) fixing & removing, With proper joint preparaton between RCC (column beam) & Blockwork using Chicken mesh, na | 52.0245 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 67 | 4 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP - Gr. Floor Passage False ceiling | Grid False Ceiling (L) | Sq.Ft | 895.06 | 15 | 13425.9 | 0 | 13425.9 | 2.5 | 895.06 | 13425.9 | 0 | 13425.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 67 | 3 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-2nd Fl shops internal Gypsum Plaster | Gypsum Plaster (L) | Sq.Ft | 38190 | 11 | 420090 | 0 | 420090 | 2.5 | 27576.2197 | 303338.42 | 0 | 303338.42 | 10613.7803 | 116751.58 | Gypsum Plaster for internal walls with required thickness including finishing even & smooth, Butt finish, line level, plumb & right angle etc. complete, Loading, shifting & unloading of material from store to required place to be done by contractor. | 72.208 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 67 | 2 | 01 Dec 2021 | KHAN KAMAR ALAM | Gypsum plaster L/S work - 1st & 3rd floor - 935.71 Sqft | Labour Lumsum | No. | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande
EAST POINT MARKET | 67 | 0 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-Gr Fl Wall Plaster (Tikki Dhada) | Tikki Dhada (L) | Sq.Ft | 1085.1 | 10 | 10851 | 0 | 10851 | 2.5 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 67 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | 2nd Floor Gypsum for Wall (Tikki Dhada) | Tikki Dhada (L) | Sq.Ft | 1843.29 | 13 | 23962.77 | 0 | 23962.77 | 2.5 | 1843.29 | 23962.77 | 0 | 23962.77 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 67 | 4 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP - Gr. Floor Passage False ceiling | Gypsum Patta Plaster (L) | R.Ft | 62.757 | 15 | 941.36 | 0 | 941.36 | 2.5 | 62.757 | 941.36 | 0 | 941.36 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 67 | 4 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP - Gr. Floor Passage False ceiling | Gypsum Plaster (L) | Sq.Ft | 250.99 | 15 | 3764.85 | 0 | 3764.85 | 2.5 | 250.99 | 3764.85 | 0 | 3764.85 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 68 | 2 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP - Gr. Floor Passage False ceiling | Grid False Ceiling (M) | Sq.Ft | 895.06 | 75 | 67129.5 | 0 | 67129.5 | 0 | 895.06 | 67129.5 | 0 | 67129.5 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 68 | 1 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-2nd Fl shops internal Gypsum Plaster | Gypsum Plaster (M) | Sq.Ft | 38190 | 11 | 420090 | 0 | 420090 | 0 | 9959.0114 | 109549.13 | 0 | 109549.13 | 28230.9886 | 310540.87 |  | 26.0775 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 68 | 0 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP-Gr Fl Wall Plaster (Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 1085.1 | 10 | 10851 | 0 | 10851 | 0 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 68 | 2 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP - Gr. Floor Passage False ceiling | Gypsum Patta Plaster (M) | R.Ft | 62.757 | 60 | 3765.42 | 0 | 3765.42 | 0 | 62.757 | 3765.42 | 0 | 3765.42 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 68 | 2 | 01 Dec 2021 | KHAN KAMAR ALAM | KEP - Gr. Floor Passage False ceiling | Gypsum Plaster (M) | Sq.Ft | 250.99 | 75 | 18824.25 | 0 | 18824.25 | 0 | 250.99 | 18824.25 | 0 | 18824.25 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 69 | 0 | 01 Dec 2021 | GRAVITY ENTERPRISES | KEP- Demolition of 2nd Fl Sales Office & Basement fl Install | Demolition work- SOf | Sq.Ft | 1810 | 15 | 27150 | 4887 | 32037 | 2.5 | 1810 | 27150 | 4887 | 32037 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 69 | 0 | 01 Dec 2021 | GRAVITY ENTERPRISES | KEP- Demolition of 2nd Fl Sales Office & Basement fl Install | Installation Work | Sq.Ft | 1526 | 30 | 45780 | 8240.4 | 54020.4 | 2.5 | 1470.5757 | 44117.27 | 7941.1 | 52058.37 | 55.4243 | 1962.03 |  | 96.368 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | DEV. Club House | Approved | chetan.jewalikar
EAST POINT MARKET | 70 | 0 | 01 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP- 2nd & 3rd Fl Reshuffle Work(Ventilation Work) | Cable Laying AIE | Mtrs | 652 | 28 | 18256 | 3286.08 | 21542.08 | 2.5 | 652 | 18256 | 3286.08 | 21542.08 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 23 Dec 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 70 | 0 | 01 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP- 2nd & 3rd Fl Reshuffle Work(Ventilation Work) | Cable removing work- UTI | Mtrs | 652 | 8 | 5216 | 938.88 | 6154.88 | 2.5 | 652 | 5216 | 938.88 | 6154.88 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 23 Dec 2021 |  | UTI. Electricity Infrastructur | Approved | chetan.jewalikar
EAST POINT MARKET | 71 | 0 | 01 Dec 2021 | NEPTUNE ENGINEERS | KEP-Ventilation Work Reshuffle(2nd&3rd Fl ) | Cable removing work- UTI | Mtrs | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | UTI. Electricity Infrastructur | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 71 | 0 | 01 Dec 2021 | NEPTUNE ENGINEERS | KEP-Ventilation Work Reshuffle(2nd&3rd Fl ) | Jet Fan Removal | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 71 | 0 | 01 Dec 2021 | NEPTUNE ENGINEERS | KEP-Ventilation Work Reshuffle(2nd&3rd Fl ) | 3C 2.5 sqmm Cu Cable (L) | Mtrs | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 72 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl Ent Canopy at Gr Fl Railway Side (MS Work) | Fastner (L) - SOSB | No. | 8 | 20 | 160 | 28.8 | 188.8 | 2.5 | 8 | 160 | 28.8 | 188.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 72 | 0 | 01 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl Ent Canopy at Gr Fl Railway Side (MS Work) | Fabrication work (L) | Kgs | 190 | 21 | 3990 | 718.2 | 4708.2 | 2.5 | 190 | 3990 | 718.2 | 4708.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 73 | 0 | 01 Dec 2021 | SURESH KUMAR MURALIDHAR | SRA Duct Closing At 5th Floor | Lumpsum work- DCW | No. | 1 | 55200 | 55200 | 0 | 55200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 74 | 0 | 01 Dec 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Fl Society Office Sand Faced Plaster(Single Coat) | Sand Face Plaster | Sq.Ft | 629.61 | 20 | 12592.2 | 0 | 12592.2 | 2.5 | 629.61 | 12592.2 | 0 | 12592.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 74 | 0 | 01 Dec 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Community Hall Sand Faced Plaster(Single Coat) | Sand Face Plaster | Sq.Ft | 1300.25 | 20 | 26005 | 0 | 26005 | 2.5 | 1096.7349 | 21934.7 | 0 | 21934.7 | 203.5151 | 4070.3 |  | 84.348 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 74 | 0 | 01 Dec 2021 | SURESH KUMAR MURALIDHAR | KEP-4th Fl Society Office Blockwork-625x240x125mm | Blockwork 5" - BC - | Sq.Ft | 52.86 | 16 | 845.76 | 0 | 845.76 | 2.5 | 0 | 0 | 0 | 0 | 52.86 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Wall Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 5377.5 | 1.25 | 6721.88 | 0 | 6721.88 | 2.5 | 0 | 0 | 0 | 0 | 5377.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Ceiling Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 2676.4 | 1.25 | 3345.5 | 0 | 3345.5 | 2.5 | 0 | 0 | 0 | 0 | 2676.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Acrylic Paint Exterior Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 9835.06 | 1.25 | 12293.83 | 0 | 12293.83 | 2.5 | 0 | 0 | 0 | 0 | 9835.06 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Food court False Ceiling painting - 1 No. | 1st Coat Ceiling Putty | Sq.Ft | 8714.209 | 1.5 | 13071.31 | 0 | 13071.31 | 2.5 | 8714.1972 | 13071.3 | 0 | 13071.3 | 0.0118 | 0.02 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Changing room Painting work - 1 No. | 1st Coat Wall Putty - | Sq.Ft | 549.125 | 1.5 | 823.69 | 0 | 823.69 | 2.5 | 549.125 | 823.69 | 0 | 823.69 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Changing room Painting work - 1 No. | 1 Coat Primer (Water Base) (L) | Sq.Ft | 549.125 | 1.5 | 823.69 | 0 | 823.69 | 2.5 | 549.125 | 823.69 | 0 | 823.69 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Ceiling Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 2676.4 | 1.25 | 3345.5 | 0 | 3345.5 | 2.5 | 0 | 0 | 0 | 0 | 2676.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Changing room Painting work - 1 No. | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 549.125 | 1.5 | 823.69 | 0 | 823.69 | 2.5 | 549.125 | 823.69 | 0 | 823.69 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF False ceiling painting work -1 No. | 1st Coat Wall Putty - | Sq.Ft | 420.6 | 1.5 | 630.9 | 0 | 630.9 | 2.5 | 420.6 | 630.9 | 0 | 630.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Acrylic Paint Exterior Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 9835.06 | 1.25 | 12293.83 | 0 | 12293.83 | 2.5 | 0 | 0 | 0 | 0 | 9835.06 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Food court False Ceiling painting - 1 No. | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 8714.209 | 1.5 | 13071.31 | 0 | 13071.31 | 2.5 | 8714.2038 | 13071.31 | 0 | 13071.31 | 0.0052 | 0.01 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor common wall Painting work - 1 No. | 1st Coat Wall Putty - | Sq.Ft | 5150.746 | 1.5 | 7726.12 | 0 | 7726.12 | 2.5 | 1126.2997 | 1689.45 | 0 | 1689.45 | 4024.4463 | 6036.67 |  | 21.8667 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Ceiling Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 2676.4 | 1.25 | 3345.5 | 0 | 3345.5 | 2.5 | 0 | 0 | 0 | 0 | 2676.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor common wall Painting work - 1 No. | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 5150.746 | 1.5 | 7726.12 | 0 | 7726.12 | 2.5 | 5150.7397 | 7726.11 | 0 | 7726.11 | 0.0063 | 0.01 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF False ceiling painting work -1 No. | 1 Coat Primer (Water Base) (L) | Sq.Ft | 420.6 | 1.5 | 630.9 | 0 | 630.9 | 2.5 | 420.6 | 630.9 | 0 | 630.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF False ceiling painting work -1 No. | 1st coat Premium Emulsion on wall | Sq.Ft | 420.6 | 1.5 | 630.9 | 0 | 630.9 | 2.5 | 420.6 | 630.9 | 0 | 630.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF False ceiling painting work -1 No. | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 420.6 | 1.5 | 630.9 | 0 | 630.9 | 2.5 | 420.6 | 630.9 | 0 | 630.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF Common Wall Painting - 1 No. | 1st Coat Wall Putty - | Sq.Ft | 1200.004 | 1.5 | 1800.01 | 0 | 1800.01 | 2.5 | 274.15 | 411.23 | 0 | 411.23 | 925.854 | 1388.78 |  | 22.8458 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Wall Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 5377.5 | 1.25 | 6721.88 | 0 | 6721.88 | 2.5 | 0 | 0 | 0 | 0 | 5377.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Ceiling Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 2676.4 | 1.25 | 3345.5 | 0 | 3345.5 | 2.5 | 0 | 0 | 0 | 0 | 2676.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF Common Wall Painting - 1 No. | 2nd Coat Wall Putty - | Sq.Ft | 1200.004 | 1.5 | 1800.01 | 0 | 1800.01 | 2.5 | 274.15 | 411.23 | 0 | 411.23 | 925.854 | 1388.78 |  | 22.8458 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF Common Wall Painting - 1 No. | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1200.004 | 1.5 | 1800.01 | 0 | 1800.01 | 2.5 | 274.1499 | 411.22 | 0 | 411.22 | 925.8541 | 1388.78 |  | 22.8457 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF Common Wall Painting - 1 No. | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1200.004 | 1.5 | 1800.01 | 0 | 1800.01 | 2.5 | 274.15 | 411.23 | 0 | 411.23 | 925.854 | 1388.78 |  | 22.8458 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF Common Wall Painting - 1 No. | 2nd coat Premium Emulsion on wall | Sq.Ft | 1200.004 | 1.5 | 1800.01 | 0 | 1800.01 | 2.5 | 274.15 | 411.23 | 0 | 411.23 | 925.854 | 1388.78 |  | 22.8458 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Food court False Ceiling painting - 1 No. | 2nd Coat Ceiling Putty | Sq.Ft | 8174.209 | 1.5 | 12261.31 | 0 | 12261.31 | 2.5 | 4946.854 | 7420.28 | 0 | 7420.28 | 3227.355 | 4841.03 |  | 60.5178 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Wall Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 5377.5 | 1.25 | 6721.88 | 0 | 6721.88 | 2.5 | 0 | 0 | 0 | 0 | 5377.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF False ceiling painting work -1 No. | 2nd Coat Wall Putty - | Sq.Ft | 420.6 | 1.5 | 630.9 | 0 | 630.9 | 2.5 | 420.6 | 630.9 | 0 | 630.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor common wall Painting work - 1 No. | 2nd Coat Wall Putty - | Sq.Ft | 5150.746 | 1.5 | 7726.12 | 0 | 7726.12 | 2.5 | 5150.7393 | 7726.11 | 0 | 7726.11 | 0.0067 | 0.01 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor common wall Painting work - 1 No. | 1 Coat Primer (Water Base) (L) | Sq.Ft | 5150.746 | 1.5 | 7726.12 | 0 | 7726.12 | 2.5 | 5150.7233 | 7726.08 | 0 | 7726.09 | 0.0227 | 0.03 |  | 99.9996 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | GF Escalator behind shop rolling - 1 No. | 2 Coat Oil Paint (M+L) | Sq.Ft | 1275.21 | 18 | 22953.78 | 0 | 22953.78 | 2.5 | 0 | 0 | 0 | 0 | 1275.21 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Food court False Ceiling painting - 1 No. | 1 Coat Primer (Water Base) (L) | Sq.Ft | 8714.209 | 1.5 | 13071.31 | 0 | 13071.31 | 2.5 | 8714.2038 | 13071.31 | 0 | 13071.31 | 0.0052 | 0.01 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor common wall Painting work - 1 No. | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 5150.746 | 1.5 | 7726.12 | 0 | 7726.12 | 2.5 | 4657.9097 | 6986.86 | 0 | 6986.86 | 492.8363 | 739.25 |  | 90.4317 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Wall Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 5377.5 | 1.25 | 6721.88 | 0 | 6721.88 | 2.5 | 0 | 0 | 0 | 0 | 5377.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Acrylic Paint Exterior Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 9835.06 | 1.25 | 12293.83 | 0 | 12293.83 | 2.5 | 0 | 0 | 0 | 0 | 9835.06 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Ceiling Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 2676.4 | 1.25 | 3345.5 | 0 | 3345.5 | 2.5 | 0 | 0 | 0 | 0 | 2676.4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-4th Fl Community Hall Wall Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 5377.5 | 1.25 | 6721.88 | 0 | 6721.88 | 2.5 | 0 | 0 | 0 | 0 | 5377.5 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Changing room Painting work - 1 No. | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 549.125 | 1.5 | 823.69 | 0 | 823.69 | 2.5 | 549.125 | 823.69 | 0 | 823.69 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Food court False Ceiling painting - 1 No. | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 8714.209 | 1.5 | 13071.31 | 0 | 13071.31 | 2.5 | 3767.3499 | 5651.02 | 0 | 5651.02 | 4946.8591 | 7420.29 |  | 43.2323 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 75 | 1 | 02 Dec 2021 | AZAM KHAN | 3rd Floor Changing room Painting work - 1 No. | 2nd Coat Wall Putty - | Sq.Ft | 549.125 | 1.5 | 823.69 | 0 | 823.69 | 2.5 | 549.125 | 823.69 | 0 | 823.69 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 13 Jan 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Axial Flow Fan isolator (L) | No. | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Axial Fan Installation | No. | 0 | 5775 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Flexible Connections (L) | No. | 0 | 500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | 24 Gauge GI Sheet Steel (TDF Flange) (L) | Sq.m. | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | 3C x 2.5sqmm Cu cable armourd (L) | Mtrs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | 4C x 4sqmm Cu cable armourd (L) | Mtrs | 0 | 38 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | Admin. Direct Expenses | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | MS Fabricated motorized louvers (L) | Sq.m. | 0 | 750 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 76 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Ventilation Panel (L) | No. | 0 | 5000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | 3C x 2.5sqmm Cu cable armourd (M) | Mtrs | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Flexible Connections (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Axial Flow Fan isolator (M) | No. | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Ventilation Panel (M) | No. | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | MS Fabricated motorized louvers (M) | Sq.m. | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | 4C x 4sqmm Cu cable armourd (M) | Mtrs | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | 24 Gauge GI Sheet Steel (TDF Flange) (M) | Sq.m. | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 77 | 0 | 02 Dec 2021 | NEPTUNE ENGINEERS | KEP-4th Fl Podium,Terrace,Ventilation System | Fabrication work (M) | Kgs | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 04 Dec 2021 |  | Admin. Direct Expenses | Cancelled | skmishra | 04 Dec 2021
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Wall Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 4492.65 | 1.25 | 5615.81 | 0 | 5615.81 | 2.5 | 0 | 0 | 0 | 0 | 4492.65 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Ceiling Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 3178.18 | 1.25 | 3972.73 | 0 | 3972.73 | 2.5 | 3175.0018 | 3968.75 | 0 | 3968.75 | 3.1782 | 3.97 |  | 99.9 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 2 | 02 Dec 2021 | AZAM KHAN | KEP - Ground Floor Toilet Painting | 1st Coat Paint | Sq.Ft | 1688.37 | 1.75 | 2954.65 | 0 | 2954.65 | 2.5 | 1688.37 | 2954.65 | 0 | 2954.65 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Ceiling Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 472.81 | 1.25 | 591.01 | 0 | 591.01 | 2.5 | 0 | 0 | 0 | 0 | 472.81 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Wall Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1085.1 | 1.25 | 1356.38 | 0 | 1356.38 | 2.5 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Ceiling Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 3178.18 | 1.25 | 3972.73 | 0 | 3972.73 | 2.5 | 0 | 0 | 0 | 0 | 3178.18 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 2 | 02 Dec 2021 | AZAM KHAN | KEP - Ground Floor Toilet Painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1688.37 | 1.75 | 2954.65 | 0 | 2954.65 | 2.5 | 1688.37 | 2954.65 | 0 | 2954.65 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Wall Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 1085.1 | 1.25 | 1356.38 | 0 | 1356.38 | 2.5 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Wall Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 4492.65 | 1.25 | 5615.81 | 0 | 5615.81 | 2.5 | 0 | 0 | 0 | 0 | 4492.65 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Ceiling Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 472.81 | 1.25 | 591.01 | 0 | 591.01 | 2.5 | 0 | 0 | 0 | 0 | 472.81 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Wall Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 4492.65 | 1.25 | 5615.81 | 0 | 5615.81 | 2.5 | 898.53 | 1123.16 | 0 | 1123.16 | 3594.12 | 4492.65 |  | 20 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Wall Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 1085.1 | 1.25 | 1356.38 | 0 | 1356.38 | 2.5 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Ceiling Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 472.81 | 1.25 | 591.01 | 0 | 591.01 | 2.5 | 0 | 0 | 0 | 0 | 472.81 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Wall Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1085.1 | 1.25 | 1356.38 | 0 | 1356.38 | 2.5 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Wall Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1085.1 | 1.25 | 1356.38 | 0 | 1356.38 | 2.5 | 0 | 0 | 0 | 0 | 1085.1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Ceiling Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 3178.18 | 1.25 | 3972.73 | 0 | 3972.73 | 2.5 | 3175.0018 | 3968.75 | 0 | 3968.75 | 3.1782 | 3.97 |  | 99.9 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 2 | 02 Dec 2021 | AZAM KHAN | KEP - Ground Floor Toilet Painting | Scrapping with 2nd Coat Putty | Sq.Ft | 1688.37 | 1.75 | 2954.65 | 0 | 2954.65 | 2.5 | 1688.37 | 2954.65 | 0 | 2954.65 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Wall Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 4492.65 | 1.25 | 5615.81 | 0 | 5615.81 | 2.5 | 898.53 | 1123.16 | 0 | 1123.16 | 3594.12 | 4492.65 |  | 20 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Ceiling Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 3178.18 | 1.25 | 3972.73 | 0 | 3972.73 | 2.5 | 3177.8622 | 3972.33 | 0 | 3972.33 | 0.3178 | 0.4 |  | 99.99 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Ceiling Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 472.81 | 1.25 | 591.01 | 0 | 591.01 | 2.5 | 0 | 0 | 0 | 0 | 472.81 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 0 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Fl Toilet Ceiling Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 472.81 | 1.25 | 591.01 | 0 | 591.01 | 2.5 | 0 | 0 | 0 | 0 | 472.81 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 2 | 02 Dec 2021 | AZAM KHAN | KEP - Ground Floor Toilet Painting | Scrapping with 1st Coat Putty | Sq.Ft | 1688.37 | 1.75 | 2954.65 | 0 | 2954.65 | 2.5 | 1688.37 | 2954.65 | 0 | 2954.65 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Ceiling Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 3178.18 | 1.25 | 3972.73 | 0 | 3972.73 | 2.5 | 0 | 0 | 0 | 0 | 3178.18 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 1 | 02 Dec 2021 | AZAM KHAN | KEP-Gr Floor Passage Wall Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 4492.65 | 1.25 | 5615.81 | 0 | 5615.81 | 2.5 | 898.53 | 1123.16 | 0 | 1123.16 | 3594.12 | 4492.65 |  | 20 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 78 | 2 | 02 Dec 2021 | AZAM KHAN | KEP - Ground Floor Toilet Painting | 2nd Coat Paint | Sq.Ft | 1688.37 | 1.75 | 2954.65 | 0 | 2954.65 | 2.5 | 1688.37 | 2954.65 | 0 | 2954.65 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Scaffolding work | Sq.Ft | 3250 | 12 | 39000 | 7020 | 46020 | 0 | 3250 | 39000 | 7020 | 46020 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 0 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work Sinages for Facade(Road& Railway Side) | Scaffolding Work - BC | No. | 0.333 | 600000 | 199800 | 35964 | 235764 | 2.5 | 0.3297 | 197820 | 35607.6 | 233427.6 | 0.0033 | 2336.4 |  | 99.009 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding for ODU Platform | Scaffolding work | Sq.Ft | 4225 | 12 | 50700 | 9126 | 59826 | 0 | 4225 | 50700 | 9126 | 59826 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 0 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Aluminium Pipe Fixing Work for Gap Closing | Aluminium Pipe Fixing | R.Ft | 552 | 220 | 121440 | 21859.2 | 143299.2 | 2.5 | 267.996 | 58959.12 | 10612.64 | 69571.76 | 284.004 | 73727.44 |  | 48.55 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 79 | 1 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work Sinages for Facade(Road& Railway Side) | Scaffolding Work - BC | No. | 1 | 184000 | 184000 | 33120 | 217120 | 0 | 1 | 184000 | 33120 | 217120 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Scaffolding work | Sq.Ft | 3250 | 12 | 39000 | 7020 | 46020 | 0 | 3250 | 39000 | 7020 | 46020 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding for ODU Platform | Scaffolding work | Sq.Ft | 4225 | 12 | 50700 | 9126 | 59826 | 0 | 4225 | 50700 | 9126 | 59826 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Scaffolding work | Sq.Ft | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 01 Jun 2022
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Scaffolding work | Sq.Ft | 7560 | 12 | 90720 | 16329.6 | 107049.6 | 0 | 7560 | 90720 | 16329.6 | 107049.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Scaffolding work | Sq.Ft | 7560 | 12 | 90720 | 16329.6 | 107049.6 | 0 | 7560 | 90720 | 16329.6 | 107049.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding for ODU Platform | Scaffolding work | Sq.Ft | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 01 Jun 2022
EAST POINT MARKET | 79 | 2 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Scaffolding work | Sq.Ft | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 01 Jun 2022
EAST POINT MARKET | 80 | 0 | 02 Dec 2021 | SUPER FACILITY SERVICES | Housekeeping Work | Housekeeping Work - SO | Month | 1 | 90000 | 90000 | 16200 | 106200 | 0 | 0.984 | 88560 | 15940.8 | 104500.8 | 0.016 | 1699.2 |  | 98.4 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 80 | 0 | 02 Dec 2021 | SUPER FACILITY SERVICES | Housekeeping Work | Housekeeping Work - SO | Month | 1 | 90000 | 90000 | 16200 | 106200 | 0 | 0.94 | 84600 | 15228 | 99828 | 0.06 | 6372 |  | 94 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 80 | 0 | 02 Dec 2021 | SUPER FACILITY SERVICES | Housekeeping Work | Housekeeping Work - SO | Month | 1 | 90000 | 90000 | 16200 | 106200 | 0 | 0.64 | 57600 | 10368 | 67968 | 0.36 | 38232 |  | 64 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 80 | 0 | 02 Dec 2021 | SUPER FACILITY SERVICES | Housekeeping Work | Housekeeping Work - SO | Month | 1 | 90000 | 90000 | 16200 | 106200 | 0 | 0.5 | 45000 | 8100 | 53100 | 0.5 | 53100 |  | 50 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 81 | 0 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-4th Floor External Glazing Work | Fabrication Work (M+L) - Mkt | Kgs | 639.99 | 270 | 172797.3 | 31103.52 | 203900.82 | 2.5 | 242.9248 | 65589.7 | 11806.14 | 77395.84 | 397.0652 | 126504.98 |  | 37.9576 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 81 | 0 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-Gr Fl Ent Canopy at Gr Fl Railway Side ACP Work | ACP Work (M+L) | Sq.Ft | 152.2 | 230 | 35006 | 6301.08 | 41307.08 | 2.5 | 152.2 | 35006 | 6301.08 | 41307.08 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 81 | 1 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-4th Floor External Glazing Work | Openable Window (M+L) | No. | 7 | 4000 | 28000 | 5040 | 33040 | 2.5 | 3 | 12000 | 2160 | 14160 | 4 | 18880 |  | 42.8571 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 81 | 0 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-4th Fl Community Hall Chajja Work In ACP | ACP Cladding (M+L)- Mkt | Sq.Ft | 200 | 260 | 52000 | 9360 | 61360 | 2.5 | 200 | 52000 | 9360 | 61360 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 81 | 0 | 02 Dec 2021 | SAHARA ENGINEERING | KEP-4th Floor External Glazing Work | Fastner (L) - SOSB | No. | 317 | 450 | 142650 | 25677 | 168327 | 2.5 | 111.9999 | 50399.96 | 9072 | 59471.96 | 205.0001 | 108855.05 |  | 35.3312 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 82 | 1 | 02 Dec 2021 | AAKAR GLAZING SYSTEM | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | ACP Work (M+L) | Sq.Ft | 754.05 | 230 | 173431.5 | 0 | 173431.5 | 2.5 | 753.9746 | 173414.16 | 31214.54 | 204628.7 | 0.0754 | -31197.2 |  | 99.99 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 82 | 1 | 02 Dec 2021 | AAKAR GLAZING SYSTEM | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | CNC Cut Design | Sq.Ft | 290.9 | 1200 | 349080 | 0 | 349080 | 2.5 | 290.9 | 349080 | 62834.4 | 411914.4 | 0 | -62834.4 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 82 | 0 | 02 Dec 2021 | AAKAR GLAZING SYSTEM | KEP-Gr Fl Entrance Canopy at Gr Fl ACP Work | ACP Work (M+L) | Sq.Ft | 1997.37 | 230 | 459395.1 | 0 | 459395.1 | 2.5 | 1997.37 | 459395.1 | 82691.12 | 542086.22 | 0 | -82691.12 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 1 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-1st FL Grid False ceiling work Passage | Grid False Ceiling (L) | Sq.Ft | 2424 | 20 | 48480 | 0 | 48480 | 2.5 | 0 | 0 | 0 | 0 | 2424 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Un-Approved
EAST POINT MARKET | 83 | 1 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP - 2nd FL Grid False ceiling work Passage | Light Gala Cutting-BC | No. | 50 | 50 | 2500 | 0 | 2500 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Un-Approved
EAST POINT MARKET | 83 | 1 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-1st FL Grid False ceiling work Passage | Light Gala Cutting-BC | No. | 50 | 50 | 2500 | 0 | 2500 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | B.C. BBM, Plaster, POP | Un-Approved
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Mall Management Office False Ceiling Work | False Ceiling Patta | R.Ft | 100 | 40 | 4000 | 0 | 4000 | 2.5 | 100 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | False Ceiling Patta | R.Ft | 500 | 40 | 20000 | 0 | 20000 | 2.5 | 500 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Mall Management Office False Ceiling Work | False Ceiling work- BCo | Sq.Ft | 900 | 75 | 67500 | 0 | 67500 | 2.5 | 900 | 67500 | 0 | 67500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | Gala Cutting | No. | 200 | 50 | 10000 | 0 | 10000 | 2.5 | 162 | 8100 | 0 | 8100 | 38 | 1900 |  | 81 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | False Ceiling work- BCo | Sq.Ft | 3206 | 90 | 288540 | 0 | 288540 | 2.5 | 2130.6269 | 191756.42 | 0 | 191756.42 | 1075.3731 | 96783.58 |  | 66.4575 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Mall Management Office False Ceiling Work | Gala Cutting | No. | 40 | 50 | 2000 | 0 | 2000 | 2.5 | 40 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 0 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | False Ceiling work- BCo | Sq.Ft | 7280 | 75 | 546000 | 0 | 546000 | 2.5 | 7159.8888 | 536991.66 | 0 | 536991.66 | 120.1112 | 9008.34 |  | 98.3501 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 83 | 1 | 04 Dec 2021 | KHAN KAMAR ALAM | KEP - 2nd FL Grid False ceiling work Passage | Grid False Ceiling (L) | Sq.Ft | 2424 | 20 | 48480 | 0 | 48480 | 2.5 | 0 | 0 | 0 | 0 | 2424 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | 05 GYPSUM & PLASTER | Un-Approved
EAST POINT MARKET | 84 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation Work Reshuffle(2nd&3rd Fl ) | 3C 2.5 sqmm Cu Cable (L) | Mtrs | 865 | 25 | 21625 | 3892.5 | 25517.5 | 0 | 436.998 | 10924.95 | 1966.5 | 12891.45 | 428.002 | 12626.05 |  | 50.52 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 84 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation Work Reshuffle(2nd&3rd Fl ) | Jet Fan Removal | No. | 17 | 1000 | 17000 | 3060 | 20060 | 0 | 17 | 17000 | 3060 | 20060 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 84 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation Work Reshuffle(2nd&3rd Fl ) | Cable removing work- UTI | Mtrs | 2168 | 8 | 17344 | 3121.92 | 20465.92 | 0 | 2168 | 17344 | 3121.92 | 20465.92 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | UTI. Electricity Infrastructur | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Refrigerant Piping (L) | Mtrs | 75 | 150 | 11250 | 2025 | 13275 | 2.5 | 0 | 0 | 0 | 0 | 75 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | MS Stand (L)- No. | No. | 7 | 1000 | 7000 | 1260 | 8260 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | No category | Un-Approved
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | MS Stand (L)- No. | No. | 0 | 1000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | No category | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | MS Fabricated motorized louvers (L) | Sq.m. | 13 | 750 | 9750 | 1755 | 11505 | 2.5 | 13 | 9750 | 1755 | 11505 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | 3Core x 1.5Sqmm Control Cabling (L) | Mtrs | 80 | 20 | 1600 | 288 | 1888 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | AC Installation & Commissioning (L) | No. | 7 | 1500 | 10500 | 1890 | 12390 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | 3Core x 1.5Sqmm Control Cabling (L) | Mtrs | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Flexible Connections (L) | No. | 4 | 500 | 2000 | 360 | 2360 | 2.5 | 4 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Drain Pipe with Insulation (L) | Mtrs | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Drain Pipe with Insulation (L) | Mtrs | 50 | 20 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | AC Installation & Commissioning (L) | No. | 0 | 1500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | 24 Gauge GI Sheet Steel (TDF Flange) (L) | Sq.m. | 21 | 170 | 3570 | 642.6 | 4212.6 | 2.5 | 8.5399 | 1451.78 | 261.32 | 1713.1 | 12.4601 | 2499.5 |  | 40.6662 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Axial Flow Fan isolator (L) | No. | 16 | 200 | 3200 | 576 | 3776 | 2.5 | 16 | 3200 | 576 | 3776 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Refrigerant Piping (L) | Mtrs | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | 4C x 4sqmm Cu cable armourd (L) | Mtrs | 240 | 38 | 9120 | 1641.6 | 10761.6 | 2.5 | 240 | 9120 | 1641.6 | 10761.6 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Axial Fan Installation | No. | 4 | 5775 | 23100 | 4158 | 27258 | 2.5 | 4 | 23100 | 4158 | 27258 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Ventilation Panel (L) | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | 3C x 2.5sqmm Cu cable armourd (L) | Mtrs | 120 | 25 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 85 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Fabrication work (L) | Kgs | 65 | 18 | 1170 | 210.6 | 1380.6 | 2.5 | 65 | 1170 | 210.6 | 1380.6 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | SecurityGuard.- SOS | Day | 150 | 433.33 | 64999.5 | 11699.92 | 76699.42 | 0 | 150 | 64999.5 | 11699.92 | 76699.42 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | Security Supervisor.- SOS | Day | 31 | 467.74 | 14499.94 | 2609.98 | 17109.92 | 0 | 31 | 14499.94 | 2609.98 | 17109.92 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | Bouncer. | Day | 62 | 629.03 | 38999.86 | 7019.98 | 46019.84 | 0 | 6.0004 | 3774.43 | 679.4 | 4453.83 | 55.9996 | 41566.01 |  | 9.6781 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | Bouncer. | Day | 62 | 629.03 | 38999.86 | 7019.98 | 46019.84 | 0 | 62 | 38999.86 | 7019.98 | 46019.84 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | SecurityGuard.- SOS | Day | 155 | 419.36 | 65000.8 | 11700.14 | 76700.94 | 0 | 15.0009 | 6290.78 | 1132.34 | 7423.12 | 139.9991 | 69277.82 |  | 9.678 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | SecurityGuard.- SOS | Day | 155 | 419.36 | 65000.8 | 11700.14 | 76700.94 | 0 | 155 | 65000.8 | 11700.14 | 76700.94 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | Bouncer. | Day | 60 | 650 | 39000 | 7020 | 46020 | 0 | 60 | 39000 | 7020 | 46020 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | Security Supervisor.- SOS | Day | 31 | 467.74 | 14499.94 | 2609.98 | 17109.92 | 0 | 3.0002 | 1403.31 | 252.6 | 1655.91 | 27.9998 | 15454.01 |  | 9.6781 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 86 | 0 | 04 Dec 2021 | TREND SECURITY SERVICE | Security Services | Security Supervisor.- SOS | Day | 30 | 483.33 | 14499.9 | 2609.98 | 17109.88 | 0 | 30 | 14499.9 | 2609.98 | 17109.88 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Dec 2021 |  | S OH Site Staff | Approved | chetan.jewalikar | 11 Dec 2021
EAST POINT MARKET | 87 | 0 | 04 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl Ent Canopy at Gr Fl Railway Side (MS Work) | Fabrication work (M) | Kgs | 190 | 84 | 15960 | 2872.8 | 18832.8 | 0 | 190 | 15960 | 2872.8 | 18832.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 87 | 0 | 04 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Fl Ent Canopy at Gr Fl Railway Side (MS Work) | Fastner (M) - SOSB | No. | 8 | 70 | 560 | 100.8 | 660.8 | 0 | 8 | 560 | 100.8 | 660.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Fabrication work (M) | Kgs | 65 | 92 | 5980 | 1076.4 | 7056.4 | 0 | 65 | 5980 | 1076.4 | 7056.4 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Drain Pipe with Insulation (M) | Mtrs | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | 3Core x 1.5Sqmm Control Cabling (M) | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | 24 Gauge GI Sheet Steel (TDF Flange) (M) | Sq.m. | 21 | 670 | 14070 | 2532.6 | 16602.6 | 0 | 8.5407 | 5722.27 | 1030 | 6752.27 | 12.4593 | 9850.33 |  | 40.67 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | MS Fabricated motorized louvers (M) | Sq.m. | 13 | 10500 | 136500 | 24570 | 161070 | 0 | 13 | 136500 | 24570 | 161070 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Ventilation Panel (M) | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 9000 | 59000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Drain Pipe with Insulation (M) | Mtrs | 50 | 65 | 3250 | 585 | 3835 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | MS Stand (M) - No. | No. | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | MS Stand (M) - No. | No. | 7 | 3500 | 24500 | 4410 | 28910 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Refrigerant Piping (M) | Mtrs | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 25 Aug 2022
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | Refrigerant Piping (M) | Mtrs | 75 | 800 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 75 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Flexible Connections (M) | No. | 4 | 1500 | 6000 | 1080 | 7080 | 0 | 4 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 1 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Guardians Ac Shifting From 3rd to 4th Fl | 3Core x 1.5Sqmm Control Cabling (M) | Mtrs | 80 | 51 | 4080 | 734.4 | 4814.4 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Dec 2021 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | 4C x 4sqmm Cu cable armourd (M) | Mtrs | 240 | 202 | 48480 | 8726.4 | 57206.4 | 0 | 240 | 48480 | 8726.4 | 57206.4 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | Axial Flow Fan isolator (M) | No. | 16 | 800 | 12800 | 2304 | 15104 | 0 | 16 | 12800 | 2304 | 15104 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 88 | 0 | 04 Dec 2021 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-4th Fl Podium,Terrace,Ventilation System | 3C x 2.5sqmm Cu cable armourd (M) | Mtrs | 120 | 118 | 14160 | 2548.8 | 16708.8 | 0 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 23 Dec 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 89 | 0 | 04 Dec 2021 | ABDUL SATTAR SHAIKH | KEP Common Plumbing Bldg Water Connection line from BMC | Lumpsum work- DCW | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 89 | 0 | 04 Dec 2021 | ABDUL SATTAR SHAIKH | KEP Common Plumbing SRA Bldg Water Tank in Basement Fl | Chamber work - cc | No. | 4 | 3000 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar
EAST POINT MARKET | 90 | 0 | 04 Dec 2021 | SAHARA ENGINEERING | KEP-4th Fl Community Hall Aluminium Window | Aluminium Window (L) - SOf | Sq.Ft | 168 | 60 | 10080 | 1814.4 | 11894.4 | 2.5 | 168 | 10080 | 1814.4 | 11894.4 | 0 | 0 | Providing and fixing of sliding window of size 6feet x 4feet =24 sqft (24x07=168 sqft) at community hall, including series of 18mm, 5mm clear glass, with powder coating sections, concealed locks, bearing, screw rubber gasket with bearing, with all require | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 90 | 0 | 04 Dec 2021 | SAHARA ENGINEERING | KEP-4th Fl Community Hall Door | Backelet Sheet Door with Alumn Frame (L) | Sq.Ft | 150 | 60 | 9000 | 1620 | 10620 | 2.5 | 150 | 9000 | 1620 | 10620 | 0 | 0 | Installation of backlelet sheet door with aluminium frame (Duct Door 4th floor) with 18mm handle section, L pipe frame work, with all tools and tackles, as per approved attachted proposal. | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 91 | 0 | 04 Dec 2021 | SAHARA ENGINEERING | 4th floor Sales Lounge work | Glass Fixing Work (M+L) | No. | 3 | 3500 | 10500 | 1890 | 12390 | 2.5 | 3 | 10500 | 1890 | 12390 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 91 | 0 | 04 Dec 2021 | SAHARA ENGINEERING | KEP-4th Fl Community Hall Aluminium Window | Aluminium Window (M) - SOf | Sq.Ft | 168 | 220 | 36960 | 6652.8 | 43612.8 | 0 | 168 | 36960 | 6652.8 | 43612.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 91 | 0 | 04 Dec 2021 | SAHARA ENGINEERING | KEP-4th Fl Community Hall Door | Backelet Sheet Door with Alumn Frame (M) | Sq.Ft | 150 | 230 | 34500 | 6210 | 40710 | 0 | 150 | 34500 | 6210 | 40710 | 0 | 0 | Supply of Backelet sheet door at 4th floor with aluminium frame, Including 18mm handle section, backelet sheet with poweder coating, locks, tower bolt, screw rubber gasket, hinges, hardware, as per approved design & specification. | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 92 | 1 | 04 Dec 2021 | PRECISE TECHNOFAB INDIA PVT LTD | Media FLEX PRINTING & MOUNTING | FLEX PRINTING | Sq.Ft | 250 | 22.2 | 5550 | 999 | 6549 | 0 | 250 | 5550 | 999 | 6549 | 0 | 0 | STAR FLEX PRINT WITH PASTING SIZE AS 25X10 SQ FT | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 08 Dec 2021 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 92 | 0 | 04 Dec 2021 | PRECISE TECHNOFAB INDIA PVT LTD | Media FLEX PRINTING & MOUNTING | FLEX PRINTING | Sq.Ft | 260 | 22 | 5720 | 1029.6 | 6749.6 | 0 | 260 | 5720 | 1029.6 | 6749.6 | 0 | 0 | STAR FLEX PRINT WITH PASTING SIZE AS 26X10 SQ FT | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 08 Dec 2021 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Deck Sheet Fixing | Sq.Ft | 7495 | 15 | 112425 | 20236.5 | 132661.5 | 2.5 | 7495 | 112425 | 20236.5 | 132661.5 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | UTI. U.G.W.T | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet Fixing (L) | Sq.Ft | 549 | 26.1 | 14328.9 | 2579.2 | 16908.1 | 2.5 | 549 | 14328.9 | 2579.2 | 16908.1 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | UTI. Vermiculture | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Bar Cutting Work - BCE | No. | 2000 | 20 | 40000 | 7200 | 47200 | 2.5 | 2000 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Elevation Features | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Bending & Cutting(L) - SOSB | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet Fixing (L) | Sq.Ft | 252.75 | 26.1 | 6596.78 | 1187.42 | 7784.2 | 2.5 | 252.75 | 6596.78 | 1187.42 | 7784.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | UTI. Vermiculture | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Fabrication work lumpsum -SOSB | No. | 1 | 8900 | 8900 | 1602 | 10502 | 2.5 | 1 | 8900 | 1602 | 10502 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Bending & Cutting(L) - SOSB | No. | 1 | 3800 | 3800 | 684 | 4484 | 2.5 | 1 | 3800 | 684 | 4484 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet Fixing (L) | Sq.Ft | 492.05 | 26.1 | 12842.51 | 2311.66 | 15154.17 | 2.5 | 492.05 | 12842.51 | 2311.66 | 15154.17 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | UTI. Vermiculture | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Fabrication work (L) | Kgs | 1371.25 | 22.5 | 30853.13 | 5553.56 | 36406.69 | 2.5 | 1371.25 | 30853.13 | 5553.56 | 36406.69 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet Fixing (L) | Sq.Ft | 81.99 | 26.1 | 2139.94 | 385.18 | 2525.12 | 2.5 | 81.99 | 2139.94 | 385.18 | 2525.12 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | UTI. Vermiculture | Approved | chetan.jewalikar
EAST POINT MARKET | 93 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Transport Charges | No. | 1 | 25000 | 25000 | 4500 | 29500 | 2.5 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 94 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet (M) | Kgs | 552.76 | 58 | 32060.08 | 5770.82 | 37830.9 | 0 | 552.76 | 32060.08 | 5770.82 | 37830.9 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 94 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | Fabrication work (M) | Kgs | 1371.25 | 49 | 67191.25 | 12094.42 | 79285.67 | 0 | 1371.25 | 67191.25 | 12094.42 | 79285.67 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 94 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet (M) | Kgs | 1076.11 | 58 | 62414.38 | 11234.58 | 73648.96 | 0 | 1076.11 | 62414.38 | 11234.58 | 73648.96 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 94 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet (M) | Kgs | 1200 | 58 | 69600 | 12528 | 82128 | 0 | 1200 | 69600 | 12528 | 82128 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 94 | 0 | 11 Dec 2021 | R.T.S. STEEL SERVICES | KEP-Structural+Attrium roofing MS Gutter channel work | GI Sheet (M) | Kgs | 179.31 | 58 | 10399.98 | 1872 | 12271.98 | 0 | 179.31 | 10399.98 | 1872 | 12271.98 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 95 | 0 | 14 Dec 2021 | KAMAL FIRE FIGHTING SYSTEM | KEP-2nd Floor Shesha World Shop.No.4 Fire Fighting | Lumpsum work- DCW | No. | 1 | 25000 | 25000 | 4500 | 29500 | 2.5 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 96 | 0 | 14 Dec 2021 | M/S ABHINAV SINGH | KEP-Foodcourt Area -Deep Cleaning Work | Deep Cleaning work | Sq.Ft | 9048.33 | 3 | 27144.99 | 4886.1 | 32031.09 | 2.5 | 0 | 0 | 0 | 0 | 9048.33 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 96 | 0 | 14 Dec 2021 | M/S ABHINAV SINGH | KEP- Staircase Basement to 4th Fl-Deep Cleaning Work | Deep Cleaning work | Sq.Ft | 2694.88 | 3 | 8084.64 | 1455.24 | 9539.88 | 2.5 | 0 | 0 | 0 | 0 | 2694.88 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 96 | 0 | 14 Dec 2021 | M/S ABHINAV SINGH | KEP-1st to 2nd Fl Commonn Passage Deep Cleaning Work | Deep Cleaning work | Sq.Ft | 5168.66 | 3 | 15505.98 | 2791.08 | 18297.06 | 2.5 | 0 | 0 | 0 | 0 | 5168.66 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 96 | 0 | 14 Dec 2021 | M/S ABHINAV SINGH | KEP-Toilets Gr Fl to 3rd Fl- Deep Cleaning Work | Deep Cleaning work | Sq.Ft | 9056.44 | 3 | 27169.32 | 4890.48 | 32059.8 | 2.5 | 0 | 0 | 0 | 0 | 9056.44 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar
EAST POINT MARKET | 97 | 0 | 17 Dec 2021 | SAHARA ENGINEERING | KEP- Front & Railway Side Scaffolding Work | Scaffolding work | Sq.Ft | 12561.75 | 12 | 150741 | 27133.38 | 177874.38 | 0 | 12561.75 | 150741 | 27133.38 | 177874.38 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | chetan.jewalikar
EAST POINT MARKET | 98 | 0 | 17 Dec 2021 | SAHARA ENGINEERING | KEP- Scaffolding for Plumbing Line Rework | Scaffolding work | Sq.Ft | 3250 | 23 | 74750 | 13455 | 88205 | 0 | 3250 | 74750 | 13455 | 88205 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Superstructure | Approved | chetan.jewalikar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 70 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 102 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 100 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 57 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 115 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 47 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 60 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 61 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 Sinage | ACP Work- (L) | Sq.Ft | 158.451 | 75 | 11883.83 | 2139.08 | 14022.91 | 2.5 | 0 | 0 | 0 | 0 | 158.451 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 55 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 46 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 94 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 54 Sinage | ACP Work- (L) | Sq.Ft | 113.002 | 75 | 8475.15 | 1525.52 | 10000.67 | 2.5 | 0 | 0 | 0 | 0 | 113.002 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 Sinage | ACP Work- (L) | Sq.Ft | 160.636 | 75 | 12047.7 | 2168.58 | 14216.28 | 2.5 | 0 | 0 | 0 | 0 | 160.636 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (L) | Sq.Ft | 81.1 | 75 | 6082.5 | 1094.86 | 7177.36 | 2.5 | 81.0533 | 6079 | 1094.22 | 7173.22 | 0.0467 | 4.14 |  | 99.9424 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (L) | Sq.Ft | 109.94 | 75 | 8245.5 | 1484.2 | 9729.7 | 2.5 | 109.9067 | 8243 | 1483.74 | 9726.74 | 0.0333 | 2.96 |  | 99.9697 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (L) | Sq.Ft | 1.731 | 75 | 129.83 | 23.36 | 153.19 | 2.5 | 1.731 | 129.83 | 23.36 | 153.19 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (L) | Sq.Ft | 145.778 | 75 | 10933.35 | 1968 | 12901.35 | 2.5 | 145.7733 | 10933 | 1967.94 | 12900.94 | 0.0047 | 0.41 |  | 99.9968 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 33 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (L) | Sq.Ft | 165.31 | 75 | 12398.25 | 2231.68 | 14629.93 | 2.5 | 165.3067 | 12398 | 2231.64 | 14629.64 | 0.0033 | 0.29 |  | 99.998 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 4th Fl. Community Hall Chajja ACP work | ACP Sheet (L) | Sq.Ft | 34 | 60 | 2040 | 367.2 | 2407.2 | 2.5 | 34 | 2040 | 367.2 | 2407.2 | 0 | 0 | Railway Station side Community hall Chajja work. | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 48 Sinage | ACP Work- (L) | Sq.Ft | 113.439 | 75 | 8507.93 | 1531.42 | 10039.35 | 2.5 | 0 | 0 | 0 | 0 | 113.439 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 19.18 | 1150.8 | 207.14 | 1357.94 | 5.685 | 402.5 |  | 77.1365 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 41 Sinage | ACP Work- (L) | Sq.Ft | 133.167 | 75 | 9987.53 | 1797.76 | 11785.29 | 2.5 | 0 | 0 | 0 | 0 | 133.167 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 95 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 79 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 105 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 47 Sinage | ACP Work- (L) | Sq.Ft | 124.801 | 75 | 9360.08 | 1684.82 | 11044.9 | 2.5 | 0 | 0 | 0 | 0 | 124.801 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 Sinage | ACP Work- (L) | Sq.Ft | 109.818 | 75 | 8236.35 | 1482.54 | 9718.89 | 2.5 | 0 | 0 | 0 | 0 | 109.818 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 Sinage | ACP Work- (L) | Sq.Ft | 200.376 | 75 | 15028.2 | 2705.08 | 17733.28 | 2.5 | 0 | 0 | 0 | 0 | 200.376 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 Sinage | ACP Work- (L) | Sq.Ft | 124.801 | 75 | 9360.08 | 1684.82 | 11044.9 | 2.5 | 124.21 | 9315.75 | 1676.84 | 10992.59 | 0.591 | 52.31 |  | 99.5264 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (L) | Sq.Ft | 12.939 | 75 | 970.43 | 174.68 | 1145.11 | 2.5 | 12.9333 | 970 | 174.6 | 1144.6 | 0.0057 | 0.51 |  | 99.9559 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 84 Sinage | ACP Work- (L) | Sq.Ft | 301.856 | 75 | 22639.2 | 4075.06 | 26714.26 | 2.5 | 254.31 | 19073.25 | 3433.18 | 22506.43 | 47.546 | 4207.83 |  | 84.2488 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 49 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 103 Sinage | ACP Work- (L) | Sq.Ft | 256.237 | 75 | 19217.78 | 3459.2 | 22676.98 | 2.5 | 234.9867 | 17624 | 3172.32 | 20796.32 | 21.2503 | 1880.65 |  | 91.7068 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 39 Sinage | ACP Work- (L) | Sq.Ft | 101.639 | 75 | 7622.93 | 1372.12 | 8995.05 | 2.5 | 0 | 0 | 0 | 0 | 101.639 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 58 Sinage | ACP Work- (L) | Sq.Ft | 152.333 | 75 | 11424.98 | 2056.5 | 13481.48 | 2.5 | 0 | 0 | 0 | 0 | 152.333 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 38 Sinage | ACP Work- (L) | Sq.Ft | 110.379 | 75 | 8278.43 | 1490.12 | 9768.55 | 2.5 | 0 | 0 | 0 | 0 | 110.379 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 27 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 98 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 95 Sinage | ACP Work- (L) | Sq.Ft | 109.942 | 75 | 8245.65 | 1484.22 | 9729.87 | 2.5 | 109.7333 | 8230 | 1481.4 | 9711.4 | 0.2087 | 18.47 |  | 99.8102 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 80 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 99 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 45 Sinage | ACP Work- (L) | Sq.Ft | 104.698 | 75 | 7852.35 | 1413.42 | 9265.77 | 2.5 | 0 | 0 | 0 | 0 | 104.698 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 29 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 112 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 81 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 117 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 56 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 39 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 80 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 89 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 94 Sinage | ACP Work- (L) | Sq.Ft | 119.12 | 75 | 8934 | 1608.12 | 10542.12 | 2.5 | 0 | 0 | 0 | 0 | 119.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (L) | Sq.Ft | 113.5 | 75 | 8512.5 | 1532.26 | 10044.76 | 2.5 | 94.98 | 7123.5 | 1282.24 | 8405.74 | 18.52 | 1639.02 |  | 83.6828 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 13 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 3 | 17 Dec 2021 | SAHARA ENGINEERING | 3rd Fl. Mall Management Office ACP work | ACP Sheet (L) | Sq.Ft | 730.33 | 88.5 | 64634.21 | 11634.16 | 76268.37 | 2.5 | 0 | 0 | 0 | 0 | 730.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 104 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 33 Sinage | ACP Work- (L) | Sq.Ft | 124.614 | 75 | 9346.05 | 1682.28 | 11028.33 | 2.5 | 0 | 0 | 0 | 0 | 124.614 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 Sinage | ACP Work- (L) | Sq.Ft | 157.112 | 75 | 11783.4 | 2121.02 | 13904.42 | 2.5 | 135.91 | 10193.25 | 1834.78 | 12028.03 | 21.202 | 1876.39 |  | 86.5052 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 13 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 96 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 33 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 94 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 30 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 81 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 97 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 108 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 31 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (L) | Sq.Ft | 3.97 | 75 | 297.75 | 53.6 | 351.35 | 2.5 | 3.97 | 297.75 | 53.6 | 351.35 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 111 Sinage | ACP Work- (L) | Sq.Ft | 129.171 | 75 | 9687.83 | 1743.8 | 11431.63 | 2.5 | 122.589 | 9194.18 | 1654.96 | 10849.14 | 6.582 | 582.49 |  | 94.9044 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 09 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 52 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 76 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 10 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 106 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 103 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 64 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 89 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 47 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (L) | Sq.Ft | 133.34 | 75 | 10000.5 | 1800.1 | 11800.6 | 2.5 | 0 | 0 | 0 | 0 | 133.34 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 93 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 80 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 38 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 41 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 109 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 88 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 75 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 91 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 113 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 78 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 110 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 14 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 37 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 28 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 corner gap covering - 1 Job | ACP Work- (L) | Sq.Ft | 12.432 | 60 | 745.92 | 134.26 | 880.18 | 2.5 | 0 | 0 | 0 | 0 | 12.432 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 44 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 47 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 83 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 61 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 32 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 93 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 22 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 36 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 117 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 95 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 111 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 27 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 82 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 38 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 73 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 105 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 31 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 99 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 71 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 26 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 77 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 42 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 87 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 48 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 58 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 74 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 106 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 04 Glass Door with fix glass - 49.78 Sq.F | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 69 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 53 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 270.1 | 75 | 20257.5 | 3646.36 | 23903.86 | 2.5 | 270.1 | 20257.5 | 3646.36 | 23903.86 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 82 Sinage | ACP Work- (L) | Sq.Ft | 103.824 | 75 | 7786.8 | 1401.62 | 9188.42 | 2.5 | 81.289 | 6096.68 | 1097.4 | 7194.08 | 22.535 | 1994.35 |  | 78.295 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 Sinage | ACP Work- (L) | Sq.Ft | 150.1 | 75 | 11257.5 | 2026.36 | 13283.86 | 2.5 | 118.178 | 8863.35 | 1595.4 | 10458.75 | 31.922 | 2825.11 |  | 78.7328 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 79 Sinage | ACP Work- (L) | Sq.Ft | 131.356 | 75 | 9851.7 | 1773.3 | 11625 | 2.5 | 0 | 0 | 0 | 0 | 131.356 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 116 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 42 Sinage | ACP Work- (L) | Sq.Ft | 328.202 | 75 | 24615.15 | 4430.72 | 29045.87 | 2.5 | 278.96 | 20922 | 3765.96 | 24687.96 | 49.242 | 4357.91 |  | 84.9964 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 Sinage | ACP Work- (L) | Sq.Ft | 119.12 | 75 | 8934 | 1608.12 | 10542.12 | 2.5 | 114.4 | 8580 | 1544.4 | 10124.4 | 4.72 | 417.72 |  | 96.0376 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 90 Sinage | ACP Work- (L) | Sq.Ft | 332.572 | 75 | 24942.9 | 4489.72 | 29432.62 | 2.5 | 0 | 0 | 0 | 0 | 332.572 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 41 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 88 Sinage | ACP Work- (L) | Sq.Ft | 286.561 | 75 | 21492.08 | 3868.58 | 25360.66 | 2.5 | 253.56 | 19017 | 3423.06 | 22440.06 | 33.001 | 2920.6 |  | 88.4838 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (L) | Sq.Ft | 9.128 | 75 | 684.6 | 123.22 | 807.82 | 2.5 | 9.128 | 684.6 | 123.22 | 807.82 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 corner gap covering | ACP Work- (L) | Sq.Ft | 22.733 | 60 | 1363.98 | 245.52 | 1609.5 | 2.5 | 19.18 | 1150.8 | 207.14 | 1357.94 | 3.553 | 251.56 |  | 84.3707 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 91 Sinage | ACP Work- (L) | Sq.Ft | 123.365 | 75 | 9252.38 | 1665.42 | 10917.8 | 2.5 | 0 | 0 | 0 | 0 | 123.365 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 Sinage | ACP Work- (L) | Sq.Ft | 105.135 | 75 | 7885.13 | 1419.32 | 9304.45 | 2.5 | 0 | 0 | 0 | 0 | 105.135 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 30 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (L) | Sq.Ft | 272.139 | 75 | 20410.43 | 3673.88 | 24084.31 | 2.5 | 272.1333 | 20410 | 3673.8 | 24083.8 | 0.0057 | 0.51 |  | 99.9979 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (L) | Sq.Ft | 11.288 | 75 | 846.6 | 152.38 | 998.98 | 2.5 | 11.288 | 846.6 | 152.38 | 998.98 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (L) | Sq.Ft | 6.277 | 75 | 470.78 | 84.74 | 555.52 | 2.5 | 6.277 | 470.78 | 84.74 | 555.52 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 36 Sinage | ACP Work- (L) | Sq.Ft | 110.817 | 75 | 8311.28 | 1496.04 | 9807.32 | 2.5 | 0 | 0 | 0 | 0 | 110.817 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 117 Sinage | ACP Work- (L) | Sq.Ft | 254.584 | 75 | 19093.8 | 3436.88 | 22530.68 | 2.5 | 241.2667 | 18095 | 3257.1 | 21352.1 | 13.3173 | 1178.58 |  | 94.769 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (L) | Sq.Ft | 12.192 | 60 | 731.52 | 131.68 | 863.2 | 2.5 | 12.192 | 731.52 | 131.68 | 863.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 98 Sinage | ACP Work- (L) | Sq.Ft | 99.766 | 75 | 7482.45 | 1346.84 | 8829.29 | 2.5 | 80.64 | 6048 | 1088.64 | 7136.64 | 19.126 | 1692.65 |  | 80.8291 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 90 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 59 Sinage | ACP Work- (L) | Sq.Ft | 280.006 | 75 | 21000.45 | 3780.08 | 24780.53 | 2.5 | 250.5998 | 18794.99 | 3383.1 | 22178.09 | 29.4062 | 2602.45 |  | 89.498 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 57 Sinage | ACP Work- (L) | Sq.Ft | 305.352 | 75 | 22901.4 | 4122.26 | 27023.66 | 2.5 | 297.04 | 22278 | 4010.04 | 26288.04 | 8.312 | 735.62 |  | 97.2779 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 27 Sinage | ACP Work- (L) | Sq.Ft | 168.065 | 75 | 12604.88 | 2268.88 | 14873.76 | 2.5 | 0 | 0 | 0 | 0 | 168.065 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 21 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd flr. Window ACP covering work | ACP Sheet (L) | Sq.Ft | 21.3 | 60 | 1278 | 230.04 | 1508.04 | 2.5 | 21.3 | 1278 | 230.04 | 1508.04 | 0 | 0 | ACP Sheet fixing for window covering. | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 52 Sinage | ACP Work- (L) | Sq.Ft | 109.505 | 75 | 8212.88 | 1478.32 | 9691.2 | 2.5 | 0 | 0 | 0 | 0 | 109.505 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 65 Sinage | ACP Work- (L) | Sq.Ft | 129.171 | 75 | 9687.83 | 1743.8 | 11431.63 | 2.5 | 0 | 0 | 0 | 0 | 129.171 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 30 Sinage | ACP Work- (L) | Sq.Ft | 293.553 | 75 | 22016.48 | 3962.96 | 25979.44 | 2.5 | 0 | 0 | 0 | 0 | 293.553 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 57 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 28 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 32 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 60 Sinage | ACP Work- (L) | Sq.Ft | 103.824 | 75 | 7786.8 | 1401.62 | 9188.42 | 2.5 | 102.71 | 7703.25 | 1386.58 | 9089.83 | 1.114 | 98.59 |  | 98.927 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 Sinage | ACP Work- (L) | Sq.Ft | 102.513 | 75 | 7688.48 | 1383.92 | 9072.4 | 2.5 | 95.41 | 7155.75 | 1288.04 | 8443.79 | 7.103 | 628.61 |  | 93.0711 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 34 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | Escalator side ACP sheet fixing | ACP Sheet (L) | Sq.Ft | 334.74 | 60 | 20084.4 | 3615.2 | 23699.6 | 2.5 | 334.74 | 20084.4 | 3615.2 | 23699.6 | 0 | 0 | Gray Colour ACP Sheet fixing work Escalator side Railing Box. | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 64 Sinage | ACP Work- (L) | Sq.Ft | 185.109 | 75 | 13883.18 | 2498.98 | 16382.16 | 2.5 | 0 | 0 | 0 | 0 | 185.109 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 112 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (L) | Sq.Ft | 142.89 | 75 | 10716.75 | 1929.02 | 12645.77 | 2.5 | 0 | 0 | 0 | 0 | 142.89 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 89 Sinage | ACP Work- (L) | Sq.Ft | 443.139 | 75 | 33235.43 | 5982.38 | 39217.81 | 2.5 | 311.16 | 23337 | 4200.66 | 27537.66 | 131.979 | 11680.15 |  | 70.2172 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 30 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 Sinage | ACP Work- (L) | Sq.Ft | 137.446 | 75 | 10308.45 | 1855.52 | 12163.97 | 2.5 | 88.09 | 6606.75 | 1189.22 | 7795.97 | 49.356 | 4368 |  | 64.0906 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 3rd Fl. Mall Management Office ACP work | ACP Sheet (L) | Sq.Ft | 45.07 | 60 | 2704.2 | 486.76 | 3190.96 | 2.5 | 45.07 | 2704.2 | 486.76 | 3190.96 | 0 | 0 | ACP Fixing for Pantry wall due to Copper wiring & Above Conferance door. | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 110 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 Sinage | ACP Work- (L) | Sq.Ft | 167.628 | 75 | 12572.1 | 2262.98 | 14835.08 | 2.5 | 0 | 0 | 0 | 0 | 167.628 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 46 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 corner gap covering - 1 Job | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 46 Sinage | ACP Work- (L) | Sq.Ft | 88.092 | 75 | 6606.9 | 1189.24 | 7796.14 | 2.5 | 0 | 0 | 0 | 0 | 88.092 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (L) | Sq.Ft | 131.356 | 75 | 9851.7 | 1773.3 | 11625 | 2.5 | 131.356 | 9851.7 | 1773.3 | 11625 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 44 Sinage | ACP Work- (L) | Sq.Ft | 116.937 | 75 | 8770.28 | 1578.66 | 10348.94 | 2.5 | 0 | 0 | 0 | 0 | 116.937 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 Sinage | ACP Work- (L) | Sq.Ft | 121.804 | 75 | 9135.3 | 1644.36 | 10779.66 | 2.5 | 0 | 0 | 0 | 0 | 121.804 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 28 Sinage | ACP Work- (L) | Sq.Ft | 165.443 | 75 | 12408.23 | 2233.48 | 14641.71 | 2.5 | 0 | 0 | 0 | 0 | 165.443 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 46 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 29 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 3rd Fl. Slab, Beam ACP sheet fixing | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | ACP Sheet fixing bothside of Escalator beam. | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Building Common Items | Cancelled | Dushant Gore | 21 Sep 2022
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (L) | Sq.Ft | 15.784 | 75 | 1183.8 | 213.08 | 1396.88 | 2.5 | 15.784 | 1183.8 | 213.08 | 1396.88 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 112 Sinage | ACP Work- (L) | Sq.Ft | 120.431 | 75 | 9032.33 | 1625.82 | 10658.15 | 2.5 | 120.431 | 9032.33 | 1625.82 | 10658.15 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 39 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 67 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 corner gap covering | ACP Work- (L) | Sq.Ft | 11.367 | 60 | 682.02 | 122.76 | 804.78 | 2.5 | 9.59 | 575.4 | 103.58 | 678.98 | 1.777 | 125.8 |  | 84.367 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 Sinage | ACP Work- (L) | Sq.Ft | 146.187 | 75 | 10964.03 | 1973.52 | 12937.55 | 2.5 | 143.7 | 10777.5 | 1939.96 | 12717.46 | 2.487 | 220.09 |  | 98.2988 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 107 Sinage | ACP Work- (L) | Sq.Ft | 128.797 | 75 | 9659.78 | 1738.76 | 11398.54 | 2.5 | 109.95 | 8246.25 | 1484.32 | 9730.57 | 18.847 | 1667.97 |  | 85.3669 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 51 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 32 Sinage | ACP Work- (L) | Sq.Ft | 319.587 | 75 | 23969.03 | 4314.42 | 28283.45 | 2.5 | 0 | 0 | 0 | 0 | 319.587 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (L) | Sq.Ft | 144.966 | 75 | 10872.45 | 1957.04 | 12829.49 | 2.5 | 144.966 | 10872.45 | 1957.04 | 12829.49 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 58 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 18 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 09 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 44 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 11 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 48 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 32 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 61 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 50 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 89 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 40 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 85 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 29 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 16 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 32 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 52 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 35 Sinage | ACP Work- (L) | Sq.Ft | 310.519 | 75 | 23288.93 | 4192 | 27480.93 | 2.5 | 0 | 0 | 0 | 0 | 310.519 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 29 Sinage | ACP Work- (L) | Sq.Ft | 138.598 | 75 | 10394.85 | 1871.08 | 12265.93 | 2.5 | 0 | 0 | 0 | 0 | 138.598 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (L) | Sq.Ft | 1.169 | 75 | 87.68 | 15.78 | 103.46 | 2.5 | 1.169 | 87.68 | 15.78 | 103.46 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 48 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 28 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 37 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 92 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 50 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 43 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 72 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 60 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 41 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 Sinage | ACP Work- (L) | Sq.Ft | 160.199 | 75 | 12014.93 | 2162.68 | 14177.61 | 2.5 | 0 | 0 | 0 | 0 | 160.199 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 45 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 41 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 108 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 92 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (L) | Sq.Ft | 9.618 | 75 | 721.35 | 129.84 | 851.19 | 2.5 | 9.6133 | 721 | 129.78 | 850.78 | 0.0047 | 0.41 |  | 99.9511 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 109 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 103 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 83 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 Sinage | ACP Work- (L) | Sq.Ft | 288.4 | 75 | 21630 | 3893.4 | 25523.4 | 2.5 | 239.159 | 17936.93 | 3228.64 | 21165.57 | 49.241 | 4357.84 |  | 82.9261 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 104 Sinage | ACP Work- (L) | Sq.Ft | 125.238 | 75 | 9392.85 | 1690.72 | 11083.57 | 2.5 | 109.9467 | 8246 | 1484.28 | 9730.28 | 15.2913 | 1353.29 |  | 87.7902 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 75 Sinage | ACP Work- (L) | Sq.Ft | 162.091 | 75 | 12156.83 | 2188.22 | 14345.05 | 2.5 | 144.9467 | 10871 | 1956.78 | 12827.78 | 17.1443 | 1517.26 |  | 89.423 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 78 Sinage | ACP Work- (L) | Sq.Ft | 109.818 | 75 | 8236.35 | 1482.54 | 9718.89 | 2.5 | 81.5 | 6112.5 | 1100.26 | 7212.76 | 28.318 | 2506.13 |  | 74.2137 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 82 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 107 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (L) | Sq.Ft | 126.112 | 75 | 9458.4 | 1702.52 | 11160.92 | 2.5 | 126.112 | 9458.4 | 1702.52 | 11160.92 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 17 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 27 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 35 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (L) | Sq.Ft | 119.557 | 75 | 8966.78 | 1614.02 | 10580.8 | 2.5 | 110.524 | 8289.3 | 1492.08 | 9781.38 | 9.033 | 799.42 |  | 92.4446 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 19 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 49 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 91 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 40 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 75 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 33 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 73 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 60 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 54 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 79 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 99 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 36 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 81 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 59 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 102 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 65 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 49 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 56 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 33 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 38 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 64 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 99 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 52 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 61 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 45 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 98 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 04 Glass Door with fix glass - 49.78 Sq.F | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 104 Glass Door with fix glass - 69.11 Sq.F | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 98 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 63 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 95 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 47 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 86 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 80 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 35 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 78 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 75 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 65 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 52 corner gap covering - 1 Job | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 64 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 90 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 60 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 103 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 31 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 83 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 39 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 30 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 62 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 59 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 36 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 107 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 71 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 65 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 39 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 68 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 17 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 46 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 23 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 91 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 10 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 104 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 42 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 67 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 14 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 11 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 34 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 56 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 66 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 79 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 54 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 112 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 103 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 51 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 54 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 48 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 45 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 42 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 0 | 17 Dec 2021 | SAHARA ENGINEERING | KEP-2nd Fl Atrium PeripheryGlass Wall | Toughen Glass 12mm (M) | Sq.Ft | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 17 Dec 2021
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 35 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 29 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 64 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 53 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 91 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 55 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 89 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 12 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 102 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 57 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 38 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 84 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 87 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 88 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 78 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 51 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 107 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 84 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 62 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 55 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 20 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 101 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 117 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 55 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 85 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 49 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 19 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 90 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 68 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 113 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 62 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 97 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 18 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 79 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 43 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 63 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 24 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 104 Glass Door with fix glass - 69.11 Sq.F | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 98 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 37 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 69 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 84 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 94 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 26 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 116 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 114 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 24 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 28 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 54 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 105 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 72 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 50 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 66 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 88 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 27 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 114 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 100 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 84 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 75 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 107 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 100 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 34 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 63 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 105 Sinage | ACP Work- (L) | Sq.Ft | 352.977 | 75 | 26473.28 | 4765.2 | 31238.48 | 2.5 | 275.9607 | 20697.05 | 3725.48 | 24422.53 | 77.0163 | 6815.94 |  | 78.1809 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 40 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 85 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 86 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 35 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 100 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 42 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 51 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 23 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 108 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 83 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 76 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 44 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 77 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 88 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 59 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 16 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 96 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 115 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 25 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 15 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 63 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 15 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 57 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 12 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 74 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 45 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 25 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 53 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 82 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 111 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 111 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 53 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 101 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 59 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 21 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd Fl. Atrium Lobby ACP sheet fixing | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Atrium lobby area Golden Colour sheet fixing work. | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Building Common Items | Cancelled | Dushant Gore | 21 Sep 2022
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 95 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 14 Oct 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 22 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 34 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 31 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 58 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 112 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 90 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 4th Fl. Slab, Beam ACP sheet fixing | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | ACP Sheet fixing for Slab Beam,Escalator Front side,Facade side beam. | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Building Common Items | Cancelled | Dushant Gore | 21 Sep 2022
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 117 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 26 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 81 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 50 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 111 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 70 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 85 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 44 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 36 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 105 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 62 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 58 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 20 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 92 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 56 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 102 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 82 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 Sinage | ACP Work- (L) | Sq.Ft | 101.202 | 75 | 7590.15 | 1366.22 | 8956.37 | 2.5 | 88.08 | 6606 | 1189.08 | 7795.08 | 13.122 | 1161.29 |  | 87.0339 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 Sinage | ACP Work- (L) | Sq.Ft | 126.986 | 75 | 9523.95 | 1714.32 | 11238.27 | 2.5 | 0 | 0 | 0 | 0 | 126.986 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 corner gap covering | ACP Work- (L) | Sq.Ft | 11.367 | 60 | 682.02 | 122.76 | 804.78 | 2.5 | 9.59 | 575.4 | 103.58 | 678.98 | 1.777 | 125.8 |  | 84.367 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (L) | Sq.Ft | 276.947 | 75 | 20771.03 | 3738.78 | 24509.81 | 2.5 | 276.947 | 20771.03 | 3738.78 | 24509.81 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 Sinage | ACP Work- (L) | Sq.Ft | 126.549 | 75 | 9491.18 | 1708.42 | 11199.6 | 2.5 | 98.5719 | 7392.89 | 1330.72 | 8723.61 | 27.9771 | 2475.98 |  | 77.8923 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 83 Sinage | ACP Work- (L) | Sq.Ft | 138.348 | 75 | 10376.1 | 1867.7 | 12243.8 | 2.5 | 107.43 | 8057.25 | 1450.3 | 9507.55 | 30.918 | 2736.25 |  | 77.652 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 56 Sinage | ACP Work- (L) | Sq.Ft | 359.542 | 75 | 26965.65 | 4853.82 | 31819.47 | 2.5 | 0 | 0 | 0 | 0 | 359.542 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 Sinage | ACP Work- (L) | Sq.Ft | 379.27 | 75 | 28445.25 | 5120.14 | 33565.39 | 2.5 | 0 | 0 | 0 | 0 | 379.27 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 65 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 94 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 Sinage | ACP Work- (L) | Sq.Ft | 159.734 | 75 | 11980.05 | 2156.4 | 14136.45 | 2.5 | 0 | 0 | 0 | 0 | 159.734 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 Sinage | ACP Work- (L) | Sq.Ft | 70.723 | 75 | 5304.23 | 954.76 | 6258.99 | 2.5 | 0 | 0 | 0 | 0 | 70.723 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 78 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (L) | Sq.Ft | 99.454 | 75 | 7459.05 | 1342.62 | 8801.67 | 2.5 | 99.454 | 7459.05 | 1342.62 | 8801.67 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 55 Sinage | ACP Work- (L) | Sq.Ft | 112.128 | 75 | 8409.6 | 1513.72 | 9923.32 | 2.5 | 0 | 0 | 0 | 0 | 112.128 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 34 Sinage | ACP Work- (L) | Sq.Ft | 111.316 | 75 | 8348.7 | 1502.76 | 9851.46 | 2.5 | 0 | 0 | 0 | 0 | 111.316 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 102 Sinage | ACP Work- (L) | Sq.Ft | 109.755 | 75 | 8231.63 | 1481.7 | 9713.33 | 2.5 | 92.6533 | 6949 | 1250.82 | 8199.82 | 17.1017 | 1513.51 |  | 84.4183 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 0 | 17 Dec 2021 | SAHARA ENGINEERING | KEP-2nd Fl Atrium PeripheryGlass Wall | Toughen Glass 12mm (L) | Sq.Ft | 1000 | 150 | 150000 | 27000 | 177000 | 2.5 | 1000 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open |  |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 corner gap covering | ACP Work- (L) | Sq.Ft | 22.733 | 60 | 1363.98 | 245.52 | 1609.5 | 2.5 | 19.18 | 1150.8 | 207.14 | 1357.94 | 3.553 | 251.56 |  | 84.3707 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (L) | Sq.Ft | 130.415 | 75 | 9781.13 | 1760.6 | 11541.73 | 2.5 | 119.06 | 8929.5 | 1607.32 | 10536.82 | 11.355 | 1004.91 |  | 91.2932 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 63 Sinage | ACP Work- (L) | Sq.Ft | 117.809 | 75 | 8835.68 | 1590.42 | 10426.1 | 2.5 | 0 | 0 | 0 | 0 | 117.809 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 80 Sinage | ACP Work- (L) | Sq.Ft | 139.222 | 75 | 10441.65 | 1879.5 | 12321.15 | 2.5 | 0 | 0 | 0 | 0 | 139.222 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 53 Sinage | ACP Work- (L) | Sq.Ft | 115.624 | 75 | 8671.8 | 1560.92 | 10232.72 | 2.5 | 0 | 0 | 0 | 0 | 115.624 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (L) | Sq.Ft | 98.58 | 75 | 7393.5 | 1330.84 | 8724.34 | 2.5 | 98.58 | 7393.5 | 1330.84 | 8724.34 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 Sinage | ACP Work- (L) | Sq.Ft | 125.113 | 75 | 9383.48 | 1689.02 | 11072.5 | 2.5 | 115.0267 | 8627 | 1552.86 | 10179.86 | 10.0863 | 892.63 |  | 91.9382 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 corner gap covering | ACP Work- (L) | Sq.Ft | 12.378 | 60 | 742.68 | 133.68 | 876.36 | 2.5 | 0 | 0 | 0 | 0 | 12.378 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 corner gap covering | ACP Work- (L) | Sq.Ft | 22.733 | 60 | 1363.98 | 245.52 | 1609.5 | 2.5 | 0 | 0 | 0 | 0 | 22.733 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 corner gap covering | ACP Work- (L) | Sq.Ft | 12.432 | 60 | 745.92 | 134.26 | 880.18 | 2.5 | 0 | 0 | 0 | 0 | 12.432 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 corner gap covering | ACP Work- (L) | Sq.Ft | 22.733 | 60 | 1363.98 | 245.52 | 1609.5 | 2.5 | 0 | 0 | 0 | 0 | 22.733 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 37 Sinage | ACP Work- (L) | Sq.Ft | 103.824 | 75 | 7786.8 | 1401.62 | 9188.42 | 2.5 | 0 | 0 | 0 | 0 | 103.824 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 50 Sinage | ACP Work- (L) | Sq.Ft | 104.261 | 75 | 7819.58 | 1407.52 | 9227.1 | 2.5 | 0 | 0 | 0 | 0 | 104.261 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 40 Sinage | ACP Work- (L) | Sq.Ft | 337.692 | 75 | 25326.9 | 4558.84 | 29885.74 | 2.5 | 0 | 0 | 0 | 0 | 337.692 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 108 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 Sinage | ACP Work- (L) | Sq.Ft | 104.261 | 75 | 7819.58 | 1407.52 | 9227.1 | 2.5 | 0 | 0 | 0 | 0 | 104.261 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | Rly. Stn. side glass replacement | Labour Lumpsum | No. | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 37 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 13.073 | 75 | 980.48 | 176.48 | 1156.96 | 2.5 | 13.0667 | 980 | 176.4 | 1156.4 | 0.0063 | 0.55 |  | 99.9518 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 49 Sinage | ACP Work- (L) | Sq.Ft | 108.194 | 75 | 8114.55 | 1460.62 | 9575.17 | 2.5 | 0 | 0 | 0 | 0 | 108.194 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 62 Sinage | ACP Work- (L) | Sq.Ft | 365.247 | 75 | 27393.53 | 4930.84 | 32324.37 | 2.5 | 0 | 0 | 0 | 0 | 365.247 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (L) | Sq.Ft | 4.189 | 75 | 314.18 | 56.56 | 370.74 | 2.5 | 4.1867 | 314 | 56.52 | 370.52 | 0.0023 | 0.21 |  | 99.9451 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 81 Sinage | ACP Work- (L) | Sq.Ft | 286.561 | 75 | 21492.08 | 3868.58 | 25360.66 | 2.5 | 270.3467 | 20276 | 3649.68 | 23925.68 | 16.2143 | 1434.97 |  | 94.3418 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (L) | Sq.Ft | 93.773 | 75 | 7032.98 | 1265.94 | 8298.92 | 2.5 | 93.7467 | 7031 | 1265.58 | 8296.58 | 0.0263 | 2.33 |  | 99.972 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 99 Sinage | ACP Work- (L) | Sq.Ft | 131.668 | 75 | 9875.1 | 1777.52 | 11652.62 | 2.5 | 99.401 | 7455.08 | 1341.92 | 8797 | 32.267 | 2855.63 |  | 75.4937 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (L) | Sq.Ft | 1.427 | 75 | 107.03 | 19.26 | 126.29 | 2.5 | 1.4267 | 107 | 19.26 | 126.26 | 0.0003 | 0.02 |  | 99.979 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 corner gap covering | ACP Work- (L) | Sq.Ft | 22.733 | 60 | 1363.98 | 245.52 | 1609.5 | 2.5 | 0 | 0 | 0 | 0 | 22.733 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (L) | Sq.Ft | 79.788 | 75 | 5984.1 | 1077.14 | 7061.24 | 2.5 | 79.7867 | 5984 | 1077.12 | 7061.12 | 0.0013 | 0.12 |  | 99.9984 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 100 Sinage | ACP Work- (L) | Sq.Ft | 125.675 | 75 | 9425.63 | 1696.62 | 11122.25 | 2.5 | 120.6 | 9045 | 1628.1 | 10673.1 | 5.075 | 449.15 |  | 95.9618 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 108 Sinage | ACP Work- (L) | Sq.Ft | 134.415 | 75 | 10081.13 | 1814.6 | 11895.73 | 2.5 | 0 | 0 | 0 | 0 | 134.415 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (L) | Sq.Ft | 24.473 | 75 | 1835.48 | 330.38 | 2165.86 | 2.5 | 24.4667 | 1835 | 330.3 | 2165.3 | 0.0063 | 0.55 |  | 99.9743 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 51 Sinage | ACP Work- (L) | Sq.Ft | 106.009 | 75 | 7950.68 | 1431.12 | 9381.8 | 2.5 | 0 | 0 | 0 | 0 | 106.009 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (L) | Sq.Ft | 24.865 | 60 | 1491.9 | 268.54 | 1760.44 | 2.5 | 24.85 | 1491 | 268.38 | 1759.38 | 0.015 | 1.06 |  | 99.9397 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 Sinage | ACP Work- (L) | Sq.Ft | 146.277 | 75 | 10970.78 | 1974.74 | 12945.52 | 2.5 | 0 | 0 | 0 | 0 | 146.277 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 85 Sinage | ACP Work- (L) | Sq.Ft | 139.222 | 75 | 10441.65 | 1879.5 | 12321.15 | 2.5 | 0 | 0 | 0 | 0 | 139.222 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 31 Sinage | ACP Work- (L) | Sq.Ft | 113.501 | 75 | 8512.58 | 1532.26 | 10044.84 | 2.5 | 111.7 | 8377.5 | 1507.96 | 9885.46 | 1.801 | 159.38 |  | 98.4132 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 02 Sinage | ACP Work- (L) | Sq.Ft | 143.873 | 75 | 10790.48 | 1942.28 | 12732.76 | 2.5 | 143.8667 | 10790 | 1942.2 | 12732.2 | 0.0063 | 0.55 |  | 99.9956 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 Sinage | ACP Work- (L) | Sq.Ft | 124.801 | 75 | 9360.08 | 1684.82 | 11044.9 | 2.5 | 0 | 0 | 0 | 0 | 124.801 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 61 Sinage | ACP Work- (L) | Sq.Ft | 224.5 | 75 | 16837.5 | 3030.76 | 19868.26 | 2.5 | 0 | 0 | 0 | 0 | 224.5 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (L) | Sq.Ft | 5.599 | 75 | 419.93 | 75.58 | 495.51 | 2.5 | 5.599 | 419.93 | 75.58 | 495.51 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (L) | Sq.Ft | 102.513 | 75 | 7688.48 | 1383.92 | 9072.4 | 2.5 | 102.5067 | 7688 | 1383.84 | 9071.84 | 0.0063 | 0.55 |  | 99.9939 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 99 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 40 corner gap covering | ACP Work- (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 16 Jun 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 38 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 46 Sinage | ACP Work- (M) | Sq.Ft | 88.09 | 175 | 15415.75 | 2774.84 | 18190.59 | 0 | 0 | 0 | 0 | 0 | 88.09 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 30 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 79 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 64 Sinage | ACP Work- (M) | Sq.Ft | 185.11 | 175 | 32394.25 | 5830.96 | 38225.21 | 0 | 0 | 0 | 0 | 0 | 185.11 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 63 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 63 Sinage | ACP Work- (M) | Sq.Ft | 117.81 | 175 | 20616.75 | 3711.02 | 24327.77 | 0 | 0 | 0 | 0 | 0 | 117.81 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 Sinage | ACP Work- (M) | Sq.Ft | 104.26 | 175 | 18245.5 | 3284.2 | 21529.7 | 0 | 0 | 0 | 0 | 0 | 104.26 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 36 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 48 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 56 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 37 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 50 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 29 Sinage | ACP Work- (M) | Sq.Ft | 138.6 | 175 | 24255 | 4365.9 | 28620.9 | 0 | 0 | 0 | 0 | 0 | 138.6 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (M) | Sq.Ft | 13.073 | 175 | 2287.78 | 411.8 | 2699.58 | 0 | 13.073 | 2287.78 | 411.8 | 2699.58 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 90 Sinage | ACP Work- (M) | Sq.Ft | 332.58 | 175 | 58201.5 | 10476.28 | 68677.78 | 0 | 0 | 0 | 0 | 0 | 332.58 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (M) | Sq.Ft | 79.79 | 175 | 13963.25 | 2513.38 | 16476.63 | 0 | 79.7886 | 13963.01 | 2513.34 | 16476.35 | 0.0014 | 0.29 |  | 99.9982 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 51 Sinage | ACP Work- (M) | Sq.Ft | 106.01 | 175 | 18551.75 | 3339.32 | 21891.07 | 0 | 0 | 0 | 0 | 0 | 106.01 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 61 Sinage | ACP Work- (M) | Sq.Ft | 224.01 | 175 | 39201.75 | 7056.32 | 46258.07 | 0 | 0 | 0 | 0 | 0 | 224.01 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 103 Sinage | ACP Work- (M) | Sq.Ft | 256.24 | 175 | 44842 | 8071.56 | 52913.56 | 0 | 234.9886 | 41123.01 | 7402.14 | 48525.15 | 21.2514 | 4388.42 |  | 91.7064 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 60 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 47 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 46 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (M) | Sq.Ft | 113.94 | 175 | 19939.5 | 3589.12 | 23528.62 | 0 | 94.98 | 16621.5 | 2991.88 | 19613.38 | 18.96 | 3915.24 |  | 83.3597 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 104 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 51 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 65 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (M) | Sq.Ft | 3.966 | 175 | 694.05 | 124.92 | 818.97 | 0 | 3.9657 | 694 | 124.92 | 818.92 | 0.0003 | 0.05 |  | 99.9924 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (M) | Sq.Ft | 165.305 | 175 | 28928.38 | 5207.1 | 34135.48 | 0 | 165.3029 | 28928.01 | 5207.04 | 34135.05 | 0.0021 | 0.43 |  | 99.9987 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 39 Sinage | ACP Work- (M) | Sq.Ft | 101.64 | 175 | 17787 | 3201.66 | 20988.66 | 0 | 0 | 0 | 0 | 0 | 101.64 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 62 Sinage | ACP Work- (M) | Sq.Ft | 365.25 | 175 | 63918.75 | 11505.38 | 75424.13 | 0 | 0 | 0 | 0 | 0 | 365.25 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 55 Sinage | ACP Work- (M) | Sq.Ft | 112.13 | 175 | 19622.75 | 3532.1 | 23154.85 | 0 | 0 | 0 | 0 | 0 | 112.13 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 81 Sinage | ACP Work- (M) | Sq.Ft | 286.56 | 175 | 50148 | 9026.64 | 59174.64 | 0 | 270.3486 | 47311.01 | 8515.98 | 55826.99 | 16.2114 | 3347.66 |  | 94.3428 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 35 Sinage | ACP Work- (M) | Sq.Ft | 306.6 | 175 | 53655 | 9657.9 | 63312.9 | 0 | 0 | 0 | 0 | 0 | 306.6 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 98 Sinage | ACP Work- (M) | Sq.Ft | 99.77 | 175 | 17459.75 | 3142.76 | 20602.51 | 0 | 80.6457 | 14113 | 2540.34 | 16653.34 | 19.1243 | 3949.17 |  | 80.8316 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 3 | 17 Dec 2021 | SAHARA ENGINEERING | 3rd Fl. Mall Management Office ACP work | ACP Sheet (M) | Sq.Ft | 730.33 | 206.5 | 150813.15 | 27146.36 | 177959.51 | 0 | 111.3801 | 22999.99 | 4140 | 27139.99 | 618.9499 | 150819.51 |  | 15.2507 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 28 Sinage | ACP Work- (M) | Sq.Ft | 165.44 | 175 | 28952 | 5211.36 | 34163.36 | 0 | 0 | 0 | 0 | 0 | 165.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 59 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (M) | Sq.Ft | 15.786 | 175 | 2762.55 | 497.26 | 3259.81 | 0 | 15.786 | 2762.55 | 497.26 | 3259.81 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 32 Sinage | ACP Work- (M) | Sq.Ft | 319.59 | 175 | 55928.25 | 10067.08 | 65995.33 | 0 | 0 | 0 | 0 | 0 | 319.59 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (M) | Sq.Ft | 119 | 175 | 20825 | 3748.5 | 24573.5 | 0 | 110.524 | 19341.7 | 3481.5 | 22823.2 | 8.476 | 1750.3 |  | 92.8773 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 107 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 37 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (M) | Sq.Ft | 4.188 | 175 | 732.9 | 131.92 | 864.82 | 0 | 4.188 | 732.9 | 131.92 | 864.82 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 0 | 17 Dec 2021 | SAHARA ENGINEERING | KEP-2nd Fl Atrium PeripheryGlass Wall | Toughen Glass 12mm (M) | Sq.Ft | 1000 | 350 | 350000 | 63000 | 413000 | 0 | 1000 | 350000 | 63000 | 413000 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 corner gap covering | ACP Work- (M) | Sq.Ft | 22.733 | 140 | 3182.62 | 572.88 | 3755.5 | 0 | 0 | 0 | 0 | 0 | 22.733 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (M) | Sq.Ft | 12.939 | 175 | 2264.33 | 407.58 | 2671.91 | 0 | 12.9371 | 2263.99 | 407.52 | 2671.51 | 0.0019 | 0.39 |  | 99.9853 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 35 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 64 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 37 Sinage | ACP Work- (M) | Sq.Ft | 103.83 | 175 | 18170.25 | 3270.64 | 21440.89 | 0 | 0 | 0 | 0 | 0 | 103.83 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 82 Sinage | ACP Work- (M) | Sq.Ft | 103.83 | 175 | 18170.25 | 3270.64 | 21440.89 | 0 | 81.289 | 14225.58 | 2560.6 | 16786.18 | 22.541 | 4654.72 |  | 78.2905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 Sinage | ACP Work- (M) | Sq.Ft | 105.14 | 175 | 18399.5 | 3311.92 | 21711.42 | 0 | 0 | 0 | 0 | 0 | 105.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 corner gap covering | ACP Work- (M) | Sq.Ft | 22.733 | 140 | 3182.62 | 572.88 | 3755.5 | 0 | 0 | 0 | 0 | 0 | 22.733 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 40 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 44 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 89 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 103 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 38 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 Sinage | ACP Work- (M) | Sq.Ft | 125.11 | 175 | 21894.25 | 3940.96 | 25835.21 | 0 | 115.0286 | 20130.01 | 3623.4 | 23753.41 | 10.0814 | 2081.81 |  | 91.942 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 38 Sinage | ACP Work- (M) | Sq.Ft | 110.38 | 175 | 19316.5 | 3476.98 | 22793.48 | 0 | 0 | 0 | 0 | 0 | 110.38 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 31 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 48 Sinage | ACP Work- (M) | Sq.Ft | 113.44 | 175 | 19852 | 3573.36 | 23425.36 | 0 | 0 | 0 | 0 | 0 | 113.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (M) | Sq.Ft | 133.34 | 175 | 23334.5 | 4200.22 | 27534.72 | 0 | 0 | 0 | 0 | 0 | 133.34 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 53 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 78 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 62 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 78 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 94 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (M) | Sq.Ft | 6.28 | 175 | 1099 | 197.82 | 1296.82 | 0 | 6.28 | 1099 | 197.82 | 1296.82 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (M) | Sq.Ft | 12.192 | 140 | 1706.88 | 307.24 | 2014.12 | 0 | 12.192 | 1706.88 | 307.24 | 2014.12 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 52 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 84 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (M) | Sq.Ft | 109.94 | 175 | 19239.5 | 3463.12 | 22702.62 | 0 | 109.9371 | 19238.99 | 3463.02 | 22702.01 | 0.0029 | 0.61 |  | 99.9974 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 79 Sinage | ACP Work- (M) | Sq.Ft | 131.36 | 175 | 22988 | 4137.84 | 27125.84 | 0 | 0 | 0 | 0 | 0 | 131.36 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (M) | Sq.Ft | 102.51 | 175 | 17939.25 | 3229.06 | 21168.31 | 0 | 102.5029 | 17938.01 | 3228.84 | 21166.85 | 0.0071 | 1.46 |  | 99.9931 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 55 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 Sinage | ACP Work- (M) | Sq.Ft | 119.12 | 175 | 20846 | 3752.28 | 24598.28 | 0 | 114.3943 | 20019 | 3603.42 | 23622.42 | 4.7257 | 975.86 |  | 96.0328 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 42 Sinage | ACP Work- (M) | Sq.Ft | 328.21 | 175 | 57436.75 | 10338.62 | 67775.37 | 0 | 278.9543 | 48817 | 8787.06 | 57604.06 | 49.2557 | 10171.31 |  | 84.9926 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 88 Sinage | ACP Work- (M) | Sq.Ft | 286.56 | 175 | 50148 | 9026.64 | 59174.64 | 0 | 253.56 | 44373 | 7987.14 | 52360.14 | 33 | 6814.5 |  | 88.4841 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 85 Sinage | ACP Work- (M) | Sq.Ft | 139.22 | 175 | 24363.5 | 4385.44 | 28748.94 | 0 | 0 | 0 | 0 | 0 | 139.22 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 42 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (M) | Sq.Ft | 131.36 | 175 | 22988 | 4137.84 | 27125.84 | 0 | 131.36 | 22988 | 4137.84 | 27125.84 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 83 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 corner gap covering | ACP Work- (M) | Sq.Ft | 12.432 | 140 | 1740.48 | 313.28 | 2053.76 | 0 | 0 | 0 | 0 | 0 | 12.432 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 98 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 Sinage | ACP Work- (M) | Sq.Ft | 70.72 | 175 | 12376 | 2227.68 | 14603.68 | 0 | 0 | 0 | 0 | 0 | 70.72 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 89 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 107 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 33 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 80 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 61 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 40 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 117 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (M) | Sq.Ft | 1.169 | 175 | 204.58 | 36.82 | 241.4 | 0 | 1.169 | 204.58 | 36.82 | 241.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 57 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 45 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 90 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 58 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 78 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 94 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 110 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 91 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 13 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 23 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 71 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 20 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 55 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 29 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 96 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 80 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 54 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 99 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 14 Oct 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 61 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 09 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 51 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 74 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 69 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 27 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (M) | Sq.Ft | 276.95 | 175 | 48466.25 | 8723.92 | 57190.17 | 0 | 276.95 | 48466.25 | 8723.92 | 57190.17 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 36 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 52 corner gap covering - 1 Job | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 64 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 109 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 47 Sinage | ACP Work- (M) | Sq.Ft | 124.8 | 175 | 21840 | 3931.2 | 25771.2 | 0 | 0 | 0 | 0 | 0 | 124.8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (M) | Sq.Ft | 98.58 | 175 | 17251.5 | 3105.28 | 20356.78 | 0 | 98.58 | 17251.5 | 3105.28 | 20356.78 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 70 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 73 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 89 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 92 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 25 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 31 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 79 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 24 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 101 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 37 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 82 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 72 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 112 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 115 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 Sinage | ACP Work- (M) | Sq.Ft | 288.47 | 175 | 50482.25 | 9086.8 | 59569.05 | 0 | 239.159 | 41852.83 | 7533.5 | 49386.33 | 49.311 | 10182.73 |  | 82.906 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 116 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 10 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 87 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 68 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 14 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 21 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 107 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 29 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (M) | Sq.Ft | 144.97 | 175 | 25369.75 | 4566.56 | 29936.31 | 0 | 144.97 | 25369.75 | 4566.56 | 29936.31 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (M) | Sq.Ft | 270.69 | 175 | 47370.75 | 8526.74 | 55897.49 | 0 | 270.69 | 47370.75 | 8526.74 | 55897.49 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 62 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 98 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 88 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 34 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 92 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 28 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 100 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 12 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 35 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 44 Sinage | ACP Work- (M) | Sq.Ft | 116.94 | 175 | 20464.5 | 3683.62 | 24148.12 | 0 | 0 | 0 | 0 | 0 | 116.94 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 39 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 corner gap covering | ACP Work- (M) | Sq.Ft | 22.733 | 140 | 3182.62 | 572.88 | 3755.5 | 0 | 19.18 | 2685.2 | 483.34 | 3168.54 | 3.553 | 586.96 |  | 84.3707 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 Sinage | ACP Work- (M) | Sq.Ft | 159.74 | 175 | 27954.5 | 5031.82 | 32986.32 | 0 | 0 | 0 | 0 | 0 | 159.74 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 104 Sinage | ACP Work- (M) | Sq.Ft | 125.24 | 175 | 21917 | 3945.06 | 25862.06 | 0 | 109.9486 | 19241.01 | 3463.38 | 22704.39 | 15.2914 | 3157.68 |  | 87.7903 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 31 Sinage | ACP Work- (M) | Sq.Ft | 113.5 | 175 | 19862.5 | 3575.26 | 23437.76 | 0 | 111.7 | 19547.5 | 3518.56 | 23066.06 | 1.8 | 371.7 |  | 98.4141 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 99 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 28 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (M) | Sq.Ft | 130.42 | 175 | 22823.5 | 4108.24 | 26931.74 | 0 | 119.06 | 20835.5 | 3750.4 | 24585.9 | 11.36 | 2345.84 |  | 91.2897 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 73 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 112 Sinage | ACP Work- (M) | Sq.Ft | 120.43 | 175 | 21075.25 | 3793.54 | 24868.79 | 0 | 120.43 | 21075.25 | 3793.54 | 24868.79 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 corner gap covering | ACP Work- (M) | Sq.Ft | 22.733 | 140 | 3182.62 | 572.88 | 3755.5 | 0 | 0 | 0 | 0 | 0 | 22.733 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 95 Sinage | ACP Work- (M) | Sq.Ft | 109.94 | 175 | 19239.5 | 3463.12 | 22702.62 | 0 | 109.73 | 19202.75 | 3456.5 | 22659.25 | 0.21 | 43.37 |  | 99.809 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 29 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 58 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 27 Sinage | ACP Work- (M) | Sq.Ft | 168.07 | 175 | 29412.25 | 5294.2 | 34706.45 | 0 | 0 | 0 | 0 | 0 | 168.07 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 93 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 14 Oct 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 Sinage | ACP Work- (M) | Sq.Ft | 146.19 | 175 | 25583.25 | 4604.98 | 30188.23 | 0 | 143.7 | 25147.5 | 4526.56 | 29674.06 | 2.49 | 514.17 |  | 98.2967 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 22 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 45 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 Sinage | ACP Work- (M) | Sq.Ft | 167.33 | 175 | 29282.75 | 5270.9 | 34553.65 | 0 | 0 | 0 | 0 | 0 | 167.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 84 Sinage | ACP Work- (M) | Sq.Ft | 301.86 | 175 | 52825.5 | 9508.6 | 62334.1 | 0 | 254.31 | 44504.25 | 8010.76 | 52515.01 | 47.55 | 9819.09 |  | 84.2477 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 90 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 19 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 33 Sinage | ACP Work- (M) | Sq.Ft | 124.61 | 175 | 21806.75 | 3925.22 | 25731.97 | 0 | 0 | 0 | 0 | 0 | 124.61 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 113 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 36 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 111 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 Sinage | ACP Work- (M) | Sq.Ft | 158.45 | 175 | 27728.75 | 4991.18 | 32719.93 | 0 | 0 | 0 | 0 | 0 | 158.45 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 Sinage | ACP Work- (M) | Sq.Ft | 109.82 | 175 | 19218.5 | 3459.34 | 22677.84 | 0 | 0 | 0 | 0 | 0 | 109.82 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 53 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 108 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 95 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd Fl. Atrium Lobby ACP sheet fixing | ACP Sheet (M) | Sq.Ft | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Atrium lobby area Golden Colour sheet fixing work. | 0 |  | Dushant Gore |  | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 21 Sep 2022
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 corner gap covering - 1 Job | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 17 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 39 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 100 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 62 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 26 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 95 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 43 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 63 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 57 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (M) | Sq.Ft | 11.286 | 175 | 1975.05 | 355.5 | 2330.55 | 0 | 11.2857 | 1975 | 355.5 | 2330.5 | 0.0003 | 0.05 |  | 99.9973 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 108 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 77 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 57 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 41 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 76 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 102 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 85 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 56 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 117 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 30 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 41 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 85 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 91 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 75 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 86 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 34 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 18 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 60 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 50 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 112 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 100 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 04 Glass Door with fix glass - 49.78 Sq.F | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 59 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 32 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 35 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 48 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 111 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 11 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 46 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 66 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 81 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 103 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 40 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 84 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 65 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 49 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 105 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 52 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 33 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (M) | Sq.Ft | 1.734 | 175 | 303.45 | 54.62 | 358.07 | 0 | 1.7314 | 303 | 54.54 | 357.54 | 0.0026 | 0.54 |  | 99.8501 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 104 Glass Door with fix glass - 69.11 Sq.F | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 111 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 38 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 31 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 Sinage | ACP Work- (M) | Sq.Ft | 101.2 | 175 | 17710 | 3187.8 | 20897.8 | 0 | 88.0799 | 15413.98 | 2774.52 | 18188.5 | 13.1201 | 2709.3 |  | 87.0355 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 98 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 48 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 32 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 corner gap covering | ACP Work- (M) | Sq.Ft | 11.367 | 140 | 1591.38 | 286.44 | 1877.82 | 0 | 9.59 | 1342.6 | 241.66 | 1584.26 | 1.777 | 293.56 |  | 84.367 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 15 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 83 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 93 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 111 Sinage | ACP Work- (M) | Sq.Ft | 129.17 | 175 | 22604.75 | 4068.86 | 26673.61 | 0 | 122.5888 | 21453.04 | 3861.54 | 25314.58 | 6.5812 | 1359.03 |  | 94.905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 104 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 Sinage | ACP Work- (M) | Sq.Ft | 379.27 | 175 | 66372.25 | 11947 | 78319.25 | 0 | 0 | 0 | 0 | 0 | 379.27 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 97 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 67 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 112 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 65 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 105 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 16 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd flr. Window ACP covering work | ACP Sheet (M) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ACP Sheet fixing for window covering. | 0 |  | Dushant Gore |  | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 09 Sep 2022
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 49 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 Sinage | ACP Work- (M) | Sq.Ft | 126.99 | 175 | 22223.25 | 4000.18 | 26223.43 | 0 | 0 | 0 | 0 | 0 | 126.99 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 42 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 99 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (M) | Sq.Ft | 99.46 | 175 | 17405.5 | 3133 | 20538.5 | 0 | 99.46 | 17405.5 | 3133 | 20538.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 19 Sinage | ACP Work- (M) | Sq.Ft | 126.55 | 175 | 22146.25 | 3986.32 | 26132.57 | 0 | 98.5719 | 17250.08 | 3105.02 | 20355.1 | 27.9781 | 5777.47 |  | 77.8917 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 41 Sinage | ACP Work- (M) | Sq.Ft | 133.17 | 175 | 23304.75 | 4194.86 | 27499.61 | 0 | 0 | 0 | 0 | 0 | 133.17 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 60 Sinage | ACP Work- (M) | Sq.Ft | 103.83 | 175 | 18170.25 | 3270.64 | 21440.89 | 0 | 102.71 | 17974.25 | 3235.36 | 21209.61 | 1.12 | 231.28 |  | 98.9213 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 4th Fl. Slab, Beam ACP sheet fixing | ACP Sheet (M) | Sq.Ft | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ACP Sheet fixing for Slab Beam,Escalator Front side,Facade side beam. | 0 |  | Dushant Gore |  | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 21 Sep 2022
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 95 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 117 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (M) | Sq.Ft | 272.14 | 175 | 47624.5 | 8572.42 | 56196.92 | 0 | 272.1371 | 47623.99 | 8572.32 | 56196.31 | 0.0029 | 0.61 |  | 99.9989 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (M) | Sq.Ft | 5.599 | 175 | 979.83 | 176.36 | 1156.19 | 0 | 5.599 | 979.83 | 176.36 | 1156.19 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 83 Sinage | ACP Work- (M) | Sq.Ft | 138.35 | 175 | 24211.25 | 4358.02 | 28569.27 | 0 | 107.43 | 18800.25 | 3384.04 | 22184.29 | 30.92 | 6384.98 |  | 77.6509 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 80 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 56 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 75 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (M) | Sq.Ft | 9.612 | 175 | 1682.1 | 302.78 | 1984.88 | 0 | 9.6114 | 1682 | 302.76 | 1984.76 | 0.0006 | 0.13 |  | 99.9938 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 19.18 | 2685.2 | 483.34 | 3168.54 | 5.685 | 939.16 |  | 77.1365 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 39 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 54 Sinage | ACP Work- (M) | Sq.Ft | 113 | 175 | 19775 | 3559.5 | 23334.5 | 0 | 0 | 0 | 0 | 0 | 113 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 51 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 91 Sinage | ACP Work- (M) | Sq.Ft | 123.37 | 175 | 21589.75 | 3886.16 | 25475.91 | 0 | 0 | 0 | 0 | 0 | 123.37 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 3rd Fl. Slab, Beam ACP sheet fixing | ACP Sheet (M) | Sq.Ft | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ACP Sheet fixing bothside of Escalator beam. | 0 |  | Dushant Gore |  | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 21 Sep 2022
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 Sinage | ACP Work- (M) | Sq.Ft | 124.8 | 175 | 21840 | 3931.2 | 25771.2 | 0 | 124.21 | 21736.75 | 3912.62 | 25649.37 | 0.59 | 121.83 |  | 99.5272 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 Sinage | ACP Work- (M) | Sq.Ft | 200.38 | 175 | 35066.5 | 6311.98 | 41378.48 | 0 | 0 | 0 | 0 | 0 | 200.38 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 Sinage | ACP Work- (M) | Sq.Ft | 124.8 | 175 | 21840 | 3931.2 | 25771.2 | 0 | 0 | 0 | 0 | 0 | 124.8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 42 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 23 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 54 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 44 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 30 Sinage | ACP Work- (M) | Sq.Ft | 293.56 | 175 | 51373 | 9247.14 | 60620.14 | 0 | 0 | 0 | 0 | 0 | 293.56 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 25 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 63 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 41 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (M) | Sq.Ft | 126.11 | 175 | 22069.25 | 3972.46 | 26041.71 | 0 | 126.11 | 22069.25 | 3972.46 | 26041.71 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 105 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 47 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 28 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 44 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 33 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 30 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 Sinage | ACP Work- (M) | Sq.Ft | 121.81 | 175 | 21316.75 | 3837.02 | 25153.77 | 0 | 0 | 0 | 0 | 0 | 121.81 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 106 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 81 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 47 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 82 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 53 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 88 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 45 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 40 Sinage | ACP Work- (M) | Sq.Ft | 337.69 | 175 | 59095.75 | 10637.24 | 69732.99 | 0 | 0 | 0 | 0 | 0 | 337.69 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 20 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | Escalator side ACP sheet fixing | ACP Sheet (M) | Sq.Ft | 334.74 | 165 | 55232.1 | 9941.78 | 65173.88 | 0 | 334.74 | 55232.1 | 9941.78 | 65173.88 | 0 | 0 | Gray Colour ACP Sheet fixing work Escalator side Railing Box. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 70 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 72 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 0 | 0 | 0 | 0 | 24.865 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 56 Sinage | ACP Work- (M) | Sq.Ft | 359.55 | 175 | 62921.25 | 11325.82 | 74247.07 | 0 | 0 | 0 | 0 | 0 | 359.55 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 49 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 49 Sinage | ACP Work- (M) | Sq.Ft | 108.2 | 175 | 18935 | 3408.3 | 22343.3 | 0 | 0 | 0 | 0 | 0 | 108.2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 27 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 Sinage | ACP Work- (M) | Sq.Ft | 160.64 | 175 | 28112 | 5060.16 | 33172.16 | 0 | 0 | 0 | 0 | 0 | 160.64 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 108 Sinage | ACP Work- (M) | Sq.Ft | 134.42 | 175 | 23523.5 | 4234.24 | 27757.74 | 0 | 0 | 0 | 0 | 0 | 134.42 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 57 Sinage | ACP Work- (M) | Sq.Ft | 305.36 | 175 | 53438 | 9618.84 | 63056.84 | 0 | 297.04 | 51982 | 9356.76 | 61338.76 | 8.32 | 1718.08 |  | 97.2753 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 90 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 02 Sinage | ACP Work- (M) | Sq.Ft | 143.873 | 175 | 25177.78 | 4532 | 29709.78 | 0 | 143.873 | 25177.78 | 4532 | 29709.78 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 53 Sinage | ACP Work- (M) | Sq.Ft | 115.62 | 175 | 20233.5 | 3642.04 | 23875.54 | 0 | 0 | 0 | 0 | 0 | 115.62 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 75 Sinage | ACP Work- (M) | Sq.Ft | 162.09 | 175 | 28365.75 | 5105.84 | 33471.59 | 0 | 144.9543 | 25367 | 4566.06 | 29933.06 | 17.1357 | 3538.53 |  | 89.4283 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 78 Sinage | ACP Work- (M) | Sq.Ft | 109.82 | 175 | 19218.5 | 3459.34 | 22677.84 | 0 | 81.5 | 14262.5 | 2567.26 | 16829.76 | 28.32 | 5848.08 |  | 74.2123 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 52 Sinage | ACP Work- (M) | Sq.Ft | 109.51 | 175 | 19164.25 | 3449.56 | 22613.81 | 0 | 0 | 0 | 0 | 0 | 109.51 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 100 Sinage | ACP Work- (M) | Sq.Ft | 125.68 | 175 | 21994 | 3958.92 | 25952.92 | 0 | 120.6057 | 21106 | 3799.08 | 24905.08 | 5.0743 | 1047.84 |  | 95.9625 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 59 Sinage | ACP Work- (M) | Sq.Ft | 280.01 | 175 | 49001.75 | 8820.32 | 57822.07 | 0 | 250.6 | 43855 | 7893.9 | 51748.9 | 29.41 | 6073.17 |  | 89.4968 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 91 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 10 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 59 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 corner gap covering - 1 Job | ACP Work- (M) | Sq.Ft | 12.432 | 140 | 1740.48 | 313.28 | 2053.76 | 0 | 0 | 0 | 0 | 0 | 12.432 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 corner gap covering | ACP Work- (M) | Sq.Ft | 12.378 | 140 | 1732.92 | 311.92 | 2044.84 | 0 | 0 | 0 | 0 | 0 | 12.378 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 11 corner gap covering | ACP Work- (M) | Sq.Ft | 11.367 | 140 | 1591.38 | 286.44 | 1877.82 | 0 | 9.59 | 1342.6 | 241.66 | 1584.26 | 1.777 | 293.56 |  | 84.367 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 Sinage | ACP Work- (M) | Sq.Ft | 160.2 | 175 | 28035 | 5046.3 | 33081.3 | 0 | 0 | 0 | 0 | 0 | 160.2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 58 Sinage | ACP Work- (M) | Sq.Ft | 152.33 | 175 | 26657.75 | 4798.4 | 31456.15 | 0 | 0 | 0 | 0 | 0 | 152.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 116 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 94 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 61 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 Sinage | ACP Work- (M) | Sq.Ft | 146.28 | 175 | 25599 | 4607.82 | 30206.82 | 0 | 0 | 0 | 0 | 0 | 146.28 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 22 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 99 Sinage | ACP Work- (M) | Sq.Ft | 131.67 | 175 | 23042.25 | 4147.6 | 27189.85 | 0 | 99.401 | 17395.18 | 3131.14 | 20526.32 | 32.269 | 6663.54 |  | 75.4925 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 117 Sinage | ACP Work- (M) | Sq.Ft | 254.82 | 175 | 44593.5 | 8026.84 | 52620.34 | 0 | 241.2686 | 42222.01 | 7599.96 | 49821.97 | 13.5514 | 2798.38 |  | 94.682 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 21 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 102 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 66 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 107 Sinage | ACP Work- (M) | Sq.Ft | 128.8 | 175 | 22540 | 4057.2 | 26597.2 | 0 | 109.95 | 19241.25 | 3463.42 | 22704.67 | 18.85 | 3892.53 |  | 85.3649 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 65 Sinage | ACP Work- (M) | Sq.Ft | 129.17 | 175 | 22604.75 | 4068.86 | 26673.61 | 0 | 0 | 0 | 0 | 0 | 129.17 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 36 Sinage | ACP Work- (M) | Sq.Ft | 110.82 | 175 | 19393.5 | 3490.84 | 22884.34 | 0 | 0 | 0 | 0 | 0 | 110.82 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 94 Sinage | ACP Work- (M) | Sq.Ft | 119.12 | 175 | 20846 | 3752.28 | 24598.28 | 0 | 0 | 0 | 0 | 0 | 119.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 09 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 17 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 26 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 4th Fl. Community Hall Chajja ACP work | ACP Sheet (M) | Sq.Ft | 34 | 165 | 5610 | 1009.8 | 6619.8 | 0 | 34 | 5610 | 1009.8 | 6619.8 | 0 | 0 | Railway Station side Community hall Chajja work. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 108 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 50 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 75 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 88 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 110 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 85 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 58 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 83 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (M) | Sq.Ft | 143.63 | 175 | 25135.25 | 4524.34 | 29659.59 | 0 | 0 | 0 | 0 | 0 | 143.63 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (M) | Sq.Ft | 24.471 | 175 | 4282.43 | 770.84 | 5053.27 | 0 | 24.4686 | 4282.01 | 770.76 | 5052.77 | 0.0024 | 0.5 |  | 99.9902 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (M) | Sq.Ft | 145.78 | 175 | 25511.5 | 4592.08 | 30103.58 | 0 | 145.7771 | 25510.99 | 4591.98 | 30102.97 | 0.0029 | 0.61 |  | 99.998 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 102 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd floor Shop 114 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 24 Dec 2021 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 06 Apr 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 34 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 Sinage | ACP Work- (M) | Sq.Ft | 102.51 | 175 | 17939.25 | 3229.06 | 21168.31 | 0 | 95.41 | 16696.75 | 3005.42 | 19702.17 | 7.1 | 1466.14 |  | 93.0738 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 103 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 24 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 79 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (M) | Sq.Ft | 81.1 | 175 | 14192.5 | 2554.66 | 16747.16 | 0 | 81.0914 | 14191 | 2554.38 | 16745.38 | 0.0086 | 1.79 |  | 99.9894 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 102 Sinage | ACP Work- (M) | Sq.Ft | 109.76 | 175 | 19208 | 3457.44 | 22665.44 | 0 | 92.6514 | 16214 | 2918.52 | 19132.52 | 17.1086 | 3532.93 |  | 84.4127 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 89 Sinage | ACP Work- (M) | Sq.Ft | 443.14 | 175 | 77549.5 | 13958.92 | 91508.42 | 0 | 311.1543 | 54452 | 9801.36 | 64253.36 | 131.9857 | 27255.06 |  | 70.2158 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 Sinage | ACP Work- (M) | Sq.Ft | 137.45 | 175 | 24053.75 | 4329.68 | 28383.43 | 0 | 88.09 | 15415.75 | 2774.84 | 18190.59 | 49.36 | 10192.84 |  | 64.0888 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 60 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 105 Sinage | ACP Work- (M) | Sq.Ft | 352.98 | 175 | 61771.5 | 11118.88 | 72890.38 | 0 | 275.961 | 48293.18 | 8692.78 | 56985.96 | 77.019 | 15904.43 |  | 78.1804 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 15 Sinage | ACP Work- (M) | Sq.Ft | 150.1 | 175 | 26267.5 | 4728.16 | 30995.66 | 0 | 118.178 | 20681.15 | 3722.6 | 24403.75 | 31.922 | 6591.91 |  | 78.7328 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (M) | Sq.Ft | 93.77 | 175 | 16409.75 | 2953.76 | 19363.51 | 0 | 93.7486 | 16406.01 | 2953.08 | 19359.09 | 0.0214 | 4.43 |  | 99.9772 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 14 Sinage | ACP Work- (M) | Sq.Ft | 157.11 | 175 | 27494.25 | 4948.96 | 32443.21 | 0 | 135.91 | 23784.25 | 4281.16 | 28065.41 | 21.2 | 4377.8 |  | 86.5063 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 12 corner gap covering | ACP Work- (M) | Sq.Ft | 22.733 | 140 | 3182.62 | 572.88 | 3755.5 | 0 | 19.18 | 2685.2 | 483.34 | 3168.54 | 3.553 | 586.96 |  | 84.3707 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 corner gap covering | ACP Work- (M) | Sq.Ft | 24.865 | 140 | 3481.1 | 626.6 | 4107.7 | 0 | 24.8643 | 3481 | 626.58 | 4107.58 | 0.0007 | 0.12 |  | 99.9972 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 46 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 45 Sinage | ACP Work- (M) | Sq.Ft | 104.7 | 175 | 18322.5 | 3298.06 | 21620.56 | 0 | 0 | 0 | 0 | 0 | 104.7 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 54 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 3rd Fl. Mall Management Office ACP work | ACP Sheet (M) | Sq.Ft | 45.07 | 165 | 7436.55 | 1338.58 | 8775.13 | 0 | 45.07 | 7436.55 | 1338.58 | 8775.13 | 0 | 0 | ACP Fixing for Pantry wall due to Copper wiring & Above Conferance door. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 18 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 80 Sinage | ACP Work- (M) | Sq.Ft | 139.22 | 175 | 24363.5 | 4385.44 | 28748.94 | 0 | 0 | 0 | 0 | 0 | 139.22 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 43 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 27 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 81 Sinage | ACP Work- (M) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 4 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (M) | Sq.Ft | 9.128 | 175 | 1597.4 | 287.54 | 1884.94 | 0 | 9.1257 | 1597 | 287.46 | 1884.46 | 0.0023 | 0.48 |  | 99.9748 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 13 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 50 Sinage | ACP Work- (M) | Sq.Ft | 104.26 | 175 | 18245.5 | 3284.2 | 21529.7 | 0 | 0 | 0 | 0 | 0 | 104.26 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 1 | 17 Dec 2021 | SAHARA ENGINEERING | 2nd flr. Window ACP covering work | ACP Sheet (M) | Sq.Ft | 21.3 | 150 | 3195 | 575.1 | 3770.1 | 0 | 21.3 | 3195 | 575.1 | 3770.1 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 34 Sinage | ACP Work- (M) | Sq.Ft | 111.32 | 175 | 19481 | 3506.58 | 22987.58 | 0 | 0 | 0 | 0 | 0 | 111.32 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 100 | 5 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (M) | Sq.Ft | 1.423 | 175 | 249.03 | 44.82 | 293.85 | 0 | 1.4229 | 249.01 | 44.82 | 293.83 | 0.0001 | 0.02 |  | 99.993 |  | abhishek bankar | abhishek bankar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 32 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 64 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 04 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 77 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 68 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 55 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 71 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 84 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 82 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 100 | 2 | 17 Dec 2021 | SAHARA ENGINEERING | ACP for Shop 69 corner gap covering | ACP Work- (M) | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 01 Jul 2023
EAST POINT MARKET | 101 | 1 | 18 Dec 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Toilet Brickbat Waterproofing | Brickbat W/P BCo | Sq.Ft | 536.32 | 40 | 21452.8 | 3861.5 | 25314.3 | 10 | 536.32 | 21452.8 | 3861.5 | 25314.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 101 | 1 | 18 Dec 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Toilet Brickbat Waterproofing | Base Coat -cc | Sq.Ft | 536.32 | 20 | 10726.4 | 1930.76 | 12657.16 | 10 | 536.32 | 10726.4 | 1930.76 | 12657.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 101 | 1 | 18 Dec 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-Gr Floor Toilet Brickbat Waterproofing | Chemical W/P - Bco | Sq.Ft | 536.32 | 25 | 13408 | 2413.44 | 15821.44 | 10 | 428.7996 | 10719.99 | 1929.6 | 12649.59 | 107.5204 | 3171.85 |  | 79.9522 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 101 | 0 | 18 Dec 2021 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Fl Toilet Block Chemical Waterproofing | Chemical W/P (L+M) | Sq.Ft | 382.55 | 25 | 9563.75 | 1721.48 | 11285.23 | 0 | 0 | 0 | 0 | 0 | 382.55 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 102 | 1 | 20 Dec 2021 | THE WOODPECKERS | Rental charges for Guardian Office | Rental Charges - So | Month | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Dec 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 102 | 1 | 20 Dec 2021 | THE WOODPECKERS | Rental charges for Guardian Office | Rental Charges - So | Month | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Dec 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 102 | 1 | 20 Dec 2021 | THE WOODPECKERS | Rental charges for Guardian Office | Rental Charges - So | Month | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Dec 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 102 | 1 | 20 Dec 2021 | THE WOODPECKERS | Rental charges for Guardian Office | Rental Charges - So | Month | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Dec 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 102 | 1 | 20 Dec 2021 | THE WOODPECKERS | Rental charges for Guardian Office | Rental Charges - So | Month | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Dec 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 102 | 1 | 20 Dec 2021 | THE WOODPECKERS | Rental charges for Guardian Office | Rental Charges - So | Month | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Dec 2021 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 102 | 0 | 20 Dec 2021 | THE WOODPECKERS | Sales Office at 2nd Fl Work (Gaurdian) | Interior/Artwork/Furnishing & Misc work | Month | 6 | 475000 | 2850000 | 513000 | 3363000 | 0 | 6 | 2850000 | 513000 | 3363000 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 20 Dec 2021 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 103 | 1 | 21 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work | Scaffolding work | Sq.Ft | 6684 | 12 | 80208 | 14437.44 | 94645.44 | 2.5 | 6684 | 80208 | 14437.44 | 94645.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 03 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 103 | 0 | 21 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding for ODU Platform | Scaffolding work | Sq.Ft | 4225 | 23 | 97175 | 17491.5 | 114666.5 | 0 | 4225 | 97175 | 17491.5 | 114666.5 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. RCC Superstructure | Approved | chetan.jewalikar
EAST POINT MARKET | 103 | 1 | 21 Dec 2021 | SAHARA ENGINEERING | KEP-Scaffolding Work | Scaffolding Work - BC | No. | 1 | 36000 | 36000 | 6480 | 42480 | 2.5 | 1 | 36000 | 6480 | 42480 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 104 | 0 | 23 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Cradle Installation Top Terrace | Fabrication Work (L) | Kgs | 329 | 21 | 6909 | 1243.62 | 8152.62 | 2.5 | 329 | 6909 | 1243.62 | 8152.62 | 0 | 0 |  | 100 |  | Aniket Mohite | Swapnil Erande | construction open | 19 Apr 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 104 | 0 | 23 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP--Dismentling work of Deluxe Front MS Platform | Fabrication Work (L) | Kgs | 2670 | 10 | 26700 | 4806 | 31506 | 2.5 | 2670 | 26700 | 4806 | 31506 | 0 | 0 |  | 100 |  | Aniket Mohite | Swapnil Erande | construction open | 19 Apr 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 104 | 1 | 23 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Cradle Installation Top Terrace | Fabrication Work (L) | Kgs | 27.6 | 21 | 579.6 | 104.32 | 683.92 | 2.5 | 27.6 | 579.6 | 104.32 | 683.92 | 0 | 0 |  | 100 |  | Aniket Mohite | Swapnil Erande | construction open | 19 Apr 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 104 | 1 | 23 Dec 2021 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Cradle Installation Top Terrace | Fabrication Work (M) | Kgs | 27.6 | 84 | 2318.4 | 417.32 | 2735.72 | 2.5 | 27.6 | 2318.4 | 417.32 | 2735.72 | 0 | 0 |  | 100 |  | Aniket Mohite | Swapnil Erande | construction open | 19 Apr 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 105 | 0 | 11 Jan 2022 | DREAMTREE EXPERIENCE | Media BRANDING | OUTDOOR DISPLAY BRANDING | No. | 1 | 10100000 | 10100000 | 1818000 | 11918000 | 0 | 0.7723 | 7799930.94 | 1403987.5 | 9203918.44 | 0.2277 | 2714081.56 | EAST POINT MARKET FACADE BRADNING GLASS + ALUMINIUM MATERIAL BRANDING- SIGNAGES | 77.23 |  | Tejas Raverkar | Tejas Raverkar | construction open | 14 Jan 2022 |  | MKT. Media | Approved | Tejas Raverkar | 11 Jan 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 6 Amp Switch (M) | No. | 17 | 108 | 1836 | 330.48 | 2166.48 | 0 | 17 | 1836 | 330.48 | 2166.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 2.5 sqmm (FRLS) Cable (M) | Mtrs | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 29 Apr 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | O/G 40A-TPN-MCB (M) | No. | 0 | 1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A DP MCB (M) | No. | 7 | 890 | 6230 | 1121.4 | 7351.4 | 0 | 7 | 6230 | 1121.4 | 7351.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | Junction Box-3 Way (M) | No. | 50 | 25 | 1250 | 225 | 1475 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Flexible Cable | 2.5 sqmm Cu wire (M) | Mtrs | 5351.5 | 27 | 144490.5 | 26008.3 | 170498.8 | 0 | 5351.5 | 144490.5 | 26008.3 | 170498.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | RJ11 Telephone Socket (M) | No. | 5 | 114 | 570 | 102.6 | 672.6 | 0 | 5 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3C 2.5sqmm Cu Armd Cable (M) | No. | 10 | 257 | 2570 | 462.6 | 3032.6 | 0 | 10 | 2570 | 462.6 | 3032.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | 25mm Dia PVC MMS Conduit | Mtrs | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 6 sqmm Cu Wire (M) | Mtrs | 1000 | 63.77 | 63770 | 11478.6 | 75248.6 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 |  | 0 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | Junction Box-2 Way (M) | No. | 50 | 21 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 205.5 | 106 | 21783 | 3920.94 | 25703.94 | 0 | 205.38 | 21770.28 | 3918.66 | 25688.94 | 0.12 | 15 |  | 99.9416 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 6 sqmm Alu. Cable (M) | Mtrs | 60 | 430 | 25800 | 4644 | 30444 | 0 | 60 | 25800 | 4644 | 30444 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 1C x 70 sqmm Copper Lead (M) | No. | 26 | 295 | 7670 | 1380.6 | 9050.6 | 0 | 26 | 7670 | 1380.6 | 9050.6 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (M) | Mtrs | 3000 | 47.46 | 142380 | 25628.4 | 168008.4 | 0 | 2330.75 | 110617.4 | 19911.12 | 130528.52 | 669.25 | 37479.89 |  | 77.6917 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 12M Base Plate | No. | 8 | 1591 | 12728 | 2291.04 | 15019.04 | 0 | 4 | 6364 | 1145.52 | 7509.52 | 4 | 7509.52 |  | 50 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 4 Module Plate (M) | No. | 10 | 107.68 | 1076.8 | 193.82 | 1270.62 | 0 | 3 | 323.04 | 58.14 | 381.18 | 7 | 889.44 |  | 30 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 2.5 sqmm Cu wire (M) | Mtrs | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Flexible Cable | Supply of Bend | No. | 80 | 13 | 1040 | 187.2 | 1227.2 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | PVC Conduit Piping (M) | Mtrs | 1250.5 | 40.33 | 50432.67 | 9077.88 | 59510.55 | 0 | 1242.9973 | 50130.08 | 9023.42 | 59153.5 | 7.5027 | 357.04 |  | 99.4 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C 6 sqmm (FRLS) Cable (M) | Mtrs | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 29 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | SITC 10A to 16 A SP MCB (M) | No. | 4 | 156 | 624 | 112.32 | 736.32 | 0 | 4 | 624 | 112.32 | 736.32 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | Fan Regulator (M) | No. | 25 | 399 | 9975 | 1795.5 | 11770.5 | 0 | 22 | 8778 | 1580.04 | 10358.04 | 3 | 1412.46 |  | 88 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3.5C x 35sqmm (M). | No. | 2 | 702 | 1404 | 252.72 | 1656.72 | 0 | 2 | 1404 | 252.72 | 1656.72 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 4 Module Box (M) | No. | 10 | 64.21 | 642.1 | 115.58 | 757.68 | 0 | 3 | 192.63 | 34.68 | 227.31 | 7 | 530.37 |  | 30 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Flexible Cable | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 290 | 104.64 | 30345.6 | 5462.2 | 35807.8 | 0 | 289.9987 | 30345.46 | 5462.18 | 35807.64 | 0.0013 | 0.16 |  | 99.9996 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | 32A-DP-MCB (M) | No. | 1 | 496 | 496 | 89.28 | 585.28 | 0 | 1 | 496 | 89.28 | 585.28 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3C 2.5sqmm Cu Armd Cable (M) | No. | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 6 sqmm Cu Wire (M) | Mtrs | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | SITC G.I Earthing Strip 25 x 3mm (M) | Mtrs | 378 | 105 | 39690 | 7144.2 | 46834.2 | 0 | 378 | 39690 | 7144.2 | 46834.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 1.5 sqmm Cu wire (M) | Mtrs | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 1 Way (M) - | No. | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 3 Way (M) | No. | 80 | 32.18 | 2574.4 | 463.4 | 3037.8 | 0 | 80 | 2574.4 | 463.38 | 3037.78 | 0 | 0.02 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (M) | Mtrs | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 29 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Coupling (M) | No. | 30 | 7 | 210 | 37.8 | 247.8 | 0 | 29.999 | 209.99 | 37.8 | 247.79 | 0.001 | 0.01 |  | 99.9967 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 1.5 sqmm Cu wire (M) | Mtrs | 1636.5 | 17 | 27820.5 | 5007.7 | 32828.2 | 0 | 1636.5 | 27820.5 | 5007.7 | 32828.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 16sqmm Alumn Armd. Cable (M) | Mtrs | 0 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Earthing & Panel | MMCB enclosure (M) | No. | 2 | 2673 | 5346 | 962.28 | 6308.28 | 0 | 2 | 5346 | 962.28 | 6308.28 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | O/G 40A-TPN-MCB (M+L) | No. | 3 | 1377 | 4131 | 743.58 | 4874.58 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Coupling (M) | No. | 30 | 7 | 210 | 37.8 | 247.8 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C x 2.5sqmm Cu cable armourd (M) | Mtrs | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | I/C 40A FP MCB (M) | No. | 1 | 1560 | 1560 | 280.8 | 1840.8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Supply of Bend | No. | 25 | 14 | 350 | 63 | 413 | 0 | 25 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 4C x 6sqmm (M) | No. | 0 | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 4 sqmm Cu wire (M) | Mtrs | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 6/16 Amp Multi pin Socket (M) | No. | 51 | 239 | 12189 | 2194.02 | 14383.02 | 0 | 51 | 12189 | 2194.02 | 14383.02 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 63A 4P MCB (M) | No. | 0 | 1681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3 Module Box (M) | No. | 8 | 51 | 408 | 73.44 | 481.44 | 0 | 8 | 408 | 73.44 | 481.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | 25mm Dia PVC MMS Conduit | Mtrs | 600 | 37.44 | 22464 | 4043.52 | 26507.52 | 0 | 600 | 22464 | 4043.52 | 26507.52 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | MKT. Marketing Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 2 Way (M) | No. | 50 | 29.54 | 1477 | 265.86 | 1742.86 | 0 | 50 | 1477 | 265.88 | 1742.88 | 0 | -0.02 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 8 Module Box (M) | No. | 30 | 122.68 | 3680.4 | 662.48 | 4342.88 | 0 | 28 | 3435.04 | 618.3 | 4053.34 | 2 | 289.54 |  | 93.3333 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 32A 2P MCB (M+L) | No. | 5 | 558 | 2790 | 502.2 | 3292.2 | 0 | 5 | 2790 | 502.2 | 3292.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 185sqmm A2XFY XLPE (M) | Mtrs | 100 | 986 | 98600 | 17748 | 116348 | 0 | 60 | 59160 | 10648.8 | 69808.8 | 40 | 46539.2 |  | 60 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 95SQMM A2XFY XLPE(M) | No. | 2 | 1076 | 2152 | 387.36 | 2539.36 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 35sqmm A2XFY XLPE (M) | Mtrs | 56 | 242 | 13552 | 2439.36 | 15991.36 | 0 | 55.3 | 13382.6 | 2408.86 | 15791.46 | 0.7 | 199.9 |  | 98.75 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | 16 way ETPN DB (M) | No. | 1 | 6663 | 6663 | 1199.34 | 7862.34 | 0 | 1 | 6663 | 1199.34 | 7862.34 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 8 Module Plate (M) | No. | 30 | 224.64 | 6739.2 | 1213.06 | 7952.26 | 0 | 28 | 6289.92 | 1132.18 | 7422.1 | 2 | 530.16 |  | 93.3333 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 29 Apr 2022
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | Supply of 25mm PVC MMS Conduit With accessories | Mtrs | 1470.5 | 35 | 51467.5 | 9264.16 | 60731.66 | 0 | 1470.5 | 51467.5 | 9264.16 | 60731.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | Sub I/C 63A DP RCCB 100mA (M) | No. | 3 | 2573 | 7719 | 1389.42 | 9108.42 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 32A 2P MCB (M) | No. | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Flexible Cable | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 6 Module Plate (M) | No. | 30 | 210.8 | 6324 | 1138.32 | 7462.32 | 0 | 12 | 2529.6 | 455.32 | 2984.92 | 18 | 4477.4 |  | 40 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 3 Way (M) | No. | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16SQMM A2XFY XLPE (M) | Mtrs | 150 | 160 | 24000 | 4320 | 28320 | 0 | 150 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 16A-SP-MCB (M) | No. | 18 | 175 | 3150 | 567 | 3717 | 0 | 18 | 3150 | 567 | 3717 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 12M Base Plate | No. | 0 | 1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16 sqmm A2XFY XLPE Cable (M) | No. | 8 | 415 | 3320 | 597.6 | 3917.6 | 0 | 8 | 3320 | 597.6 | 3917.6 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 16sqmm Alumn Armd. Cable (M) | Mtrs | 8 | 191 | 1528 | 275.04 | 1803.04 | 0 | 8 | 1528 | 275.04 | 1803.04 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | I/C-40A-4P-MCB (M) | No. | 2 | 1560 | 3120 | 561.6 | 3681.6 | 0 | 1 | 1560 | 280.8 | 1840.8 | 1 | 1840.8 |  | 50 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | PVC Conduit Bend-(M)-BC | No. | 25 | 14 | 350 | 63 | 413 | 0 | 25 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-2 Way (M) | No. | 50 | 30 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | 8 way VTPN DB (M) | No. | 2 | 9917 | 19834 | 3570.12 | 23404.12 | 0 | 1 | 9917 | 1785.06 | 11702.06 | 1 | 11702.06 |  | 50 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Earthing & Panel | 160 Amp DPX MCCB 16KA (M) | No. | 2 | 6738 | 13476 | 2425.68 | 15901.68 | 0 | 2 | 13476 | 2425.68 | 15901.68 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 way ETPN DB (M) | No. | 1 | 4037 | 4037 | 726.66 | 4763.66 | 0 | 1 | 4037 | 726.66 | 4763.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | O/P 16A SP MCB (M) | No. | 12 | 156 | 1872 | 336.96 | 2208.96 | 0 | 12 | 1872 | 336.96 | 2208.96 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | 8 way ETPN DB (M) | No. | 1 | 3589 | 3589 | 646.02 | 4235.02 | 0 | 1 | 3589 | 646.02 | 4235.02 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A FP MCB (M) | No. | 2 | 2422 | 4844 | 871.92 | 5715.92 | 0 | 2 | 4844 | 871.92 | 5715.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 1 Way (M) - | No. | 50 | 28.96 | 1448 | 260.64 | 1708.64 | 0 | 50 | 1448 | 260.64 | 1708.64 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | 12 Way ETPN DB (M) | No. | 1 | 5375 | 5375 | 967.5 | 6342.5 | 0 | 1 | 5375 | 967.5 | 6342.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C 6 sqmm (FRLS) Cable (M) | Mtrs | 3000 | 69.36 | 208080 | 37454.4 | 245534.4 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 4 Way (M) | No. | 100 | 36.56 | 3656 | 658.08 | 4314.08 | 0 | 100 | 3656 | 658.08 | 4314.08 | 0 | 0 |  | 100 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | Wiring Accessories Switches, Socket etc. (M) | No. | 5 | 1273 | 6365 | 1145.7 | 7510.7 | 0 | 4 | 5092 | 916.56 | 6008.56 | 1 | 1502.14 |  | 80 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A 100mA FP RCCB (M) | No. | 1 | 2784 | 2784 | 501.12 | 3285.12 | 0 | 1 | 2784 | 501.12 | 3285.12 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | 20 & 25mm Flexible Pipe (M) | Mtrs | 200 | 13 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Casing Ptti 100/50 (M) | Mtrs | 50 | 560.43 | 28021.5 | 5043.88 | 33065.38 | 0 | 13.1 | 7341.63 | 1321.48 | 8663.11 | 36.9 | 24402.27 |  | 26.2 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3 Module Plate (M) | No. | 8 | 118 | 944 | 169.92 | 1113.92 | 0 | 8 | 944 | 169.92 | 1113.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 1514.3 | 21.29 | 32239.45 | 5803.1 | 38042.55 | 0 | 1514.3 | 32239.45 | 5803.1 | 38042.55 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | O/G 10/16A SP MCB (M) | No. | 18 | 156 | 2808 | 505.44 | 3313.44 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 6/16 Amp Multi pin Socket (M) | No. | 30 | 207.16 | 6214.8 | 1118.66 | 7333.46 | 0 | 29.9998 | 6214.76 | 1118.64 | 7333.4 | 0.0002 | 0.06 |  | 99.9993 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Casing Ptti 38/25 (M) | Mtrs | 300 | 60 | 18000 | 3240 | 21240 | 0 | 297.2979 | 17837.87 | 3210.82 | 21048.69 | 2.7021 | 191.31 |  | 99.0993 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 32A SP MCB (M) | No. | 7 | 175 | 1225 | 220.5 | 1445.5 | 0 | 7 | 1225 | 220.5 | 1445.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | I/C 40A FP MCB (M) | No. | 1 | 1560 | 1560 | 280.8 | 1840.8 | 0 | 1 | 1560 | 280.8 | 1840.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 SWG GI Earthing Wire (M) | Mtrs | 230 | 94 | 21620 | 3891.6 | 25511.6 | 0 | 230 | 21620 | 3891.6 | 25511.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 6 sqmm A2XFY XLPE Cable (M) | Mtrs | 400 | 115 | 46000 | 8280 | 54280 | 0 | 394 | 45310 | 8155.8 | 53465.8 | 6 | 814.2 |  | 98.5 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 95sqmm A2XFY XLPE (M) | Mtrs | 100 | 538 | 53800 | 9684 | 63484 | 0 | 60 | 32280 | 5810.4 | 38090.4 | 40 | 25393.6 |  | 60 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 10SQMM 2XFY (M) | Mtrs | 45 | 541 | 24345 | 4382.1 | 28727.1 | 0 | 45 | 24345 | 4382.1 | 28727.1 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 Way SPN DB (M) | No. | 7 | 1366 | 9562 | 1721.16 | 11283.16 | 0 | 7 | 9562 | 1721.16 | 11283.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 185SQMM A2XFY XLPE(M) | No. | 2 | 1679 | 3358 | 604.44 | 3962.44 | 0 | 2 | 3358 | 604.44 | 3962.44 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 70sqmm A2XFY XLPE (M) | Mtrs | 41 | 419 | 17179 | 3092.22 | 20271.22 | 0 | 41 | 17179 | 3092.22 | 20271.22 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | I/C 25A DP MCB(M) | No. | 1 | 462 | 462 | 83.16 | 545.16 | 0 | 1 | 462 | 83.16 | 545.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 6 way ETPN (M) | No. | 1 | 3365 | 3365 | 605.7 | 3970.7 | 0 | 1 | 3365 | 605.7 | 3970.7 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 4C x 6sqmm (M) | No. | 2 | 386 | 772 | 138.96 | 910.96 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 250 Amp SFU with Encloser Box (M) | No. | 1 | 64350 | 64350 | 11583 | 75933 | 0 | 1 | 64350 | 11583 | 75933 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 way VTPN DB (M) | No. | 2 | 11157 | 22314 | 4016.52 | 26330.52 | 0 | 2 | 22314 | 4016.52 | 26330.52 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | O/G 10/16A SP MCB (M) | No. | 30 | 156 | 4680 | 842.4 | 5522.4 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 16A-SP-MCB (M) | No. | 18 | 175 | 3150 | 567 | 3717 | 0 | 18 | 3150 | 567 | 3717 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C x 2.5sqmm Cu cable armourd (M) | Mtrs | 100 | 167 | 16700 | 3006 | 19706 | 0 | 100 | 16700 | 3006 | 19706 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | 8 Way SPN DB (M) | No. | 1 | 1214 | 1214 | 218.52 | 1432.52 | 0 | 1 | 1214 | 218.52 | 1432.52 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Encloser Box (M) | No. | 14 | 429 | 6006 | 1081.08 | 7087.08 | 0 | 9 | 3861 | 694.98 | 4555.98 | 5 | 2531.1 |  | 64.2857 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | O/G 10/16A SP MCB (M) | No. | 6 | 156 | 936 | 168.48 | 1104.48 | 0 | 6 | 936 | 168.48 | 1104.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | Coupling (M) | No. | 50 | 7 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | Sub I/C 40A DP RCCB 30mA (M) | No. | 3 | 2015 | 6045 | 1088.1 | 7133.1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-4 Way (M) | No. | 100 | 37 | 3700 | 666 | 4366 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 20 & 25mm Flexible Pipe (M) | Mtrs | 200 | 14 | 2800 | 504 | 3304 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-3 Way (M) | No. | 80 | 32 | 2560 | 460.8 | 3020.8 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (M) | Mtrs | 6015 | 47.46 | 285471.9 | 51384.94 | 336856.84 | 0 | 6015 | 285471.9 | 51384.94 | 336856.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | I/C 63A FP MCB (M) | No. | 1 | 1560 | 1560 | 280.8 | 1840.8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | 500 Amp SFU with Encloser Box (M) | No. | 1 | 64350 | 64350 | 11583 | 75933 | 0 | 1 | 64350 | 11583 | 75933 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 10SQMM 2XFY(M) | No. | 2 | 345 | 690 | 124.2 | 814.2 | 0 | 2 | 690 | 124.2 | 814.2 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 4 sqmm Cu wire (M) | Mtrs | 1500 | 42.71 | 64065 | 11531.7 | 75596.7 | 0 | 1499.99 | 64064.57 | 11531.62 | 75596.19 | 0.01 | 0.51 |  | 99.9993 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | 8 Way SPN DB (M) | No. | 1 | 1495 | 1495 | 269.1 | 1764.1 | 0 | 1 | 1495 | 269.1 | 1764.1 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 6SQMM A2XFY XLPE(M) | No. | 22 | 298 | 6556 | 1180.08 | 7736.08 | 0 | 16 | 4768 | 858.24 | 5626.24 | 6 | 2109.84 |  | 72.7273 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 1.5 sqmm Cu wire (M) | Mtrs | 3000 | 17.55 | 52650 | 9477 | 62127 | 0 | 2999.88 | 52647.89 | 9476.62 | 62124.51 | 0.12 | 2.49 |  | 99.996 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 6 Amp Switch (M) | No. | 40 | 57 | 2280 | 410.4 | 2690.4 | 0 | 40 | 2280 | 410.4 | 2690.4 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 3 Module Plate (M) | No. | 35 | 102.21 | 3577.35 | 643.92 | 4221.27 | 0 | 35 | 3577.35 | 643.92 | 4221.27 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | PVC Conduit Piping (M) | Mtrs | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 29 Apr 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 63A 4P MCB (M+L) | No. | 9 | 1681 | 15129 | 2723.22 | 17852.22 | 0 | 9 | 15129 | 2723.22 | 17852.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16 sqmm A2XFY XLPE Cable(M) | Mtrs | 250 | 800 | 200000 | 36000 | 236000 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 1C x 70 sqmm Copper Lead(M) | Mtrs | 100 | 839 | 83900 | 15102 | 99002 | 0 | 92.4 | 77523.6 | 13954.24 | 91477.84 | 7.6 | 7524.16 |  | 92.4 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 6 Module Box (M) | No. | 20 | 82.55 | 1651 | 297.18 | 1948.18 | 0 | 13 | 1073.15 | 193.16 | 1266.31 | 7 | 681.87 |  | 65 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | O/G 10/16A SP MCB (M) | No. | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 06 Dec 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 2 Way (M) | No. | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 3 Module Box (M) | No. | 35 | 55.03 | 1926.05 | 346.68 | 2272.73 | 0 | 34.9997 | 1926.03 | 346.68 | 2272.71 | 0.0003 | 0.02 |  | 99.9991 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 2.5 sqmm (FRLS) Cable (M) | Mtrs | 1156.1 | 32.25 | 37284.23 | 6711.16 | 43995.39 | 0 | 1156.1 | 37284.23 | 6711.16 | 43995.39 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 20 Amp Switch (M) | No. | 100 | 162 | 16200 | 2916 | 19116 | 0 | 99 | 16038 | 2886.84 | 18924.84 | 1 | 191.16 |  | 99 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Casing Ptti 38/25 (M) | Mtrs | 300 | 60.26 | 18078 | 3254.04 | 21332.04 | 0 | 297.298 | 17915.18 | 3224.72 | 21139.9 | 2.702 | 192.14 |  | 99.0993 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Junction Box 4 Way (M) | No. | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | Junction Box-4 Way (M) | No. | 50 | 28 | 1400 | 252 | 1652 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 70SQMM A2XFY XLPE(M) | No. | 2 | 854 | 1708 | 307.44 | 2015.44 | 0 | 2 | 1708 | 307.44 | 2015.44 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A 100mA DP RCCB (M) | No. | 3 | 2422 | 7266 | 1307.88 | 8573.88 | 0 | 3 | 7266 | 1307.88 | 8573.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (M) | Mtrs | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 29 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | 20 & 25mm Flexible Pipe (M) | Mtrs | 100 | 14 | 1400 | 252 | 1652 | 0 | 100 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3.5C x 35sqmm (M). | No. | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | O/P-40A-TP MCB (M) | No. | 16 | 1377 | 22032 | 3965.76 | 25997.76 | 0 | 16 | 22032 | 3965.76 | 25997.76 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | RJ 45 Data Socket (M) | No. | 5 | 115 | 575 | 103.5 | 678.5 | 0 | 5 | 575 | 103.5 | 678.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Casing Ptti 100/50 (M) | Mtrs | 50 | 577 | 28850 | 5193 | 34043 | 0 | 13.1 | 7558.7 | 1360.56 | 8919.26 | 36.9 | 25123.74 |  | 26.2 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16SQMM 2XFY (M) | No. | 8 | 509 | 4072 | 732.96 | 4804.96 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Casing Ptti 100/50 (M) | Mtrs | 0 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-1 Way (M) | No. | 50 | 29 | 1450 | 261 | 1711 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | Sub I/C 40A DP RCCB 30mA (M) | No. | 3 | 2015 | 6045 | 1088.1 | 7133.1 | 0 | 3 | 6045 | 1088.1 | 7133.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | 6 Amp Socket (M) | No. | 100 | 149.66 | 14966 | 2693.88 | 17659.88 | 0 | 95 | 14217.7 | 2559.18 | 16776.88 | 5 | 883 |  | 95 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Point Wiring | 2.5 sqmm Cu wire (M) | Mtrs | 3500 | 28.08 | 98280 | 17690.4 | 115970.4 | 0 | 3499.9699 | 98279.15 | 17690.24 | 115969.39 | 0.0301 | 1.01 |  | 99.9991 |  | vaibhav biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A FP MCB (M) | No. | 1 | 1681 | 1681 | 302.58 | 1983.58 | 0 | 1 | 1681 | 302.58 | 1983.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Flexible Cable | CAT 6 Cable (M) | Mtrs | 258.5 | 25 | 6462.5 | 1163.26 | 7625.76 | 0 | 258.5 | 6462.5 | 1163.26 | 7625.76 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A 100mA DP RCCB (M) | No. | 7 | 2422 | 16954 | 3051.72 | 20005.72 | 0 | 7 | 16954 | 3051.72 | 20005.72 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | O/G 10/16A SP MCB (M) | No. | 36 | 156 | 5616 | 1010.88 | 6626.88 | 0 | 36 | 5616 | 1010.88 | 6626.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | O/P-40A-TP MCB (M) | No. | 4 | 1224 | 4896 | 881.28 | 5777.28 | 0 | 4 | 4896 | 881.28 | 5777.28 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open |  |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 106 | 1 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 6 sqmm Alu. Cable (M) | Mtrs | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 106 | 0 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Casing Ptti 38/25 (M) | Mtrs | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 13 Jan 2022
EAST POINT MARKET | 106 | 2 | 11 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | Junction Box-1 Way (M) | No. | 80 | 20 | 1600 | 288 | 1888 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (M) | Mtrs | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Casing Ptti 100/50 (M) | Mtrs | 0 | 577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 16sqmm Alumn Armd. Cable (L) | Mtrs | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Primary Light Pt. (Controlled by Sw. Board) | No. | 100 | 300 | 30000 | 5400 | 35400 | 2.5 | 63 | 18900 | 3402 | 22302 | 37 | 13098 |  | 63 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 Way SPN DB (M) | No. | 0 | 1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | O/G 40A-TPN-MCB (M+L) | No. | 0 | 1377 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 28 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-3 Way (M) | No. | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 16sqmm Alumn Armd. Cable (L) | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | SITC G.I Earthing Strip 25 x 3mm (M) | Mtrs | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 16A-SP-MCB (M) | No. | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 250 Amp SFU with Encloser Box (M) | No. | 0 | 64350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | RJ11 Telephone Socket (M) | No. | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A 100mA DP RCCB (M) | No. | 0 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C x 2.5sqmm Cu cable armourd (L) | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Secondary Light Points controlled by MCB | No. | 20 | 150 | 3000 | 540 | 3540 | 2.5 | 20 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C x 2.5sqmm Cu cable armourd (M) | Mtrs | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 10SQMM 2XFY(L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | O/P-40A-TP MCB (M) | No. | 0 | 1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Power Point -BC | No. | 15 | 450 | 6750 | 1215 | 7965 | 2.5 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 way ETPN DB (M) | No. | 0 | 4037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 SWG GI Earthing Wire (M) | Mtrs | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3 Module Plate (M) | No. | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 20 & 25mm Flexible Pipe (M) | Mtrs | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 way VTPN DB (M) | No. | 0 | 11157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 6 sqmm Alu. Cable (L) | Mtrs | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 16sqmm Alumn Armd. Cable (M) | Mtrs | 0 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A 100mA FP RCCB (M) | No. | 0 | 2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 6 sqmm Alu. Cable (M) | Mtrs | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3C 2.5sqmm Cu Armd Cable (M) | No. | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 6/16 Amp Multi pin Socket (M) | No. | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C x 2.5sqmm Cu cable armourd (L) | Mtrs | 100 | 55 | 5500 | 990 | 6490 | 2.5 | 100 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | 500 Amp SFU with Encloser Box (L) | No. | 1 | 4500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | 6 way ETPN (M) | No. | 0 | 3365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16 sqmm A2XFY XLPE Cable(L) | Mtrs | 250 | 75 | 18750 | 3375 | 22125 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 10SQMM 2XFY (L) | Mtrs | 45 | 60 | 2700 | 486 | 3186 | 2.5 | 45 | 2700 | 486 | 3186 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C x 2.5sqmm Cu cable armourd (L) | Mtrs | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Fan Points Controlled by Switch | No. | 60 | 350 | 21000 | 3780 | 24780 | 2.5 | 46 | 16100 | 2898 | 18998 | 14 | 5782 |  | 76.6667 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A FP MCB (M) | No. | 0 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 Way SPN DB (L) | No. | 0 | 1150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Jan 2022 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 185SQMM A2XFY XLPE(L) | No. | 2 | 420 | 840 | 151.2 | 991.2 | 2.5 | 2 | 840 | 151.2 | 991.2 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3.5C x 35sqmm (M). | No. | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 250 Amp SFU with Encloser Box (L) | No. | 1 | 4500 | 4500 | 810 | 5310 | 2.5 | 1 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Main Wiring for Shop | 4X6 SQMM + 1X4 SQMM Insulated Cu conductor. | No. | 5 | 1200 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Secondary Light Pt. (Controlled by Sw. Board) | No. | 100 | 150 | 15000 | 2700 | 17700 | 2.5 | 100 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Casing Ptti 38/25 (M) | Mtrs | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 63A 4P MCB (M) | No. | 0 | 1681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A 100mA DP RCCB (M) | No. | 0 | 2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 32A SP MCB (M) | No. | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 63A 4P MCB (M+L) | No. | 0 | 1681 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 28 Apr 2022
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | 8 Way SPN DB (L) | No. | 1 | 1150 | 1150 | 207 | 1357 | 2.5 | 1 | 1150 | 207 | 1357 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | O/G 40A-TPN-MCB (M) | No. | 0 | 1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Earthing & Panel | SITC G.I Earthing Strip 25 x 3mm (L) | Mtrs | 300 | 40 | 12000 | 2160 | 14160 | 2.5 | 300 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A FP MCB (M) | No. | 0 | 1681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (M) | Mtrs | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 4C x 6sqmm (M) | No. | 0 | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Encloser Box (M) | No. | 0 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Miscellaneous Expenses | No. | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-2 Way (M) | No. | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Flexible Cable | CAT 6 Cable (L) | Mtrs | 258.5 | 22 | 5687 | 1023.66 | 6710.66 | 2.5 | 258.5 | 5687 | 1023.66 | 6710.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Light Fixtures Installation Only | Installation LED Tube | No. | 30 | 200 | 6000 | 1080 | 7080 | 2.5 | 30 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 16A Socket & Switch | No. | 4 | 600 | 2400 | 432 | 2832 | 2.5 | 4 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation of Panel,SFU&Breaker | 8 way ETPN DB (L) | No. | 1 | 1250 | 1250 | 225 | 1475 | 2.5 | 1 | 1250 | 225 | 1475 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | 16A Socket & Switch | No. | 15 | 600 | 9000 | 1620 | 10620 | 2.5 | 14 | 8400 | 1512 | 9912 | 1 | 708 |  | 93.3333 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | AC Points Controlled by Switch | No. | 15 | 600 | 9000 | 1620 | 10620 | 2.5 | 10 | 6000 | 1080 | 7080 | 5 | 3540 |  | 66.6667 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-1 Way (M) | No. | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 6 Amp Switch (M) | No. | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 Way SPN DB (L) | No. | 7 | 1200 | 8400 | 1512 | 9912 | 2.5 | 7 | 8400 | 1512 | 9912 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 12M Base Plate | No. | 0 | 1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 300 x 50mm | Mtrs | 93 | 100 | 9300 | 1674 | 10974 | 2.5 | 93 | 9300 | 1674 | 10974 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Junction Box-4 Way (M) | No. | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | No category | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 300mm Perforated Cable Tray Removal | Mtrs | 29 | 50 | 1450 | 261 | 1711 | 0 | 29 | 1450 | 261 | 1711 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 2.5 sqmm (FRLS) Cable (M) | Mtrs | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | PVC Conduit Bend-(M)-BC | No. | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | RJ 45 Data Socket (M) | No. | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Coupling (M) | No. | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 32A 2P MCB (M) | No. | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3C 2.5sqmm Cu Armd Cable (L) | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C 6 sqmm (FRLS) Cable (M) | Mtrs | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 32A 2P MCB (M+L) | No. | 0 | 558 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 28 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 4C x 6sqmm (L) | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16 sqmm A2XFY XLPE Cable (L) | No. | 8 | 180 | 1440 | 259.2 | 1699.2 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | PVC Conduit Piping (M) | Mtrs | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 12M Base Plate | No. | 8 | 65 | 520 | 93.6 | 613.6 | 2.5 | 4 | 260 | 46.8 | 306.8 | 4 | 306.8 |  | 50 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Earthing & Panel | 160 Amp DPX MCCB 16KA (L) | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 10mm Rod Removal | No. | 350 | 15 | 5250 | 945 | 6195 | 0 | 350 | 5250 | 945 | 6195 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3.5C x 35 Sqmm. (L) | No. | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | LED Downlight Fitting | No. | 112 | 200 | 22400 | 4032 | 26432 | 2.5 | 112 | 22400 | 4032 | 26432 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 Way VTPN DB (L) | No. | 0 | 1650 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 185sqmm A2XFY XLPE (L) | Mtrs | 100 | 200 | 20000 | 3600 | 23600 | 2.5 | 60 | 12000 | 2160 | 14160 | 40 | 9440 |  | 60 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | 8 Way VTPN DB (L) | No. | 2 | 2000 | 4000 | 720 | 4720 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 150 x 50mm | Mtrs | 93 | 70 | 6510 | 1171.8 | 7681.8 | 2.5 | 93 | 6510 | 1171.8 | 7681.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3 Module Box (M) | No. | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 way ETPN DB (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 6 sqmm Alu. Cable (L) | Mtrs | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 40A DP MCB (M) | No. | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Earthing & Panel | 8SWG GI Earthing Wire (L) | Mtrs | 100 | 10 | 1000 | 180 | 1180 | 2.5 | 100 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | Primary Light Points (Controlled by MCB) | No. | 30 | 800 | 24000 | 4320 | 28320 | 2.5 | 30 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | SITC G.I Earthing Strip 25 x 3mm (L) | Mtrs | 378 | 40 | 15120 | 2721.6 | 17841.6 | 2.5 | 378 | 15120 | 2721.6 | 17841.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Termination of Cables - 1 No. | 3.5C x 70SQMM A2XFY XLPE(L) | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Primary Point Controlled by MCB | Primary Light Points (Controlled by MCB) | No. | 38 | 800 | 30400 | 5472 | 35872 | 2.5 | 38 | 30400 | 5472 | 35872 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 16sqmm Alumn Armd. Cable (L) | Mtrs | 8 | 80 | 640 | 115.2 | 755.2 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 16A-SP-MCB (M) | No. | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 26 Apr 2022
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Secondary Pt. above Primary Pt. Looped (L) | No. | 257 | 150 | 38550 | 6939 | 45489 | 2.5 | 175.9981 | 26399.72 | 4751.94 | 31151.66 | 81.0019 | 14337.35 |  | 68.4818 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply of Switch & Sockets | Primary Light Pt. (Controlled by Sw. Board) | No. | 23 | 300 | 6900 | 1242 | 8142 | 2.5 | 23 | 6900 | 1242 | 8142 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 1C x 70 sqmm Copper Lead (L) | No. | 26 | 75 | 1950 | 351 | 2301 | 2.5 | 26 | 1950 | 351 | 2301 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Miscellaneous Expenses | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Flexible Cable | 3C 2.5sqmm Flex. Cable (L) | Mtrs | 290 | 40 | 11600 | 2088 | 13688 | 0 | 290 | 11600 | 2088 | 13688 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 150 x 50mm | Mtrs | 365 | 35 | 12775 | 2299.5 | 15074.5 | 0 | 365 | 12775 | 2299.5 | 15074.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 150 x 50mm | Mtrs | 133 | 70 | 9310 | 1675.8 | 10985.8 | 2.5 | 133 | 9310 | 1675.8 | 10985.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16SQMM 2XFY (L) | No. | 8 | 180 | 1440 | 259.2 | 1699.2 | 2.5 | 8 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Refixing Work- DER | No. | 50 | 75 | 3750 | 675 | 4425 | 2.5 | 50 | 3750 | 675 | 4425 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | DEV. Extrawork/Rework | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 95sqmm A2XFY XLPE (L) | Mtrs | 100 | 140 | 14000 | 2520 | 16520 | 2.5 | 60 | 8400 | 1512 | 9912 | 40 | 6608 |  | 60 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | 16 way ETPN DB (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 6 sqmm A2XFY XLPE Cable (L) | Mtrs | 400 | 30 | 12000 | 2160 | 14160 | 2.5 | 394 | 11820 | 2127.6 | 13947.6 | 6 | 212.4 |  | 98.5 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 35sqmm A2XFY XLPE (L) | Mtrs | 56 | 100 | 5600 | 1008 | 6608 | 2.5 | 55.3 | 5530 | 995.4 | 6525.4 | 0.7 | 82.6 |  | 98.75 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Primary Light Points (Controlled by MCB) | No. | 17 | 800 | 13600 | 2448 | 16048 | 2.5 | 17 | 13600 | 2448 | 16048 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8 Way VTPN DB (L) | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Above Ceiling Conduit &Accessories for Wiring | 6A Socket Switch | No. | 60 | 300 | 18000 | 3240 | 21240 | 2.5 | 45.9996 | 13799.88 | 2483.98 | 16283.86 | 14.0004 | 4956.14 |  | 76.666 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 300 x 50mm | Mtrs | 203.5 | 50 | 10175 | 1831.5 | 12006.5 | 0 | 203.5 | 10175 | 1831.5 | 12006.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | LED Strip (Normal) (L) | Mtrs | 409 | 105 | 42945 | 7730.1 | 50675.1 | 2.5 | 190 | 19950 | 3591 | 23541 | 219 | 27134.1 |  | 46.4548 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply&Installation FP MCCB,MCB,EB | 12 Way ETPN DB (L) | No. | 1 | 1450 | 1450 | 261 | 1711 | 2.5 | 1 | 1450 | 261 | 1711 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 16A Socket & Switch | No. | 23 | 600 | 13800 | 2484 | 16284 | 2.5 | 23 | 13800 | 2484 | 16284 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 4C x 6sqmm (L) | No. | 2 | 100 | 200 | 36 | 236 | 2.5 | 2 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 70sqmm A2XFY XLPE (L) | Mtrs | 41 | 120 | 4920 | 885.6 | 5805.6 | 2.5 | 41 | 4920 | 885.6 | 5805.6 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 3.5C x 95SQMM A2XFY XLPE(L) | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 6SQMM A2XFY XLPE(L) | No. | 22 | 90 | 1980 | 356.4 | 2336.4 | 2.5 | 15.9999 | 1439.99 | 259.2 | 1699.19 | 6.0001 | 637.21 |  | 72.7268 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 1C x 70 sqmm Copper Lead(L) | Mtrs | 100 | 35 | 3500 | 630 | 4130 | 2.5 | 92.4 | 3234 | 582.12 | 3816.12 | 7.6 | 313.88 |  | 92.4 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4SQMM FRLS Wire (L) | Mtrs | 6015 | 21 | 126315 | 22736.7 | 149051.7 | 2.5 | 6015 | 126315 | 22736.7 | 149051.7 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | No category | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3C 2.5sqmm Cu Armd Cable (L) | No. | 10 | 100 | 1000 | 180 | 1180 | 2.5 | 10 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl HT Cable | 4C x 16SQMM A2XFY XLPE (L) | Mtrs | 150 | 40 | 6000 | 1080 | 7080 | 2.5 | 150 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 300 x 50mm | Mtrs | 29 | 100 | 2900 | 522 | 3422 | 2.5 | 29 | 2900 | 522 | 3422 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Sensor Point-Mkt | No. | 12 | 200 | 2400 | 432 | 2832 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 300 x 50mm | Mtrs | 90 | 100 | 9000 | 1620 | 10620 | 2.5 | 90 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 4C 6 sqmm Alu. Cable (L) | Mtrs | 60 | 55 | 3300 | 594 | 3894 | 2.5 | 60 | 3300 | 594 | 3894 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply of Switch & Sockets | Secondary Light Pt. (Controlled by Sw. Board) | No. | 27 | 150 | 4050 | 729 | 4779 | 2.5 | 27 | 4050 | 729 | 4779 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | GI Perforated Tray 150 x 50mm | Mtrs | 14 | 70 | 980 | 176.4 | 1156.4 | 2.5 | 14 | 980 | 176.4 | 1156.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | LED Light Fitting | No. | 164 | 250 | 41000 | 7380 | 48380 | 2.5 | 164 | 41000 | 7380 | 48380 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | Secondary Light Pt. (Controlled by Sw. Board) | No. | 52 | 150 | 7800 | 1404 | 9204 | 2.5 | 0 | 0 | 0 | 0 | 52 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 3C 2.5sqmm Flex. Cable (L) | Mtrs | 205.5 | 15 | 3082.5 | 554.86 | 3637.36 | 2.5 | 205.4795 | 3082.19 | 554.78 | 3636.97 | 0.0205 | 0.39 |  | 99.99 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | End Termination 3.5C x 35 Sqmm. (L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 2 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Supply of Switch & Sockets | Secondary Pt. above Primary Pt. Looped (L) | No. | 269 | 150 | 40350 | 7263 | 47613 | 2.5 | 269 | 40350 | 7263 | 47613 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Distribution Board&MCBS | 8 Way SPN DB (L) | No. | 1 | 1150 | 1150 | 207 | 1357 | 0 | 1 | 1150 | 207 | 1357 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | MKT. Marketing Infrastructure | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 8SWG GI Earthing Wire (L) | Mtrs | 230 | 10 | 2300 | 414 | 2714 | 2.5 | 230 | 2300 | 414 | 2714 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Power Socket Outlets | Wiring Accessories Switches, Socket etc. (L) | No. | 5 | 65 | 325 | 58.5 | 383.5 | 2.5 | 4 | 260 | 46.8 | 306.8 | 1 | 76.7 |  | 80 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Main Wiring for Shop | 2X4 SQMM + 1X2.5 SQMM Insulated Cu conductor. | No. | 10 | 800 | 8000 | 1440 | 9440 | 2.5 | 9 | 7200 | 1296 | 8496 | 1 | 944 |  | 90 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 107 | 1 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Common Common Electrical work | 6 way ETPN (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 22 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 107 | 0 | 12 Jan 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Light Fixtures Installation Only | LED Downlight Fitting | No. | 50 | 250 | 12500 | 2250 | 14750 | 2.5 | 50 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Vaibhav Biradar | CHETAN.JEWALIKAR | construction open | 22 Jan 2022 |  | B.C. Building Common Items | Approved | CHETAN.JEWALIKAR
EAST POINT MARKET | 108 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | 3rd Floor Misc work | Labour Lumpsum | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jan 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 108 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | 3rd Floor Misc work | ACP Work (M+L) | Sq.Ft | 168.315 | 250 | 42078.75 | 7574.18 | 49652.93 | 2.5 | 0 | 0 | 0 | 0 | 168.315 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 108 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (m) -BC | Sq.Ft | 0 | 181.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 15 Jan 2022 |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 27 Jan 2022
EAST POINT MARKET | 108 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | 3rd Floor Misc work | Labour Lumpsum | No. | 1 | 18000 | 18000 | 3240 | 21240 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jan 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 108 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | 3rd Floor Misc work | Labour Lumpsum | No. | 1 | 8000 | 8000 | 1440 | 9440 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jan 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 108 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (m) -BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 15 Jan 2022 |  | B.C. Internal Finishing Itmes | Cancelled | vaibhav biradar | 15 Jan 2022
EAST POINT MARKET | 109 | 0 | 15 Jan 2022 | SAHARA ENGINEERING | KEP-4th Fl Atrium Lobby False Ceiling Work | False Ceiling (l) -BC | Sq.Ft | 0 | 73.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 27 Jan 2022 |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 27 Jan 2022
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Vitrified Flooring work | Sq.Ft | 698.38 | 28 | 19554.64 | 3519.84 | 23074.48 | 2.5 | 0 | 0 | 0 | 0 | 698.38 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | 11 TILING WORK | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | V Groove making- BC | R.Ft | 518.53 | 40 | 20741.2 | 3733.42 | 24474.62 | 2.5 | 0 | 0 | 0 | 0 | 518.53 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Granite Patti | R.Ft | 542.19 | 55 | 29820.45 | 5367.68 | 35188.13 | 2.5 | 0 | 0 | 0 | 0 | 542.19 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | MKT. Marketing Infrastructure | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Wash Basin Counter-AIE | No. | 12 | 3000 | 36000 | 6480 | 42480 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | B.C. Internal Finishing Itmes | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Granite Door Frame- BCV | R.Ft | 106.32 | 55 | 5847.6 | 1052.56 | 6900.16 | 2.5 | 0 | 0 | 0 | 0 | 106.32 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | B.C. Internal Finishing Itmes | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Granite Dado Work - Dld | Sq.Ft | 1323.79 | 75 | 99284.25 | 17871.16 | 117155.41 | 2.5 | 0 | 0 | 0 | 0 | 1323.79 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | DEV. Landscape/Equipment | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Vitrified Tile Border | R.Ft | 205.75 | 28 | 5761 | 1036.98 | 6797.98 | 2.5 | 0 | 0 | 0 | 0 | 205.75 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | 11 TILING WORK | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | Granite Skirting Patti Fixing | No. | 31 | 28 | 868 | 156.24 | 1024.24 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | 11 TILING WORK | Un-Approved
EAST POINT MARKET | 110 | 0 | 15 Jan 2022 | M/S ABHINAV SINGH | KEP-Gr Floor Toilet Block Flooring&Tiling | L Groove - BCV | R.Ft | 152 | 35 | 5320 | 957.6 | 6277.6 | 2.5 | 0 | 0 | 0 | 0 | 152 | 0 |  | 0 |  | vaibhav biradar |  | construction open |  |  | B.C. Building Common Items | Un-Approved
EAST POINT MARKET | 111 | 1 | 15 Jan 2022 | ANTS DESIGN | Interior Fitout for Sample retail space | Interior Fituout | No. | 1 | 158000 | 158000 | 28440 | 186440 | 0 | 1 | 158000 | 28440 | 186440 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 15 Jan 2022 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 111 | 0 | 15 Jan 2022 | ANTS DESIGN | Interior Fitout for Sample retail space | Interior Fituout | No. | 1 | 1620000 | 1620000 | 291600 | 1911600 | 0 | 1 | 1620000 | 291600 | 1911600 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 15 Jan 2022 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 112 | 1 | 22 Jan 2022 | K K SHINDE MANDAP DECORATORS | KEP-Guardians Rental charges Chair&Table | Rental Charges - So | Month | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 09 Nov 2022
EAST POINT MARKET | 112 | 2 | 22 Jan 2022 | K K SHINDE MANDAP DECORATORS | KEP-Guardians Rental charges Chair&Table | Rental Charges - So | Month | 5 | 26000 | 130000 | 0 | 130000 | 0 | 4.5 | 117000 | 0 | 117000 | 0.5 | 13000 |  | 90 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 03 Feb 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 112 | 0 | 22 Jan 2022 | K K SHINDE MANDAP DECORATORS | KEP-Guardians Rental charges Chair&Table | Rental Charges - So | Month | 6 | 20000 | 120000 | 0 | 120000 | 0 | 6 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 112 | 1 | 22 Jan 2022 | K K SHINDE MANDAP DECORATORS | KEP-Guardians Rental charges Chair&Table | Rental Charges - So | Month | 6 | 6000 | 36000 | 0 | 36000 | 0 | 6 | 36000 | 0 | 36000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 03 Feb 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 113 | 0 | 24 Jan 2022 | GUARDIANS REAL ESTATE ADVISORY LLP | Media BRANDING | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 1 | 550000 | 550000 | 99000 | 649000 | 0 | 1 | 550000 | 99000 | 649000 | 0 | 0 | EAST POINT MARKET - SALES PROMOTION - DESIGNING CHARGES (ATTACHED SCOPE OF WORK) FOR GUARDIANS REAL ESTATE | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 24 Jan 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 114 | 0 | 25 Jan 2022 | ARACELI HOSPITALITY MANAGEMENT PRIVATE LIMITED | Interior Work Foodcourt Rltailers | Interior Work - BC | No. | 1 | 1216589 | 1216589 | 218986.02 | 1435575.02 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for brand - THE MOMO FACTORY | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 25 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 114 | 1 | 25 Jan 2022 | ARACELI HOSPITALITY MANAGEMENT PRIVATE LIMITED | Interior Work Foodcourt Rltailers | Interior Work - BC | No. | 1 | 218986 | 218986 | 0 | 218986 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 30 Jun 2023
EAST POINT MARKET | 115 | 0 | 25 Jan 2022 | UNIVERSAL KITCHENS | Interior Work Foodcourt Rltailers | Interior Work - BC | No. | 1 | 1597103 | 1597103 | 287478.54 | 1884581.54 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 25 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 115 | 1 | 25 Jan 2022 | UNIVERSAL KITCHENS | Interior Work Foodcourt Rltailers | Interior Work - BC | No. | 1 | 287478 | 287478 | 0 | 287478 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 30 Jun 2023
EAST POINT MARKET | 116 | 0 | 25 Jan 2022 | BIG BANG VENTURES | Interior Work Foodcourt Rltailers | Interior Work - BC | No. | 1 | 880142 | 880142 | 158425.56 | 1038567.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 25 Jan 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Stool | No. | 1 | 8800 | 8800 | 1584 | 10384 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Lockers Storage | Sq.Ft | 144 | 1232 | 177408 | 31933.44 | 209341.44 | 2.5 | 117 | 144144 | 25945.92 | 170089.92 | 27 | 39251.52 | Size of Lockers Storage 16 feet x 9 feet x 12 inch. | 81.25 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 52.5 | 704 | 36960 | 6652.8 | 43612.8 | 2.5 | 52.5 | 36960 | 6652.8 | 43612.8 | 0 | 0 | Size of Door frames 7.5 feet + 7.5 feet + 2.5 feet | 100 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 4th Floor Misc works | Labour lumpsum | No. | 1 | 2325 | 2325 | 418.5 | 2743.5 | 2.5 | 1 | 2325 | 418.5 | 2743.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Feb 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Overhead Storage | Sq.Ft | 45 | 1320 | 59400 | 10692 | 70092 | 2.5 | 41.2497 | 54449.6 | 9800.92 | 64250.52 | 3.7503 | 5841.48 | Size of Overhead Storage 15 feet x 3 feet x 15 inch. | 91.666 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Partition | Sq.Ft | 85.5 | 704 | 60192 | 10834.56 | 71026.56 | 2.5 | 85.5 | 60192 | 10834.56 | 71026.56 | 0 | 0 | Size of Partition 4 feet 9 inch x 9 feet . | 100 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 52.5 | 572 | 30030 | 5405.4 | 35435.4 | 2.5 | 45 | 25740 | 4633.2 | 30373.2 | 7.5 | 5062.2 | Size of mirror panelling 7 feet x 2.5 feet. | 85.7143 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 2nd Floor Misc Works | Labour Lumpsum | No. | 1 | 51150 | 51150 | 9207 | 60357 | 2.5 | 1 | 51150 | 9207 | 60357 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Feb 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 18 | 704 | 12672 | 2280.96 | 14952.96 | 2.5 | 18 | 12672 | 2280.96 | 14952.96 | 0 | 0 | Size of Door frames 7.5 feet + 7.5 feet + 3 feet | 100 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Partition | Sq.Ft | 67.5 | 704 | 47520 | 8553.6 | 56073.6 | 2.5 | 67.5 | 47520 | 8553.6 | 56073.6 | 0 | 0 | Size of Partition 2.5 feet x 9 feet. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 2nd Floor Misc Works | Labour Lumpsum | No. | 1 | 4650 | 4650 | 837 | 5487 | 2.5 | 1 | 4650 | 837 | 5487 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Feb 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 0 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | KEP-Gr Floor Fire Ply Fixing Work (Meter Room) | Plywood fixing-Bco | Sq.Ft | 592.46 | 25 | 14811.5 | 2666.08 | 17477.58 | 2.5 | 592.46 | 14811.5 | 2666.08 | 17477.58 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Partition | Sq.Ft | 71.25 | 704 | 50160 | 9028.8 | 59188.8 | 2.5 | 71.25 | 50160 | 9028.8 | 59188.8 | 0 | 0 | Size of Partition 5 feet x 4 feet 9 inch. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 4th Floor Misc works | Labour lumpsum | No. | 1 | 1395 | 1395 | 251.1 | 1646.1 | 2.5 | 1 | 1395 | 251.1 | 1646.1 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Feb 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 4th Floor Misc works | Labour lumpsum | No. | 0 | 500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 03 Feb 2022 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 05 Jul 2023
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of Ledge with MS Support | R.Ft | 18 | 880 | 15840 | 2851.2 | 18691.2 | 2.5 | 13.5 | 11880 | 2138.4 | 14018.4 | 4.5 | 4672.8 | Size of Ledge with MS Supports 18 feet x 2 feet . | 75 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 4th Floor Misc works | Labour lumpsum | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 03 Feb 2022 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 05 Jul 2023
EAST POINT MARKET | 117 | 1 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of door | No. | 5 | 11440 | 57200 | 10296 | 67496 | 2.5 | 4 | 45760 | 8236.8 | 53996.8 | 1 | 13499.2 | Size of Door 3 feet x 8 feet | 80 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 2nd Floor Misc Works | Labour Lumpsum | No. | 0 | 5000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 03 Feb 2022 |  | DEV. Ext Development | Cancelled | DUSHANT.GORE | 05 Jul 2023
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 4th Floor Misc works | Labour lumpsum | No. | 0 | 1500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 03 Feb 2022 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 05 Jul 2023
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 4th Floor Misc works | Labour lumpsum | No. | 1 | 480 | 480 | 86.4 | 566.4 | 2.5 | 1 | 480 | 86.4 | 566.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Feb 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 117 | 2 | 27 Jan 2022 | ANAND FURNITURE AND INTERIOR | 2nd Floor Misc Works | Labour Lumpsum | No. | 0 | 55000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 03 Feb 2022 |  | DEV. Ext Development | Cancelled | DUSHANT.GORE | 05 Jul 2023
EAST POINT MARKET | 118 | 0 | 27 Jan 2022 | M/S ABHINAV SINGH | 3rd Fl Flooring & Tiling 3rd Fl-Foodcourt Flooring & Skirtin | Vitrified Flooring -BC | Sq.Ft | 6328.52 | 28 | 177198.56 | 31895.74 | 209094.3 | 2.5 | 6328.5074 | 177198.21 | 27644.04 | 204842.25 | 0.0126 | 4252.05 |  | 99.9998 |  | Dushant Gore | skmishra | construction open | 25 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 118 | 0 | 27 Jan 2022 | M/S ABHINAV SINGH | 3rd Fl Flooring & Tiling 3rd Fl-Foodcourt Flooring & Skirtin | Granite Patti- BCo | R.Ft | 772.29 | 55 | 42475.95 | 7645.68 | 50121.63 | 2.5 | 772.2892 | 42475.91 | 2455.02 | 44930.93 | 0.0008 | 5190.7 |  | 99.9999 |  | Dushant Gore | skmishra | construction open | 25 Feb 2022 |  | B.C. Building Common Items | Approved | skmishra
EAST POINT MARKET | 119 | 0 | 27 Jan 2022 | MUKUL KUMAR CHOUDHARY | Site Staff | Site Staff | Month | 4 | 14000 | 56000 | 0 | 56000 | 0 | 2 | 28000 | 0 | 28000 | 2 | 28000 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | S OH Site Staff | Approved | chetan.jewalikar
EAST POINT MARKET | 120 | 0 | 27 Jan 2022 | GANESH SINGH | KEP-4th Below Duct Skirting | Vitrified Skirting -Bco | R.Ft | 83.44 | 28 | 2336.32 | 0 | 2336.32 | 2.5 | 83.44 | 2336.32 | 0 | 2336.32 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 120 | 0 | 27 Jan 2022 | GANESH SINGH | KEP-4th Community Hall&Society Office Flooring | Vitrified Flooring -Bco | Sq.Ft | 2175.41 | 28 | 60911.48 | 0 | 60911.48 | 2.5 | 2175.41 | 60911.48 | 0 | 60911.48 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 120 | 0 | 27 Jan 2022 | GANESH SINGH | KEP-4th Below Duct Flooring | Vitrified Flooring -Bco | Sq.Ft | 106.99 | 28 | 2995.72 | 0 | 2995.72 | 2.5 | 106.99 | 2995.72 | 0 | 2995.72 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 120 | 0 | 27 Jan 2022 | GANESH SINGH | KEP-4th Passage Skirting | Vitrified Skirting -Bco | R.Ft | 374.7 | 28 | 10491.6 | 0 | 10491.6 | 2.5 | 374.7 | 10491.6 | 0 | 10491.6 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 120 | 0 | 27 Jan 2022 | GANESH SINGH | KEP-4th Community Hall&Society Office Skirting | Vitrified Skirting -Bco | R.Ft | 572.55 | 28 | 16031.4 | 0 | 16031.4 | 2.5 | 572.55 | 16031.4 | 0 | 16031.4 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 120 | 0 | 27 Jan 2022 | GANESH SINGH | KEP-4th Passage Flooring | Vitrified Flooring -Bco | Sq.Ft | 1106.75 | 28 | 30989 | 0 | 30989 | 2.5 | 1106.75 | 30989 | 0 | 30989 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | 2C 1.5 sqmm (FRLS) Cable (L) | Mtrs | 0 | 108 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 31 Jan 2022 |  | 04 ELECTRICAL WORK | Cancelled | skmishra | 31 Jan 2022
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (L) | No. | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New Pipe 25mm Rate Diff (L) | Mtrs | 3 | 40 | 120 | 21.6 | 141.6 | 2.5 | 3 | 120 | 21.6 | 141.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (L) | No. | 0 | 18.9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (L) | Mtrs | 0 | 121.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class old Pipe 25mm Re Installation Rate Diff | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Smoke Detector Removal Rate Diff.(L) | No. | 100 | 21 | 2100 | 378 | 2478 | 2.5 | 100 | 2100 | 378 | 2478 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | 2 Core1.5 Sqmm cable re install rate diff (L) | No. | 0 | 3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Smoke Detector Removal Rate Diff.(L) | No. | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (L) | No. | 0 | 16.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 50mm Reinstallation Rate Diff | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | 2 Core1.5 Sqmm cable re install rate diff (L) | No. | 1025 | 7 | 7175 | 1291.5 | 8466.5 | 2.5 | 1025 | 7175 | 1291.5 | 8466.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Old Smoke Detector Refixing Rate Diff.(L) | No. | 40 | 70 | 2800 | 504 | 3304 | 2.5 | 40 | 2800 | 504 | 3304 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 65mm Reinstallation Rate Diff | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 25mm removing Rate Diff | Mtrs | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New Pipe 25mm Rate Diff (L) | Mtrs | 0 | 40.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Water Curtain Nozzle (L) | No. | 50 | 195 | 9750 | 1755 | 11505 | 2.5 | 18 | 3510 | 631.8 | 4141.8 | 32 | 7363.2 |  | 36 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 65 mm removing Rate Diff | Mtrs | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Old Smoke Detector Refixing Rate Diff.(L) | No. | 31 | 70 | 2170 | 390.6 | 2560.6 | 2.5 | 31 | 2170 | 390.6 | 2560.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (L) | No. | 1 | 560 | 560 | 100.8 | 660.8 | 2.5 | 1 | 560 | 100.8 | 660.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (L) | No. | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Addressable Electric Smoke Detector (L) | No. | 0 | 2850 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 31 Jan 2022
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 100mm Installation Rate Diff (L) | Mtrs | 20 | 73.5 | 1470 | 264.6 | 1734.6 | 2.5 | 20 | 1470 | 264.6 | 1734.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 50mm Reinstallation Rate Diff | Mtrs | 9 | 70 | 630 | 113.4 | 743.4 | 2.5 | 9 | 630 | 113.4 | 743.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 50mm Installation Rate Diff (L) | Mtrs | 162 | 115.5 | 18711 | 3367.98 | 22078.98 | 2.5 | 162 | 18711 | 3367.98 | 22078.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Old Smoke Detector Refixing Rate Diff.(L) | No. | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Pendent Sprinkler (L) | No. | 0 | 67.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 31 Jan 2022
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 100mm-(L) | No. | 0 | 5700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 31 Jan 2022
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 100mm removing Rate Diff | Mtrs | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 100mm Reinstallation Rate Diff | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (L) | Mtrs | 13 | 126 | 1638 | 294.84 | 1932.84 | 0 | 13 | 1638 | 294.84 | 1932.84 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 50 mm | No. | 4 | 1350 | 5400 | 972 | 6372 | 2.5 | 4 | 5400 | 972 | 6372 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 80mm-(L) | No. | 3 | 1575 | 4725 | 850.5 | 5575.5 | 2.5 | 3 | 4725 | 850.5 | 5575.5 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Addressable Smoke detector fixing Rate diff (L) | No. | 10 | 108.5 | 1085 | 195.3 | 1280.3 | 2.5 | 10 | 1085 | 195.3 | 1280.3 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 25mm removing Rate Diff | Mtrs | 220 | 70 | 15400 | 2772 | 18172 | 0 | 220 | 15400 | 2772 | 18172 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | 2C 1.5 sqmm (FRLS) Cable (L) | Mtrs | 270 | 32.4 | 8748 | 1574.64 | 10322.64 | 2.5 | 0 | 0 | 0 | 0 | 270 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class old Pipe 25mm Re Installation Rate Diff | Mtrs | 200 | 343 | 68600 | 12348 | 80948 | 2.5 | 200 | 68600 | 12348 | 80948 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 25mm removing Rate Diff | Mtrs | 200.1 | 70 | 14007 | 2521.26 | 16528.26 | 0 | 200.1 | 14007 | 2521.26 | 16528.26 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | 2 Core1.5 Sqmm cable re install rate diff (L) | No. | 778 | 14 | 10892 | 1960.56 | 12852.56 | 2.5 | 778 | 10892 | 1960.56 | 12852.56 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 65 mm removing Rate Diff | Mtrs | 20 | 70 | 1400 | 252 | 1652 | 0 | 20 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 100mm-(L) | No. | 1 | 1710 | 1710 | 307.8 | 2017.8 | 2.5 | 1 | 1710 | 307.8 | 2017.8 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 100mm Butterfly Installation Rate Diff (L) | No. | 1 | 798 | 798 | 143.64 | 941.64 | 2.5 | 1 | 798 | 143.64 | 941.64 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Addressable Electric Smoke Detector (L) | No. | 25 | 855 | 21375 | 3847.5 | 25222.5 | 2.5 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 100mm Reinstallation Rate Diff | Mtrs | 50 | 70 | 3500 | 630 | 4130 | 2.5 | 50 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 100mm removing Rate Diff | Mtrs | 50 | 70 | 3500 | 630 | 4130 | 0 | 50 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Addressable Smoke detector fixing Rate diff (L) | No. | 6 | 139.3 | 835.8 | 150.44 | 986.24 | 2.5 | 6 | 835.8 | 150.44 | 986.24 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (L) | No. | 3 | 262.5 | 787.5 | 141.76 | 929.26 | 2.5 | 3 | 787.5 | 141.76 | 929.26 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | SITC GI Pipe C Class 50mm dia.(L) | Mtrs | 200 | 270 | 54000 | 9720 | 63720 | 2.5 | 162 | 43740 | 7873.2 | 51613.2 | 38 | 12106.8 |  | 81 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (L) | No. | 79 | 19.95 | 1576.05 | 283.68 | 1859.73 | 2.5 | 79 | 1576.05 | 283.68 | 1859.73 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class old Pipe 25mm Re Installation Rate Diff | Mtrs | 190.3 | 70 | 13321 | 2397.78 | 15718.78 | 2.5 | 190.3 | 13321 | 2397.78 | 15718.78 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Pendent Sprinkler (L) | No. | 120 | 67.5 | 8100 | 1458 | 9558 | 2.5 | 78.9996 | 5332.47 | 959.84 | 6292.31 | 41.0004 | 3265.69 |  | 65.833 |  | chetan.jewalikar | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Flexible Hose Pipe1500mm Rate diff (L) | Mtrs | 70 | 241.5 | 16905 | 3042.9 | 19947.9 | 2.5 | 70 | 16905 | 3042.9 | 19947.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | SITC GI Pipe C Class 80mm dia.(L) | Mtrs | 80 | 405 | 32400 | 5832 | 38232 | 2.5 | 80 | 32400 | 5832 | 38232 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (L) | No. | 50 | 18 | 900 | 162 | 1062 | 2.5 | 50 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New Pipe 25mm Rate Diff (L) | Mtrs | 36.5 | 59.5 | 2171.75 | 390.92 | 2562.67 | 2.5 | 36.5 | 2171.75 | 390.92 | 2562.67 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Addressable Smoke detector fixing Rate diff (L) | No. | 0 | 83.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (L) | Mtrs | 22.7 | 238.14 | 5405.78 | 973.04 | 6378.82 | 2.5 | 22.7 | 5405.78 | 973.04 | 6378.82 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | SITC GI C Class Pipe 100mm dia.(L) | Mtrs | 20 | 630 | 12600 | 2268 | 14868 | 2.5 | 20 | 12600 | 2268 | 14868 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (L) | No. | 2 | 665 | 1330 | 239.4 | 1569.4 | 2.5 | 2 | 1330 | 239.4 | 1569.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (L) | Mtrs | 79.9 | 126 | 10067.4 | 1812.14 | 11879.54 | 2.5 | 79.9 | 10067.4 | 1812.14 | 11879.54 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 100mm Butterfly Installation Rate Diff (L) | No. | 0 | 855 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 121 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class Old pipe 65mm Reinstallation Rate Diff | Mtrs | 15.8 | 70 | 1106 | 199.08 | 1305.08 | 2.5 | 15.8 | 1106 | 199.08 | 1305.08 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Addressable Electric Smoke Detector (M) | No. | 25 | 1955 | 48875 | 8797.5 | 57672.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Flexible Hose Pipe1500mm Rate diff (M) | Mtrs | 70 | 140 | 9800 | 1764 | 11564 | 0 | 70 | 9800 | 1764 | 11564 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New Pipe 25mm Rate Diff (M) | Mtrs | 3 | 98 | 294 | 52.92 | 346.92 | 0 | 3 | 294 | 52.92 | 346.92 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (M) | No. | 79 | 46.55 | 3677.45 | 661.94 | 4339.39 | 0 | 79 | 3677.45 | 661.94 | 4339.39 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (M) | Mtrs | 79.9 | 294 | 23490.6 | 4228.3 | 27718.9 | 0 | 79.9 | 23490.6 | 4228.3 | 27718.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | SITC GI C Class Pipe 100mm dia.(M) | Mtrs | 20 | 1470 | 29400 | 5292 | 34692 | 0 | 20 | 29400 | 5292 | 34692 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 270 | 75.6 | 20412 | 3674.16 | 24086.16 | 0 | 0 | 0 | 0 | 0 | 270 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Water Curtain Nozzle (M) | No. | 50 | 455 | 22750 | 4095 | 26845 | 0 | 18 | 8190 | 1474.2 | 9664.2 | 32 | 17180.8 |  | 36 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Butterfly Valve 65mm (M) (Rate diff.) | No. | 2 | 700 | 1400 | 252 | 1652 | 0 | 2 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (M) | No. | 0 | 37.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 100mm-(M) | No. | 1 | 3990 | 3990 | 718.2 | 4708.2 | 0 | 1 | 3990 | 718.2 | 4708.2 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Pendent Sprinkler (M) | No. | 120 | 157.5 | 18900 | 3402 | 22302 | 0 | 78.9996 | 12442.44 | 2239.64 | 14682.08 | 41.0004 | 7619.92 |  | 65.833 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 100mm Butterfly Installation Rate Diff (M) | No. | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | SITC GI Pipe C Class 80mm dia.(M) | Mtrs | 80 | 945 | 75600 | 13608 | 89208 | 0 | 80 | 75600 | 13608 | 89208 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 50mm Installation Rate Diff (M) | Mtrs | 162 | 269.5 | 43659 | 7858.62 | 51517.62 | 0 | 162 | 43659 | 7858.62 | 51517.62 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Addressable smoke detector (M) (Rate Diff.) - No. | No. | 6 | 49.7 | 298.2 | 53.68 | 351.88 | 0 | 6 | 298.2 | 53.68 | 351.88 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 100mm Butterfly Installation Rate Diff (M) | No. | 1 | 1862 | 1862 | 335.16 | 2197.16 | 0 | 1 | 1862 | 335.16 | 2197.16 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 100mm Installation Rate Diff (M) | Mtrs | 20 | 171.5 | 3430 | 617.4 | 4047.4 | 0 | 20 | 3430 | 617.4 | 4047.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | SITC GI Pipe C Class 50mm dia.(M) | Mtrs | 200 | 630 | 126000 | 22680 | 148680 | 0 | 162 | 102060 | 18370.8 | 120430.8 | 38 | 28249.2 |  | 81 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 80mm-(M) | No. | 3 | 3675 | 11025 | 1984.5 | 13009.5 | 0 | 3 | 11025 | 1984.5 | 13009.5 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 4th Fl-Community Hall,Society Office Fire Fighting Work | Butterfly Valve 50 mm (M) | No. | 4 | 3150 | 12600 | 2268 | 14868 | 0 | 4 | 12600 | 2268 | 14868 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 31 Jan 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (M) | No. | 0 | 44.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (M) | Mtrs | 13 | 294 | 3822 | 687.96 | 4509.96 | 0 | 13 | 3822 | 687.96 | 4509.96 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (M) | No. | 3 | 612.5 | 1837.5 | 330.76 | 2168.26 | 0 | 3 | 1837.5 | 330.76 | 2168.26 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Addressable Smoke Detector Fixing New (M) | No. | 10 | 374.5 | 3745 | 674.1 | 4419.1 | 0 | 10 | 3745 | 674.1 | 4419.1 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (M) | No. | 2 | 385 | 770 | 138.6 | 908.6 | 0 | 2 | 770 | 138.6 | 908.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (M) | Mtrs | 0 | 283.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI 80mm Butterfly Installation Rate Diff (M) | No. | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New Pipe 25mm Rate Diff (M) | Mtrs | 0 | 94.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New Pipe 25mm Rate Diff (M) | Mtrs | 103.5 | 52.5 | 5433.75 | 978.08 | 6411.83 | 0 | 103.5 | 5433.75 | 978.08 | 6411.83 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | GI C Class New pipe 80mm Installation Rate Diff (M) | Mtrs | 22.7 | 270.2 | 6133.54 | 1104.04 | 7237.58 | 0 | 22.7 | 6133.54 | 1104.04 | 7237.58 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Pendent Sprinkler Rate Diff. (M) | No. | 50 | 42.14 | 2107 | 379.26 | 2486.26 | 0 | 50 | 2107 | 379.26 | 2486.26 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jan 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 122 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-4th floor Fire Fighting Work Rate Difference | Addressable Smoke Detector Fixing New (M) | No. | 0 | 321.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jan 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Fire Alarm Panel | No. | 1 | 100000 | 100000 | 18000 | 118000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Hooter (L) | No. | 4 | 300 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Monitor module device (L) | No. | 20 | 400 | 8000 | 1440 | 9440 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Smoke Detector Refixing | No. | 100 | 100 | 10000 | 1800 | 11800 | 2.5 | 31 | 3100 | 558 | 3658 | 69 | 8142 |  | 31 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Telephone Jack/Receiver (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 1500 | 35 | 52500 | 9450 | 61950 | 2.5 | 499.995 | 17499.83 | 3149.96 | 20649.79 | 1000.005 | 41300.22 |  | 33.333 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jewalikar |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 31 Jan 2022
EAST POINT MARKET | 123 | 1 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | Ground Floor Dismentalling work at Railway Side | Labour Lumpsum | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 | G.I 6" Pipe & G.I 6" Bend (M+L) | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Addressable smoke detector (M) | No. | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jewalikar |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Cancelled | skmishra | 31 Jan 2022
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Smoke Detector removal | No. | 100 | 70 | 7000 | 1260 | 8260 | 2.5 | 100 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm cable for PA System (L) | Mtrs | 500 | 30 | 15000 | 2700 | 17700 | 2.5 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Addressable smoke detector (L) | No. | 10 | 560 | 5600 | 1008 | 6608 | 2.5 | 10 | 5600 | 1008 | 6608 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Response Indicator (L) | No. | 30 | 220 | 6600 | 1188 | 7788 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Fire Alarm Programme | No. | 1 | 20000 | 20000 | 3600 | 23600 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm cable reinstall | Mtrs | 1500 | 60 | 90000 | 16200 | 106200 | 2.5 | 1024.95 | 61497 | 11069.46 | 72566.46 | 475.05 | 33633.54 |  | 68.33 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm cable removal | Mtrs | 1500 | 30 | 45000 | 8100 | 53100 | 2.5 | 1500 | 45000 | 8100 | 53100 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 123 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Addressable integration system | No. | 1 | 235000 | 235000 | 42300 | 277300 | 2.5 | 0.8511 | 200008.5 | 36001.54 | 236010.04 | 0.1489 | 41289.96 |  | 85.11 |  | chetan.jewalikar | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Manual Cell Point (M) | No. | 4 | 2250 | 9000 | 1620 | 10620 | 0 | 2 | 4500 | 810 | 5310 | 2 | 5310 |  | 50 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Monitor module device (M) | No. | 20 | 2850 | 57000 | 10260 | 67260 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm cable for PA System (M) | Mtrs | 500 | 90 | 45000 | 8100 | 53100 | 0 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Addressable smoke detector (M) | No. | 10 | 1600 | 16000 | 2880 | 18880 | 0 | 10 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Telephone Jack/Receiver (M) | No. | 2 | 4200 | 8400 | 1512 | 9912 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 1500 | 100 | 150000 | 27000 | 177000 | 0 | 499.995 | 49999.5 | 8999.92 | 58999.42 | 1000.005 | 118000.58 |  | 33.333 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Manual Cell Point (L) | No. | 4 | 300 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 124 | 0 | 31 Jan 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP- 1st,2nd,3rd Fl Fire &PA System Reshuffle | Hooter (M) | No. | 4 | 3200 | 12800 | 2304 | 15104 | 0 | 2 | 6400 | 1152 | 7552 | 2 | 7552 |  | 50 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | SITC GI Pipe C Class 25mm dia-(L) | Mtrs | 250 | 110 | 27500 | 4950 | 32450 | 2.5 | 36.5 | 4015 | 722.7 | 4737.7 | 213.5 | 27712.3 |  | 14.6 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | SITC GI Pipe C Class 32mm dia.(L) | Mtrs | 10 | 165 | 1650 | 297 | 1947 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Removing GI C Class Old Pipe | Mtrs | 220 | 200 | 44000 | 7920 | 51920 | 0 | 220 | 44000 | 7920 | 51920 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Reinstall of GI C Class Pipe | Mtrs | 50 | 500 | 25000 | 4500 | 29500 | 2.5 | 50 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Pendent Sprinkler (L) | No. | 234 | 64 | 14976 | 2695.68 | 17671.68 | 2.5 | 21 | 1344 | 241.92 | 1585.92 | 213 | 16085.76 |  | 8.9744 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Pendent Sprinkler (L) | No. | 0 | 64 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 11 Nov 2022
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | 25mm Barallel Nipple & Union (L) | No. | 10 | 90 | 900 | 162 | 1062 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | GI Pipe C Class 100 NB-(L) | Mtrs | 5 | 384 | 1920 | 345.6 | 2265.6 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 80 NB-(L) | Mtrs | 50 | 405 | 20250 | 3645 | 23895 | 2.5 | 13 | 5265 | 947.7 | 6212.7 | 37 | 17682.3 |  | 26 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Reinstall of GI C Class Pipe | Mtrs | 460 | 110 | 50600 | 9108 | 59708 | 2.5 | 200.1 | 22011 | 3961.98 | 25972.98 | 259.9 | 33735.02 |  | 43.5 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Ball Valve 32mm (L) | No. | 3 | 330 | 990 | 178.2 | 1168.2 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC Ball Valve 25mm (L) | No. | 48 | 330 | 15840 | 2851.2 | 18691.2 | 2.5 | 36.9997 | 12209.9 | 2197.78 | 14407.68 | 11.0003 | 4283.52 |  | 77.0827 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 25 NB-(L) | Mtrs | 0 | 110 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 11 Nov 2022
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Reinstall of GI C Class Pipe | Mtrs | 220 | 500 | 110000 | 19800 | 129800 | 2.5 | 190.1988 | 95099.4 | 17117.9 | 112217.3 | 29.8012 | 17582.7 |  | 86.454 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | 2 core x 1.5 sqmm cable removal | Mtrs | 800 | 20 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 800 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Addressable smoke detector (L) | No. | 18 | 560 | 10080 | 1814.4 | 11894.4 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 25 NB-(L) | Mtrs | 20 | 110 | 2200 | 396 | 2596 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | SITC Ball Valve 25mm (L) | No. | 95 | 330 | 31350 | 5643 | 36993 | 2.5 | 63 | 20790 | 3742.2 | 24532.2 | 32 | 12460.8 |  | 66.3158 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Removing GI C Class Old Pipe | Mtrs | 20 | 200 | 4000 | 720 | 4720 | 0 | 20 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | 32mm Barallel Nipple & Union (L) | No. | 3 | 90 | 270 | 48.6 | 318.6 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC Ball Valve 25mm (L) | No. | 10 | 330 | 3300 | 594 | 3894 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | 32mm Barallel Nipple & Union (L) | No. | 3 | 90 | 270 | 48.6 | 318.6 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Pendent Sprinkler (L) | No. | 70 | 64 | 4480 | 806.4 | 5286.4 | 2.5 | 63 | 4032 | 725.76 | 4757.76 | 7 | 528.64 |  | 90 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Pendent Sprinkler (L) | No. | 50 | 70.2 | 3510 | 631.8 | 4141.8 | 2.5 | 50 | 3510 | 631.8 | 4141.8 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | 25mm Barallel Nipple & Union (L) | No. | 95 | 90 | 8550 | 1539 | 10089 | 2.5 | 63 | 5670 | 1020.6 | 6690.6 | 32 | 3398.4 |  | 66.3158 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Reinstall of GI C Class Pipe | Mtrs | 20 | 500 | 10000 | 1800 | 11800 | 2.5 | 15.8 | 7900 | 1422 | 9322 | 4.2 | 2478 |  | 79 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | 2C 1.5 sqmm (FRLS) Cable (L) | Mtrs | 2359 | 32.4 | 76431.6 | 13757.68 | 90189.28 | 2.5 | 363.9998 | 11793.59 | 2122.84 | 13916.43 | 1995.0002 | 76272.85 |  | 15.4303 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Ball Valve 32mm (L) | No. | 3 | 330 | 990 | 178.2 | 1168.2 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Flexible Hose Pipe 1500 mm with Bushing (L) | No. | 100 | 225 | 22500 | 4050 | 26550 | 2.5 | 70 | 15750 | 2835 | 18585 | 30 | 7965 |  | 70 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Smoke Detector Refixing | No. | 100 | 100 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Smoke Detector Refixing | No. | 100 | 100 | 10000 | 1800 | 11800 | 2.5 | 40 | 4000 | 720 | 4720 | 60 | 7080 |  | 40 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | 2C 1.5 sqmm (FRLS) Cable (L) | Mtrs | 450 | 32.4 | 14580 | 2624.4 | 17204.4 | 2.5 | 300 | 9720 | 1749.6 | 11469.6 | 150 | 5734.8 |  | 66.6667 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Dismentaling of GI C Class Pipe | Mtrs | 40 | 200 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 25 NB-(L) | Mtrs | 100 | 135 | 13500 | 2430 | 15930 | 2.5 | 3 | 405 | 72.9 | 477.9 | 97 | 15452.1 |  | 3 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | 2 core x 1.5 sqmm cable reinstall | Mtrs | 800 | 50 | 40000 | 7200 | 47200 | 2.5 | 778 | 38900 | 7002 | 45902 | 22 | 1298 |  | 97.25 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Removing GI C Class Old Pipe | Mtrs | 460 | 200 | 92000 | 16560 | 108560 | 0 | 200.1 | 40020 | 7203.6 | 47223.6 | 259.9 | 61336.4 |  | 43.5 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | 25mm Barallel Nipple & Union (L) | No. | 48 | 90 | 4320 | 777.6 | 5097.6 | 2.5 | 34.9997 | 3149.97 | 567 | 3716.97 | 13.0003 | 1380.63 |  | 72.916 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC GI Pipe C Class 32mm dia.(L) | Mtrs | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 11 Nov 2022
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Removing GI C Class Old Pipe | Mtrs | 50 | 200 | 10000 | 1800 | 11800 | 2.5 | 50 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC GI Pipe C Class 40mm dia.(L) | Mtrs | 40 | 200 | 8000 | 1440 | 9440 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP - 2nd Floor Fire Fighting work | Addressable smoke detector (L) | No. | 132 | 560 | 73920 | 13305.6 | 87225.6 | 2.5 | 0 | 0 | 0 | 0 | 132 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Reinstall of GI C Class Pipe | Mtrs | 20 | 500 | 10000 | 1800 | 11800 | 2.5 | 9 | 4500 | 810 | 5310 | 11 | 6490 |  | 45 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Removing GI C Class Old Pipe | Mtrs | 20 | 200 | 4000 | 720 | 4720 | 2.5 | 20 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 125 | 1 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Butterfly Valve 100mm-(L) | No. | 1 | 1710 | 1710 | 307.8 | 2017.8 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | 25mm Barallel Nipple & Union (M) | No. | 48 | 210 | 10080 | 1814.4 | 11894.4 | 0 | 35 | 7350 | 1323 | 8673 | 13 | 3221.4 |  | 72.9167 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | Pendent Sprinkler (M) | No. | 50 | 163.8 | 8190 | 1474.2 | 9664.2 | 0 | 50 | 8190 | 1474.2 | 9664.2 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | CI Butterfly Valve | No. | 3 | 4500 | 13500 | 2430 | 15930 | 0 | 2 | 9000 | 1620 | 10620 | 1 | 5310 |  | 66.6667 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | CI Butterfly Valve | No. | 1 | 5700 | 5700 | 1026 | 6726 | 0 | 1 | 5700 | 1026 | 6726 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 25 NB-(M) | Mtrs | 100 | 315 | 31500 | 5670 | 37170 | 0 | 3 | 945 | 170.1 | 1115.1 | 97 | 36054.9 |  | 3 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC Ball Valve 25mm (M) | No. | 48 | 770 | 36960 | 6652.8 | 43612.8 | 0 | 37 | 28490 | 5128.2 | 33618.2 | 11 | 9994.6 |  | 77.0833 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 126 | 0 | 01 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 80 NB-(M) | Mtrs | 50 | 945 | 47250 | 8505 | 55755 | 0 | 13 | 12285 | 2211.3 | 14496.3 | 37 | 41258.7 |  | 26 |  | chetan.jewalikar | chetan.jewalikar | construction open | 03 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 127 | 0 | 02 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Anchor Bolt-MWB | No. | 40 | 40 | 1600 | 288 | 1888 | 2.5 | 40 | 1600 | 288 | 1888 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 02 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 127 | 0 | 02 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Motor fitting- UDR | No. | 1 | 30000 | 30000 | 5400 | 35400 | 2.5 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 02 Feb 2022 |  | UTI. Drainage | Approved | chetan.jewalikar
EAST POINT MARKET | 127 | 0 | 02 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Rolling Shutter (L) | Sq.Ft | 680 | 90 | 61200 | 11016 | 72216 | 2.5 | 680 | 61200 | 11016 | 72216 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 02 Feb 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 128 | 0 | 02 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Anchor Bolt (M) | No. | 40 | 120 | 4800 | 864 | 5664 | 0 | 40 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 128 | 0 | 02 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Rolling Shutter Motor(M) - No. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 128 | 0 | 02 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Main entrance below canopy Rolling shutter work | Rolling Shutter (M) | Sq.Ft | 680 | 210 | 142800 | 25704 | 168504 | 0 | 680 | 142800 | 25704 | 168504 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 129 | 0 | 08 Feb 2022 | GANESH SINGH | KEP- Misc work/Repair Work | Department Labour- BC | No. | 50 | 2200 | 110000 | 0 | 110000 | 2.5 | 50 | 110000 | 0 | 110000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 130 | 0 | 08 Feb 2022 | R.F. CONSULTANTS | Consultancy 6th Slab RCC Dwgs&MS Dwgs ,Visit Charges | Consultancy Charges | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 08 Feb 2022 |  | Consultacy Architectural | Approved | chetan.jewalikar
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 0 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 0 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 0 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 0 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA CHOUGULE | 08 Feb 2022
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 2 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE |  | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 20 Sep 2023
EAST POINT MARKET | 131 | 1 | 08 Feb 2022 | HICARE SERVICES PRIVATE LIMITED | Pest Control | Pest Control | Month | 1 | 12500 | 12500 | 2250 | 14750 | 0 | 1 | 12500 | 2250 | 14750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 132 | 1 | 12 Feb 2022 | S N RAUT CONSULTANTS | Consultancy HVAC Consultancy | HVAC Consultancy. | No. | 1 | 27750 | 27750 | 4995 | 32745 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Prev. WO no- 224.0 & 224.1 (East point Kurla) Billing Done- 157250 Rs/- Remaining WO.- 27750 Rs/- | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Feb 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 132 | 0 | 12 Feb 2022 | S N RAUT CONSULTANTS | Consultancy HVAC Consultancy | HVAC Consultancy. | No. | 1 | 120000 | 120000 | 21600 | 141600 | 0 | 0.55 | 66000 | 11880 | 77880 | 0.45 | 63720 |  | 55 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar
EAST POINT MARKET | 133 | 4 | 14 Feb 2022 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Eco Vinyal With Foam Sheet | Sq.Ft | 560 | 100 | 56000 | 10080 | 66080 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | ECO VINYAL WITH 5 MM FOAM SHEET FOR SITE SALES PROMOTION WITH BRANDING | 0 |  | Tejas Raverkar |  | construction open |  |  | MKT. Media | Un-Approved
EAST POINT MARKET | 133 | 3 | 14 Feb 2022 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | ACRYLIC LETTER WORK | No. | 1 | 175000 | 175000 | 31500 | 206500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ACRYLIC LETTER FOR BRANDING AT SITE QTY. 1 | 0 |  | Tejas Raverkar |  | construction open |  |  | MKT. Media | Un-Approved
EAST POINT MARKET | 133 | 2 | 14 Feb 2022 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Black Back Flex | Sq.Ft | 2082 | 25 | 52050 | 9369 | 61419 | 0 | 0 | 0 | 0 | 0 | 2082 | 0 | STAR BLACK BACK FLEX PRINT WITH PAST ON MS FRAME AT SITE FOR SALES PROMOTION WITH BRANDING | 0 |  | Tejas Raverkar |  | construction open |  |  | MKT. Media | Un-Approved
EAST POINT MARKET | 133 | 1 | 14 Feb 2022 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Star Flex | Sq.Ft | 3026 | 25 | 75650 | 13617 | 89267 | 0 | 0 | 0 | 0 | 0 | 3026 | 0 | STAR FLEX PRINT WITH PAST ON MS FRAME AT EAST POINT MARKET SITE - SALES PROMOTION WITH BRANDING SIZE AS 27X10, 16X8 QTY.2, 15X50 QTY 2 AND EXTRA WORK 1000 SQ FT. | 0 |  | Tejas Raverkar |  | construction open |  |  | MKT. Media | Un-Approved
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 2C 1.5 sqmm (FRLS) Cable (L) | Mtrs | 200 | 21.6 | 4320 | 777.6 | 5097.6 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Air Release Valve (L) | No. | 2 | 290 | 580 | 104.4 | 684.4 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 3C 2.5 sqmm Cu Cable (L) | Mtrs | 100 | 62 | 6200 | 1116 | 7316 | 2.5 | 100 | 6200 | 1116 | 7316 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Butterfly Valve 80mm-(L) | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 2 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | SITC Pressure Gauge (L) | set | 2 | 330 | 660 | 118.8 | 778.8 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 3C 1.5 Sqmm Copper Armoured Cable (L) | Mtrs | 100 | 56 | 5600 | 1008 | 6608 | 2.5 | 100 | 5600 | 1008 | 6608 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | GI Pipe C Class 80 NB-(L) | Mtrs | 24.5 | 244.8 | 5997.6 | 1079.56 | 7077.16 | 2.5 | 22.7 | 5556.96 | 1000.26 | 6557.22 | 1.8 | 519.94 |  | 92.6531 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Addressable Electric Smoke Detector (L) | No. | 0 | 516 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 18 Feb 2022
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Push Button (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 10HP Booster Pump (L) | No. | 0.08 | 13000 | 1040 | 187.2 | 1227.2 | 2.5 | 0 | 0 | 0 | 0 | 0.08 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Manual Pull Station (L) | No. | 2 | 696 | 1392 | 250.56 | 1642.56 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Addressable Electric Smoke Detector (L) | No. | 20 | 516 | 10320 | 1857.6 | 12177.6 | 2.5 | 6 | 3096 | 557.28 | 3653.28 | 14 | 8524.32 |  | 30 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | NRV 80mm Dia. (L) | No. | 2 | 1100 | 2200 | 396 | 2596 | 2.5 | 2 | 2200 | 396 | 2596 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Pendent Sprinkler (L) | No. | 7 | 64 | 448 | 80.64 | 528.64 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | GI Pipe C Class 100 NB-(L) | Mtrs | 29.4 | 384 | 11289.6 | 2032.12 | 13321.72 | 2.5 | 0 | 0 | 0 | 0 | 29.4 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 134 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 6C 1.5sqmm Cable (L) | Mtrs | 50 | 62 | 3100 | 558 | 3658 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open |  |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | Addressable Relay Module (M+L) | No. | 4 | 5000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 6C 1.5sqmm Cable (M) | Mtrs | 50 | 248 | 12400 | 2232 | 14632 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 2359 | 75.6 | 178340.4 | 32101.28 | 210441.68 | 0 | 1367.9999 | 103420.79 | 18615.74 | 122036.53 | 991.0001 | 88405.15 |  | 57.9907 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | Pendent Sprinkler (M) | No. | 70 | 256 | 17920 | 3225.6 | 21145.6 | 0 | 63 | 16128 | 2903.04 | 19031.04 | 7 | 2114.56 |  | 90 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | GI Pipe C Class 25 NB-(M) | Mtrs | 20 | 380 | 7600 | 1368 | 8968 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | Flexible Hose Pipe 1500 mm with Bushing (M) | No. | 100 | 1130 | 113000 | 20340 | 133340 | 0 | 70 | 79100 | 14238 | 93338 | 30 | 40002 |  | 70 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Addressable Electric Smoke Detector (M) | No. | 20 | 2064 | 41280 | 7430.4 | 48710.4 | 0 | 6 | 12384 | 2229.12 | 14613.12 | 14 | 34097.28 |  | 30 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | SITC GI Pipe C Class 32mm dia.(M) | Mtrs | 10 | 480 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC Ball Valve 25mm (M) | No. | 10 | 770 | 7700 | 1386 | 9086 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | GI Pipe C Class 100 NB-(M) | Mtrs | 29.4 | 1536 | 45158.4 | 8128.52 | 53286.92 | 0 | 0 | 0 | 0 | 0 | 29.4 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 3C 2.5 sqmm Cu Cable (M) | Mtrs | 100 | 248 | 24800 | 4464 | 29264 | 0 | 100 | 24800 | 4464 | 29264 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | Addressable smoke detector (M) | No. | 132 | 1600 | 211200 | 38016 | 249216 | 0 | 50 | 80000 | 14400 | 94400 | 82 | 154816 |  | 37.8788 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Push Button (M) | No. | 2 | 2000 | 4000 | 720 | 4720 | 0 | 2 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | GI Pipe C Class 80 NB-(M) | Mtrs | 24.5 | 979.2 | 23990.4 | 4318.28 | 28308.68 | 0 | 22.7 | 22227.84 | 4001.02 | 26228.86 | 1.8 | 2079.82 |  | 92.6531 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | Pendent Sprinkler (M) | No. | 234 | 256 | 59904 | 10782.72 | 70686.72 | 0 | 40.9999 | 10495.97 | 1889.28 | 12385.25 | 193.0001 | 58301.47 |  | 17.5213 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | Addressable smoke detector (M) | No. | 18 | 1600 | 28800 | 5184 | 33984 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 200 | 86.4 | 17280 | 3110.4 | 20390.4 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | 3C 1.5 Sqmm Copper Armoured Cable (M) | Mtrs | 100 | 224 | 22400 | 4032 | 26432 | 0 | 100 | 22400 | 4032 | 26432 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | SITC GI Pipe C Class 25mm dia.(M) | Mtrs | 250 | 380 | 95000 | 17100 | 112100 | 0 | 103.5 | 39330 | 7079.4 | 46409.4 | 146.5 | 65690.6 |  | 41.4 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | 32mm Barallel Nipple & Union (M) | No. | 3 | 210 | 630 | 113.4 | 743.4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Butterfly Valve 80mm-(M) | No. | 2 | 4000 | 8000 | 1440 | 9440 | 0 | 2 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | GI Pipe C Class 100 NB-(M) | Mtrs | 5 | 1536 | 7680 | 1382.4 | 9062.4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | SITC Ball Valve 25mm (M) | No. | 95 | 770 | 73150 | 13167 | 86317 | 0 | 95 | 73150 | 13167 | 86317 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Pendent Sprinkler (M) | No. | 7 | 256 | 1792 | 322.56 | 2114.56 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Butterfly Valve 100mm-(M) | No. | 1 | 3990 | 3990 | 718.2 | 4708.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Manual Pull Station (M) | No. | 2 | 2784 | 5568 | 1002.24 | 6570.24 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | SITC Pressure Gauge (M) | set | 2 | 1320 | 2640 | 475.2 | 3115.2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work Ground Floor FF work | Addressable Relay Module (M+L) | No. | 6 | 5000 | 30000 | 5400 | 35400 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | SITC GI Pipe C Class 40mm dia.(M) | Mtrs | 40 | 550 | 22000 | 3960 | 25960 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | NRV 80mm Dia. (M) - | No. | 2 | 4400 | 8800 | 1584 | 10384 | 2.5 | 2 | 8800 | 1584 | 10384 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | 32mm Barallel Nipple & Union (M) | No. | 3 | 210 | 630 | 113.4 | 743.4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | Ball Valve 32mm (M) | No. | 3 | 770 | 2310 | 415.8 | 2725.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 450 | 75.6 | 34020 | 6123.6 | 40143.6 | 0 | 300 | 22680 | 4082.4 | 26762.4 | 150 | 13381.2 |  | 66.6667 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | Ball Valve 32mm (M) | No. | 3 | 770 | 2310 | 415.8 | 2725.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-3rd Floor fire fighting,sprinkler system- rework | 25mm Barallel Nipple & Union (M) | No. | 10 | 210 | 2100 | 378 | 2478 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 135 | 0 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP-Fire Fighting Work 4th FL- Fire Fighting work (Market) | Air Release Valve (M) | No. | 2 | 1160 | 2320 | 417.6 | 2737.6 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar
EAST POINT MARKET | 135 | 1 | 18 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP - 2nd Floor Fire Fighting work | 25mm Barallel Nipple & Union (M) | No. | 95 | 210 | 19950 | 3591 | 23541 | 0 | 95 | 19950 | 3591 | 23541 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 136 | 3 | 21 Feb 2022 | MILLENNIUM ARTS | Media BRANDING | T SHIRT / BAGS / PENS / DRESS - BRANDING | No. | 500 | 48 | 24000 | 4320 | 28320 | 0 | 500 | 24000 | 4320 | 28320 | 0 | 0 | EAST POINT MARKET PAPER BAG PRINT QTY. 500 @ 48/- | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 22 Feb 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 136 | 1 | 21 Feb 2022 | MILLENNIUM ARTS | Media BRANDING | Booklet / Notepad / Diary / Pocket Print | No. | 500 | 85 | 42500 | 7650 | 50150 | 0 | 500 | 42500 | 7650 | 50150 | 0 | 0 | EAST POINT MARKET PROJECT BROCHURE 4 COLOUR 32 PAGES WITH 2 COVER QTY. 500 @ 85/- | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 22 Feb 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 136 | 2 | 21 Feb 2022 | MILLENNIUM ARTS | Media BRANDING | Booklet / Notepad / Diary / Pocket Print | No. | 25 | 1150 | 28750 | 5175 | 33925 | 0 | 25 | 28750 | 5175 | 33925 | 0 | 0 | EAST POINT MARKET PROJECT BROCHURE 4 COLOUR 32 PAGES WITH GALLYQTY 25 @ 1125/- | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 22 Feb 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 136 | 5 | 21 Feb 2022 | MILLENNIUM ARTS | Media BRANDING | PRINTING | No. | 1000 | 32 | 32000 | 5760 | 37760 | 0 | 1000 | 32000 | 5760 | 37760 | 0 | 0 | EAST POINT MARKET FLOOR PLAN PRINT QTY 1000 SIZE AS A-3 F/B COLOUR @32/- | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 22 Feb 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 136 | 0 | 21 Feb 2022 | MILLENNIUM ARTS | Media BRANDING | Booklet / Notepad / Diary / Pocket Print | No. | 1000 | 15 | 15000 | 2700 | 17700 | 0 | 1000 | 15000 | 2700 | 17700 | 0 | 0 | EAST POINT MARKET PROJECT BROCHURE 4 PAGER COLOUR PTINT QTY. 1000 | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 22 Feb 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 136 | 4 | 21 Feb 2022 | MILLENNIUM ARTS | Media BRANDING | FOAM SHEET | Sq.Ft | 50 | 325 | 16250 | 2925 | 19175 | 0 | 50 | 16250 | 2925 | 19175 | 0 | 0 | EAST POINT MARKET SALES PROMOTION ON FOAM SHEET BOARD SIZE AS A-3 F/B QTY. 50 @ 325/- EACH BOARD | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 22 Feb 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 137 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Scaffolding Work (M+L) | Sq.Ft | 5707.66 | 5 | 28538.3 | 0 | 28538.3 | 2.5 | 5707.66 | 28538.3 | 0 | 28538.3 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 22 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 137 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Crack Filling (L) | Sq.Ft | 5707.66 | 2 | 11415.32 | 0 | 11415.32 | 2.5 | 5707.66 | 11415.32 | 0 | 11415.32 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 22 Feb 2022 |  | 12 MASONARY WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 137 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | 1 Coat Primer (External) (L) - | Sq.Ft | 5707.66 | 1.5 | 8561.49 | 0 | 8561.49 | 2.5 | 5707.66 | 8561.49 | 0 | 8561.49 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 22 Feb 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 137 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Damp Proof Course (L) | Sq.Ft | 5707.66 | 1.5 | 8561.49 | 0 | 8561.49 | 2.5 | 5707.66 | 8561.49 | 0 | 8561.49 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 22 Feb 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 137 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Apex Paint -1st Coat (L) | Sq.Ft | 5707.66 | 2 | 11415.32 | 0 | 11415.32 | 2.5 | 5707.66 | 11415.32 | 0 | 11415.32 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 22 Feb 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 137 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Apex Paint -2nd Coat (L) | Sq.Ft | 5707.66 | 2 | 11415.32 | 0 | 11415.32 | 2.5 | 5707.66 | 11415.32 | 0 | 11415.32 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 22 Feb 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 138 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Apex Paint -1st Coat (M) | Sq.Ft | 5707.66 | 4 | 22830.64 | 0 | 22830.64 | 0 | 5707.66 | 22830.64 | 0 | 22830.64 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 138 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | 1 Coat Primer (External) (M) | Sq.Ft | 5707.66 | 1 | 5707.66 | 0 | 5707.66 | 0 | 5707.66 | 5707.66 | 0 | 5707.66 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 138 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Crack Filling (M) | Sq.Ft | 5707.66 | 1 | 5707.66 | 0 | 5707.66 | 0 | 5707.66 | 5707.66 | 0 | 5707.66 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | 12 MASONARY WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 138 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Apex Paint -2nd Coat (M) | Sq.Ft | 5707.66 | 4 | 22830.64 | 0 | 22830.64 | 0 | 5707.66 | 22830.64 | 0 | 22830.64 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 138 | 0 | 22 Feb 2022 | AZAM KHAN | KEP- External Painting Work(Apex Paint) | Damp Proof Course (M) | Sq.Ft | 5707.66 | 1 | 5707.66 | 0 | 5707.66 | 0 | 5707.66 | 5707.66 | 0 | 5707.66 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 139 | 0 | 23 Feb 2022 | AZAM KHAN | Basement Fl -Painting Work - 1 No. | Oil Paint (m+l) - DCW | Sq.Ft | 569.45 | 17 | 9680.65 | 0 | 9680.65 | 2.5 | 569.45 | 9680.65 | 0 | 9680.65 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 139 | 0 | 23 Feb 2022 | AZAM KHAN | Basement Fl -Painting Work - 1 No. | Painter - SM | No. | 100 | 850 | 85000 | 0 | 85000 | 2.5 | 100 | 85000 | 0 | 85000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar
EAST POINT MARKET | 140 | 0 | 26 Feb 2022 | M/S ABHINAV SINGH | Entrance Plaza Ent Plaza -Civil Work | Department Labour- BC | Pair | 12.864 | 2200 | 28300.8 | 5094.14 | 33394.94 | 2.5 | 12 | 26400 | 0 | 26400 | 0.864 | 6994.94 |  | 93.2836 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar
EAST POINT MARKET | 141 | 0 | 26 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-4th Fl Atrium Lobby False Ceiling M.S. Support | Fabrication Work (M) | Kgs | 3080 | 84 | 258720 | 46569.6 | 305289.6 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 142 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting System (m+l) | No. | 1 | 33000 | 33000 | 5940 | 38940 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
EAST POINT MARKET | 142 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting System (m+l) | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
EAST POINT MARKET | 142 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting System (m+l) | No. | 1 | 60000 | 60000 | 10800 | 70800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
EAST POINT MARKET | 143 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | Mall-Utilies & PA System Fire Fighting Work | Mountable Music Source (M) | No. | 1 | 6000 | 6000 | 1080 | 7080 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 143 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | Mall-Utilies & PA System Fire Fighting Work | Interconnecting Cables (M) | No. | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 143 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | Mall-Utilies & PA System Fire Fighting Work | Floor Mounted Closed Rack (M) | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 143 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | Mall-Utilies & PA System Fire Fighting Work | 6 Zone Call Station with Mike (M) | No. | 1 | 35500 | 35500 | 6390 | 41890 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 143 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | Mall-Utilies & PA System Fire Fighting Work | CAT 6 Cable (M) | Mtrs | 500 | 45 | 22500 | 4050 | 26550 | 0 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | CAT 6 Cable (L) | Mtrs | 500 | 20 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Mountable Music Source (L) | No. | 1 | 500 | 500 | 90 | 590 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | SITC PA Main Console (L) | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Power Amplifer (L) | No. | 1 | 8000 | 8000 | 1440 | 9440 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | 6W Ceiling Speakers (L) | No. | 30 | 300 | 9000 | 1620 | 10620 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Service Charges | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | S OH Repair & Maintenance | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | 6 Zone Call Station with Mike (L) | No. | 1 | 4500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Interconnecting Cables (L) | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 144 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Floor Mounted Closed Rack (L) | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 1 | 6050 | 1089 | 7139 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 1 | 6050 | 1089 | 7139 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 1 | 6050 | 1089 | 7139 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 6050 | 6050 | 1089 | 7139 | 0 | 1 | 6050 | 1089 | 7139 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 145 | 0 | 26 Feb 2022 | KAMAL FIRE FIGHTING SYSTEM | Mall-Utilies & PA System Fire Fighting Work | Fire Fighting Maintenance - | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 1 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 146 | 0 | 26 Feb 2022 | AZAM KHAN | KEP 6th Slab Fabrication Repainting Work | Department Labour- BC | No. | 12 | 850 | 10200 | 0 | 10200 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 147 | 0 | 26 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-4th Fl Atrium Lobby False Ceiling M.S. Support | Fabrication Work (L) | Kgs | 3080 | 21 | 64680 | 11642.4 | 76322.4 | 2.5 | 0 | 0 | 0 | 0 | 3080 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 148 | 0 | 28 Feb 2022 | SAHARA ENGINEERING | Ladder providing for site work. | Labour Lumpsum - SOS | No. | 1 | 35000 | 35000 | 6300 | 41300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 149 | 0 | 28 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Anchor Fastener (L) | No. | 768 | 40 | 30720 | 5529.6 | 36249.6 | 2.5 | 768 | 30720 | 5529.6 | 36249.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 149 | 0 | 28 Feb 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Chequred Plate | Kgs | 4608 | 21 | 96768 | 17418.24 | 114186.24 | 2.5 | 4608 | 96768 | 17418.24 | 114186.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 150 | 0 | 28 Feb 2022 | SHINE COATS | Basement Fl -Painting Work - 1 No. | P.U. Paint Patta- BCo | R.Ft | 1704.05 | 17 | 28968.85 | 5214.4 | 34183.25 | 2.5 | 0 | 0 | 0 | 0 | 1704.05 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 151 | 0 | 28 Feb 2022 | PRAMOD DEVNARAYAN JHA | Site Maintenance work | Labour Lumpsum (month) | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 152 | 0 | 28 Feb 2022 | GRAVITY ENTERPRISES | 3rd Floor Aerocon Panel-75mm-(Sq.Ft) | Aerocon Partition (M+L) BC | Sq.Ft | 778.38 | 30 | 23351.4 | 4203.26 | 27554.66 | 2.5 | 778.38 | 23351.4 | 4203.26 | 27554.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 152 | 0 | 28 Feb 2022 | GRAVITY ENTERPRISES | 3rd Floor Aerocon Panel-75mm-(Sq.Ft) | Panel Shifting - UTI | No. | 98 | 150 | 14700 | 2646 | 17346 | 0 | 98 | 14700 | 2646 | 17346 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 11 Mar 2022 |  | UTI. Electricity Infrastructur | Approved | chetan.jewalikar
EAST POINT MARKET | 152 | 1 | 28 Feb 2022 | GRAVITY ENTERPRISES | 3rd Floor (R2) Shops Aerocon Panel work | Aerocon Panel Installation | Sq.Ft | 523.02 | 30 | 15690.6 | 2824.3 | 18514.9 | 2.5 | 523.02 | 15690.6 | 2824.3 | 18514.9 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 11 Mar 2022 |  | 12 MASONARY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Double Coat Plaster work (L) | Sq.Ft | 540.76 | 30 | 16222.8 | 0 | 16222.8 | 2.5 | 540.76 | 16222.8 | 0 | 16222.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Single Coat Plaster (L) | Sq.Ft | 1358.06 | 20 | 27161.2 | 0 | 27161.2 | 2.5 | 1358.06 | 27161.2 | 0 | 27161.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Hacking Work | Sq.Ft | 1659.41 | 5 | 8297.05 | 0 | 8297.05 | 0 | 1659.41 | 8297.05 | 0 | 8297.05 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 02 RCC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Debris Removing & Shifting Work | No. | 1 | 6479 | 6479 | 0 | 6479 | 0 | 1 | 6479 | 0 | 6479 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Male Coolie | No. | 50 | 500 | 25000 | 0 | 25000 | 0 | 50 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Double Coat Plaster work (L) | Sq.Ft | 841.656 | 30 | 25249.68 | 0 | 25249.68 | 2.5 | 841.656 | 25249.68 | 0 | 25249.68 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Debris Removing & Shifting Work | No. | 1 | 21600 | 21600 | 0 | 21600 | 0 | 1 | 21600 | 0 | 21600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Debris Removing & Shifting Work | No. | 1 | 8500 | 8500 | 0 | 8500 | 0 | 1 | 8500 | 0 | 8500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Blockwork- BC | Sq.Ft | 262.45 | 16 | 4199.2 | 0 | 4199.2 | 2.5 | 262.45 | 4199.2 | 0 | 4199.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | B.C. BBM, Plaster, POP | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Unloading of AAC Blocks | No. | 784 | 3 | 2352 | 0 | 2352 | 0 | 784 | 2352 | 0 | 2352 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | S OH Expenses | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | PCC | Sq.Ft | 360.75 | 6 | 2164.5 | 0 | 2164.5 | 2.5 | 360.75 | 2164.5 | 0 | 2164.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Debris Removing & Shifting Work | No. | 1 | 5412.56 | 5412.56 | 0 | 5412.56 | 0 | 1 | 5412.56 | 0 | 5412.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 14 MISC WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Blockwork- BC | Sq.Ft | 679.03 | 16 | 10864.48 | 0 | 10864.48 | 2.5 | 679.03 | 10864.48 | 0 | 10864.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | B.C. BBM, Plaster, POP | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Single Coat Plaster (L) | Sq.Ft | 524.9 | 20 | 10498 | 0 | 10498 | 2.5 | 524.9 | 10498 | 0 | 10498 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Ghadai work- BCP | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 28 Feb 2022
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Ghadai work- BCP | Sq.Ft | 499.77 | 5 | 2498.85 | 0 | 2498.85 | 0 | 499.77 | 2498.85 | 0 | 2498.85 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | B.C. Building Common Items | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Dismantling work | No. | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Single Coat Plaster (L) | Sq.Ft | 985.5 | 20 | 19710 | 0 | 19710 | 2.5 | 985.5 | 19710 | 0 | 19710 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Weld mesh fixing(L) BC | Sq.Ft | 461.13 | 5 | 2305.65 | 0 | 2305.65 | 2.5 | 461.13 | 2305.65 | 0 | 2305.65 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Demolishing Blockwork- Dld | Sq.Ft | 3058.69 | 2 | 6117.38 | 0 | 6117.38 | 0 | 3058.69 | 6117.38 | 0 | 6117.38 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 1 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Dismantling work | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 153 | 0 | 28 Feb 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Mason - DCW | No. | 30 | 850 | 25500 | 0 | 25500 | 0 | 30 | 25500 | 0 | 25500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open |  |  | DEV. Compound Wall | Approved | chetan.jewalikar
EAST POINT MARKET | 154 | 0 | 02 Mar 2022 | ANTS DESIGN | Media BRANDING | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 1000000 | 1000000 | 180000 | 1180000 | 0 | 0.2075 | 207500 | 37350 | 244850 | 0.7925 | 935150 | EAST POINT MARKET, KURLA PROJECT SALES PROMOTION WITH LEAD GENERATION, BRANDING ETC. THROUGH ONLINE, DIGITAL PAID CAMPAIN FOR 1 MONTH | 20.75 |  | Tejas Raverkar | sunita shirolkar | construction open | 02 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 155 | 0 | 05 Mar 2022 | SAHARA ENGINEERING | KEP- Railing,ACP,CNC Cut Jali,Glass Work | S.S. Railing (m+l)- BC | R.Ft | 177 | 800 | 141600 | 25488 | 167088 | 2.5 | 177 | 141600 | 25488 | 167088 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Fixing Work-Mkt | Sq.Ft | 152.28 | 350 | 53298 | 9593.64 | 62891.64 | 2.5 | 152.28 | 53298 | 9593.64 | 62891.64 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 0 | 10 Mar 2022 | FINE TRADERS | KEP - 3rd FL Atrium Glass Railing Glass Railing | Glass Railing (L) | R.Ft | 92.82 | 350 | 32487 | 5847.66 | 38334.66 | 2.5 | 92.82 | 32487 | 5847.66 | 38334.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 0 | 10 Mar 2022 | FINE TRADERS | KEP-4th Fl Atrium Glass Glass Railing | Glass Railing (L) | R.Ft | 92.82 | 350 | 32487 | 5847.66 | 38334.66 | 2.5 | 92.82 | 32487 | 5847.66 | 38334.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 2 | 10 Mar 2022 | FINE TRADERS | 2nd flr. Window ACP covering work | ACP Sheet (L) | Sq.Ft | 440.333 | 60 | 26419.98 | 4755.6 | 31175.58 | 2.5 | 440.333 | 26419.98 | 4755.6 | 31175.58 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 22.85 | 350 | 7997.5 | 1439.56 | 9437.06 | 2.5 | 22.85 | 7997.5 | 1439.56 | 9437.06 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 2 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 119 | 350 | 41650 | 7497 | 49147 | 2.5 | 119 | 41650 | 7497 | 49147 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 0 | 10 Mar 2022 | FINE TRADERS | KEP - 1st FL Atrium Glass Railing Glass Railing | Glass Railing (L) | R.Ft | 92.82 | 350 | 32487 | 5847.66 | 38334.66 | 2.5 | 92.82 | 32487 | 5847.66 | 38334.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 28.5 | 350 | 9975 | 1795.5 | 11770.5 | 2.5 | 28.5 | 9975 | 1795.5 | 11770.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 27.153 | 350 | 9503.55 | 1710.64 | 11214.19 | 2.5 | 27.153 | 9503.55 | 1710.64 | 11214.19 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 25.65 | 350 | 8977.5 | 1615.96 | 10593.46 | 2.5 | 25.65 | 8977.5 | 1615.96 | 10593.46 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Fixing Work-Mkt | Sq.Ft | 81.64 | 350 | 28574 | 5143.32 | 33717.32 | 2.5 | 81.64 | 28574 | 5143.32 | 33717.32 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | Dushant Gore | 02 Dec 2022
EAST POINT MARKET | 156 | 2 | 10 Mar 2022 | FINE TRADERS | 3rd Fl. Mall Management Office ACP work | ACP Sheet (L) | Sq.Ft | 440.333 | 60 | 26419.98 | 4755.6 | 31175.58 | 2.5 | 440.333 | 26419.98 | 4755.6 | 31175.58 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 2 | 10 Mar 2022 | FINE TRADERS | 2nd flr. Window ACP covering work | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 03 Dec 2022
EAST POINT MARKET | 156 | 0 | 10 Mar 2022 | FINE TRADERS | KEP - 2nd FL Atrium Glass Railing Glass Railing | Glass Railing (L) | R.Ft | 92.82 | 350 | 32487 | 5847.66 | 38334.66 | 2.5 | 92.82 | 32487 | 5847.66 | 38334.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Fixing Work-Mkt | Sq.Ft | 152.28 | 350 | 53298 | 9593.64 | 62891.64 | 2.5 | 152.28 | 53298 | 9593.64 | 62891.64 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Framing Removing work | Sq.Ft | 3075 | 50 | 153750 | 27675 | 181425 | 0 | 3075 | 153750 | 27675 | 181425 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | 2nd flr. Window ACP covering work | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 02 Dec 2022
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | 3rd Fl. Mall Management Office ACP work | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 02 Dec 2022
EAST POINT MARKET | 156 | 2 | 10 Mar 2022 | FINE TRADERS | 3rd Fl. Mall Management Office ACP work | ACP Sheet (L) | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 03 Dec 2022
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Rework | R.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | Dushant Gore | 22 Sep 2022
EAST POINT MARKET | 156 | 2 | 10 Mar 2022 | FINE TRADERS | 4th Fl. Slab, Beam ACP sheet fixing | ACP Sheet (L) | Sq.Ft | 440.333 | 60 | 26419.98 | 4755.6 | 31175.58 | 2.5 | 440.333 | 26419.98 | 4755.6 | 31175.58 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Rework | R.Ft | 119 | 175 | 20825 | 3748.5 | 24573.5 | 2.5 | 119 | 20825 | 3748.5 | 24573.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 156 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (L) | R.Ft | 26.74 | 350 | 9359 | 1684.62 | 11043.62 | 2.5 | 26.74 | 9359 | 1684.62 | 11043.62 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 2 | 10 Mar 2022 | FINE TRADERS | 3rd Fl. Mall Management Office ACP work | ACP Sheet (M) | Sq.Ft | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 03 Dec 2022
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Fastner (M) - SOSB | No. | 140 | 90 | 12600 | 2268 | 14868 | 0 | 140 | 12600 | 2268 | 14868 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 2 | 10 Mar 2022 | FINE TRADERS | 4th Fl. Slab, Beam ACP sheet fixing | ACP Sheet (M) | Sq.Ft | 440.333 | 152 | 66930.62 | 12047.52 | 78978.14 | 0 | 440.333 | 66930.62 | 12047.52 | 78978.14 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 2 | 10 Mar 2022 | FINE TRADERS | 2nd flr. Window ACP covering work | ACP Sheet (M) | Sq.Ft | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 03 Dec 2022
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (M) | R.Ft | 26.74 | 2700 | 72198 | 12995.64 | 85193.64 | 0 | 26.74 | 72198 | 12995.64 | 85193.64 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (M) | R.Ft | 25.65 | 2700 | 69255 | 12465.9 | 81720.9 | 0 | 25.65 | 69255 | 12465.9 | 81720.9 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (M) | R.Ft | 27.153 | 2700 | 73313.1 | 13196.36 | 86509.46 | 0 | 27.153 | 73313.1 | 13196.36 | 86509.46 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (M) | R.Ft | 22.85 | 2700 | 61695 | 11105.1 | 72800.1 | 0 | 22.85 | 61695 | 11105.1 | 72800.1 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 2 | 10 Mar 2022 | FINE TRADERS | 3rd Fl. Mall Management Office ACP work | ACP Sheet (M) | Sq.Ft | 440.333 | 152 | 66930.62 | 12047.52 | 78978.14 | 0 | 440.333 | 66930.62 | 12047.52 | 78978.14 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Glass Railing (M) | R.Ft | 28.5 | 1500 | 42750 | 7695 | 50445 | 0 | 28.5 | 42750 | 7695 | 50445 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 0 | 10 Mar 2022 | FINE TRADERS | KEP-4th Fl Atrium Glass Glass Railing | Glass Railing (M) | R.Ft | 92.82 | 2700 | 250614 | 45110.52 | 295724.52 | 0 | 92.82 | 250614 | 45110.52 | 295724.52 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 05 Apr 2022
EAST POINT MARKET | 157 | 1 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | Handle Fixing BC | No. | 14 | 2500 | 35000 | 6300 | 41300 | 0 | 14 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 157 | 2 | 10 Mar 2022 | FINE TRADERS | 2nd flr. Window ACP covering work | ACP Sheet (M) | Sq.Ft | 440.333 | 152 | 66930.62 | 12047.52 | 78978.14 | 0 | 440.333 | 66930.62 | 12047.5 | 78978.12 | 0 | 0.02 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 158 | 0 | 10 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Smart Manager (L) | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 158 | 0 | 10 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 11 TR Ductable Unit (L) | No. | 1 | 9000 | 9000 | 1620 | 10620 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 158 | 0 | 10 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 17 TR Ductable Unit | No. | 1 | 16000 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 158 | 0 | 10 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Outdoor Unit 78 HP (L) | No. | 1 | 62400 | 62400 | 11232 | 73632 | 2.5 | 1 | 62400 | 11232 | 73632 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 158 | 0 | 10 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Cassette A.C. Unit 4 Way (L) | No. | 16 | 3500 | 56000 | 10080 | 66080 | 2.5 | 16 | 56000 | 10080 | 66080 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 159 | 0 | 10 Mar 2022 | AQUARIUS WATERPROOFING | Waterproofing Basement Fl-Retaining Wall Waterproofing | Grouting Work - Dld | No. | 15 | 3000 | 45000 | 8100 | 53100 | 10 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 159 | 0 | 10 Mar 2022 | AQUARIUS WATERPROOFING | KEP - 4th FL Expansion Joint Treatment-(Job) | Expansion Joint BC R.Mtrs - | Mtrs | 17 | 1100 | 18700 | 3366 | 22066 | 10 | 0 | 0 | 0 | 0 | 17 | 0 | 1) Apply PERMA SBR 2) Fix Foam sheet (50mm) 3) Fix PERMA BUTYALE TAPE 100mnm both side 4) Apply Masking tape on Perma Butyale Tape on corner 5) Apply NEOPROOF RC 200+50 GSM Non-woven cloth in 3 Coats. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 159 | 0 | 10 Mar 2022 | AQUARIUS WATERPROOFING | KEP - Basement FL - Tank Chemical Waterproofing | Chemical W/P (L+M) | Sq.Ft | 170 | 60 | 10200 | 1836 | 12036 | 10 | 0 | 0 | 0 | 0 | 170 | 0 | 1) Open all joints by Perma Polycreate + SBR Bond 2) Apply NEOPROOF RC 200+50 GSM coating on RCC wall. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 159 | 0 | 10 Mar 2022 | AQUARIUS WATERPROOFING | Waterproofing Pocket Terrace & Wall Waterproofing | Chemical W/P (L+M) | Sq.Ft | 3300 | 60 | 198000 | 35640 | 233640 | 10 | 2396.7207 | 143803.24 | 25884.58 | 169687.82 | 903.2793 | 63952.18 | 1) Open all major Cracks and fill by PERMA ACRTSEAL 2) Apply NEOPROOF RC-200 (1:1) 3) Apply NEOPROOF RC 200+50 GSM Non Woven cloth in 2 coats. | 72.6279 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Butterfly Valve 50 mm | No. | 0 | 840 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Reducer Elbow Removing (L) | No. | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Reducer Elbow Removing (L) | No. | 24 | 40 | 960 | 172.8 | 1132.8 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Reducer Elbow 25x15 (L) | No. | 24 | 42 | 1008 | 181.44 | 1189.44 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | SITC Ball Valve 25mm (L) | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Reducer Elbow 25x15 (L) | No. | 0 | 42 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Butterfly Valve 50 mm | No. | 2 | 840 | 1680 | 302.4 | 1982.4 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 160 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | SITC Ball Valve 25mm (L) | No. | 4 | 300 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 161 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Butterfly Valve 50 mm (M) | No. | 2 | 1960 | 3920 | 705.6 | 4625.6 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 161 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Reducer Elbow 25x15 (M) | No. | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 161 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Reducer Elbow 25x15 (M) | No. | 24 | 98 | 2352 | 423.36 | 2775.36 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 161 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | SITC Ball Valve 25mm (M) | No. | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 161 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | Butterfly Valve 50 mm (M) | No. | 0 | 1960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 10 Mar 2022
EAST POINT MARKET | 161 | 0 | 10 Mar 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP-Fire Fighting Work Fire Fighting Work-(Job) | SITC Ball Valve 25mm (M) | No. | 4 | 700 | 2800 | 504 | 3304 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 162 | 0 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (L)-BCo | Sq.Ft | 343.56 | 60 | 20613.6 | 3710.44 | 24324.04 | 2.5 | 0 | 0 | 0 | 0 | 343.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 162 | 0 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (L)-BCo | Sq.Ft | 343.56 | 60 | 20613.6 | 3710.44 | 24324.04 | 2.5 | 343.56 | 20613.6 | 3710.44 | 24324.04 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 162 | 0 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (L)-BCo | Sq.Ft | 343.56 | 60 | 20613.6 | 3710.44 | 24324.04 | 2.5 | 343.56 | 20613.6 | 3710.44 | 24324.04 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 162 | 0 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (L)-BCo | Sq.Ft | 343.56 | 60 | 20613.6 | 3710.44 | 24324.04 | 2.5 | 343.56 | 20613.6 | 3710.44 | 24324.04 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 163 | 0 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (M)-BCo | Sq.Ft | 343.56 | 162 | 55656.72 | 10018.2 | 65674.92 | 0 | 309.2926 | 50105.4 | 9018.98 | 59124.38 | 34.2674 | 6550.54 |  | 90.0258 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 163 | 0 | 10 Mar 2022 | FINE TRADERS | KEP- Railing,ACP,CNC Cut Jali,Glass Work | ACP Cladding (M)-BCo | Sq.Ft | 343.56 | 130 | 44662.8 | 8039.3 | 52702.1 | 0 | 343.56 | 44662.8 | 8039.3 | 52702.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 164 | 0 | 10 Mar 2022 | SHINE COATS | KEP-MS Work MS Gutter Anticorrosive Painting | Anti Corrosive Paint (M+L) | Sq.Ft | 1226 | 70 | 85820 | 15447.6 | 101267.6 | 2.5 | 1226 | 85820 | 15447.6 | 101267.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 1st Coat Wall Putty - | Sq.Ft | 6218.54 | 1.25 | 7773.18 | 0 | 7773.18 | 2.5 | 6218.54 | 7773.18 | 0 | 7773.18 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 2 | 10 Mar 2022 | AZAM KHAN | KEP-4th Fl Painting For Launching | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 15067.145 | 1.25 | 18833.93 | 0 | 18833.93 | 2.5 | 15067.145 | 18833.93 | 0 | 18833.93 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor painting work | Paint Touchup work.-BRE | Sq.Ft | 42129.15 | 1.25 | 52661.44 | 0 | 52661.44 | 2.5 | 42129.15 | 52661.44 | 0 | 52661.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 2 | 10 Mar 2022 | AZAM KHAN | KEP-4th Fl Painting For Launching | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 15067.145 | 1.25 | 18833.93 | 0 | 18833.93 | 2.5 | 15067.145 | 18833.93 | 0 | 18833.93 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 215.33 | 1.25 | 269.16 | 0 | 269.16 | 2.5 | 0 | 0 | 0 | 0 | 215.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | Scrapping with 1st Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 2 | 10 Mar 2022 | AZAM KHAN | KEP-4th Fl Painting For Launching | 1 Coat Primer (Water Base) (L) | Sq.Ft | 15067.145 | 1.25 | 18833.93 | 0 | 18833.93 | 2.5 | 15067.145 | 18833.93 | 0 | 18833.93 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1279.12 | 1.25 | 1598.9 | 0 | 1598.9 | 2.5 | 0 | 0 | 0 | 0 | 1279.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor Sample Shop painting | 1st Coat Paint | Sq.Ft | 4276.94 | 1.25 | 5346.18 | 0 | 5346.18 | 2.5 | 4276.94 | 5346.18 | 0 | 5346.18 | 0 | 0 | Shop No.- 16,17,18,19,43,44,45,46,103. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor Sample Shop painting | 1st Coat Wall Putty - | Sq.Ft | 4276.94 | 1.25 | 5346.18 | 0 | 5346.18 | 2.5 | 4276.94 | 5346.18 | 0 | 5346.18 | 0 | 0 | Shop No.- 16,17,18,19,43,44,45,46,103. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | Scrapping with 2nd Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | Scrapping with 1st Coat Putty | Sq.Ft | 1279.12 | 1.25 | 1598.9 | 0 | 1598.9 | 2.5 | 0 | 0 | 0 | 0 | 1279.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1279.12 | 1.25 | 1598.9 | 0 | 1598.9 | 2.5 | 0 | 0 | 0 | 0 | 1279.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor painting work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 42129.15 | 1.25 | 52661.44 | 0 | 52661.44 | 2.5 | 42129.15 | 52661.44 | 0 | 52661.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | 1 Coat Primer (Water Base) (L) | Sq.Ft | 215.33 | 1.25 | 269.16 | 0 | 269.16 | 2.5 | 0 | 0 | 0 | 0 | 215.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor Sample Shop painting | 2nd Coat Wall Putty - | Sq.Ft | 4276.94 | 1.25 | 5346.18 | 0 | 5346.18 | 2.5 | 4276.94 | 5346.18 | 0 | 5346.18 | 0 | 0 | Shop No.- 16,17,18,19,43,44,45,46,103. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | Scrapping with 2nd Coat Putty | Sq.Ft | 215.33 | 1.25 | 269.16 | 0 | 269.16 | 2.5 | 0 | 0 | 0 | 0 | 215.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 2nd Coat Paint | Sq.Ft | 10778.98 | 1.25 | 13473.73 | 0 | 13473.73 | 2.5 | 10778.98 | 13473.73 | 0 | 13473.73 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor Sample Shop painting | 2nd Coat Paint | Sq.Ft | 4276.94 | 1.25 | 5346.18 | 0 | 5346.18 | 2.5 | 4276.94 | 5346.18 | 0 | 5346.18 | 0 | 0 | Shop No.- 16,17,18,19,43,44,45,46,103. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | 1 Coat Primer (Water Base) (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1279.12 | 1.25 | 1598.9 | 0 | 1598.9 | 2.5 | 0 | 0 | 0 | 0 | 1279.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor Sample Shop painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 4276.94 | 1.25 | 5346.18 | 0 | 5346.18 | 2.5 | 4276.94 | 5346.18 | 0 | 5346.18 | 0 | 0 | Shop No.- 16,17,18,19,43,44,45,46,103. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 1st Coat Ceiling Putty | Sq.Ft | 4560.44 | 1.25 | 5700.55 | 0 | 5700.55 | 2.5 | 4560.44 | 5700.55 | 0 | 5700.55 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 10778.98 | 1.25 | 13473.73 | 0 | 13473.73 | 2.5 | 10778.98 | 13473.73 | 0 | 13473.73 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 1st Coat Paint | Sq.Ft | 10778.98 | 1.25 | 13473.73 | 0 | 13473.73 | 2.5 | 10778.98 | 13473.73 | 0 | 13473.73 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 2nd Coat Wall Putty - | Sq.Ft | 6218.54 | 1.25 | 7773.18 | 0 | 7773.18 | 2.5 | 6218.54 | 7773.18 | 0 | 7773.18 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 215.33 | 1.25 | 269.16 | 0 | 269.16 | 2.5 | 0 | 0 | 0 | 0 | 215.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 2nd Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | Scrapping with 2nd Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | Scrapping with 2nd Coat Putty | Sq.Ft | 1279.12 | 1.25 | 1598.9 | 0 | 1598.9 | 2.5 | 0 | 0 | 0 | 0 | 1279.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 3rd Floor Guardians telecalling area painting | 2nd Coat Ceiling Putty | Sq.Ft | 4560.44 | 1.25 | 5700.55 | 0 | 5700.55 | 2.5 | 4560.44 | 5700.55 | 0 | 5700.55 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor painting work | 2nd Coat Paint | Sq.Ft | 42129.15 | 1.25 | 52661.44 | 0 | 52661.44 | 2.5 | 42129.15 | 52661.44 | 0 | 52661.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 2 | 10 Mar 2022 | AZAM KHAN | KEP-4th Fl Painting For Launching | Painter - SM | No. | 100 | 850 | 85000 | 0 | 85000 | 2.5 | 24 | 20400 | 0 | 20400 | 76 | 64600 |  | 24 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 2 | 10 Mar 2022 | AZAM KHAN | KEP-4th Fl Painting For Launching | Paint Touchup work.-BRE | Sq.Ft | 15067.145 | 1.25 | 18833.93 | 0 | 18833.93 | 2.5 | 0 | 0 | 0 | 0 | 15067.145 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 2nd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Basement FL Staircase 1&2 Painitng Work Premium Emulsion Pai | Scrapping with 1st Coat Putty | Sq.Ft | 215.33 | 1.25 | 269.16 | 0 | 269.16 | 2.5 | 0 | 0 | 0 | 0 | 215.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 4th FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 1 | 10 Mar 2022 | AZAM KHAN | 2nd floor painting work | 1st Coat Paint | Sq.Ft | 42129.15 | 1.25 | 52661.44 | 0 | 52661.44 | 2.5 | 42129.15 | 52661.44 | 0 | 52661.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | Scrapping with 1st Coat Putty | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | 1 Coat Primer (Water Base) (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 1st FL Staircase 1 &2 Painitng Work Premium Emulsion Paint | 1 Coat Primer (Water Base) (L) | Sq.Ft | 476.92 | 1.25 | 596.15 | 0 | 596.15 | 2.5 | 0 | 0 | 0 | 0 | 476.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | Ground FL Staircase 1 & 2 Painitng Work Premium Emulsion Pai | Scrapping with 1st Coat Putty | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 165 | 0 | 10 Mar 2022 | AZAM KHAN | 3rd FL Staircase 1 & 2 Painitng Work Premium Emulsion Paint | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1749.03 | 1.25 | 2186.29 | 0 | 2186.29 | 2.5 | 0 | 0 | 0 | 0 | 1749.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 166 | 1 | 10 Mar 2022 | MILLENNIUM ARTS | Media BRANDING | LEAFLET PRINTING | No. | 504000 | 1.05 | 529200 | 95256 | 624456 | 0 | 504000 | 529200 | 95256 | 624456 | 0 | 0 | EAST POINT MARKET PROJECT SALES PROMOTION WITH PROJECT BRANDING LEAFLET PRINT SIZE AS A-4 (56 NAMES DIFF. TOTAL QTY. 504000) | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 12 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 166 | 0 | 10 Mar 2022 | MILLENNIUM ARTS | Media BRANDING | LEAFLET PRINTING | No. | 55000 | 0.7 | 38500 | 6930 | 45430 | 0 | 55000 | 38500 | 6930 | 45430 | 0 | 0 | EAST POINT MARKET PROJECT SALES PROMOTION WITH PROJECT BRANDING LEAFLET PRINT SIZE AS A-5 (11 NAME X 5000 EACH) | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 12 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 167 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | SITC of Drain Pipe (M) | Mtrs | 20 | 50 | 1000 | 180 | 1180 | 0 | 20 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 167 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | 3C 2.5 sqmm Cu Cable (M) | Mtrs | 35 | 84 | 2940 | 529.2 | 3469.2 | 0 | 35 | 2940 | 529.2 | 3469.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Pressure Testing, Vaccumising, Refrigerant Copper piping (M) | Mtrs | 322 | 40 | 12880 | 2318.4 | 15198.4 | 0 | 321.9993 | 12879.97 | 2318.4 | 15198.37 | 0.0007 | 0.03 |  | 99.9998 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Refrigerant Piping (M) | Mtrs | 322 | 1550 | 499100 | 89838 | 588938 | 0 | 321.9999 | 499099.85 | 89837.98 | 588937.83 | 0.0001 | 0.18 |  | 100 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | skmishra
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Refnuts (M) | No. | 21 | 4646 | 97566 | 17561.88 | 115127.88 | 0 | 21 | 97566 | 17561.88 | 115127.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 167 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | Copper Pipe with Insulation (M) | Mtrs | 30 | 800 | 24000 | 4320 | 28320 | 0 | 30 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Drain Piping 25mm (M) | Mtrs | 200 | 110 | 22000 | 3960 | 25960 | 0 | 62.7 | 6897 | 1241.46 | 8138.46 | 137.3 | 17821.54 |  | 31.35 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Drain Piping 32mm (M) | Mtrs | 100 | 130 | 13000 | 2340 | 15340 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | T Joints (M) | No. | 2 | 4300 | 8600 | 1548 | 10148 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Gas Charging (M). | Kgs | 58 | 1250 | 72500 | 13050 | 85550 | 0 | 28 | 35000 | 6300 | 41300 | 30 | 44250 |  | 48.2759 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | skmishra
EAST POINT MARKET | 167 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | Gas charging,Pressure testing- BC | No. | 5 | 25 | 125 | 22.5 | 147.5 | 0 | 5 | 125 | 22.5 | 147.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 167 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Stand for ODU unit (M) | No. | 2 | 9250 | 18500 | 3330 | 21830 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | AC Installation & Commissioning (L) | No. | 5 | 1500 | 7500 | 1350 | 8850 | 2.5 | 5 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Stand for ODU unit (L) | No. | 2 | 250 | 500 | 90 | 590 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Refrigerant Piping (L) | Mtrs | 322 | 200 | 64400 | 11592 | 75992 | 2.5 | 321.9999 | 64399.98 | 11592 | 75991.98 | 0.0001 | 0.02 |  | 100 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | skmishra
EAST POINT MARKET | 168 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | Copper Piping with insulation (L) | Mtrs | 30 | 175 | 5250 | 945 | 6195 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Drain Piping 32mm (L) | Mtrs | 100 | 20 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | 16 Hp Top Discharge VRF ODU (L) | No. | 1 | 16000 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | Dismentling & Installation work (L) | No. | 4 | 800 | 3200 | 576 | 3776 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Refnuts (L) | No. | 21 | 200 | 4200 | 756 | 4956 | 2.5 | 21 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Drain Piping 25mm (L) | Mtrs | 200 | 20 | 4000 | 720 | 4720 | 2.5 | 62.7 | 1254 | 225.72 | 1479.72 | 137.3 | 3240.28 |  | 31.35 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | 24 Hp Top Discharge VRF ODU (L) | No. | 1 | 24000 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | Gas charging,Pressure testing- BC | No. | 5 | 15 | 75 | 13.5 | 88.5 | 2.5 | 5 | 75 | 13.5 | 88.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 168 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | 3C 2.5 sqmm Cu Cable (L) | Mtrs | 35 | 20 | 700 | 126 | 826 | 2.5 | 35 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | T Joints (L) | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Unloading,Handling,Shifting,Transport charges | No. | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Indoor Hi Wall type Unit | No. | 23 | 4000 | 92000 | 16560 | 108560 | 2.5 | 10 | 40000 | 7200 | 47200 | 13 | 61360 |  | 43.4783 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | skmishra
EAST POINT MARKET | 168 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-AC Work 3rd Fl Mall Management Office AC Work | SITC of Drain Pipe (L) | Mtrs | 20 | 20 | 400 | 72 | 472 | 2.5 | 20 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 168 | 1 | 12 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | 3rd Fl Foodcourt VRF System Low side | Pressure Testing, Vaccumising, Refrigerant Copper piping (L) | Mtrs | 322 | 25 | 8050 | 1449 | 9499 | 2.5 | 74.57 | 1864.25 | 335.56 | 2199.81 | 247.43 | 7299.19 |  | 23.1584 |  | ADITYA CHOUGULE | skmishra | construction open | 14 Mar 2022 |  | No category | Approved | skmishra
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | GI Ducting (M) | Sq.m. | 35 | 1010 | 35350 | 6363 | 41713 | 0 | 0 | 0 | 0 | 0 | 35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Piping with insulation (M) | Mtrs | 90 | 900 | 81000 | 14580 | 95580 | 0 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Fabrication work (M) | Kgs | 950 | 85 | 80750 | 14535 | 95285 | 0 | 0 | 0 | 0 | 0 | 950 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Refnet Joints (M) | No. | 15 | 3400 | 51000 | 9180 | 60180 | 0 | 15 | 51000 | 9180 | 60180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Gas Charging (M). | Kgs | 90 | 700 | 63000 | 11340 | 74340 | 0 | 85 | 59500 | 10710 | 70210 | 5 | 4130 |  | 94.4444 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Pressure Testing, Vaccumising, Gas Charging | Mtrs | 505 | 25 | 12625 | 2272.5 | 14897.5 | 0 | 183.4998 | 4587.5 | 825.76 | 5413.26 | 321.5002 | 9484.25 |  | 36.3366 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | GI Ducting (M) | Sq.m. | 495 | 895 | 443025 | 79744.5 | 522769.5 | 0 | 468.86 | 419629.7 | 75533.36 | 495163.06 | 26.14 | 27606.44 |  | 94.7192 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Suply,Inst &Tstng-24G Ducting | Sq.m. | 142 | 895 | 127090 | 22876.2 | 149966.2 | 0 | 18.92 | 16933.4 | 3048.02 | 19981.42 | 123.08 | 129984.78 |  | 13.3239 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | T-Joints (M) | No. | 2 | 4000 | 8000 | 1440 | 9440 | 0 | 2 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 9 mm thk Nitrile Insulation | Sq.m. | 350 | 440 | 154000 | 27720 | 181720 | 0 | 120.99 | 53235.6 | 9582.4 | 62818 | 229.01 | 118902 |  | 34.5686 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Alu. Powder Coated VCD (M) | Sq.m. | 6 | 4700 | 28200 | 5076 | 33276 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | SITC of Drain Pipe (M) | Mtrs | 100 | 50 | 5000 | 900 | 5900 | 0 | 51.4 | 2570 | 462.6 | 3032.6 | 48.6 | 2867.4 |  | 51.4 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | PVC Conduit Piping (M) | Mtrs | 505 | 15 | 7575 | 1363.5 | 8938.5 | 0 | 238.5999 | 3579 | 644.22 | 4223.22 | 266.4001 | 4715.28 |  | 47.2475 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Alu. Powder Coated VCD (M) | Sq.m. | 8 | 5700 | 45600 | 8208 | 53808 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Piping with insulation (M) | Mtrs | 90 | 900 | 81000 | 14580 | 95580 | 0 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Piping with insulation (M) | Mtrs | 185 | 1100 | 203500 | 36630 | 240130 | 0 | 183.4999 | 201849.89 | 36332.98 | 238182.87 | 1.5001 | 1947.13 |  | 99.1891 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Canvas Connection (M) | No. | 2 | 1500 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 3C x 1.5sqmm (M) | Mtrs | 285 | 104.82 | 29873.7 | 5377.26 | 35250.96 | 0 | 238.6 | 25010.05 | 4501.8 | 29511.85 | 46.4 | 5739.11 |  | 83.7193 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Acostic Insulation (M) | Sq.m. | 100 | 650 | 65000 | 11700 | 76700 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Cable Tray-(M) | Mtrs | 25 | 440 | 11000 | 1980 | 12980 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Suply,Inst &Tstng-22G Ducting | Sq.m. | 40 | 1010 | 40400 | 7272 | 47672 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 3C x 1.5sqmm (M) | Mtrs | 220 | 104.82 | 23060.4 | 4150.88 | 27211.28 | 0 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 169 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | SITC of Drain Pipe (M) | Mtrs | 150 | 60 | 9000 | 1620 | 10620 | 0 | 67.5 | 4050 | 729 | 4779 | 82.5 | 5841 |  | 45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Acostic Insulation (L) | Sq.m. | 100 | 150 | 15000 | 2700 | 17700 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | GI Ducting (L) | Sq.m. | 35 | 168 | 5880 | 1058.4 | 6938.4 | 2.5 | 0 | 0 | 0 | 0 | 35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Piping with insulation (L) | Mtrs | 90 | 175 | 15750 | 2835 | 18585 | 2.5 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Alu. Powder Coated VCD (L) | Sq.m. | 6 | 800 | 4800 | 864 | 5664 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | PVC Conduit Piping (L) | Mtrs | 505 | 8 | 4040 | 727.2 | 4767.2 | 2.5 | 238.6 | 1908.8 | 343.58 | 2252.38 | 266.4 | 2514.82 |  | 47.2475 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Cable Tray- (L) | Mtrs | 25 | 50 | 1250 | 225 | 1475 | 2.5 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | SITC of Drain Pipe (L) | Mtrs | 150 | 20 | 3000 | 540 | 3540 | 2.5 | 67.5 | 1350 | 243 | 1593 | 82.5 | 1947 |  | 45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Suply,Inst &Tstng-24G Ducting | Sq.m. | 142 | 147 | 20874 | 3757.32 | 24631.32 | 2.5 | 0 | 0 | 0 | 0 | 142 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Canvas Connection (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Suply,Inst &Tstng-22G Ducting | Sq.m. | 40 | 168 | 6720 | 1209.6 | 7929.6 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Refnet Joints (L) | No. | 15 | 200 | 3000 | 540 | 3540 | 2.5 | 15 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Axial Fan Installation | No. | 1 | 5775 | 5775 | 1039.5 | 6814.5 | 2.5 | 1 | 5775 | 1039.5 | 6814.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Alu. Powder Coated VCD (L) | Sq.m. | 8 | 800 | 6400 | 1152 | 7552 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Pressure Testing, Vaccumising, Gas Charging | Mtrs | 505 | 15 | 7575 | 1363.5 | 8938.5 | 2.5 | 183.4998 | 2752.5 | 495.46 | 3247.96 | 321.5002 | 5690.54 |  | 36.3366 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | SITC of Drain Pipe (L) | Mtrs | 100 | 20 | 2000 | 360 | 2360 | 2.5 | 51.4 | 1028 | 185.04 | 1213.04 | 48.6 | 1146.96 |  | 51.4 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 9 mm thk Nitrile Insulation | Sq.m. | 350 | 120 | 42000 | 7560 | 49560 | 2.5 | 120.99 | 14518.8 | 2613.38 | 17132.18 | 229.01 | 32427.82 |  | 34.5686 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Piping with insulation (L) | Mtrs | 90 | 175 | 15750 | 2835 | 18585 | 2.5 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | GI Ducting (L) | Sq.m. | 495 | 147 | 72765 | 13097.7 | 85862.7 | 2.5 | 468.86 | 68922.42 | 12406.04 | 81328.46 | 26.14 | 4534.24 |  | 94.7192 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | T-Joints (L) | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 2 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 3C x 1.5sqmm (L) | Mtrs | 220 | 20 | 4400 | 792 | 5192 | 2.5 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | 3C x 1.5sqmm (L) | Mtrs | 285 | 20 | 5700 | 1026 | 6726 | 2.5 | 238.5997 | 4771.99 | 858.96 | 5630.95 | 46.4003 | 1095.05 |  | 83.7192 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Axial Fan Installation | No. | 0 | 5775 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 12 Mar 2022
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Fabrication work (L) | Kgs | 950 | 18.8 | 17860 | 3214.8 | 21074.8 | 2.5 | 0 | 0 | 0 | 0 | 950 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Direct Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Axial Fan Installation | No. | 1 | 5775 | 5775 | 1039.5 | 6814.5 | 2.5 | 1 | 5775 | 1039.5 | 6814.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 170 | 0 | 12 Mar 2022 | NEPTUNE ENGINEERS | KEP-Ventilation 3rd Floor Foodcourt -Ventilation System | Copper Piping with insulation (L) | Mtrs | 185 | 175 | 32375 | 5827.5 | 38202.5 | 2.5 | 183.4999 | 32112.48 | 5780.24 | 37892.72 | 1.5001 | 309.78 |  | 99.1891 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 171 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | B.O.C.W. Act Registration &Compliance. | No. | 1 | 34500 | 34500 | 6210 | 40710 | 0 | 1 | 34500 | 6210 | 40710 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | Consultancy Labour act Regist. | Approved | chetan.jewalikar
EAST POINT MARKET | 171 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | Registration of Company (RC) | No. | 1 | 50400 | 50400 | 9072 | 59472 | 0 | 1 | 50400 | 9072 | 59472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar
EAST POINT MARKET | 171 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | Registration Charges | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar
EAST POINT MARKET | 171 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | Registration Charges | No. | 1 | 1000 | 1000 | 180 | 1180 | 0 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Painting Work | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | DEV. Ext Development | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding | R.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Patti Fixing 8" | R.Ft | 419.04 | 125 | 52380 | 9428.4 | 61808.4 | 2.5 | 0 | 0 | 0 | 0 | 419.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | SS Clamp (L) | No. | 0 | 67.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Fastner (L) - SOSB | No. | 0 | 67.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Expansion Joint (L)-BC | R.Ft | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | SS Clamp (L) | No. | 370 | 67.5 | 24975 | 4495.5 | 29470.5 | 2.5 | 370 | 24975 | 4495.5 | 29470.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Carpetch (L) | Kgs | 35 | 54 | 1890 | 340.2 | 2230.2 | 2.5 | 35 | 1890 | 340.2 | 2230.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Expansion Joint (L)-BC | R.Ft | 160 | 150 | 24000 | 4320 | 28320 | 2.5 | 160 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tinex (L) | Kgs | 0 | 270 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tinex (L) | Kgs | 30 | 270 | 8100 | 1458 | 9558 | 2.5 | 30 | 8100 | 1458 | 9558 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding-(L) | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Square Bar (L) | Mtrs | 294 | 126 | 37044 | 6667.92 | 43711.92 | 2.5 | 0 | 0 | 0 | 0 | 294 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 02 RCC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Square Pipe (L) | Kgs | 0 | 26.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Full Moulding- DWB | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | DEV. Water Body | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Carpetch (L) | Kgs | 0 | 54 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding | R.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding | R.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Cladex (L) | Kgs | 0 | 450 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Plate (L) | Kgs | 0 | 26.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | SS Patti (L) | Mtrs | 0 | 126 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tile Adhesive (L) - Kgs | Kgs | 24.79 | 450 | 11155.5 | 2008 | 13163.5 | 2.5 | 0 | 0 | 0 | 0 | 24.79 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding | R.Ft | 239 | 125 | 29875 | 5377.5 | 35252.5 | 2.5 | 239 | 29875 | 5377.5 | 35252.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Fabrication work (L) | Kgs | 57.59 | 26.1 | 1503.1 | 270.56 | 1773.66 | 2.5 | 0 | 0 | 0 | 0 | 57.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | V Groove - AIE | R.Ft | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Fastner (L) - SOSB | No. | 352 | 67.5 | 23760 | 4276.8 | 28036.8 | 2.5 | 352 | 23760 | 4276.8 | 28036.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tile Adhesive (L) - Kgs | Kgs | 19.64 | 54 | 1060.56 | 190.9 | 1251.46 | 2.5 | 0 | 0 | 0 | 0 | 19.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Square Pipe (L) | Kgs | 1869 | 26.1 | 48780.9 | 8780.56 | 57561.46 | 2.5 | 1869 | 48780.9 | 8780.56 | 57561.46 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Painting Work | Sq.Ft | 2158.09 | 7.5 | 16185.68 | 2913.42 | 19099.1 | 2.5 | 2158.09 | 16185.68 | 2913.42 | 19099.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Cladex (L) | Kgs | 37 | 450 | 16650 | 2997 | 19647 | 2.5 | 37 | 16650 | 2997 | 19647 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding-(L) | Sq.Ft | 394 | 125 | 49250 | 8865 | 58115 | 2.5 | 394 | 49250 | 8865 | 58115 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Plate (L) | Kgs | 328.65 | 26.1 | 8577.77 | 1544 | 10121.77 | 2.5 | 328.65 | 8577.77 | 1544 | 10121.77 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 172 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tile Adhesive (L) - Kgs | Kgs | 19.72 | 270 | 5324.4 | 958.4 | 6282.8 | 2.5 | 0 | 0 | 0 | 0 | 19.72 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tile Adhesive | Kgs | 19.43 | 120 | 2331.6 | 419.68 | 2751.28 | 0 | 0 | 0 | 0 | 0 | 19.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding-(M) | Sq.Ft | 2.42 | 375 | 907.5 | 163.36 | 1070.86 | 0 | 0 | 0 | 0 | 0 | 2.42 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Cladex (M) | Kgs | 37 | 1000 | 37000 | 6660 | 43660 | 0 | 37 | 37000 | 6660 | 43660 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Plate (M) | Kgs | 328.65 | 58 | 19061.7 | 3431.1 | 22492.8 | 0 | 328.65 | 19061.7 | 3431.1 | 22492.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Carpetch (M) | Kgs | 35 | 120 | 4200 | 756 | 4956 | 0 | 35 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Fastner (M) - SOSB | No. | 352 | 150 | 52800 | 9504 | 62304 | 0 | 352 | 52800 | 9504 | 62304 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tile Adhesive | Kgs | 19.72 | 600 | 11832 | 2129.76 | 13961.76 | 0 | 0 | 0 | 0 | 0 | 19.72 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tile Adhesive | Kgs | 25 | 1000 | 25000 | 4500 | 29500 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Square Bar (M) | Mtrs | 294 | 280 | 82320 | 14817.6 | 97137.6 | 0 | 0 | 0 | 0 | 0 | 294 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 02 RCC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Fastner (M) - SOSB | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tinex (M) | Kgs | 30 | 600 | 18000 | 3240 | 21240 | 0 | 30 | 18000 | 3240 | 21240 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Plate (M) | Kgs | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Tinex (M) | Kgs | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Square Pipe (M) | Kgs | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding-(M) | Sq.Ft | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Cladex (M) | Kgs | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Italian Marble Cladding-(M) | Sq.Ft | 283 | 375 | 106125 | 19102.5 | 125227.5 | 0 | 283 | 106125 | 19102.5 | 125227.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | MS Square Pipe (M) | Kgs | 1869 | 58 | 108402 | 19512.36 | 127914.36 | 0 | 1869 | 108402 | 19512.36 | 127914.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | SS Clamp (M) | No. | 370 | 150 | 55500 | 9990 | 65490 | 0 | 370 | 55500 | 9990 | 65490 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Carpetch (M) | Kgs | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | SS Patti (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 1 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | SS Clamp (M) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 02 Sep 2022
EAST POINT MARKET | 173 | 0 | 15 Mar 2022 | NAGAUR STONES | KEP - Atrium Column cladding | Fabrication work (M) | Kgs | 56.59 | 58 | 3282.22 | 590.8 | 3873.02 | 0 | 0 | 0 | 0 | 0 | 56.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -40 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 115.61 | 28 | 3237.08 | 0 | 3237.08 | 2.5 | 108.8214 | 3047 | 0 | 3047 | 6.7886 | 190.08 |  | 94.128 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -04 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.28 | 28 | 791.84 | 0 | 791.84 | 2.5 | 28.28 | 791.84 | 0 | 791.84 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -63 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.5 | 28 | 994 | 0 | 994 | 2.5 | 33.1429 | 928 | 0 | 928 | 2.3571 | 66 |  | 93.3603 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling Granite Flooring | Granite Flooring | Sq.Ft | 149.62 | 55 | 8229.1 | 0 | 8229.1 | 2.5 | 0 | 0 | 0 | 0 | 149.62 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -64 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 177.82 | 28 | 4978.96 | 0 | 4978.96 | 2.5 | 158.4643 | 4437 | 0 | 4437 | 19.3557 | 541.96 |  | 89.115 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -28 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 42.95 | 28 | 1202.6 | 0 | 1202.6 | 2.5 | 0 | 0 | 0 | 0 | 42.95 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -15 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 32.74 | 28 | 916.72 | 0 | 916.72 | 2.5 | 32.74 | 916.72 | 0 | 916.72 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -29 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 101.61 | 28 | 2845.08 | 0 | 2845.08 | 2.5 | 101.61 | 2845.08 | 0 | 2845.08 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Wash Basin Counter-AIE | No. | 0 | 4000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -21 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.7 | 28 | 1111.6 | 0 | 1111.6 | 2.5 | 39.7 | 1111.6 | 0 | 1111.6 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -14 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.59 | 28 | 828.52 | 0 | 828.52 | 2.5 | 29.59 | 828.52 | 0 | 828.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -69 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 38.09 | 28 | 1066.52 | 0 | 1066.52 | 2.5 | 38.09 | 1066.52 | 0 | 1066.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Shelf. | No. | 0 | 12000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | 11 TILING WORK | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -24 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 53.12 | 28 | 1487.36 | 0 | 1487.36 | 2.5 | 0 | 0 | 0 | 0 | 53.12 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -40 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.24 | 28 | 986.72 | 0 | 986.72 | 2.5 | 21.8929 | 613 | 0 | 613 | 13.3471 | 373.72 |  | 62.1251 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Patti | R.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -01 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 80.22 | 28 | 2246.16 | 0 | 2246.16 | 2.5 | 80 | 2240 | 0 | 2240 | 0.22 | 6.16 |  | 99.7258 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -55 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 101.72 | 28 | 2848.16 | 0 | 2848.16 | 2.5 | 21.2857 | 596 | 0 | 596 | 80.4343 | 2252.16 |  | 20.9258 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -42 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 33.33 | 28 | 933.24 | 0 | 933.24 | 2.5 | 33.3214 | 933 | 0 | 933 | 0.0086 | 0.24 |  | 99.9742 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -101 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 102.26 | 28 | 2863.28 | 0 | 2863.28 | 2.5 | 0 | 0 | 0 | 0 | 102.26 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -21 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 178.25 | 28 | 4991 | 0 | 4991 | 2.5 | 178.25 | 4991 | 0 | 4991 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -48 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 108.39 | 28 | 3034.92 | 0 | 3034.92 | 2.5 | 0 | 0 | 0 | 0 | 108.39 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Vitrified Flooring 2ftx2ft-BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Flooring | Sq.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Wash Basin Counter-AIE | No. | 6 | 4000 | 24000 | 0 | 24000 | 2.5 | 6 | 24000 | 0 | 24000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | V Groove making- BC | R.Ft | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -63 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 107.21 | 28 | 3001.88 | 0 | 3001.88 | 2.5 | 95.3571 | 2670 | 0 | 2670 | 11.8529 | 331.88 |  | 88.9442 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -31 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 54.57 | 28 | 1527.96 | 0 | 1527.96 | 2.5 | 54.57 | 1527.96 | 0 | 1527.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -27 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 49.28 | 28 | 1379.84 | 0 | 1379.84 | 2.5 | 0 | 0 | 0 | 0 | 49.28 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -79 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.34 | 28 | 1101.52 | 0 | 1101.52 | 2.5 | 38.4643 | 1077 | 0 | 1077 | 0.8757 | 24.52 |  | 97.774 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Dado Work - Dld | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | DEV. Landscape/Equipment | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-4th Community Hall&Society Office Vitrified Tile Floorin | Vitrified Flooring -BC | Sq.Ft | 60.56 | 28 | 1695.68 | 0 | 1695.68 | 2.5 | 60.56 | 1695.68 | 0 | 1695.68 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -61 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.11 | 28 | 1095.08 | 0 | 1095.08 | 2.5 | 39.11 | 1095.08 | 0 | 1095.08 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -09 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 103.12 | 28 | 2887.36 | 0 | 2887.36 | 2.5 | 103.12 | 2887.36 | 0 | 2887.36 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -61 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 113.34 | 28 | 3173.52 | 0 | 3173.52 | 2.5 | 113.34 | 3173.52 | 0 | 3173.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 3 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Dish Washer Area Work - 1 No. | Departmental Labour - SO | No. | 50 | 2200 | 110000 | 0 | 110000 | 2.5 | 50 | 110000 | 0 | 110000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -35 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 52.76 | 28 | 1477.28 | 0 | 1477.28 | 2.5 | 0 | 0 | 0 | 0 | 52.76 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -86 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 46.69 | 28 | 1307.32 | 0 | 1307.32 | 2.5 | 46.69 | 1307.32 | 0 | 1307.32 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -05 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 32.32 | 28 | 904.96 | 0 | 904.96 | 2.5 | 29.9643 | 839 | 0 | 839 | 2.3557 | 65.96 |  | 92.7113 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -25 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 61.09 | 28 | 1710.52 | 0 | 1710.52 | 2.5 | 0 | 0 | 0 | 0 | 61.09 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -95 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 24.61 | 28 | 689.08 | 0 | 689.08 | 2.5 | 6 | 168 | 0 | 168 | 18.61 | 521.08 |  | 24.3803 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -50 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.42 | 28 | 963.76 | 0 | 963.76 | 2.5 | 27.7143 | 776 | 0 | 776 | 6.7057 | 187.76 |  | 80.518 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -114 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 44.29 | 28 | 1240.12 | 0 | 1240.12 | 2.5 | 44.29 | 1240.12 | 0 | 1240.12 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -116 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 27.82 | 28 | 778.96 | 0 | 778.96 | 2.5 | 27.82 | 778.96 | 0 | 778.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -45 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.45 | 28 | 964.6 | 0 | 964.6 | 2.5 | 0 | 0 | 0 | 0 | 34.45 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -106 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 26.15 | 28 | 732.2 | 0 | 732.2 | 2.5 | 26.15 | 732.2 | 0 | 732.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -76 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 15.36 | 28 | 430.08 | 0 | 430.08 | 2.5 | 15.36 | 430.08 | 0 | 430.08 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -44 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.43 | 28 | 992.04 | 0 | 992.04 | 2.5 | 0 | 0 | 0 | 0 | 35.43 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -103 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 25.3 | 28 | 708.4 | 0 | 708.4 | 2.5 | 0 | 0 | 0 | 0 | 25.3 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -80 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.9 | 28 | 1117.2 | 0 | 1117.2 | 2.5 | 39.9 | 1117.2 | 0 | 1117.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -12 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 132.29 | 28 | 3704.12 | 0 | 3704.12 | 2.5 | 132.29 | 3704.12 | 0 | 3704.12 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -45 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 99.35 | 28 | 2781.8 | 0 | 2781.8 | 2.5 | 0 | 0 | 0 | 0 | 99.35 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -68 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 132.72 | 28 | 3716.16 | 0 | 3716.16 | 2.5 | 115.3929 | 3231 | 0 | 3231 | 17.3271 | 485.16 |  | 86.9446 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -58 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.47 | 28 | 993.16 | 0 | 993.16 | 2.5 | 35.47 | 993.16 | 0 | 993.16 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -74 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 22.51 | 28 | 630.28 | 0 | 630.28 | 2.5 | 22.51 | 630.28 | 0 | 630.28 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -75 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 26.44 | 28 | 740.32 | 0 | 740.32 | 2.5 | 26.44 | 740.32 | 0 | 740.32 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -62 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.7 | 28 | 1111.6 | 0 | 1111.6 | 2.5 | 32.7143 | 916 | 0 | 916 | 6.9857 | 195.6 |  | 82.4038 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -08 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 146.5 | 28 | 4102 | 0 | 4102 | 2.5 | 136.8929 | 3833 | 0 | 3833 | 9.6071 | 269 |  | 93.4423 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -112 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 83.96 | 28 | 2350.88 | 0 | 2350.88 | 2.5 | 83.9599 | 2350.88 | 0 | 2350.88 | 0.0001 | 0 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -102 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 59.74 | 28 | 1672.72 | 0 | 1672.72 | 2.5 | 0 | 0 | 0 | 0 | 59.74 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -96 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 110.55 | 28 | 3095.4 | 0 | 3095.4 | 2.5 | 0 | 0 | 0 | 0 | 110.55 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -05 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 116.14 | 28 | 3251.92 | 0 | 3251.92 | 2.5 | 116.14 | 3251.92 | 0 | 3251.92 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -53 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 36.65 | 28 | 1026.2 | 0 | 1026.2 | 2.5 | 18.3571 | 514 | 0 | 514 | 18.2929 | 512.2 |  | 50.0876 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -98 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 24.21 | 28 | 677.88 | 0 | 677.88 | 2.5 | 0 | 0 | 0 | 0 | 24.21 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -85 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 47.28 | 28 | 1323.84 | 0 | 1323.84 | 2.5 | 47.28 | 1323.84 | 0 | 1323.84 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -53 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 109.9 | 28 | 3077.2 | 0 | 3077.2 | 2.5 | 0 | 0 | 0 | 0 | 109.9 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -66 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 216.79 | 28 | 6070.12 | 0 | 6070.12 | 2.5 | 194.8571 | 5456 | 0 | 5456 | 21.9329 | 614.12 |  | 89.8829 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -29 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.63 | 28 | 997.64 | 0 | 997.64 | 2.5 | 35.63 | 997.64 | 0 | 997.64 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -71 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 36.09 | 28 | 1010.52 | 0 | 1010.52 | 2.5 | 36.09 | 1010.52 | 0 | 1010.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -84 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 30.09 | 28 | 842.52 | 0 | 842.52 | 2.5 | 30.09 | 842.52 | 0 | 842.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-1st Fl Flooring&Tiling Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 104.5 | 28 | 2926 | 0 | 2926 | 2.5 | 104.5 | 2926 | 0 | 2926 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Door Frame -BRE - | R.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Rework/Extrawork | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-1st Fl Flooring&Tiling Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 0 | 28 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 16 Mar 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -27 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 173.84 | 28 | 4867.52 | 0 | 4867.52 | 2.5 | 0 | 0 | 0 | 0 | 173.84 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Edge Polish - Dld | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | DEV. Landscape/Equipment | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -51 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.52 | 28 | 966.56 | 0 | 966.56 | 2.5 | 0 | 0 | 0 | 0 | 34.52 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-4th Fl Flooring&Tiling Sadhrali Granite (Border) | Granite Border Fixing- | R.Ft | 50.25 | 55 | 2763.75 | 0 | 2763.75 | 2.5 | 50.25 | 2763.75 | 0 | 2763.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -41 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 115.82 | 28 | 3242.96 | 0 | 3242.96 | 2.5 | 100.9643 | 2827 | 0 | 2827 | 14.8557 | 415.96 |  | 87.1735 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -108 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 170.82 | 28 | 4782.96 | 0 | 4782.96 | 2.5 | 170.82 | 4782.96 | 0 | 4782.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -34 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 64.14 | 28 | 1795.92 | 0 | 1795.92 | 2.5 | 0 | 0 | 0 | 0 | 64.14 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -41 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.43 | 28 | 992.04 | 0 | 992.04 | 2.5 | 34.6429 | 970 | 0 | 970 | 0.7871 | 22.04 |  | 97.7784 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -22 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 45.15 | 28 | 1264.2 | 0 | 1264.2 | 2.5 | 45.15 | 1264.2 | 0 | 1264.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -43 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.6 | 28 | 1108.8 | 0 | 1108.8 | 2.5 | 0 | 0 | 0 | 0 | 39.6 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -65 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 121.85 | 28 | 3411.8 | 0 | 3411.8 | 2.5 | 105.3214 | 2949 | 0 | 2949 | 16.5286 | 462.8 |  | 86.4353 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -92 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 116.57 | 28 | 3263.96 | 0 | 3263.96 | 2.5 | 0 | 0 | 0 | 0 | 116.57 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -69 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 125.29 | 28 | 3508.12 | 0 | 3508.12 | 2.5 | 125.29 | 3508.12 | 0 | 3508.12 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -37 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 133.47 | 28 | 3737.16 | 0 | 3737.16 | 2.5 | 0 | 0 | 0 | 0 | 133.47 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -60 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 87.08 | 28 | 2438.24 | 0 | 2438.24 | 2.5 | 87.08 | 2438.24 | 0 | 2438.24 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -101 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.63 | 28 | 997.64 | 0 | 997.64 | 2.5 | 0 | 0 | 0 | 0 | 35.63 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Shelf. | No. | 1 | 12000 | 12000 | 0 | 12000 | 2.5 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -77 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 73.3 | 28 | 2052.4 | 0 | 2052.4 | 2.5 | 73.3 | 2052.4 | 0 | 2052.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -26 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 64.41 | 28 | 1803.48 | 0 | 1803.48 | 2.5 | 0 | 0 | 0 | 0 | 64.41 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -100 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 24.44 | 28 | 684.32 | 0 | 684.32 | 2.5 | 0 | 0 | 0 | 0 | 24.44 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -93 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 116.47 | 28 | 3261.16 | 0 | 3261.16 | 2.5 | 0 | 0 | 0 | 0 | 116.47 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -111 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.87 | 28 | 808.36 | 0 | 808.36 | 2.5 | 28.87 | 808.36 | 0 | 808.36 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -47 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 119.7 | 28 | 3351.6 | 0 | 3351.6 | 2.5 | 0 | 0 | 0 | 0 | 119.7 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -14 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 123.03 | 28 | 3444.84 | 0 | 3444.84 | 2.5 | 123.03 | 3444.84 | 0 | 3444.84 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -39 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 74.7 | 28 | 2091.6 | 0 | 2091.6 | 2.5 | 69 | 1932 | 0 | 1932 | 5.7 | 159.6 |  | 92.3695 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP Basement Flooring Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 632.5 | 28 | 17710 | 0 | 17710 | 2.5 | 632.5 | 17710 | 0 | 17710 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -15 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 113.78 | 28 | 3185.84 | 0 | 3185.84 | 2.5 | 113.78 | 3185.84 | 0 | 3185.84 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -51 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 97.52 | 28 | 2730.56 | 0 | 2730.56 | 2.5 | 0 | 0 | 0 | 0 | 97.52 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -89 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 113.56 | 28 | 3179.68 | 0 | 3179.68 | 2.5 | 0 | 0 | 0 | 0 | 113.56 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP Basement Flooring Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 825.75 | 28 | 23121 | 0 | 23121 | 2.5 | 0 | 0 | 0 | 0 | 825.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -87 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.76 | 28 | 833.28 | 0 | 833.28 | 2.5 | 0 | 0 | 0 | 0 | 29.76 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -23 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 268.35 | 28 | 7513.8 | 0 | 7513.8 | 2.5 | 268.35 | 7513.8 | 0 | 7513.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -100 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 124.54 | 28 | 3487.12 | 0 | 3487.12 | 2.5 | 0 | 0 | 0 | 0 | 124.54 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -39 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.77 | 28 | 805.56 | 0 | 805.56 | 2.5 | 28.2143 | 790 | 0 | 790 | 0.5557 | 15.56 |  | 98.0685 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -06 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.64 | 28 | 801.92 | 0 | 801.92 | 2.5 | 28.5714 | 800 | 0 | 800 | 0.0686 | 1.92 |  | 99.7605 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -48 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.11 | 28 | 983.08 | 0 | 983.08 | 2.5 | 31.4286 | 880 | 0 | 880 | 3.6814 | 103.08 |  | 89.5147 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -09 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 27.4 | 28 | 767.2 | 0 | 767.2 | 2.5 | 27.4 | 767.2 | 0 | 767.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -52 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.61 | 28 | 969.08 | 0 | 969.08 | 2.5 | 27.1786 | 761 | 0 | 761 | 7.4314 | 208.08 |  | 78.5282 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -59 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.79 | 28 | 834.12 | 0 | 834.12 | 2.5 | 29.79 | 834.12 | 0 | 834.12 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -76 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 50.7 | 28 | 1419.6 | 0 | 1419.6 | 2.5 | 50.7 | 1419.6 | 0 | 1419.6 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 3 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Dish Washer Area Work - 1 No. | Dado Work - BC | Sq.Ft | 318.2 | 25 | 7955 | 0 | 7955 | 2.5 | 253.1585 | 6328.96 | 0 | 6328.96 | 65.0415 | 1626.04 |  | 79.5596 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -73 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 56.27 | 28 | 1575.56 | 0 | 1575.56 | 2.5 | 56.27 | 1575.56 | 0 | 1575.56 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -31 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 23.52 | 28 | 658.56 | 0 | 658.56 | 2.5 | 23.52 | 658.56 | 0 | 658.56 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -115 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 43.15 | 28 | 1208.2 | 0 | 1208.2 | 2.5 | 43.1496 | 1208.19 | 0 | 1208.19 | 0.0004 | 0.01 |  | 99.9991 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -116 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 71.47 | 28 | 2001.16 | 0 | 2001.16 | 2.5 | 71.47 | 2001.16 | 0 | 2001.16 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -58 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 132.07 | 28 | 3697.96 | 0 | 3697.96 | 2.5 | 132.07 | 3697.96 | 0 | 3697.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -26 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 265.12 | 28 | 7423.36 | 0 | 7423.36 | 2.5 | 0 | 0 | 0 | 0 | 265.12 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -103 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 54.68 | 28 | 1531.04 | 0 | 1531.04 | 2.5 | 0 | 0 | 0 | 0 | 54.68 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Edge Polish - Dld | R.Ft | 947.59 | 10 | 9475.9 | 0 | 9475.9 | 2.5 | 947.59 | 9475.9 | 0 | 9475.9 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -72 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 137.99 | 28 | 3863.72 | 0 | 3863.72 | 2.5 | 137.99 | 3863.72 | 0 | 3863.72 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -104 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 59.31 | 28 | 1660.68 | 0 | 1660.68 | 2.5 | 0 | 0 | 0 | 0 | 59.31 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -49 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 103.23 | 28 | 2890.44 | 0 | 2890.44 | 2.5 | 0 | 0 | 0 | 0 | 103.23 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -82 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.54 | 28 | 799.12 | 0 | 799.12 | 2.5 | 28.54 | 799.12 | 0 | 799.12 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -111 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 90.42 | 28 | 2531.76 | 0 | 2531.76 | 2.5 | 90.42 | 2531.76 | 0 | 2531.76 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -08 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 30.78 | 28 | 861.84 | 0 | 861.84 | 2.5 | 27.1071 | 759 | 0 | 759 | 3.6729 | 102.84 |  | 88.0673 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -83 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 31.07 | 28 | 869.96 | 0 | 869.96 | 2.5 | 31.07 | 869.96 | 0 | 869.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -50 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 99.03 | 28 | 2772.84 | 0 | 2772.84 | 2.5 | 0 | 0 | 0 | 0 | 99.03 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -60 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 31.3 | 28 | 876.4 | 0 | 876.4 | 2.5 | 31.3 | 876.4 | 0 | 876.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -96 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 36.35 | 28 | 1017.8 | 0 | 1017.8 | 2.5 | 36.35 | 1017.8 | 0 | 1017.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -108 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 45.31 | 28 | 1268.68 | 0 | 1268.68 | 2.5 | 45.31 | 1268.68 | 0 | 1268.68 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -117 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 25.17 | 28 | 704.76 | 0 | 704.76 | 2.5 | 25.17 | 704.76 | 0 | 704.76 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 3 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Dish Washer Area Work - 1 No. | Granite work Lumpsum | No. | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -07 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 248.64 | 28 | 6961.92 | 0 | 6961.92 | 2.5 | 248.6071 | 6961 | 0 | 6961 | 0.0329 | 0.92 |  | 99.9868 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -75 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 41.44 | 28 | 1160.32 | 0 | 1160.32 | 2.5 | 41.44 | 1160.32 | 0 | 1160.32 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -59 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 69.86 | 28 | 1956.08 | 0 | 1956.08 | 2.5 | 69.86 | 1956.08 | 0 | 1956.08 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -107 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 75.78 | 28 | 2121.84 | 0 | 2121.84 | 2.5 | 75.78 | 2121.84 | 0 | 2121.84 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -52 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 99.14 | 28 | 2775.92 | 0 | 2775.92 | 2.5 | 0 | 0 | 0 | 0 | 99.14 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -36 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 150.05 | 28 | 4201.4 | 0 | 4201.4 | 2.5 | 0 | 0 | 0 | 0 | 150.05 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -23 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 49.05 | 28 | 1373.4 | 0 | 1373.4 | 2.5 | 49.05 | 1373.4 | 0 | 1373.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling Granite Flooring | Granite Flooring | Sq.Ft | 1905.58 | 55 | 104806.9 | 0 | 104806.9 | 2.5 | 1905.5781 | 104806.8 | 0 | 104806.8 | 0.0019 | 0.1 |  | 99.9999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Champher Polish (L) | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | B.C. Building Common Items | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -12 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.59 | 28 | 828.52 | 0 | 828.52 | 2.5 | 29.59 | 828.52 | 0 | 828.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -55 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.81 | 28 | 974.68 | 0 | 974.68 | 2.5 | 14.7857 | 414 | 0 | 414 | 20.0243 | 560.68 |  | 42.4754 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -113 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 82.34 | 28 | 2305.52 | 0 | 2305.52 | 2.5 | 82.34 | 2305.52 | 0 | 2305.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -72 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 38.32 | 28 | 1072.96 | 0 | 1072.96 | 2.5 | 38.32 | 1072.96 | 0 | 1072.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -07 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.68 | 28 | 971.04 | 0 | 971.04 | 2.5 | 34.6071 | 969 | 0 | 969 | 0.0729 | 2.04 |  | 99.7898 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -11 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 101.18 | 28 | 2833.04 | 0 | 2833.04 | 2.5 | 101.18 | 2833.04 | 0 | 2833.04 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -32 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 89.88 | 28 | 2516.64 | 0 | 2516.64 | 2.5 | 89.88 | 2516.64 | 0 | 2516.64 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-1st Fl Flooring&Tiling Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 876.75 | 28 | 24549 | 0 | 24549 | 2.5 | 876.75 | 24549 | 0 | 24549 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -114 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 174.81 | 28 | 4894.68 | 0 | 4894.68 | 2.5 | 174.81 | 4894.68 | 0 | 4894.68 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -34 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 193.11 | 28 | 5407.08 | 0 | 5407.08 | 2.5 | 0 | 0 | 0 | 0 | 193.11 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP Basement Flooring Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 190 | 28 | 5320 | 0 | 5320 | 2.5 | 190 | 5320 | 0 | 5320 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -70 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 38.45 | 28 | 1076.6 | 0 | 1076.6 | 2.5 | 38.4286 | 1076 | 0 | 1076 | 0.0214 | 0.6 |  | 99.9443 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Dado Work - Dld | Sq.Ft | 1213.94 | 75 | 91045.5 | 0 | 91045.5 | 2.5 | 1213.94 | 91045.5 | 0 | 91045.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -67 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 43.81 | 28 | 1226.68 | 0 | 1226.68 | 2.5 | 39.7143 | 1112 | 0 | 1112 | 4.0957 | 114.68 |  | 90.6512 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -02 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 73.75 | 28 | 2065 | 0 | 2065 | 2.5 | 69.5357 | 1947 | 0 | 1947 | 4.2143 | 118 |  | 94.2857 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Patti Fixing 6" | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | 11 TILING WORK | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -78 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 69.1 | 28 | 1934.8 | 0 | 1934.8 | 2.5 | 69.1 | 1934.8 | 0 | 1934.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -49 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 34.68 | 28 | 971.04 | 0 | 971.04 | 2.5 | 30.6071 | 857 | 0 | 857 | 4.0729 | 114.04 |  | 88.2558 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -105 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 77.18 | 28 | 2161.04 | 0 | 2161.04 | 2.5 | 77 | 2156 | 0 | 2156 | 0.18 | 5.04 |  | 99.7668 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -82 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 77.39 | 28 | 2166.92 | 0 | 2166.92 | 2.5 | 77.39 | 2166.92 | 0 | 2166.92 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -85 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 185.68 | 28 | 5199.04 | 0 | 5199.04 | 2.5 | 185.68 | 5199.04 | 0 | 5199.04 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -81 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29 | 28 | 812 | 0 | 812 | 2.5 | 29 | 812 | 0 | 812 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -113 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.05 | 28 | 785.4 | 0 | 785.4 | 2.5 | 28.05 | 785.4 | 0 | 785.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -56 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 40.32 | 28 | 1128.96 | 0 | 1128.96 | 2.5 | 11.3214 | 317 | 0 | 317 | 28.9986 | 811.96 |  | 28.0789 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -112 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.51 | 28 | 798.28 | 0 | 798.28 | 2.5 | 28.51 | 798.28 | 0 | 798.28 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -90 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 100.11 | 28 | 2803.08 | 0 | 2803.08 | 2.5 | 0 | 0 | 0 | 0 | 100.11 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -28 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 183.53 | 28 | 5138.84 | 0 | 5138.84 | 2.5 | 0 | 0 | 0 | 0 | 183.53 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -35 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 241.44 | 28 | 6760.32 | 0 | 6760.32 | 2.5 | 0 | 0 | 0 | 0 | 241.44 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -57 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 31.6 | 28 | 884.8 | 0 | 884.8 | 2.5 | 31.6 | 884.8 | 0 | 884.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -105 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.74 | 28 | 804.72 | 0 | 804.72 | 2.5 | 28 | 784 | 0 | 784 | 0.74 | 20.72 |  | 97.4252 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | V Groove making- BC | R.Ft | 385.728 | 40 | 15429.12 | 0 | 15429.12 | 2.5 | 385.7241 | 15428.96 | 0 | 15428.96 | 0.0039 | 0.16 |  | 99.999 |  | Dushant Gore | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -36 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 47.97 | 28 | 1343.16 | 0 | 1343.16 | 2.5 | 0 | 0 | 0 | 0 | 47.97 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -70 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 124.54 | 28 | 3487.12 | 0 | 3487.12 | 2.5 | 107 | 2996 | 0 | 2996 | 17.54 | 491.12 |  | 85.9162 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Door Frame -BRE - | R.Ft | 79.83 | 60 | 4789.8 | 0 | 4789.8 | 2.5 | 79.83 | 4789.8 | 0 | 4789.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -56 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 115.61 | 28 | 3237.08 | 0 | 3237.08 | 2.5 | 115.6071 | 3237 | 0 | 3237 | 0.0029 | 0.08 |  | 99.9975 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -91 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 67.06 | 28 | 1877.68 | 0 | 1877.68 | 2.5 | 0 | 0 | 0 | 0 | 67.06 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -94 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 64.91 | 28 | 1817.48 | 0 | 1817.48 | 2.5 | 0 | 0 | 0 | 0 | 64.91 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -110 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 85.57 | 28 | 2395.96 | 0 | 2395.96 | 2.5 | 85.5614 | 2395.72 | 0 | 2395.72 | 0.0086 | 0.24 |  | 99.9899 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Patti Fixing 6" | R.Ft | 132.78 | 22 | 2921.16 | 0 | 2921.16 | 2.5 | 132.78 | 2921.16 | 0 | 2921.16 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Flooring | Sq.Ft | 112.211 | 50 | 5610.55 | 0 | 5610.55 | 2.5 | 112.211 | 5610.55 | 0 | 5610.55 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -91 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 26.15 | 28 | 732.2 | 0 | 732.2 | 2.5 | 0 | 0 | 0 | 0 | 26.15 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -10 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 25.2 | 28 | 705.6 | 0 | 705.6 | 2.5 | 25.2 | 705.6 | 0 | 705.6 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -30 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 32.02 | 28 | 896.56 | 0 | 896.56 | 2.5 | 32.02 | 896.56 | 0 | 896.56 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -74 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 46.5 | 28 | 1302 | 0 | 1302 | 2.5 | 46.5 | 1302 | 0 | 1302 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -71 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 129.6 | 28 | 3628.8 | 0 | 3628.8 | 2.5 | 129.6 | 3628.8 | 0 | 3628.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -43 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 136.27 | 28 | 3815.56 | 0 | 3815.56 | 2.5 | 0 | 0 | 0 | 0 | 136.27 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -30 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 76.32 | 28 | 2136.96 | 0 | 2136.96 | 2.5 | 76.32 | 2136.96 | 0 | 2136.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -97 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 91.06 | 28 | 2549.68 | 0 | 2549.68 | 2.5 | 0 | 0 | 0 | 0 | 91.06 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -13 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 131 | 28 | 3668 | 0 | 3668 | 2.5 | 131 | 3668 | 0 | 3668 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -57 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 89.02 | 28 | 2492.56 | 0 | 2492.56 | 2.5 | 89 | 2492 | 0 | 2492 | 0.02 | 0.56 |  | 99.9775 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -11 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 25.39 | 28 | 710.92 | 0 | 710.92 | 2.5 | 25.39 | 710.92 | 0 | 710.92 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -102 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 24.05 | 28 | 673.4 | 0 | 673.4 | 2.5 | 0 | 0 | 0 | 0 | 24.05 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -78 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 27.23 | 28 | 762.44 | 0 | 762.44 | 2.5 | 27.23 | 762.44 | 0 | 762.44 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -88 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 27.79 | 28 | 778.12 | 0 | 778.12 | 2.5 | 0 | 0 | 0 | 0 | 27.79 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 3 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Dish Washer Area Work - 1 No. | Granite Work | No. | 26 | 2000 | 52000 | 0 | 52000 | 2.5 | 16 | 32000 | 0 | 32000 | 10 | 20000 |  | 61.5385 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -22 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 260.6 | 28 | 7296.8 | 0 | 7296.8 | 2.5 | 260.6 | 7296.8 | 0 | 7296.8 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -44 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 109.36 | 28 | 3062.08 | 0 | 3062.08 | 2.5 | 0 | 0 | 0 | 0 | 109.36 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -13 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.59 | 28 | 828.52 | 0 | 828.52 | 2.5 | 29.59 | 828.52 | 0 | 828.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -65 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 37.08 | 28 | 1038.24 | 0 | 1038.24 | 2.5 | 33.5357 | 939 | 0 | 939 | 3.5443 | 99.24 |  | 90.4415 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Patti | R.Ft | 448.99 | 30 | 13469.7 | 0 | 13469.7 | 2.5 | 448.99 | 13469.7 | 0 | 13469.7 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -73 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 190.63 | 28 | 5337.64 | 0 | 5337.64 | 2.5 | 190.63 | 5337.64 | 0 | 5337.64 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -46 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 83.96 | 28 | 2350.88 | 0 | 2350.88 | 2.5 | 0 | 0 | 0 | 0 | 83.96 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -117 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 69.97 | 28 | 1959.16 | 0 | 1959.16 | 2.5 | 69.97 | 1959.16 | 0 | 1959.16 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -10 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 106.67 | 28 | 2986.76 | 0 | 2986.76 | 2.5 | 106.67 | 2986.76 | 0 | 2986.76 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -99 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 26.64 | 28 | 745.92 | 0 | 745.92 | 2.5 | 0 | 0 | 0 | 0 | 26.64 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -115 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 160.49 | 28 | 4493.72 | 0 | 4493.72 | 2.5 | 160.4898 | 4493.71 | 0 | 4493.71 | 0.0002 | 0.01 |  | 99.9999 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -38 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 30.61 | 28 | 857.08 | 0 | 857.08 | 2.5 | 30.5357 | 855 | 0 | 855 | 0.0743 | 2.08 |  | 99.7573 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -94 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 27.43 | 28 | 768.04 | 0 | 768.04 | 2.5 | 0 | 0 | 0 | 0 | 27.43 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -20 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.7 | 28 | 1111.6 | 0 | 1111.6 | 2.5 | 39.7 | 1111.6 | 0 | 1111.6 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -87 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 93.22 | 28 | 2610.16 | 0 | 2610.16 | 2.5 | 93.22 | 2610.16 | 0 | 2610.16 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -54 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 99.14 | 28 | 2775.92 | 0 | 2775.92 | 2.5 | 14 | 392 | 0 | 392 | 85.14 | 2383.92 |  | 14.1214 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -62 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 119.05 | 28 | 3333.4 | 0 | 3333.4 | 2.5 | 119.0357 | 3333 | 0 | 3333 | 0.0143 | 0.4 |  | 99.988 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling Granite Skirting | Granite Skirting | R.Ft | 405.5 | 55 | 22302.5 | 0 | 22302.5 | 2.5 | 405.5 | 22302.5 | 0 | 22302.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling Granite Skirting | Granite Skirting | R.Ft | 50.167 | 55 | 2759.19 | 0 | 2759.19 | 2.5 | 0 | 0 | 0 | 0 | 50.167 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -81 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 81.81 | 28 | 2290.68 | 0 | 2290.68 | 2.5 | 81.81 | 2290.68 | 0 | 2290.68 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -88 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 83.85 | 28 | 2347.8 | 0 | 2347.8 | 2.5 | 83.8416 | 2347.56 | 0 | 2347.56 | 0.0084 | 0.24 |  | 99.99 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -01 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 27.63 | 28 | 773.64 | 0 | 773.64 | 2.5 | 26.5357 | 743 | 0 | 743 | 1.0943 | 30.64 |  | 96.0394 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -89 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 43.21 | 28 | 1209.88 | 0 | 1209.88 | 2.5 | 20.8929 | 585 | 0 | 585 | 22.3171 | 624.88 |  | 48.352 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Granite Champher Polish (L) | R.Ft | 700.61 | 20 | 14012.2 | 0 | 14012.2 | 2.5 | 700.61 | 14012.2 | 0 | 14012.2 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -95 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 65.01 | 28 | 1820.28 | 0 | 1820.28 | 2.5 | 24 | 672 | 0 | 672 | 41.01 | 1148.28 |  | 36.9174 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 103 | 28 | 2884 | 0 | 2884 | 2.5 | 103 | 2884 | 0 | 2884 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-4th Community Hall&Society Office Dado | Dado BC | Sq.Ft | 287.87 | 25 | 7196.75 | 0 | 7196.75 | 2.5 | 287.87 | 7196.75 | 0 | 7196.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -38 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 78.25 | 28 | 2191 | 0 | 2191 | 2.5 | 68.4286 | 1916 | 0 | 1916 | 9.8214 | 275 |  | 87.4487 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -77 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 26.71 | 28 | 747.88 | 0 | 747.88 | 2.5 | 26.71 | 747.88 | 0 | 747.88 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -02 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.3 | 28 | 820.4 | 0 | 820.4 | 2.5 | 28 | 784 | 0 | 784 | 1.3 | 36.4 |  | 95.5631 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -54 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.89 | 28 | 1004.92 | 0 | 1004.92 | 2.5 | 25.8929 | 725 | 0 | 725 | 9.9971 | 279.92 |  | 72.1452 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -67 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 14.5 | 28 | 406 | 0 | 406 | 2.5 | 14.4286 | 404 | 0 | 404 | 0.0714 | 2 |  | 99.5076 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -66 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 44.33 | 28 | 1241.24 | 0 | 1241.24 | 2.5 | 36.2143 | 1014 | 0 | 1014 | 8.1157 | 227.24 |  | 81.6925 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP Basement Flooring Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 231.5 | 28 | 6482 | 0 | 6482 | 2.5 | 0 | 0 | 0 | 0 | 231.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -84 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 93.97 | 28 | 2631.16 | 0 | 2631.16 | 2.5 | 93.97 | 2631.16 | 0 | 2631.16 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 1 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | Ground floor Toilet Flooring & Dado | Vitrified Flooring 2ftx2ft-BC | Sq.Ft | 396.48 | 22 | 8722.56 | 0 | 8722.56 | 2.5 | 396.48 | 8722.56 | 0 | 8722.56 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -107 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.32 | 28 | 792.96 | 0 | 792.96 | 2.5 | 28.32 | 792.96 | 0 | 792.96 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -83 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 104.41 | 28 | 2923.48 | 0 | 2923.48 | 2.5 | 104.41 | 2923.48 | 0 | 2923.48 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -37 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 45.51 | 28 | 1274.28 | 0 | 1274.28 | 2.5 | 0 | 0 | 0 | 0 | 45.51 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -86 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 174.27 | 28 | 4879.56 | 0 | 4879.56 | 2.5 | 174.27 | 4879.56 | 0 | 4879.56 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -98 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 50.59 | 28 | 1416.52 | 0 | 1416.52 | 2.5 | 8 | 224 | 0 | 224 | 42.59 | 1192.52 |  | 15.8134 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -79 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 140.25 | 28 | 3927 | 0 | 3927 | 2.5 | 132.1786 | 3701 | 0 | 3701 | 8.0714 | 226 |  | 94.245 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -93 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 41.05 | 28 | 1149.4 | 0 | 1149.4 | 2.5 | 41.0357 | 1149 | 0 | 1149 | 0.0143 | 0.4 |  | 99.9652 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -109 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 46.16 | 28 | 1292.48 | 0 | 1292.48 | 2.5 | 46.16 | 1292.48 | 0 | 1292.48 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 493.75 | 28 | 13825 | 0 | 13825 | 2.5 | 493.75 | 13825 | 0 | 13825 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -106 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 77.18 | 28 | 2161.04 | 0 | 2161.04 | 2.5 | 77.18 | 2161.04 | 0 | 2161.04 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -03 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 73.2 | 28 | 2049.6 | 0 | 2049.6 | 2.5 | 67.1786 | 1881 | 0 | 1881 | 6.0214 | 168.6 |  | 91.774 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -06 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 188.15 | 28 | 5268.2 | 0 | 5268.2 | 2.5 | 181.1071 | 5071 | 0 | 5071 | 7.0429 | 197.2 |  | 96.2568 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -46 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 33.3 | 28 | 932.4 | 0 | 932.4 | 2.5 | 33.2857 | 932 | 0 | 932 | 0.0143 | 0.4 |  | 99.9571 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -92 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.31 | 28 | 1100.68 | 0 | 1100.68 | 2.5 | 39.31 | 1100.68 | 0 | 1100.68 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -47 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 35.96 | 28 | 1006.88 | 0 | 1006.88 | 2.5 | 35.96 | 1006.88 | 0 | 1006.88 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 0 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-4th Fl Flooring&Tiling Sadhrali Granite Flooring | Granite Flooring | Sq.Ft | 535.7 | 55 | 29463.5 | 0 | 29463.5 | 2.5 | 535.7 | 29463.5 | 0 | 29463.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -04 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 67.38 | 28 | 1886.64 | 0 | 1886.64 | 2.5 | 67.38 | 1886.64 | 0 | 1886.64 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -109 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 186.11 | 28 | 5211.08 | 0 | 5211.08 | 2.5 | 186.11 | 5211.08 | 0 | 5211.08 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -25 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 277.6 | 28 | 7772.8 | 0 | 7772.8 | 2.5 | 0 | 0 | 0 | 0 | 277.6 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -80 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 149.3 | 28 | 4180.4 | 0 | 4180.4 | 2.5 | 149.3 | 4180.4 | 0 | 4180.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -24 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 293.32 | 28 | 8212.96 | 0 | 8212.96 | 2.5 | 0 | 0 | 0 | 0 | 293.32 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -68 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 41.08 | 28 | 1150.24 | 0 | 1150.24 | 2.5 | 38.3571 | 1074 | 0 | 1074 | 2.7229 | 76.24 |  | 93.3717 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -110 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 28.38 | 28 | 794.64 | 0 | 794.64 | 2.5 | 28.38 | 794.64 | 0 | 794.64 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -104 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 22.98 | 28 | 643.44 | 0 | 643.44 | 2.5 | 0 | 0 | 0 | 0 | 22.98 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 3 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Dish Washer Area Work - 1 No. | Flooring work- cc | Sq.Ft | 153.257 | 28 | 4291.2 | 0 | 4291.2 | 2.5 | 131.148 | 3672.14 | 0 | 3672.14 | 22.109 | 619.05 |  | 85.5739 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -99 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 71.15 | 28 | 1992.2 | 0 | 1992.2 | 2.5 | 0 | 0 | 0 | 0 | 71.15 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -20 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 179.01 | 28 | 5012.28 | 0 | 5012.28 | 2.5 | 179.01 | 5012.28 | 0 | 5012.28 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -33 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 79.44 | 28 | 2224.32 | 0 | 2224.32 | 2.5 | 0 | 0 | 0 | 0 | 79.44 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -97 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 36.32 | 28 | 1016.96 | 0 | 1016.96 | 2.5 | 0 | 0 | 0 | 0 | 36.32 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -33 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 32.74 | 28 | 916.72 | 0 | 916.72 | 2.5 | 0 | 0 | 0 | 0 | 32.74 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -32 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 32.22 | 28 | 902.16 | 0 | 902.16 | 2.5 | 32.22 | 902.16 | 0 | 902.16 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -64 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 39.93 | 28 | 1118.04 | 0 | 1118.04 | 2.5 | 37.7143 | 1056 | 0 | 1056 | 2.2157 | 62.04 |  | 94.451 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -42 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 103.12 | 28 | 2887.36 | 0 | 2887.36 | 2.5 | 0 | 0 | 0 | 0 | 103.12 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -90 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 29.1 | 28 | 814.8 | 0 | 814.8 | 2.5 | 20.0714 | 562 | 0 | 562 | 9.0286 | 252.8 |  | 68.9739 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 174 | 2 | 16 Mar 2022 | ARVIND KUMAR SINGH KALAPNATH SINGH | 2nd Floor Shop -03 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 26.9 | 28 | 753.2 | 0 | 753.2 | 2.5 | 16.4643 | 461 | 0 | 461 | 10.4357 | 292.2 |  | 61.2056 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Misc Work - DCH | No. | 1 | 7500 | 7500 | 0 | 7500 | 0 | 1 | 7500 | 0 | 7500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Misc Work - DCH | No. | 1 | 5500 | 5500 | 0 | 5500 | 0 | 1 | 5500 | 0 | 5500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Ghadai work- BCP | Sq.Ft | 17849 | 5 | 89245 | 0 | 89245 | 0 | 10382.226 | 51911.13 | 0 | 51911.13 | 7466.774 | 37333.87 |  | 58.167 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Misc Work - DCH | No. | 1 | 9500 | 9500 | 0 | 9500 | 0 | 1 | 9500 | 0 | 9500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Site Expenses - Material Unloading & Shifting | Jointing Mortar Unloading | Bags | 40 | 5 | 200 | 0 | 200 | 0 | 40 | 200 | 0 | 200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Male Coolie | No. | 70 | 550 | 38500 | 0 | 38500 | 0 | 69.9999 | 38499.95 | 0 | 38499.95 | 0.0001 | 0.06 |  | 99.9999 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Blockwork - USS | Sq.Ft | 1075 | 18 | 19350 | 0 | 19350 | 2.5 | 1075 | 19350 | 0 | 19350 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | UTI. Solar System | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Loading - BRE | No. | 1 | 400 | 400 | 0 | 400 | 0 | 1 | 400 | 0 | 400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Mason - DCW | No. | 23 | 850 | 19550 | 0 | 19550 | 0 | 23 | 19550 | 0 | 19550 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Demolishing Plaster Dld | Sq.Ft | 169.12 | 10 | 1691.2 | 0 | 1691.2 | 0 | 169.12 | 1691.2 | 0 | 1691.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Single Coat Plaster (L) | Sq.Ft | 58.08 | 20 | 1161.6 | 0 | 1161.6 | 2.5 | 58.08 | 1161.6 | 0 | 1161.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Male Coolie | No. | 26.5 | 550 | 14575 | 0 | 14575 | 0 | 26.5 | 14575 | 0 | 14575 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Mason - DCW | No. | 30 | 850 | 25500 | 0 | 25500 | 0 | 30 | 25500 | 0 | 25500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Site Expenses - Material Unloading & Shifting | Labour Lumpsum | No. | 1 | 9000 | 9000 | 0 | 9000 | 0 | 1 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Misc Work - DCH | No. | 1 | 22000 | 22000 | 0 | 22000 | 0 | 1 | 22000 | 0 | 22000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Blockwork - USS | Sq.Ft | 237.7 | 18 | 4278.6 | 0 | 4278.6 | 2.5 | 237.7 | 4278.6 | 0 | 4278.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | UTI. Solar System | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Site Misc Misc. Work | Breaker | Day | 4 | 1300 | 5200 | 0 | 5200 | 0 | 4 | 5200 | 0 | 5200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Granite Flooring removing-BCV | Sq.Ft | 119.25 | 15 | 1788.75 | 0 | 1788.75 | 0 | 119.25 | 1788.75 | 0 | 1788.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Male Coolie | No. | 30 | 500 | 15000 | 0 | 15000 | 0 | 30 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | POP removing | Removing Work | Sq.Ft | 199.5 | 5 | 997.5 | 0 | 997.5 | 0 | 199.5 | 997.5 | 0 | 997.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Mason - DCW | No. | 40 | 850 | 34000 | 0 | 34000 | 0 | 40 | 34000 | 0 | 34000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Misc Work - DCH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Rework Extrawork Misc. Works | Unloading of AAC Blocks | No. | 1320 | 2 | 2640 | 0 | 2640 | 0 | 1320 | 2640 | 0 | 2640 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 175 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Site Expenses - Material Unloading & Shifting | Unloading of AAC Blocks | No. | 12980 | 3 | 38940 | 0 | 38940 | 0 | 11706 | 35118 | 0 | 35118 | 1274 | 3822 |  | 90.1849 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 176 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | KEP-2nd Fl Blockwork-100mm | 4'' Blockwork Rate Diff. | Sq.Ft | 17888.69 | 4 | 71554.76 | 0 | 71554.76 | 2.5 | 16288.511 | 65154.04 | 0 | 65154.04 | 1600.179 | 6400.72 |  | 91.0548 |  | Dushant Gore | Swapnil Erande | construction open | 02 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 176 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | KEP-2nd Fl Concrete Band for blockwork | Patli (Band)- BC | R.Ft | 3640 | 10 | 36400 | 0 | 36400 | 2.5 | 2840.4857 | 28404.86 | 0 | 28404.86 | 799.5143 | 7995.14 |  | 78.0353 |  | Dushant Gore | Swapnil Erande | construction open | 02 Apr 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 176 | 1 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | 4th Flr Shop No. 5 Single Coat Plaster for Toilet & Pantry | Single Coat Plaster (L) | Sq.Ft | 713.85 | 20 | 14277 | 0 | 14277 | 2.5 | 713.85 | 14277 | 0 | 14277 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Apr 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 176 | 0 | 16 Mar 2022 | SURESH KUMAR MURALIDHAR | Basement Fl Drain Line of Water Drain in Sump Gutter Work | BBM/Plaster work | R.Ft | 200.08 | 45 | 9003.6 | 0 | 9003.6 | 2.5 | 200.08 | 9003.6 | 0 | 9003.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- Sample Office (Shop No. 5) waterproofing work | Screeding work- BC | Sq.Ft | 1029.08 | 25 | 25727 | 4630.86 | 30357.86 | 10 | 1029.08 | 25727 | 4630.86 | 30357.86 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Brickbat W/P | Sq.Ft | 33.75 | 40 | 1350 | 243 | 1593 | 10 | 33.75 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Waterproofing 6th Slab Waterproofing | Chemical W/P (L+M) DCH | Sq.Ft | 116.32 | 20 | 2326.4 | 418.76 | 2745.16 | 10 | 116.32 | 2326.4 | 418.76 | 2745.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | 1st Floor Pizzahut waterproofing | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 16 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical W/P (L+M) DCH | Sq.Ft | 63 | 20 | 1260 | 226.8 | 1486.8 | 10 | 63 | 1260 | 226.8 | 1486.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Waterproofing 6th Slab Waterproofing | Brickbat W/P | Sq.Ft | 58.16 | 40 | 2326.4 | 418.76 | 2745.16 | 10 | 58.16 | 2326.4 | 418.76 | 2745.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | 1st Floor Pizzahut waterproofing | Chemical W/P (L+M) DCH | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Club House | Cancelled | ADITYA CHOUGULE | 19 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical W/P (L+M) DCH | Sq.Ft | 64.5 | 20 | 1290 | 232.2 | 1522.2 | 10 | 64.5 | 1290 | 232.2 | 1522.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- Sample Office (Shop No. 5) waterproofing work | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 16 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Brickbat W/P | Sq.Ft | 163.24 | 40 | 6529.6 | 1175.32 | 7704.92 | 10 | 163.24 | 6529.6 | 1175.32 | 7704.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- Sample Office (Shop No. 5) waterproofing work | Chemical W/P (L+M) DCH | Sq.Ft | 1029.08 | 20 | 20581.6 | 3704.68 | 24286.28 | 10 | 1029.08 | 20581.6 | 3704.68 | 24286.28 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Bldg 12th floor terrace waterproofing | Screeding Work - DSP | Sq.Ft | 398 | 25 | 9950 | 1791 | 11741 | 10 | 398 | 9950 | 1791 | 11741 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Swimming Pool | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Waterproofing 6th Slab Waterproofing | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 16 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 16 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 16 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 09 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical W/P (L+M) DCH | Sq.Ft | 188.91 | 20 | 3778.2 | 680.08 | 4458.28 | 10 | 188.91 | 3778.2 | 680.08 | 4458.28 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 0 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP-3rd Floor 3rd Fl-Foodcourt area Siporex Broken Blocks Wa | Siporex Filling | Sq.Ft | 3186.9 | 40 | 127476 | 22945.68 | 150421.68 | 10 | 2740.9431 | 109637.72 | 19734.8 | 129372.52 | 445.9569 | 21049.16 |  | 86.0066 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | 1st Floor Pizzahut waterproofing | Screeding work- BC | Sq.Ft | 956.77 | 25 | 23919.25 | 4305.46 | 28224.71 | 10 | 956.77 | 23919.25 | 4305.46 | 28224.71 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Basecoat W/P BC | Sq.Ft | 56.12 | 20 | 1122.4 | 202.04 | 1324.44 | 10 | 56.12 | 1122.4 | 202.04 | 1324.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 2 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Floor shop Chemical waterproofing | Base Coat -cc | Sq.Ft | 693.54 | 25 | 17338.5 | 3120.94 | 20459.44 | 10 | 693.54 | 17338.5 | 3120.94 | 20459.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Customer Changes | Foreclose | abhishek bankar | 25 Aug 2023
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Bldg 12th floor terrace waterproofing | Waterproofing work- BCo | Sq.Ft | 438.5 | 45 | 19732.5 | 3551.86 | 23284.36 | 10 | 0 | 0 | 0 | 0 | 438.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 2 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP-4th Floor shop Chemical waterproofing | Chemical W/ P (M+L)- SO | Sq.Ft | 693.5385 | 22 | 15257.85 | 2746.42 | 18004.27 | 10 | 693.5385 | 15257.85 | 2746.42 | 18004.27 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | S OH Infrastructure | Foreclose | abhishek bankar | 25 Aug 2023
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | 1st Floor Pizzahut waterproofing | Chemical W/P (L+M) DCH | Sq.Ft | 956.77 | 20 | 19135.4 | 3444.38 | 22579.78 | 10 | 956.77 | 19135.4 | 3444.38 | 22579.78 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Chemical Coating- DPo | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | DEV. Podium | Cancelled | ADITYA CHOUGULE | 16 Jul 2022
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Refuge area waterproofing | Wata Making | R.Ft | 554.32 | 40 | 22172.8 | 3991.1 | 26163.9 | 10 | 554.32 | 22172.8 | 3991.1 | 26163.9 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Brickbat W/P | Sq.Ft | 32.62 | 40 | 1304.8 | 234.86 | 1539.66 | 10 | 32.62 | 1304.8 | 234.86 | 1539.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP- 4th Floor Labour Toilet & Community Hall Toilet waterpr | Screeding work- BC | Sq.Ft | 163.24 | 25 | 4081 | 734.58 | 4815.58 | 10 | 163.24 | 4081 | 734.58 | 4815.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 0 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP-3rd Floor Passage&Shop area Chemical Waterproofing-(Sq.F | Chemical W/P (L+M) | Sq.Ft | 3186.9 | 25 | 79672.5 | 14341.06 | 94013.56 | 10 | 0 | 0 | 0 | 0 | 3186.9 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 1 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | Basement Trimix | Trimix Repair work | R.Ft | 427 | 25 | 10675 | 1921.5 | 12596.5 | 0 | 427 | 10675 | 1921.5 | 12596.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 177 | 0 | 16 Mar 2022 | THE FAMOUS INDIA ENTERPRISES | KEP-3rd Floor Passage&Shop area Base Coat Waterproofing | Base Coat -cc | Sq.Ft | 3186.9 | 20 | 63738 | 11472.84 | 75210.84 | 10 | 31.5997 | 631.99 | 113.76 | 745.75 | 3155.3003 | 74465.09 |  | 0.9915 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande
EAST POINT MARKET | 178 | 1 | 17 Mar 2022 | KHAN KAMAR ALAM | 3rd Floor Grid Ceiling supply to US for repairing purpose | Labour lumpsum- SOS | No. | 1 | 3200 | 3200 | 0 | 3200 | 0 | 1 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | MONALI CHAUDHAR | 13 Jul 2024
EAST POINT MARKET | 178 | 1 | 17 Mar 2022 | KHAN KAMAR ALAM | 3rd Floor Shop No.11 Vertical Gypsum & Old false ceiling bre | Labour lumpsum- SOS | No. | 1 | 8000 | 8000 | 0 | 8000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | MONALI CHAUDHAR | 13 Jul 2024
EAST POINT MARKET | 178 | 1 | 17 Mar 2022 | KHAN KAMAR ALAM | 3rd Floor Gypsum work Lift No.1 Railway side Lift | Labour lumpsum- SOS | No. | 1 | 4500 | 4500 | 0 | 4500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | MONALI CHAUDHAR | 13 Jul 2024
EAST POINT MARKET | 178 | 0 | 17 Mar 2022 | KHAN KAMAR ALAM | KEP-1st FL Grid False ceiling work Passage | Grid False Ceiling (M) | Sq.Ft | 2424 | 70 | 169680 | 0 | 169680 | 0 | 0 | 0 | 0 | 0 | 2424 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 05 GYPSUM & PLASTER | Un-Approved
EAST POINT MARKET | 178 | 0 | 17 Mar 2022 | KHAN KAMAR ALAM | KEP - 2nd FL Grid False ceiling work Passage | Grid False Ceiling (M) | Sq.Ft | 2424 | 70 | 169680 | 0 | 169680 | 0 | 0 | 0 | 0 | 0 | 2424 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 05 GYPSUM & PLASTER | Un-Approved
EAST POINT MARKET | 178 | 1 | 17 Mar 2022 | KHAN KAMAR ALAM | 3rd Floor Electrical DB top False Ceiling work | Labour lumpsum- SOS | No. | 1 | 3500 | 3500 | 0 | 3500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | MONALI CHAUDHAR | 13 Jul 2024
EAST POINT MARKET | 178 | 1 | 17 Mar 2022 | KHAN KAMAR ALAM | 3rd Floor Grid Ceiling from Toilet outside passage to MMD Do | Labour lumpsum- SOS | No. | 1 | 15000 | 15000 | 0 | 15000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | MONALI CHAUDHAR | 13 Jul 2024
EAST POINT MARKET | 178 | 1 | 17 Mar 2022 | KHAN KAMAR ALAM | 3rd Floor Shop 14 False Ceiling with framing | Labour lumpsum- SOS | No. | 1 | 9000 | 9000 | 0 | 9000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | MONALI CHAUDHAR | 13 Jul 2024
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 23 Mar 2022
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 1 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 179 | 0 | 23 Mar 2022 | TARUSH ATUL GOEL | Rental Expenses | Rent Charges | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 180 | 0 | 29 Mar 2022 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153154216 | KEP-Gr Fl Electricity Meter | Service connection charges | No. | 1 | 12000 | 12000 | 2160 | 14160 | 0 | 1 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 180 | 0 | 29 Mar 2022 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153154216 | KEP-Gr Fl Electricity Meter | Security Deposit | No. | 1 | 10850 | 10850 | 0 | 10850 | 0 | 1 | 10850 | 0 | 10850 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 180 | 0 | 29 Mar 2022 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153154216 | KEP-Gr Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 110 | 110 | 19.8 | 129.8 | 0 | 1 | 110 | 19.8 | 129.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 181 | 0 | 29 Mar 2022 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153153828 | KEP-Gr Fl Electricity Meter | Security Deposit | No. | 1 | 9700 | 9700 | 0 | 9700 | 0 | 1 | 9700 | 0 | 9700 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 181 | 0 | 29 Mar 2022 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153153828 | KEP-Gr Fl Electricity Meter | Service connection charges | No. | 1 | 12000 | 12000 | 2160 | 14160 | 0 | 1 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 181 | 0 | 29 Mar 2022 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153153828 | KEP-Gr Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 110 | 110 | 19.8 | 129.8 | 0 | 1 | 110 | 19.8 | 129.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | MS Bracket (M+L) | No. | 10 | 322 | 3220 | 579.6 | 3799.6 | 2.5 | 10 | 3220 | 579.6 | 3799.6 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Drawing Printing | No. | 1 | 7360 | 7360 | 1324.8 | 8684.8 | 2.5 | 1 | 7360 | 1324.8 | 8684.8 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | Consultacy Architectural | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Brass pinset (M+L) | No. | 6 | 902.5 | 5415 | 974.7 | 6389.7 | 2.5 | 5 | 4512.5 | 812.26 | 5324.76 | 1 | 1064.94 |  | 83.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | Commissioning & Testing | No. | 2 | 13800 | 27600 | 4968 | 32568 | 0 | 2 | 27600 | 4968 | 32568 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 54 | 161 | 8694 | 1564.92 | 10258.92 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 2" Dia Pipe Fixing BC | R.Ft | 77.25 | 150 | 11587.5 | 2085.76 | 13673.26 | 2.5 | 77.25 | 11587.5 | 2085.76 | 13673.26 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5'' Dia line Painting (1+2 coats) (M+L) | R.Ft | 100 | 32.2 | 3220 | 579.6 | 3799.6 | 2.5 | 56.3433 | 1814.25 | 326.56 | 2140.81 | 43.6567 | 1658.79 |  | 56.3433 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5 '' Dia MS C Class 10 Cylinder (M+L) | No. | 2 | 13775 | 27550 | 4959 | 32509 | 2.5 | 2 | 27550 | 4959 | 32509 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | Drawing Printing | No. | 1 | 7360 | 7360 | 1324.8 | 8684.8 | 0 | 1 | 7360 | 1324.8 | 8684.8 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | Consultacy Architectural | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 20 Cylinder MS Gas bank (M+L) | No. | 1 | 60325 | 60325 | 10858.5 | 71183.5 | 2.5 | 1 | 60325 | 10858.5 | 71183.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 1.5 inch dia pipe fixing | R.Ft | 26.08 | 60 | 1564.8 | 281.66 | 1846.46 | 2.5 | 26.08 | 1564.8 | 281.66 | 1846.46 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 2" Dia Pipe Fixing BC | R.Ft | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 01 Apr 2022 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 10 Feb 2024
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Bracket M.S readymade (M+L) | No. | 65 | 138 | 8970 | 1614.6 | 10584.6 | 2.5 | 28 | 3864 | 695.52 | 4559.52 | 37 | 6025.08 |  | 43.0769 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2'' Ball Valve (M+L) | No. | 4 | 3910 | 15640 | 2815.2 | 18455.2 | 2.5 | 2 | 7820 | 1407.6 | 9227.6 | 2 | 9227.6 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Bracket M.S Fabricated 35 x 35 x3mm (M+L) | No. | 5 | 332.5 | 1662.5 | 299.26 | 1961.76 | 2.5 | 5 | 1662.5 | 299.26 | 1961.76 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Ball Valve (M+L) | No. | 8 | 1282.5 | 10260 | 1846.8 | 12106.8 | 2.5 | 5 | 6412.5 | 1154.26 | 7566.76 | 3 | 4540.04 |  | 62.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Gas strainer with meter inlet with fittings | No. | 27 | 2254 | 60858 | 10954.44 | 71812.44 | 2.5 | 6 | 13524 | 2434.32 | 15958.32 | 21 | 55854.12 |  | 22.2222 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 3'' Elbow seamless sch 40 (M+L) | No. | 10 | 391 | 3910 | 703.8 | 4613.8 | 2.5 | 10 | 3910 | 703.8 | 4613.8 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Elbow seamless sch 40 (M+L) | No. | 15 | 50.6 | 759 | 136.62 | 895.62 | 2.5 | 2 | 101.2 | 18.2 | 119.4 | 13 | 776.22 |  | 13.3333 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Non Return Valve -UWR | No. | 20 | 332.5 | 6650 | 1197 | 7847 | 2.5 | 20 | 6650 | 1197 | 7847 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | UTI. Water Supply | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 1.5 Sq.mm x 4C Cu Arm.Cable(M+L) | Mtrs | 150 | 142.6 | 21390 | 3850.2 | 25240.2 | 2.5 | 150 | 21390 | 3850.2 | 25240.2 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2'' x 1'' Tee Seamless sch 40 (M+L) | No. | 24 | 322 | 7728 | 1391.04 | 9119.04 | 2.5 | 22 | 7084 | 1275.12 | 8359.12 | 2 | 759.92 |  | 91.6667 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2nd Stage high pressure regulator (M+L) | No. | 6 | 4275 | 25650 | 4617 | 30267 | 2.5 | 6 | 25650 | 4617 | 30267 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5'' Elbow seamless sch 40 (M+L) | No. | 15 | 101.2 | 1518 | 273.24 | 1791.24 | 2.5 | 5 | 506 | 91.08 | 597.08 | 10 | 1194.16 |  | 33.3333 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Bracket M.S readymade (M+L) | No. | 8 | 142.5 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 570 | 102.6 | 672.6 | 4 | 672.6 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Safety Board- MWB | No. | 1 | 1425 | 1425 | 256.5 | 1681.5 | 2.5 | 1 | 1425 | 256.5 | 1681.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 3'' Ball Valve (M+L) | No. | 2 | 18832.4 | 37664.8 | 6779.66 | 44444.46 | 2.5 | 1 | 18832.4 | 3389.84 | 22222.24 | 1 | 22222.22 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Commissioning & Testing | No. | 1 | 13800 | 13800 | 2484 | 16284 | 2.5 | 1 | 13800 | 2484 | 16284 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1st Stage high pressure regulator (M+L) | No. | 2 | 6175 | 12350 | 2223 | 14573 | 2.5 | 2 | 12350 | 2223 | 14573 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 6 | 185.25 | 1111.5 | 200.08 | 1311.58 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 8 | 253 | 2024 | 364.32 | 2388.32 | 2.5 | 4 | 1012 | 182.16 | 1194.16 | 4 | 1194.16 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Safety Board- MWB | No. | 1 | 9200 | 9200 | 1656 | 10856 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2'' Dia line Painting (1+2 coats) (M+L) | R.Ft | 400 | 41.4 | 16560 | 2980.8 | 19540.8 | 2.5 | 400 | 16560 | 2980.8 | 19540.8 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Cylinder Adaptors (M+L) | No. | 20 | 403.75 | 8075 | 1453.5 | 9528.5 | 2.5 | 20 | 8075 | 1453.5 | 9528.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Transport Charges | No. | 1 | 23000 | 23000 | 4140 | 27140 | 0 | 1 | 23000 | 4140 | 27140 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 3'' Dia M.S ERW Pipe (M+L) | R.Ft | 260 | 455.4 | 118404 | 21312.72 | 139716.72 | 2.5 | 211.0888 | 96129.84 | 17303.38 | 113433.22 | 48.9112 | 26283.5 |  | 81.188 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Dia M.S ERW Pipe (M+L) | R.Ft | 180 | 174.8 | 31464 | 5663.52 | 37127.52 | 2.5 | 45.83 | 8011.08 | 1442 | 9453.08 | 134.17 | 27674.44 |  | 25.4611 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 3'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 4 | 363.4 | 1453.6 | 261.64 | 1715.24 | 2.5 | 2 | 726.8 | 130.82 | 857.62 | 2 | 857.62 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Cylinder Flexible Hose (M+L) | No. | 20 | 375.25 | 7505 | 1350.9 | 8855.9 | 2.5 | 20 | 7505 | 1350.9 | 8855.9 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 2 Inch Pipe Painting (M+L) | R.Ft | 29.25 | 41.4 | 1210.95 | 217.98 | 1428.93 | 2.5 | 29.25 | 1210.95 | 217.98 | 1428.93 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 3'' Dia line Painting (1+2 coats) (M+L) | R.Ft | 260 | 50.6 | 13156 | 2368.08 | 15524.08 | 2.5 | 211.09 | 10681.15 | 1922.6 | 12603.75 | 48.91 | 2920.33 |  | 81.1885 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 1" Ball Valve Fixing - UWR | No. | 5 | 1150 | 5750 | 1035 | 6785 | 2.5 | 5 | 5750 | 1035 | 6785 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | UTI. Water Supply | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Commissioning & Testing | No. | 1 | 4750 | 4750 | 855 | 5605 | 2.5 | 1 | 4750 | 855 | 5605 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Pressure Guage with fittings (M+L) | No. | 3 | 1567.5 | 4702.5 | 846.46 | 5548.96 | 2.5 | 3 | 4702.5 | 846.46 | 5548.96 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Dia M.S ERW Pipe (M+L) | R.Ft | 40 | 199.5 | 7980 | 1436.4 | 9416.4 | 2.5 | 6 | 1197 | 215.46 | 1412.46 | 34 | 8003.94 |  | 15 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 3'' x 2'' Tee Seamless sch 40 (M+L) | No. | 4 | 506 | 2024 | 364.32 | 2388.32 | 2.5 | 1 | 506 | 91.08 | 597.08 | 3 | 1791.24 |  | 25 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1/2'' Ball Valve (M+L) | No. | 4 | 506 | 2024 | 364.32 | 2388.32 | 2.5 | 2 | 1012 | 182.16 | 1194.16 | 2 | 1194.16 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5'' Dia M.S ERW Pipe (M+L) | R.Ft | 100 | 165.6 | 16560 | 2980.8 | 19540.8 | 2.5 | 30.26 | 5011.06 | 902 | 5913.06 | 69.74 | 13627.74 |  | 30.26 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2'' Elbow seamless sch 40 (M+L) | No. | 25 | 142.6 | 3565 | 641.7 | 4206.7 | 2.5 | 24 | 3422.4 | 616.02 | 4038.42 | 1 | 168.28 |  | 96 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | Removing of 2 inch Dia pipe | R.Ft | 77.25 | 50 | 3862.5 | 695.26 | 4557.76 | 0 | 77.25 | 3862.5 | 695.26 | 4557.76 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 2 inch x 1 inch MS Tee | No. | 0 | 322 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 01 Apr 2022 |  | No category | Cancelled | MONALI CHAUDHAR | 14 Feb 2024
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Pressure Guage with fittings (M+L) | No. | 6 | 1426 | 8556 | 1540.08 | 10096.08 | 2.5 | 2 | 2852 | 513.36 | 3365.36 | 4 | 6730.72 |  | 33.3333 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5'' x 1'' Tee Seamless sch 40 (M+L) | No. | 4 | 253 | 1012 | 182.16 | 1194.16 | 2.5 | 2 | 506 | 91.08 | 597.08 | 2 | 597.08 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 2'' Dia M.S ERW Pipe (M+L) | R.Ft | 400 | 345 | 138000 | 24840 | 162840 | 2.5 | 358.06 | 123530.7 | 22235.52 | 145766.22 | 41.94 | 17073.78 |  | 89.515 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | Pressure Gauge (M+L) | set | 2 | 1567.5 | 3135 | 564.3 | 3699.3 | 2.5 | 2 | 3135 | 564.3 | 3699.3 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Ball Valve (M+L) | No. | 25 | 1150 | 28750 | 5175 | 33925 | 2.5 | 25 | 28750 | 5175 | 33925 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Gas Detector Point | No. | 2 | 13775 | 27550 | 4959 | 32509 | 2.5 | 2 | 27550 | 4959 | 32509 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5'' Ball Valve (M+L) | No. | 6 | 3082 | 18492 | 3328.56 | 21820.56 | 2.5 | 3 | 9246 | 1664.28 | 10910.28 | 3 | 10910.28 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 1 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Transport Charges | No. | 1 | 9500 | 9500 | 1710 | 11210 | 0 | 1 | 9500 | 1710 | 11210 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | 2 inch x 1 inch MS Tee | No. | 1 | 322 | 322 | 57.96 | 379.96 | 2.5 | 1 | 322 | 57.96 | 379.96 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1.5'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 4 | 207 | 828 | 149.04 | 977.04 | 2.5 | 2 | 414 | 74.52 | 488.52 | 2 | 488.52 |  | 50 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | 1'' Dia line Painting (1+2 coats) (M+L) | R.Ft | 180 | 23 | 4140 | 745.2 | 4885.2 | 2.5 | 45.83 | 1054.09 | 189.74 | 1243.83 | 134.17 | 3641.37 |  | 25.4611 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 0 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Gas Piping System-(No.) | Bracket M.S Fabricated 35 x 35 x3mm (M+L) | No. | 65 | 322 | 20930 | 3767.4 | 24697.4 | 2.5 | 65 | 20930 | 3767.4 | 24697.4 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Apr 2022 |  | 08 PLUMBING WORK | Approved | chetan.jewalikar
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | Removing of 1.5 inch Dia pipe | R.Ft | 26.08 | 20 | 521.6 | 93.88 | 615.48 | 0 | 26.08 | 521.6 | 93.88 | 615.48 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 182 | 2 | 01 Apr 2022 | VED ENGINEERS AND CONTRACTORS | Mall Internal pipe line Re-route & extra work | Removing of 1.5 inch Dia pipe | R.Ft | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 01 Apr 2022 |  | No category | Cancelled | MONALI CHAUDHAR | 10 Feb 2024
EAST POINT MARKET | 183 | 0 | 01 Apr 2022 | SAHARA ENGINEERING | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Contractor Profit-Mkt | No. | 1 | 23910 | 23910 | 4303.8 | 28213.8 | 0 | 1 | 23910 | 4303.8 | 28213.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 183 | 0 | 01 Apr 2022 | SAHARA ENGINEERING | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Tube fitting-BCo | No. | 180 | 525 | 94500 | 17010 | 111510 | 0 | 180 | 94500 | 17010 | 111510 | 0 | 0 | 36 W- warm white. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 183 | 0 | 01 Apr 2022 | SAHARA ENGINEERING | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Transport Charges | No. | 1 | 3000 | 3000 | 540 | 3540 | 0 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 183 | 0 | 01 Apr 2022 | SAHARA ENGINEERING | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | Tube fitting-BCo | No. | 70 | 315 | 22050 | 3969 | 26019 | 0 | 70 | 22050 | 3969 | 26019 | 0 | 0 | 20 W- warm white. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 31 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | In General Shift 9Hrs. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 60 | 543.8 | 32628 | 5873.04 | 38501.04 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 31 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 290.997 | 141220.84 | 25419.76 | 166640.6 | 19.003 | 10882.14 | 10 Manpower for Housekeeping work. | 93.87 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 300 | 501.5 | 150450 | 27081 | 177531 | 0 | 300 | 150450 | 27081 | 177531 | 0 | 0 | 10 Manpower for Housekeeping work. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 30 | 775 | 23250 | 4185 | 27435 | 0 | 22 | 17050 | 3069 | 20119 | 8 | 7316 |  | 73.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 253.9985 | 123265.47 | 22187.78 | 145453.25 | 56.0015 | 32069.49 | 10 Manpower for Housekeeping work. | 81.935 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 30 | 501.46 | 15043.8 | 2707.88 | 17751.68 | 0 | 30 | 15043.8 | 2707.88 | 17751.68 | 0 | 0 | In General Shift 9Hrs. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 30 | 501.46 | 15043.8 | 2707.88 | 17751.68 | 0 | 20 | 10029.2 | 1805.26 | 11834.46 | 10 | 5917.22 | In General Shift 9 Hrs. | 66.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 30 | 501.46 | 15043.8 | 2707.88 | 17751.68 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 60 | 509.73 | 30583.8 | 5505.08 | 36088.88 | 0 | 27 | 13762.71 | 2477.28 | 16239.99 | 33 | 19848.89 |  | 45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 28 | 537.28 | 15043.84 | 2707.9 | 17751.74 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 493.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In General Shift 9Hrs. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 300 | 501.5 | 150450 | 27081 | 177531 | 0 | 300 | 150450 | 27081 | 177531 | 0 | 0 | 10 Manpower for Housekeeping work. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 56 | 546.14 | 30583.84 | 5505.1 | 36088.94 | 0 | 56 | 30583.84 | 5505.1 | 36088.94 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 45.9997 | 22691.65 | 4084.5 | 26776.15 | 16.0003 | 9313.67 |  | 74.1931 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 30 | 501.46 | 15043.8 | 2707.88 | 17751.68 | 0 | 24 | 12035.04 | 2166.3 | 14201.34 | 6 | 3550.34 | In General Shift 9Hrs. | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 30 | 775 | 23250 | 4185 | 27435 | 0 | 30 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 60 | 543.8 | 32628 | 5873.04 | 38501.04 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 120 | 550.6 | 66072 | 11892.96 | 77964.96 | 0 | 83 | 45699.8 | 8225.96 | 53925.76 | 37 | 24039.2 | 1. 2 Security in Day. 2. 2 Security in Night. | 69.1667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 30 | 775 | 23250 | 4185 | 27435 | 0 | 30 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 29 | 14073.7 | 2533.26 | 16606.96 | 2 | 1145.32 | In General Shift 9Hrs. | 93.5484 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 112 | 590 | 66080 | 11894.4 | 77974.4 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 20 | 9706 | 1747.08 | 11453.08 | 11 | 6299.2 | In General Shift 9 Hrs. | 64.5161 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 23 | 11161.9 | 2009.14 | 13171.04 | 8 | 4581.24 | In General Shift 9Hrs. | 74.1935 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 300 | 501.5 | 150450 | 27081 | 177531 | 0 | 286.9998 | 143930.4 | 25907.48 | 169837.88 | 13.0002 | 7693.12 | 10 Manpower for Housekeeping work. | 95.6666 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 60.9999 | 30091.25 | 5416.42 | 35507.67 | 1.0001 | 582.15 |  | 98.3869 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 59.9974 | 29596.72 | 5327.4 | 34924.12 | 2.0026 | 1165.7 |  | 96.77 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 56 | 546.14 | 30583.84 | 5505.1 | 36088.94 | 0 | 30 | 16384.2 | 2949.16 | 19333.36 | 26 | 16755.58 |  | 53.5714 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 93 | 526.29 | 48944.97 | 8810.1 | 57755.07 | 0 | 41 | 21577.89 | 3884.02 | 25461.91 | 52 | 32293.16 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 44.086 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 280 | 537.3 | 150444 | 27079.92 | 177523.92 | 0 | 276.9998 | 148831.99 | 26789.76 | 175621.75 | 3.0002 | 1902.17 | 10 Manpower for Housekeeping work. | 98.9285 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 118.9999 | 63403.15 | 11412.56 | 74815.71 | 5.0001 | 3143.59 | 1. 2 Security in Day. 2. 2 Security in Night. | 95.9677 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 87.9999 | 46886.35 | 8439.54 | 55325.89 | 36.0001 | 22633.41 | 1. 2 Security in Day. 2. 2 Security in Night. | 70.9677 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 60 | 543.8 | 32628 | 5873.04 | 38501.04 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 60 | 509.73 | 30583.8 | 5505.08 | 36088.88 | 0 | 60 | 30583.8 | 5505.08 | 36088.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 57 | 29998.53 | 5399.74 | 35398.27 | 5 | 3105.11 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 91.9355 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 93 | 526.29 | 48944.97 | 8810.1 | 57755.07 | 0 | 89.9999 | 47366.05 | 8525.88 | 55891.93 | 3.0001 | 1863.14 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 96.7741 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 0 | 0 | 0 | 0 | 62 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 30 | 501.46 | 15043.8 | 2707.88 | 17751.68 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 295 | 143163.5 | 25769.44 | 168932.94 | 15 | 8589.8 | 1. 5 Manpower in Morning. 2. 5 Manpower in Evening. | 95.1613 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 90 | 543.8 | 48942 | 8809.56 | 57751.56 | 0 | 79 | 42960.2 | 7732.84 | 50693.04 | 11 | 7058.52 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 87.7778 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 84 | 582.67 | 48944.28 | 8809.98 | 57754.26 | 0 | 39 | 22724.13 | 4090.34 | 26814.47 | 45 | 30939.79 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 46.4286 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 31 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 30 | 501.46 | 15043.8 | 2707.88 | 17751.68 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 302 | 146560.6 | 26380.9 | 172941.5 | 8 | 4581.24 | 1. 5 Manpower in Morning. 2. 5 Manpower in Evening. | 97.4194 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 62 | 30584.6 | 5505.22 | 36089.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 30 | 775 | 23250 | 4185 | 27435 | 0 | 25.9998 | 20149.85 | 3626.98 | 23776.83 | 4.0002 | 3658.18 |  | 86.666 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 60 | 29598 | 5327.64 | 34925.64 | 2 | 1164.18 |  | 96.7742 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 54.994 | 27128.54 | 4883.14 | 32011.68 | 7.006 | 4078.14 |  | 88.7 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 60 | 509.73 | 30583.8 | 5505.08 | 36088.88 | 0 | 30.9996 | 15801.43 | 2844.26 | 18645.69 | 29.0004 | 17443.19 |  | 51.666 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 120 | 550.6 | 66072 | 11892.96 | 77964.96 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 509.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 29 Aug 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 280 | 537.3 | 150444 | 27079.92 | 177523.92 | 0 | 113 | 60714.9 | 10928.68 | 71643.58 | 167 | 105880.34 | 1. 5 Manpower in Morning. 2. 5 Manpower in Evening. | 40.3571 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 29.9999 | 22499.93 | 4049.98 | 26549.91 | 1.0001 | 885.1 |  | 96.7739 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 29.0011 | 15451.79 | 2781.32 | 18233.11 | 94.9989 | 59726.19 | 1. 2 Security in Day 2. 2 Security in Night. | 23.388 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 28 | 830.35 | 23249.8 | 4184.96 | 27434.76 | 0 | 19.9998 | 16606.83 | 2989.22 | 19596.05 | 8.0002 | 7838.71 |  | 71.4279 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 31 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 28.9909 | 21743.18 | 3913.78 | 25656.96 | 2.0091 | 1778.05 |  | 93.519 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 120 | 550.6 | 66072 | 11892.96 | 77964.96 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 120 | 550.6 | 66072 | 11892.96 | 77964.96 | 0 | 70.9992 | 39092.16 | 7036.58 | 46128.74 | 49.0008 | 31836.22 | 1. 2 Security in Day 2. 2 Security in Night. | 59.166 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 30 | 775 | 23250 | 4185 | 27435 | 0 | 21.9999 | 17049.92 | 3068.98 | 20118.9 | 8.0001 | 7316.1 |  | 73.333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 509.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In General Shift 9Hrs. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 537.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 543.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 02 Apr 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 29 Aug 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 62 | 30584.6 | 5505.22 | 36089.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 310 | 150443 | 27079.74 | 177522.74 | 0 | 0 | 10 Manpower for Housekeeping work. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 28 | 830.35 | 23249.8 | 4184.96 | 27434.76 | 0 | 16 | 13285.6 | 2391.4 | 15677 | 12 | 11757.76 |  | 57.1429 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 582.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 300 | 501.5 | 150450 | 27081 | 177531 | 0 | 294 | 147441 | 26539.38 | 173980.38 | 6 | 3550.62 | 1. 5 Manpower in Morning. 2. 5 Manpower in Evening. | 98 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 543.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 60 | 543.8 | 32628 | 5873.04 | 38501.04 | 0 | 30 | 16314 | 2936.52 | 19250.52 | 30 | 19250.52 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 493.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In General Shift 9Hrs. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 543.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 75 | 39960 | 7192.8 | 47152.8 | 49 | 30806.5 | 1. 2 Security in Day 2. 2 Security in Night. | 60.4839 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 62 | 30584.6 | 5505.22 | 36089.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 299.9994 | 145589.71 | 26206.14 | 171795.85 | 10.0006 | 5726.89 | 10 Manpower for Housekeeping work. | 96.774 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 293.9978 | 142677.13 | 25681.88 | 168359.01 | 16.0022 | 9163.73 | 10 Manpower for Housekeeping work. | 94.838 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 60 | 509.73 | 30583.8 | 5505.08 | 36088.88 | 0 | 52.9998 | 27015.59 | 4862.8 | 31878.39 | 7.0002 | 4210.49 |  | 88.333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 90 | 543.8 | 48942 | 8809.56 | 57751.56 | 0 | 72 | 39153.6 | 7047.64 | 46201.24 | 18 | 11550.32 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 26.9998 | 20249.85 | 3644.98 | 23894.83 | 4.0002 | 3540.17 |  | 87.0961 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 56 | 582.67 | 32629.52 | 5873.32 | 38502.84 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 298.9981 | 145103.78 | 26118.68 | 171222.46 | 11.0019 | 6300.28 | 10 Manpower for Housekeeping work. | 96.451 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 120 | 550.6 | 66072 | 11892.96 | 77964.96 | 0 | 90 | 49554 | 8919.72 | 58473.72 | 30 | 19491.24 | 1. 2 Security in Day 2. 2 Security in Night. | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 29.9987 | 22499.03 | 4049.82 | 26548.85 | 1.0013 | 886.16 |  | 96.77 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 28 | 537.28 | 15043.84 | 2707.9 | 17751.74 | 0 | 14 | 7521.92 | 1353.94 | 8875.86 | 14 | 8875.88 | In General Shift 9Hrs. | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 0 | 0 | 0 | 0 | 310 | 0 | 10 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 543.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 62 | 526.29 | 32629.98 | 5873.4 | 38503.38 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 1. 1 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 300 | 501.5 | 150450 | 27081 | 177531 | 0 | 298.998 | 149947.5 | 26990.56 | 176938.06 | 1.002 | 592.94 | 1. 5 Manpower in Morning. 2. 5 Manpower in Evening. | 99.666 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 300 | 501.5 | 150450 | 27081 | 177531 | 0 | 211 | 105816.5 | 19046.98 | 124863.48 | 89 | 52667.52 | 10 Manpower for Housekeeping work. | 70.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 31 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 93 | 526.29 | 48944.97 | 8810.1 | 57755.07 | 0 | 70.9999 | 37366.54 | 6725.98 | 44092.52 | 22.0001 | 13662.55 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 76.344 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 485.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 31 | 750 | 23250 | 4185 | 27435 | 0 | 31 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 493.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In General Shift 9Hrs. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 1. 2 Security in Day 2. 2 Security in Night. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 120 | 550.6 | 66072 | 11892.96 | 77964.96 | 0 | 96 | 52857.6 | 9514.36 | 62371.96 | 24 | 15593 | 1. 2 Security in Day. 2. 2 Security in Night. | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 60 | 509.73 | 30583.8 | 5505.08 | 36088.88 | 0 | 60 | 30583.8 | 5505.08 | 36088.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 60 | 509.73 | 30583.8 | 5505.08 | 36088.88 | 0 | 60 | 30583.8 | 5505.08 | 36088.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses | Valet Driver | Day | 0 | 526.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. 2 Manpower in Morning. 2. 1 Manpower in Evening. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 124 | 532.8 | 66067.2 | 11892.1 | 77959.3 | 0 | 111 | 59140.8 | 10645.34 | 69786.14 | 13 | 8173.16 | 1. 2 Security in Day. 2. 2 Security in Night. | 89.5161 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 546.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In General Shift 9Hrs. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 0 | 493.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In General Shift 9Hrs. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 14 MISC WORK | Cancelled | skmishra | 04 Apr 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Security Services | SecurityGuard.- SOS | Day | 112 | 590 | 66080 | 11894.4 | 77974.4 | 0 | 53 | 31270 | 5628.6 | 36898.6 | 59 | 41075.8 | 1. 2 Security in Day. 2. 2 Security in Night. | 47.3214 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Site Staff | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 310 | 485.3 | 150443 | 27079.74 | 177522.74 | 0 | 310 | 150443 | 27079.74 | 177522.74 | 0 | 0 | 1. 5 Manpower in Morning. 2. 5 Manpower in Evening. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Office Boy | Day | 31 | 485.3 | 15044.3 | 2707.98 | 17752.28 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | In General Shift 9 Hrs. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 1 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Housekeeping Work- | Day | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 Manpower for Housekeeping work. | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 18. Maintenance & Repair Work | Cancelled | ADITYA CHOUGULE | 08 Nov 2022
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Supervisor | Day | 30 | 775 | 23250 | 4185 | 27435 | 0 | 30 | 23250 | 4185 | 27435 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande
EAST POINT MARKET | 184 | 0 | 02 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Pantry Boy | Day | 62 | 493.3 | 30584.6 | 5505.22 | 36089.82 | 0 | 57 | 28118.1 | 5061.26 | 33179.36 | 5 | 2910.46 |  | 91.9355 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 185 | 0 | 06 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Deep Cleaning work | Sq.Ft | 19819.91 | 3 | 59459.73 | 10702.76 | 70162.49 | 0 | 19819.91 | 59459.73 | 10702.76 | 70162.49 | 0 | 0 | Ground Floor Passage, Atrium Flooring & column, MS cleaning-6844.28 Sq.Ft.; First Floor Passage, Railing Glass- 3985.03Sq.Ft. Second Floor Passage, Toilet, Guardians shop- 8984.6 Sq.Ft. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 185 | 1 | 06 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Site Expenses 2nd Floor Housekeeping | Housekeeping (M)-AIE | No. | 1 | 49183 | 49183 | 8852.94 | 58035.94 | 0 | 1 | 49183 | 8852.94 | 58035.94 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 186 | 0 | 06 Apr 2022 | SFS SOLUTION FACILITY SERVICES | Housekeeping Work | Deep Cleaning work | Sq.Ft | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ground Floor Plaza work, Ground Floor Atrium work, Second Floor Passage and Guardians sales office work, toilets First, second and third floor (ladies & gents). | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Apr 2022 |  | B.C. Rework/Extrawork | Cancelled | ADITYA CHOUGULE | 08 Apr 2022
EAST POINT MARKET | 187 | 0 | 08 Apr 2022 | JINAVANI FACILITIES MANAGEMENT SERVICES PRIVATE LIMITED | Housekeeping Work | Deep Cleaning work | Sq.Ft | 12314.002 | 3 | 36942.01 | 6649.56 | 43591.57 | 0 | 12314.002 | 36942.01 | 6649.56 | 43591.57 | 0 | 0 | Ground Floor Plaza work, Ground Floor Atrium work, Second Floor Passage and Guardians sales office work, toilets first, second and third floor (ladies & gents). | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | B.C. Rework/Extrawork | Approved | ADITYA CHOUGULE | 08 Apr 2022
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP GF MS platform Work | 200mm I Section (L) | Kgs | 885.6 | 25 | 22140 | 3985.2 | 26125.2 | 2.5 | 0 | 0 | 0 | 0 | 885.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP GF MS platform Work | M.S. Plate (M+L)-Mkt | Kgs | 216 | 105 | 22680 | 4082.4 | 26762.4 | 2.5 | 0 | 0 | 0 | 0 | 216 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP GF MS platform Work | Chequred Plate | Kgs | 631.5 | 21 | 13261.5 | 2387.08 | 15648.58 | 2.5 | 0 | 0 | 0 | 0 | 631.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF opp. KFC M.S frame work for food court | Department Labour - Day | Day | 5 | 3000 | 15000 | 2700 | 17700 | 2.5 | 5 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP GF MS platform Work | MS Angle 75 x 6mm (M+L) | Kgs | 147 | 105 | 15435 | 2778.3 | 18213.3 | 2.5 | 0 | 0 | 0 | 0 | 147 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP GF MS platform Work | Crane Charges - | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 0 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | ACP Work (M+L) | Sq.Ft | 0 | 230 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Apr 2022 |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 13 Apr 2022
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | 3rd Floor Shifting work | Labour Lumpsum - BC | No. | 1 | 8000 | 8000 | 1440 | 9440 | 2.5 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | GF Misc MS Work | MS Window Grill (m+l)-ULT. | No. | 9 | 1100 | 9900 | 1782 | 11682 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 188 | 0 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Entrance Canopy at Gr Floor(MS Work) | CNC Cut Design | Sq.Ft | 0 | 1200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Apr 2022 |  | No category | Cancelled | skmishra | 13 Apr 2022
EAST POINT MARKET | 188 | 1 | 09 Apr 2022 | ANAND ROLLING SHUTTER & FABRICATOR | KEP GF MS platform Work | Anchor Fastner (M+L) | No. | 40 | 150 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Apr 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Talk Back System (M) | No. | 20 | 4000 | 80000 | 14400 | 94400 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Addressable Electric Smoke Detector (M) | No. | 20 | 1800 | 36000 | 6480 | 42480 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Conventional Sounder cum Strobe (M) | No. | 1 | 2800 | 2800 | 504 | 3304 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Fittings & Accessories | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | 2C 1.5 sqmm (FRLS) Cable (M) | Mtrs | 1990 | 52 | 103480 | 18626.4 | 122106.4 | 0 | 0 | 0 | 0 | 0 | 1990 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Control Panel (M) | No. | 1 | 80000 | 80000 | 14400 | 94400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Cat 5 E 4Pair Armd. Cable (M) | Mtrs | 800 | 45 | 36000 | 6480 | 42480 | 0 | 0 | 0 | 0 | 0 | 800 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 189 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM (MATERIAL) | KEP Fire fighting work-FAS System | Manual Pull Station (M) | No. | 1 | 2550 | 2550 | 459 | 3009 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Service Charges | No. | 1 | 20000 | 20000 | 3600 | 23600 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | S OH Repair & Maintenance | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | SITC Fireman's Phone Jack (L) | No. | 3 | 300 | 900 | 162 | 1062 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Cat 5 E 4Pair Armd. Cable (L) | Mtrs | 800 | 25 | 20000 | 3600 | 23600 | 2.5 | 0 | 0 | 0 | 0 | 800 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | 2C 1.5 sqmm (FRLS) Cable (L) | Mtrs | 2467 | 38 | 93746 | 16874.28 | 110620.28 | 2.5 | 0 | 0 | 0 | 0 | 2467 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Manual Pull Station (L) | No. | 3 | 350 | 1050 | 189 | 1239 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Talk Back System (L) | No. | 20 | 300 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Addressable Fire Alarm Panel (L) | No. | 1 | 18000 | 18000 | 3240 | 21240 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Response Indicator (L) | No. | 167 | 40 | 6680 | 1202.4 | 7882.4 | 2.5 | 0 | 0 | 0 | 0 | 167 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Fault Isolator Base / Module (L) | No. | 30 | 300 | 9000 | 1620 | 10620 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Addressable Monitor Module (L) | No. | 9 | 350 | 3150 | 567 | 3717 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Conventional Sounder cum Strobe (L) | No. | 3 | 350 | 1050 | 189 | 1239 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Control Panel (L) | No. | 1 | 12000 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 190 | 0 | 14 Apr 2022 | KAMAL FIRE FIGHTING SYSTEM | KEP Fire fighting work-FAS System | Addressable Electric Smoke Detector (L) | No. | 34 | 350 | 11900 | 2142 | 14042 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 191 | 0 | 25 Apr 2022 | URJAL CONSULTANT PRIVATE LIMITED | Plumbing Consultancy | Plumbing Consultancy. | No. | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.283 | 28300 | 0 | 28300 | 0.717 | 71700 |  | 28.3 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.446 | 44600 | 0 | 44600 | 0.554 | 55400 |  | 44.6 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5256 | 52560 | 0 | 52560 | 0.4744 | 47440 |  | 52.56 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.6075 | 60750 | 0 | 60750 | 0.3925 | 39250 |  | 60.75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.7274 | 72740 | 0 | 72740 | 0.2726 | 27260 |  | 72.74 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4922 | 49220 | 0 | 49220 | 0.5078 | 50780 |  | 49.22 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.2219 | 22190 | 0 | 22190 | 0.7781 | 77810 |  | 22.19 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4761 | 47610 | 0 | 47610 | 0.5239 | 52390 |  | 47.61 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.6354 | 63540 | 0 | 63540 | 0.3646 | 36460 |  | 63.54 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.3481 | 34810 | 0 | 34810 | 0.6519 | 65190 |  | 34.81 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5037 | 50370 | 0 | 50370 | 0.4963 | 49630 |  | 50.37 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.8186 | 81860 | 0 | 81860 | 0.1814 | 18140 |  | 81.86 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.3271 | 32710 | 0 | 32710 | 0.6729 | 67290 |  | 32.71 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4365 | 43650 | 0 | 43650 | 0.5635 | 56350 |  | 43.65 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.3577 | 35770 | 0 | 35770 | 0.6423 | 64230 |  | 35.77 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5312 | 53120 | 0 | 53120 | 0.4688 | 46880 |  | 53.12 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.7133 | 71330 | 0 | 71330 | 0.2867 | 28670 |  | 71.33 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.9036 | 90360 | 0 | 90360 | 0.0964 | 9640 |  | 90.36 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.494 | 49400 | 0 | 49400 | 0.506 | 50600 |  | 49.4 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4062 | 40620 | 0 | 40620 | 0.5938 | 59380 |  | 40.62 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.3584 | 35840 | 0 | 35840 | 0.6416 | 64160 |  | 35.84 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5263 | 52630 | 0 | 52630 | 0.4737 | 47370 |  | 52.63 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4736 | 47360 | 0 | 47360 | 0.5264 | 52640 |  | 47.36 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.6432 | 64320 | 0 | 64320 | 0.3568 | 35680 |  | 64.32 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4989 | 49890 | 0 | 49890 | 0.5011 | 50110 |  | 49.89 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4941 | 49410 | 0 | 49410 | 0.5059 | 50590 |  | 49.41 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4422 | 44220 | 0 | 44220 | 0.5578 | 55780 |  | 44.22 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.7107 | 71070 | 0 | 71070 | 0.2893 | 28930 |  | 71.07 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 2 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.8417 | 84170 | 0 | 84170 | 0.1583 | 15830 |  | 84.17 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4028 | 40280 | 0 | 40280 | 0.5972 | 59720 |  | 40.28 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.6022 | 60220 | 0 | 60220 | 0.3978 | 39780 |  | 60.22 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5882 | 58820 | 0 | 58820 | 0.4118 | 41180 |  | 58.82 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 0 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5229 | 52290 | 0 | 52290 | 0.4771 | 47710 |  | 52.29 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 192 | 1 | 14 May 2022 | ZUBIN JAMSHED JALL | Marketing Operating Expenses | Miscellaneous Expenses. - SO | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.5066 | 50660 | 0 | 50660 | 0.4934 | 49340 |  | 50.66 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 193 | 0 | 18 May 2022 | SATISH RAMCHANDRA JAGTAP | KEP Common Plumbing Bldg Water Connection line from BMC | Lumpsum work- DCW | No. | 1 | 20560 | 20560 | 0 | 20560 | 0 | 1 | 20560 | 0 | 20560 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 194 | 0 | 21 May 2022 | AJAY KUMAR GUPTA | Expansion Joint Work | Expansion Joint (M+L) | Mtrs | 0 | 900 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | Transporatation and Food charges included | 0 |  | Dushant Gore |  | construction open | 21 May 2022 |  | No category | Cancelled | Dushant Gore | 21 May 2022
EAST POINT MARKET | 194 | 0 | 21 May 2022 | AJAY KUMAR GUPTA | Expansion Joint Work | Expansion Joint (M+L) | Mtrs | 64 | 900 | 57600 | 0 | 57600 | 10 | 64 | 57600 | 0 | 57600 | 0 | 0 | Transporatation and Food charges included. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 May 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 195 | 0 | 24 May 2022 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | LEAFLET PRINTING | No. | 1000 | 6.5 | 6500 | 780 | 7280 | 0 | 1000 | 6500 | 780 | 7280 | 0 | 0 | EAST POINT MARKET A-3 FLOOR PLAN MULTICOLOUR PRINTED 170 GSM ART PAPER SINGLE SIDED PRINTING. QTY. 500 + 500 | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 27 May 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 195 | 1 | 24 May 2022 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | PRINTING | No. | 1500 | 38 | 57000 | 6840 | 63840 | 0 | 1500 | 57000 | 6840 | 63840 | 0 | 0 | EAST POINT MARKET NEW BROCHURE PRINTING ( 2 GATE FOLD TYPE) 270 GSM RENDEZVOUS PAPER + AQUAS COATING BOTH SIDED MULTICOLOUR PRINTING QTY 1500 X 38/- + TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 27 May 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 196 | 0 | 24 May 2022 | WOW ENTERTAINMENT AND MEDIA PRIVATE LIMITED | Media BRANDING | Event Expenses | No. | 1 | 241645 | 241645 | 43496.1 | 285141.1 | 0 | 1 | 241645 | 43496.1 | 285141.1 | 0 | 0 | CP MEET AT EAST POINT MARKET KURLA DTD. 25TH MAY 2022 HOLE VENUE BRANDING (BOX GATE, EASEL BOAR, CHECKER BOARD, PAINTER, CARPENTER, TRANSPORT ETC | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 27 May 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 196 | 1 | 24 May 2022 | WOW ENTERTAINMENT AND MEDIA PRIVATE LIMITED | Media BRANDING | EXECUTION / MONETORING / MANAGEMENT CHARGES - FEES | No. | 1 | 8355 | 8355 | 1503.9 | 9858.9 | 0 | 1 | 8355 | 1503.9 | 9858.9 | 0 | 0 | EXECUTION / EVENT MANAGEMENT CHARGES | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 27 May 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 197 | 0 | 26 May 2022 | GOOD OLD DELIGHT | Media BRANDING | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 1050000 | 1050000 | 189000 | 1239000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | EAST POINT MARKET ONLINE DIGITAL MARKETING PLAN FOR 1 MONTH (TEXT ADVT, STATIC BANNERS, VEDIO, CAROUSEL, ETC. ON GOOGLE, FACEBOOK, LINKDIN, MONEY CONTROL ETC PLATFORM | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 27 May 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 9100 | 9100 | 0 | 9100 | 0 | 1 | 9100 | 0 | 9100 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 198 | 0 | 27 May 2022 | RATHOD DAYARAM BABULALJI | Food Expenses | Food Expenses-SO | Month | 1 | 4550 | 4550 | 0 | 4550 | 0 | 1 | 4550 | 0 | 4550 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.5417 | 3250.2 | 0 | 3250.2 | 0.4583 | 2749.8 |  | 54.17 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.9667 | 5800.2 | 0 | 5800.2 | 0.0333 | 199.8 |  | 96.67 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.9667 | 5800.2 | 0 | 5800.2 | 0.0333 | 199.8 |  | 96.67 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 31 May 2022 |  | Consultancy Proffessional | Cancelled | Dushant Gore | 31 May 2022
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.9667 | 5800.2 | 0 | 5800.2 | 0.0333 | 199.8 |  | 96.67 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 199 | 0 | 31 May 2022 | DURGA SHANKAR | Travelling Expenses | Travelling Allowance | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.9667 | 5800.2 | 0 | 5800.2 | 0.0333 | 199.8 |  | 96.67 |  | Dushant Gore | Swapnil Erande | construction open | 31 May 2022 |  | Consultancy Proffessional | Approved | Swapnil Erande
EAST POINT MARKET | 200 | 0 | 01 Mar 2022 | PIONEER ADVERTISING | Media BRANDING | LEAFLET PRINTING | No. | 142000 | 1.3 | 184600 | 33228 | 217828 | 0 | 142000 | 184600 | 33228 | 217828 | 0 | 0 | EAST POINT KURLA MARKET LEAFLET PRINT FOR NEWS PAPER INSERTION SIZE AS A-4 FRONT BACK BOTH SIDED PRINTING WITH DISTRIBUTION QTY. 142000 @ 1.30/- + TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 28 Jun 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 201 | 0 | 02 Jun 2022 | PIONEER ADVERTISING | Media BRANDING | LEAFLET PRINTING | No. | 142000 | 1.45 | 205900 | 37062 | 242962 | 0 | 142000 | 205900 | 37062 | 242962 | 0 | 0 | EAST POINT KURLA MARKET LEAFLET PRINT FOR NEWS PAPER INSERTION SIZE AS A-4 FRONT BACK BOTH SIDED PRINTING WITH DISTRIBUTION QTY. 142000 @ 1.45/- + TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 28 Jun 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 202 | 0 | 06 Jun 2022 | SS ARTS | Media BRANDING | ACRYLIC LETTER WORK | No. | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ACRYLIC LOGO INLIT AT RECEIPTION AREA EAST POINT MARLL- KURLA SIZE AS 5 FT X 1 FT (720 INCHES) MATERIAL WITH LED LIGHT + LABOUR + TRANSPORT ETC. | 0 |  | Tejas Raverkar |  | construction open |  |  | MKT. Media | Un-Approved
EAST POINT MARKET | 203 | 0 | 11 Jun 2022 | THE FAMOUS INDIA ENTERPRISES | Site Misc Misc. Work | Breaker | Day | 2 | 1550 | 3100 | 558 | 3658 | 0 | 2 | 3100 | 558 | 3658 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 203 | 0 | 11 Jun 2022 | THE FAMOUS INDIA ENTERPRISES | Site Misc Misc. Work | Labour Lumsum | No. | 1 | 1800 | 1800 | 324 | 2124 | 0 | 1 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande
EAST POINT MARKET | 204 | 0 | 11 Jun 2022 | RATHI CATERERS | Catering service for Event | Catering Services Exp. | No. | 1 | 90600 | 90600 | 16308 | 106908 | 0 | 1 | 90600 | 4530 | 95130 | 0 | 11778 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | MKT. Media | Approved | Swapnil Erande
EAST POINT MARKET | 204 | 0 | 11 Jun 2022 | RATHI CATERERS | Catering service for Event | Catering Services Exp. | No. | 1 | 120000 | 120000 | 21600 | 141600 | 0 | 1 | 120000 | 6000 | 126000 | 0 | 15600 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | MKT. Media | Approved | Swapnil Erande
EAST POINT MARKET | 205 | 0 | 11 Jun 2022 | A-1 ENTERPRISES | UGWT Cleaning | Cleaning Charges | No. | 1 | 11000 | 11000 | 1980 | 12980 | 0 | 1 | 11000 | 1980 | 12980 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 205 | 0 | 11 Jun 2022 | A-1 ENTERPRISES | UGWT Cleaning | Cleaning Charges | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 12 Sep 2022
EAST POINT MARKET | 205 | 0 | 11 Jun 2022 | A-1 ENTERPRISES | UGWT Cleaning | Cleaning Charges | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jun 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 12 Sep 2022
EAST POINT MARKET | 206 | 1 | 21 Jun 2022 | MILLENNIUM ARTS | Media BRANDING | PRINTING | No. | 1000 | 30 | 30000 | 5400 | 35400 | 0 | 1000 | 30000 | 5400 | 35400 | 0 | 0 | EAST POINT KURLA PROJECT BROCHURE PRINTING SIZE AS CLOSED A-4, GATE 2 FOLD BOTH SIDE MULTICOLOUR ON 270 GSM WITH RENDEZVOUS PAPER WITHAQUAS COATING | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 21 Jun 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 206 | 2 | 21 Jun 2022 | MILLENNIUM ARTS | Media BRANDING | Booklet / Notepad / Diary / Pocket Print | No. | 40 | 30 | 1200 | 216 | 1416 | 0 | 40 | 1200 | 216 | 1416 | 0 | 0 | BROCHURE PRINTING - INSTANT GAIN 3 GOLD (6 PAGES) 4 COLOUR PRINTING SIZEAS A-4 @30/- | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 21 Jun 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 206 | 0 | 21 Jun 2022 | MILLENNIUM ARTS | Media BRANDING | LEAFLET PRINTING | No. | 28000 | 1.7 | 47600 | 8568 | 56168 | 0 | 28000 | 47600 | 8568 | 56168 | 0 | 0 | east point kurla project leaflet print with paper insert size as a-4, 100 gsm art paper | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 21 Jun 2022 |  | MKT. Media | Approved | Tejas Raverkar
EAST POINT MARKET | 207 | 1 | 11 Jul 2022 | KHAN KAMAR ALAM | 4th Floor Show Office (Shop No. 5) Gypsum work | Gypsum Partition (M+L) | R.Ft | 113.16 | 70 | 7921.2 | 0 | 7921.2 | 2.5 | 0 | 0 | 0 | 0 | 113.16 | 0 | Both Side Gypsum with Patti in Middle. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Jul 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 207 | 1 | 11 Jul 2022 | KHAN KAMAR ALAM | 4th Floor Show Office (Shop No. 5) Gypsum work | Gypsum Patta (M+L) | R.Ft | 65.6 | 50 | 3280 | 0 | 3280 | 2.5 | 0 | 0 | 0 | 0 | 65.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Jul 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 207 | 0 | 11 Jul 2022 | KHAN KAMAR ALAM | 4th Floor Show office Gypsum work on labour basis | Gypsum on Wall (L) | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Qty= 44.98+8.064+17.856+12.16+20.52+18.354+5.4+5.38 = 132.716 Sq.m i.e- 1428.55 Sq.ft. | 0 |  | ADITYA CHOUGULE |  | construction open | 11 Jul 2022 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA CHOUGULE | 11 Jul 2022
EAST POINT MARKET | 207 | 0 | 11 Jul 2022 | KHAN KAMAR ALAM | 4th Floor Show office Gypsum work on labour basis | Gypsum on Wall (L) | Sq.Ft | 1428.55 | 15 | 21428.25 | 0 | 21428.25 | 2.5 | 1428.55 | 21428.25 | 0 | 21428.25 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Jul 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 207 | 1 | 11 Jul 2022 | KHAN KAMAR ALAM | 4th Floor Show Office (Shop No. 5) Gypsum work | Gypsum Board Partition (M+L)-BC | Sq.Ft | 314.95 | 115 | 36219.25 | 0 | 36219.25 | 2.5 | 314.95 | 36219.25 | 0 | 36219.25 | 0 | 0 | Both Side Gypsum with Channel. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Jul 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande
EAST POINT MARKET | 207 | 1 | 11 Jul 2022 | KHAN KAMAR ALAM | 4th Floor Show Office (Shop No. 5) Gypsum work | False Ceiling (M+L)- SOS | Sq.Ft | 1004.711 | 75 | 75353.33 | 0 | 75353.33 | 2.5 | 1004.7009 | 75352.57 | 0 | 75352.57 | 0.0101 | 0.76 |  | 99.999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Jul 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 208 | 0 | 11 Jul 2022 | DILIP NAMDEV PAWAR | Rolling shutter Grease work | Rolling Shutter Grease Work - No. | No. | 10 | 500 | 5000 | 0 | 5000 | 2.5 | 10 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 209 | 0 | 14 Jul 2022 | KHAN KAMAR ALAM | Gr Floor Gypsum plaster L/S work - Toilet - 750.04 Sqft - | Labour Lumsum | No. | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 1 | 20000 | 0 | 20000 | 0 | 0 | 1.Ladies Toilet- SS Patta Behind-33.6Mtr, Behind Mirror- 7.459 sqm, Above Marble- 27.972 sqm. 2.Gents Toilet- SS Patta Behind-33.6Mtr, Behind Mirror- 16.506 sqm, Above Marble- 10.134 sqm. | 100 |  | aditya chougule | Swapnil Erande | construction open | 19 Jul 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande
EAST POINT MARKET | 209 | 1 | 14 Jul 2022 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | Gala Cutting | No. | 90 | 60 | 5400 | 0 | 5400 | 2.5 | 90 | 5400 | 0 | 5400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Unloading of AAC Blocks | No. | 1705 | 3 | 5115 | 0 | 5115 | 0 | 1705 | 5115 | 0 | 5115 | 0 | 0 | 1.17/5/2022- 220 Nos. 2.18/5/2022- 230 Nos. 3.20/5/2022- 1255 Nos. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Unloading work-SO | No. | 362 | 3 | 1086 | 0 | 1086 | 0 | 362 | 1086 | 0 | 1086 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 1st Floor Pizza hut Ghadai & Debris shifting | Breaker-BC | No. | 3 | 1300 | 3900 | 0 | 3900 | 0 | 3 | 3900 | 0 | 3900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Flr Shop No. 5 Single Coat Plaster for Toilet & Pantry | Single Coat Plaster (L) | Sq.Ft | 826.16 | 20 | 16523.2 | 0 | 16523.2 | 2.5 | 826.16 | 16523.2 | 0 | 16523.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Misc works | Tile breaking Work - AIE | Sq.Ft | 670 | 13 | 8710 | 0 | 8710 | 0 | 670 | 8710 | 0 | 8710 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | Admin. Indirect Expenses | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 3 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | KEP-5th Floor RCC Gutter Pardi Casting work | RCC Work -SOI | No. | 1 | 15600 | 15600 | 2808 | 18408 | 2.5 | 1 | 15600 | 0 | 15600 | 0 | 2808 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Misc works | Material Shifting | Sq.Ft | 2496.7 | 2 | 4993.4 | 0 | 4993.4 | 0 | 1451.5 | 2903 | 0 | 2903 | 1045.2 | 2090.4 |  | 58.1367 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | S OH Infrastructure | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement Storage Toilet Making | RCC Lintel BC | No. | 2 | 100 | 200 | 0 | 200 | 2.5 | 2 | 200 | 0 | 200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Mason - DCW | No. | 73.5 | 850 | 62475 | 0 | 62475 | 0 | 73.5 | 62475 | 0 | 62475 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement Storage Toilet Making | Blockwork - USS | Sq.Ft | 269 | 16 | 4304 | 0 | 4304 | 2.5 | 269 | 4304 | 0 | 4304 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. Solar System | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Front Plaza KFC Store front | Blockwork - USS | Sq.Ft | 70 | 20 | 1400 | 0 | 1400 | 2.5 | 70 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. Solar System | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement partition Block work | Lumpsum work- DCW | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 1st Floor Pizza hut Ghadai & Debris shifting | Debris Removing & Shifting Work | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | Unloading of AAC Blocks | No. | 10000 | 3 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 |  | 0 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | S OH Expenses | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Blockwork ULT | Sq.Ft | 195.81 | 18 | 3524.58 | 0 | 3524.58 | 2.5 | 195.81 | 3524.58 | 0 | 3524.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Front Plaza KFC Store front | Lumpsum work- DCW | No. | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Shop No. 5 Block work | Blockwork - Utv | Sq.Ft | 947.58 | 18 | 17056.44 | 0 | 17056.44 | 2.5 | 947.58 | 17056.44 | 0 | 17056.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. Vermiculture | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Mall Maintenance Departmetal work | Male Coolie | No. | 23 | 500 | 11500 | 0 | 11500 | 0 | 23 | 11500 | 0 | 11500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 1 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | KEP-4th Fl Flooring PCC Work | PCC Work | Sq.Ft | 1794.33 | 10 | 17943.3 | 0 | 17943.3 | 2.5 | 1405.75 | 14057.5 | 0 | 14057.5 | 388.58 | 3885.8 |  | 78.344 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 02 RCC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Beam Casting - Cu.Ft | Cu.Ft | 60 | 50 | 3000 | 0 | 3000 | 2.5 | 60 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 02 RCC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Double Coat Plaster work (L) | Sq.Ft | 315 | 30 | 9450 | 0 | 9450 | 2.5 | 315 | 9450 | 0 | 9450 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Front Plaza KFC Store front | Lumpsum work- DCW | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 25 Jul 2022
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Shop No. 5 Slab Ghadai & PCC | PCC | Sq.Ft | 612.23 | 10 | 6122.3 | 0 | 6122.3 | 2.5 | 612.23 | 6122.3 | 0 | 6122.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement Storage Toilet Making | Breaker-BC | No. | 3 | 1300 | 3900 | 0 | 3900 | 0 | 3 | 3900 | 0 | 3900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Misc works | Tile breaking Work - AIE | Sq.Ft | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | Admin. Indirect Expenses | Cancelled | ADITYA.CHOUGULE | 15 Jul 2023
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Front Plaza KFC Store front | Single Coat Plaster (L) | Sq.Ft | 126 | 20 | 2520 | 0 | 2520 | 2.5 | 126 | 2520 | 0 | 2520 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Excavation | Cu.Ft | 100 | 8 | 800 | 0 | 800 | 0 | 100 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | Breaker | Day | 10 | 1300 | 13000 | 0 | 13000 | 0 | 4 | 5200 | 0 | 5200 | 6 | 7800 |  | 40 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | B.C. Building Common Items | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Flr Shop No. 5 Single Coat Plaster for Toilet & Pantry | Single Coat Plaster (L) | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA CHOUGULE | 23 Jul 2022
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Ground Floor Soil excavation for BMC water connection | Breaker-BC | No. | 2 | 1300 | 2600 | 0 | 2600 | 0 | 2 | 2600 | 0 | 2600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Excavation | Cu.Ft | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. RCC Substructure | Cancelled | ADITYA CHOUGULE | 25 Jul 2022
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Shop No. 5 Slab Ghadai & PCC | Breaker-BC | No. | 1 | 1300 | 1300 | 0 | 1300 | 0 | 1 | 1300 | 0 | 1300 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | Mason - DCW | No. | 30 | 950 | 28500 | 0 | 28500 | 0 | 14.5 | 13775 | 0 | 13775 | 15.5 | 14725 |  | 48.3333 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | DEV. Compound Wall | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Front Plaza KFC Store front | Lumpsum work- DCW | No. | 1 | 4500 | 4500 | 0 | 4500 | 2.5 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 1 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | KEP-4th Floor Ghadai work | Ghadai work- BCP | Sq.Ft | 8432.37 | 5 | 42161.85 | 0 | 42161.85 | 2.5 | 4060.32 | 20301.6 | 0 | 20301.6 | 4372.05 | 21860.25 |  | 48.1516 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Front Plaza KFC Store front | Single Coat Plaster (L) | Sq.Ft | 140 | 20 | 2800 | 0 | 2800 | 2.5 | 140 | 2800 | 0 | 2800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Shop No. 5 Slab Ghadai & PCC | Breaker-BC | No. | 2 | 1300 | 2600 | 0 | 2600 | 0 | 2 | 2600 | 0 | 2600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement New Storage Floor PCC | PCC | Sq.Ft | 301.87 | 10 | 3018.7 | 0 | 3018.7 | 2.5 | 301.87 | 3018.7 | 0 | 3018.7 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 1st Floor Shop No. 13 PCC | PCC | Sq.Ft | 861 | 10 | 8610 | 0 | 8610 | 2.5 | 861 | 8610 | 0 | 8610 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Lumpsum work- DCW | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | OHWT Cover fixing in brickwork | M.S. Cover- UWT | No. | 4 | 800 | 3200 | 0 | 3200 | 2.5 | 4 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. U.G.W.T | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Misc works | PCC Work BCE | Sq.Ft | 2496.7 | 10 | 24967 | 0 | 24967 | 2.5 | 1451.3 | 14513 | 0 | 14513 | 1045.4 | 10454 |  | 58.1287 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | B.C. Elevation Features | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Misc works | Breaking Work - Dld | Sq.Ft | 188 | 12 | 2256 | 0 | 2256 | 0 | 188 | 2256 | 0 | 2256 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | DEV. Landscape/Equipment | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement ramp entrance work | Debris Removing & Shifting Work | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | Blockwork 4" - BC | Sq.Ft | 820.43 | 18 | 14767.74 | 0 | 14767.74 | 2.5 | 0 | 0 | 0 | 0 | 820.43 | 0 |  | 0 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | B.C. BBM, Plaster, POP | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | Helper - SM | No. | 30 | 600 | 18000 | 0 | 18000 | 0 | 11.5 | 6900 | 0 | 6900 | 18.5 | 11100 |  | 38.3333 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | UTI. Strom Line | Approved | raviraj agarwal
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement partition Block work | Blockwork - Utv | Sq.Ft | 244.75 | 18 | 4405.5 | 0 | 4405.5 | 2.5 | 244.75 | 4405.5 | 0 | 4405.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | UTI. Vermiculture | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement Storage Toilet Making | Single Coat Plaster (L) | Sq.Ft | 432.43 | 20 | 8648.6 | 0 | 8648.6 | 2.5 | 432.43 | 8648.6 | 0 | 8648.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Ground Floor Soil excavation for BMC water connection | Excavation | Cu.Ft | 427.5 | 6.5 | 2778.75 | 0 | 2778.75 | 0 | 427.5 | 2778.75 | 0 | 2778.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 0 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | Basement partition Block work | Unloading of Cement | Bags | 70 | 10 | 700 | 0 | 700 | 0 | 70 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 210 | 2 | 23 Jul 2022 | SURESH KUMAR MURALIDHAR | 4th Floor Misc works | Tile breaking Work - AIE | Sq.Ft | 174.37 | 15 | 2615.55 | 0 | 2615.55 | 0 | 174.3333 | 2615 | 0 | 2615 | 0.0367 | 0.55 |  | 99.979 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | Admin. Indirect Expenses | Approved | raviraj agarwal
EAST POINT MARKET | 211 | 0 | 25 Jul 2022 | AMPLE IMPRESSIONS | Media BRANDING | PRINTING | No. | 400 | 155 | 62000 | 11160 | 73160 | 0 | 400 | 62000 | 11160 | 73160 | 0 | 0 | INVITE PRINT SIZE AS 6X10 INCH GREEN CARD 250 GSM, GOLD METALIC PAPER + ENVELOPE SIZE AS 6.15 X 10.15 INCH 130 GSM GOLD METALIC PAPER QTY 400 @ 155 + TAX | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 08 Sep 2022 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 212 | 0 | 04 Aug 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Develpement Parking area barricading work | M.S.Chain Fixing (M+L) | R.Ft | 42 | 100 | 4200 | 756 | 4956 | 2.5 | 42 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Aug 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 212 | 0 | 04 Aug 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Develpement Parking area barricading work | MS Channel Fixing BCo | Kgs | 857.099 | 21 | 17999.08 | 3239.84 | 21238.92 | 2.5 | 857.099 | 17999.08 | 3239.84 | 21238.92 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Aug 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 213 | 0 | 23 Aug 2022 | SAHARA ENGINEERING | Sales Office Shifting From 2nd to 3rd Fl | Lumpsum work- DCW | No. | 1 | 65000 | 65000 | 11700 | 76700 | 0 | 0.4615 | 29997.5 | 5399.56 | 35397.06 | 0.5385 | 41302.94 |  | 46.15 |  | Dushant Gore | Swapnil Erande | construction open | 06 Sep 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 214 | 0 | 29 Aug 2022 | AZAM KHAN | M.S. Fabrication material painting | Rust-o-cap Paint (M) | Drum | 2 | 7500 | 15000 | 0 | 15000 | 0 | 2 | 15000 | 0 | 15000 | 0 | 0 | 20 litres x 2 Drum. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 214 | 0 | 29 Aug 2022 | AZAM KHAN | M.S. Fabrication material painting | Transport Charges | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 214 | 0 | 29 Aug 2022 | AZAM KHAN | M.S. Fabrication material painting | Turpentine | Ltrs | 50 | 20 | 1000 | 0 | 1000 | 0 | 50 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 214 | 0 | 29 Aug 2022 | AZAM KHAN | M.S. Fabrication material painting | Thinner (M) | Ltrs | 40 | 150 | 6000 | 0 | 6000 | 0 | 40 | 6000 | 0 | 6000 | 0 | 0 | 20 litres x 2 Drum. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 214 | 0 | 29 Aug 2022 | AZAM KHAN | M.S. Fabrication material painting | Turpentine | Ltrs | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 29 Aug 2022
EAST POINT MARKET | 215 | 0 | 29 Aug 2022 | MD JAFAR IMAM | AC Dismentalling & Repair Work | AC Repairing work (M) | No. | 1 | 1092 | 1092 | 0 | 1092 | 0 | 1 | 1092 | 0 | 1092 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 215 | 0 | 29 Aug 2022 | MD JAFAR IMAM | AC Dismentalling & Repair Work | Pipe Leakage work | No. | 3 | 1000 | 3000 | 0 | 3000 | 0 | 3 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 215 | 0 | 29 Aug 2022 | MD JAFAR IMAM | AC Dismentalling & Repair Work | Dismentalling work-UTI | No. | 4 | 1500 | 6000 | 0 | 6000 | 0 | 4 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 215 | 0 | 29 Aug 2022 | MD JAFAR IMAM | AC Dismentalling & Repair Work | Gas Charging | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 216 | 0 | 02 Sep 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Site Infra Labour Huts making | Hut Making | No. | 12 | 2000 | 24000 | 4320 | 28320 | 2.5 | 12 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 11 Oct 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 216 | 0 | 02 Sep 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Site Infra Labour Huts making | Street Light Pole fixing (L). | Kgs | 170 | 21 | 3570 | 642.6 | 4212.6 | 2.5 | 170 | 3570 | 642.6 | 4212.6 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 11 Oct 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 216 | 0 | 02 Sep 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Site Infra Labour Huts making | Dismentalling work-UTI | No. | 13 | 615 | 7995 | 1439.1 | 9434.1 | 0 | 13 | 7995 | 1439.1 | 9434.1 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 11 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 217 | 0 | 02 Sep 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Site Infra Labour Huts making | Street Light Pole fixing (M). | Kgs | 170 | 84 | 14280 | 2570.4 | 16850.4 | 0 | 170 | 14280 | 2570.4 | 16850.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 11 Oct 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 02 Sep 2022
EAST POINT MARKET | 217 | 0 | 02 Sep 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Site Infra Labour Huts making | M.S. Bracket | No. | 9 | 800 | 7200 | 1296 | 8496 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 11 Oct 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 217 | 0 | 02 Sep 2022 | ANAND ROLLING SHUTTER & FABRICATOR | Site Infra Labour Huts making | MS Square Pipe (M) | Kgs | 165 | 84 | 13860 | 2494.8 | 16354.8 | 0 | 165 | 13860 | 2494.8 | 16354.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 11 Oct 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 02 Sep 2022
EAST POINT MARKET | 218 | 0 | 02 Sep 2022 | THE KREATOR | Media BRANDING | Event Expenses | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 | 15TH AUGUST - EVENT AT PROJECT SITE BALOON DECORATION GROUND FLOOR - MAIN ENTRANCE, ESCALATOR FROM GROUND TO 3RD FLOOR, 2ND FLOOR GUARDIAN OFFICE ENTRANCE GATE, 3RD FLOOR MANAGEMENT OFFICE ENTRANCE GATE | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 07 Sep 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 219 | 0 | 02 Sep 2022 | KRISHNA DECORATORS | Media BRANDING | Event Expenses | No. | 1 | 54000 | 54000 | 9720 | 63720 | 0 | 1 | 54000 | 9720 | 63720 | 0 | 0 | 15TH AUGUST INDEPENDANCE DAY CELIBRATION AT PROJECT SITE (LIGHTS, 70 MTR LACH) | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 07 Sep 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR | 05 Sep 2022
EAST POINT MARKET | 220 | 0 | 07 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Maintenance of Utilities -Lift AMC Work | Lift Maintenance | Month | 12 | 5512.5 | 66150 | 11907 | 78057 | 0 | 12 | 66150 | 11907.1 | 78057.1 | 0 | -0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Sep 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 220 | 2 | 07 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Maintenance of Utilities -Lift AMC Work | Lift Maintenance | Month | 0 | 5788.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Sep 2022 |  | SOC. M. Maintenace of Utilitie | Cancelled | DUSHANT.GORE | 12 Dec 2023
EAST POINT MARKET | 220 | 1 | 07 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Maintenance of Utilities -Lift AMC Work | Lift Maintenance | Month | 0 | 5788.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 07 Sep 2022 |  | SOC. M. Maintenace of Utilitie | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 221 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 1 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SANKET PATIL |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 221 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 1 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 222 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 2 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 222 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 2 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 223 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 3 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 223 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 3 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 224 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 4 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 224 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 4 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 225 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 5 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 225 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 5 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 226 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 6 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 226 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 6 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 227 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 7 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 227 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 7 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 228 | 2 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 8 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 228 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 8 AMC Charges | AMC Charges | Month | 0 | 7083.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 19 Sep 2022
EAST POINT MARKET | 228 | 1 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 8 AMC Charges | AMC Charges | Month | 0 | 7437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 20 Oct 2023
EAST POINT MARKET | 228 | 0 | 19 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Escalator - 8 AMC Charges | AMC Charges | Month | 12 | 7083.33 | 84999.96 | 15300 | 100299.96 | 0 | 12 | 84999.96 | 15299.9 | 100299.86 | 0 | 0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 229 | 1 | 23 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Maintenance of Utilities - Lift No. 2 AMC Work | Lift Maintenance | Month | 0 | 5788.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | AKSHADA MAHAJAN |  | construction open | 23 Sep 2022 |  | SOC. M. Maintenace of Utilitie | Cancelled | DUSHANT.GORE | 21 Oct 2023
EAST POINT MARKET | 229 | 2 | 23 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Maintenance of Utilities - Lift No. 2 AMC Work | Lift Maintenance | Month | 0 | 5788.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2022 |  | SOC. M. Maintenace of Utilitie | Cancelled | DUSHANT.GORE | 12 Dec 2023
EAST POINT MARKET | 229 | 0 | 23 Sep 2022 | SCHINDLER INDIA PVT. LTD. | Maintenance of Utilities - Lift No. 2 AMC Work | Lift Maintenance | Month | 12 | 5512.5 | 66150 | 11907 | 78057 | 0 | 12 | 66150 | 11907.1 | 78057.1 | 0 | -0.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 23 Sep 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 48 | 528 | 25344 | 4561.92 | 29905.92 | 2.5 | 48 | 25344 | 4561.92 | 29905.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Consiled Door Closer (M+L) | No. | 2 | 4400 | 8800 | 1584 | 10384 | 2.5 | 2 | 8800 | 1584 | 10384 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Repairing Work Mkt | No. | 1 | 17600 | 17600 | 3168 | 20768 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 28 | 572 | 16016 | 2882.88 | 18898.88 | 2.5 | 28 | 16016 | 2882.88 | 18898.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Ply fixing (L) | Sq.Ft | 500 | 70.4 | 35200 | 6336 | 41536 | 2.5 | 311.36 | 21919.74 | 3945.56 | 25865.3 | 188.64 | 15670.7 |  | 62.272 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 22 | 572 | 12584 | 2265.12 | 14849.12 | 2.5 | 22 | 12584 | 2265.12 | 14849.12 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Doors with door closer. | No. | 2 | 13200 | 26400 | 4752 | 31152 | 2.5 | 2 | 26400 | 4752 | 31152 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door with consiled door closer. | No. | 2 | 17600 | 35200 | 6336 | 41536 | 2.5 | 2 | 35200 | 6336 | 41536 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & fixing of Patta. | R.Ft | 200 | 220 | 44000 | 7920 | 51920 | 2.5 | 200 | 44000 | 7920 | 51920 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | 2" Handle (M+L) | set | 6 | 3080 | 18480 | 3326.4 | 21806.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 1 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | 3rd Floor Meter Room Ply Removing & Fixing work | Ply fixing (L) | Sq.Ft | 661.124 | 75 | 49584.3 | 8925.18 | 58509.48 | 2.5 | 330.23 | 24767.25 | 4458.1 | 29225.35 | 330.894 | 29284.13 |  | 49.9498 |  | DUSHANT.GORE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 0 | 600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 0 | 600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 144 | 528 | 76032 | 13685.76 | 89717.76 | 2.5 | 0 | 0 | 0 | 0 | 144 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 0 | 600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 66.5 | 572 | 38038 | 6846.84 | 44884.84 | 2.5 | 42.25 | 24167 | 4350.06 | 28517.06 | 24.25 | 16367.78 |  | 63.5338 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Glass Door fitting, removing & refixing. | No. | 0 | 2000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 0 | 600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Dummy Frames. | R.Ft | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 14 | 572 | 8008 | 1441.44 | 9449.44 | 2.5 | 14 | 8008 | 1441.44 | 9449.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 56 | 572 | 32032 | 5765.76 | 37797.76 | 2.5 | 51.56 | 29492.32 | 5308.62 | 34800.94 | 4.44 | 2996.82 |  | 92.0714 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing & Making of door | No. | 4 | 11440 | 45760 | 8236.8 | 53996.8 | 2.5 | 3 | 34320 | 6177.6 | 40497.6 | 1 | 13499.2 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Glass Door fitting, removing & refixing. | No. | 6 | 1760 | 10560 | 1900.8 | 12460.8 | 2.5 | 5 | 8800 | 1584 | 10384 | 1 | 2076.8 |  | 83.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 150 | 528 | 79200 | 14256 | 93456 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Dummy Frames. | R.Ft | 120 | 704 | 84480 | 15206.4 | 99686.4 | 2.5 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 1 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | 3rd Floor Meter Room Ply Removing & Fixing work | Plywood Removing-BRE | Sq.Ft | 655.75 | 35 | 22951.25 | 4131.22 | 27082.47 | 0 | 303.65 | 10627.75 | 1913 | 12540.75 | 352.1 | 14541.72 |  | 46.3058 |  | DUSHANT.GORE | Swapnil Erande | construction open | 05 Nov 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Door Lock (M+L) | set | 2 | 1760 | 3520 | 633.6 | 4153.6 | 2.5 | 2 | 3520 | 633.6 | 4153.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 100 | 704 | 70400 | 12672 | 83072 | 2.5 | 100 | 70400 | 12672 | 83072 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 16 | 572 | 9152 | 1647.36 | 10799.36 | 2.5 | 16 | 9152 | 1647.36 | 10799.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 1 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | GF Meter Room Ply Fixing work | Ply fixing (L) | Sq.Ft | 473.93 | 75 | 35544.75 | 6398.06 | 41942.81 | 2.5 | 0 | 0 | 0 | 0 | 473.93 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 05 Nov 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Ply Panelling. | Sq.Ft | 147 | 528 | 77616 | 13970.88 | 91586.88 | 2.5 | 0 | 0 | 0 | 0 | 147 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 19 | 704 | 13376 | 2407.68 | 15783.68 | 2.5 | 19 | 13376 | 2407.68 | 15783.68 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 28 | 572 | 16016 | 2882.88 | 18898.88 | 2.5 | 26 | 14872 | 2676.96 | 17548.96 | 2 | 1349.92 |  | 92.8571 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Repairing Work Mkt | No. | 0 | 20000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making of Door Frames. | R.Ft | 19 | 704 | 13376 | 2407.68 | 15783.68 | 2.5 | 19 | 13376 | 2407.68 | 15783.68 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Providing and Making 6mm mirror panel. | Sq.Ft | 15 | 572 | 8580 | 1544.4 | 10124.4 | 2.5 | 15 | 8580 | 1544.4 | 10124.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Nov 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 230 | 0 | 05 Nov 2022 | ANAND FURNITURE AND INTERIOR | Furniture Work | Ply fixing (L) | Sq.Ft | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Nov 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 05 Nov 2022
EAST POINT MARKET | 231 | 0 | 06 Dec 2022 | SATISH RAMCHANDRA JAGTAP | Staff incentive | Incentive | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 231 | 0 | 06 Dec 2022 | SATISH RAMCHANDRA JAGTAP | Staff incentive | Incentive | No. | 1 | 110000 | 110000 | 0 | 110000 | 0 | 1 | 110000 | 0 | 110000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 231 | 0 | 06 Dec 2022 | SATISH RAMCHANDRA JAGTAP | Staff incentive | Incentive | No. | 1 | 124000 | 124000 | 0 | 124000 | 0 | 1 | 124000 | 0 | 124000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 231 | 0 | 06 Dec 2022 | SATISH RAMCHANDRA JAGTAP | Staff incentive | Incentive | No. | 1 | 70000 | 70000 | 0 | 70000 | 0 | 1 | 70000 | 0 | 70000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 231 | 0 | 06 Dec 2022 | SATISH RAMCHANDRA JAGTAP | Staff incentive | Incentive | No. | 1 | 15050 | 15050 | 0 | 15050 | 0 | 1 | 15050 | 0 | 15050 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 8 Module Box (M) | No. | 50 | 94 | 4700 | 846 | 5546 | 0 | 33 | 3102 | 558.36 | 3660.36 | 17 | 1885.64 |  | 66 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 16 Amp Switch (M) | No. | 50 | 133 | 6650 | 1197 | 7847 | 0 | 33 | 4389 | 790.02 | 5179.02 | 17 | 2667.98 |  | 66 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Ceiling Rose (M) | No. | 30 | 25 | 750 | 135 | 885 | 0 | 30 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | PVC Conduit Piping (M) | Mtrs | 260 | 35 | 9100 | 1638 | 10738 | 0 | 260 | 9100 | 1638 | 10738 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Fan Hook (M) | No. | 18 | 94 | 1692 | 304.56 | 1996.56 | 0 | 18 | 1692 | 304.56 | 1996.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Cable 2.5 sqmm (M) | Mtrs | 200 | 28 | 5600 | 1008 | 6608 | 0 | 200 | 5600 | 1008 | 6608 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Square Box (M) | No. | 30 | 15 | 450 | 81 | 531 | 0 | 30 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 1.5 Sqmm Cable laying (M) | Mtrs | 250 | 17 | 4250 | 765 | 5015 | 0 | 250 | 4250 | 765 | 5015 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 12 Way ETPN DB (M) | No. | 1 | 5375 | 5375 | 967.5 | 6342.5 | 0 | 1 | 5375 | 967.5 | 6342.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 3C 2.5 sqmm Cu Cable (M) | Mtrs | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Dec 2022
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 300 | 96 | 28800 | 5184 | 33984 | 0 | 300 | 28800 | 5184 | 33984 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | End Termination 4C x 6sqmm (M) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 1 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 8 Module Plate (M) | No. | 50 | 195 | 9750 | 1755 | 11505 | 0 | 33 | 6435 | 1158.3 | 7593.3 | 17 | 3911.7 |  | 66 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 232 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 13 Amp Socket (M) | No. | 50 | 167 | 8350 | 1503 | 9853 | 0 | 50 | 8350 | 1503 | 9853 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Cable 2.5 sqmm (L) | Mtrs | 200 | 12 | 2400 | 432 | 2832 | 2.5 | 200 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 3C 2.5 sqmm Cu Cable (L) | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Dec 2022
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | End Termination 4C x 6sqmm (L) | No. | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Dec 2022
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Ceiling Fan Fitting | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Dec 2022
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | DB Control Secondary Point for Fan (L) | No. | 15 | 150 | 2250 | 405 | 2655 | 2.5 | 15 | 2250 | 405 | 2655 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | T5 Light Fitting | No. | 32 | 100 | 3200 | 576 | 3776 | 2.5 | 32 | 3200 | 576 | 3776 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 12 Way ETPN DB (L) | No. | 1 | 1250 | 1250 | 225 | 1475 | 2.5 | 1 | 1250 | 225 | 1475 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Fan Hook (L) | No. | 18 | 75 | 1350 | 243 | 1593 | 2.5 | 18 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | PVC Conduit Piping (L) | Mtrs | 260 | 25 | 6500 | 1170 | 7670 | 2.5 | 260 | 6500 | 1170 | 7670 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 1.5 Sqmm Cable laying (L) | Mtrs | 250 | 12 | 3000 | 540 | 3540 | 2.5 | 250 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | DB Control Primary Point for LTG (L) | No. | 3 | 800 | 2400 | 432 | 2832 | 2.5 | 3 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | DB Control Secondary Point for LTG (L) | No. | 29 | 150 | 4350 | 783 | 5133 | 2.5 | 29 | 4350 | 783 | 5133 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Workstation Point | No. | 50 | 450 | 22500 | 4050 | 26550 | 2.5 | 50 | 22500 | 4050 | 26550 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Ceiling Fan Fitting | No. | 15 | 250 | 3750 | 675 | 4425 | 2.5 | 15 | 3750 | 675 | 4425 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Ceiling Rose (L) | No. | 30 | 10 | 300 | 54 | 354 | 2.5 | 30 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | End Termination 4C x 6sqmm (L) | No. | 1 | 100 | 100 | 18 | 118 | 2.5 | 1 | 100 | 18 | 118 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | DB Control Primary Point for Fan (L) | No. | 3 | 800 | 2400 | 432 | 2832 | 2.5 | 3 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | T5 Light Fitting | No. | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Dec 2022
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | 3C 2.5sqmm Flex. Cable (L) | Mtrs | 300 | 15 | 4500 | 810 | 5310 | 2.5 | 300 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Workstation Point | No. | 0 | 600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Dec 2022
EAST POINT MARKET | 233 | 0 | 07 Dec 2022 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Call centre office electrical work | Square Box (L) | No. | 30 | 10 | 300 | 54 | 354 | 2.5 | 30 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 0 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Printer on Rental Basis | Rental Charges. | Month | 1 | 3500 | 3500 | 630 | 4130 | 0 | 1 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jan 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 1 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Leasing/Management Office Cartridge Refilling | Toner Refilling (No.) | No. | 4 | 3500 | 14000 | 2520 | 16520 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jan 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 1 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Leasing/Management Office Cartridge Refilling | Toner Refilling (No.) | No. | 4 | 3500 | 14000 | 2520 | 16520 | 0 | 4 | 14000 | 2520 | 16520 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jan 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 1 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Leasing/Management Office Cartridge Refilling | Toner Refilling (No.) | No. | 4 | 3500 | 14000 | 2520 | 16520 | 0 | 3.6429 | 12750.15 | 2295 | 15045.15 | 0.3571 | 1474.85 |  | 91.0725 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jan 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 1 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Leasing/Management Office Cartridge Refilling | Toner Refilling (No.) | No. | 4 | 3500 | 14000 | 2520 | 16520 | 0 | 1 | 3500 | 630 | 4130 | 3 | 12390 |  | 25 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jan 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 0 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Printer on Rental Basis | Toner Refilling (No.) | No. | 4 | 3000 | 12000 | 2160 | 14160 | 0 | 4 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jan 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 0 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Printer on Rental Basis | Rental Charges. | Month | 1 | 3500 | 3500 | 630 | 4130 | 0 | 1 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jan 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 234 | 0 | 27 Dec 2022 | POWER POINT CARTRIDGES PRIVATE LIMITED | Printer on Rental Basis | Rental Charges. | Month | 1 | 3500 | 3500 | 630 | 4130 | 0 | 1 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jan 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 235 | 0 | 04 Jan 2023 | ZAK BUSINESS SERVICES PVT LTD | Site Expenses.. | Site Expenses -SO | Month | 12 | 11250 | 135000 | 0 | 135000 | 0 | 11.0004 | 123754.5 | 0 | 123754.5 | 0.9996 | 11245.5 |  | 91.67 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 235 | 1 | 04 Jan 2023 | ZAK BUSINESS SERVICES PVT LTD | Site Expenses.. | Site Expenses -SO | Month | 12 | 11250 | 135000 | 0 | 135000 | 0 | 7.9999 | 89998.7 | 0 | 89998.7 | 4.0001 | 45001.3 |  | 66.6658 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 236 | 0 | 04 Jan 2023 | MANOJ NAVIN PAREKH | Site Expenses.. | Site Expenses -SO | Month | 12 | 15000 | 180000 | 0 | 180000 | 0 | 10.8328 | 162492.01 | 0 | 162492.01 | 1.1672 | 17507.99 |  | 90.2733 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 236 | 1 | 04 Jan 2023 | MANOJ NAVIN PAREKH | Site Expenses.. | Site Expenses -SO | Month | 12 | 15000 | 180000 | 0 | 180000 | 0 | 6.1832 | 92748.63 | 0 | 92748.63 | 5.8168 | 87251.37 |  | 51.5267 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-1st Fl Electric Meter Liasening Charges | C.T. Meter Fixing Work. | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Three Phase Meter Sanction | No. | 14 | 8000 | 112000 | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Three Phase Meter Sanction | No. | 3 | 8000 | 24000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Single Phase Meter Sanction | No. | 19 | 4000 | 76000 | 0 | 76000 | 0 | 0 | 0 | 0 | 0 | 19 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Meter Cabin Sanction | No. | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Cancelled | DUSHANT GORE | 10 Jan 2023
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Meter Cabin Sanction | No. | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 4 | 22000 | 88000 | 0 | 88000 | 0 | 4 | 88000 | 0 | 88000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-Gr Fl GF Electric Meter Liasening Charges | Labour Lumpsum | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | Land Cost | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 24 | 6000 | 144000 | 0 | 144000 | 0 | 24 | 144000 | 0 | 144000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-1st Fl Electric Meter Liasening Charges | C.T. Meter Fixing Work. | No. | 4 | 22000 | 88000 | 0 | 88000 | 0 | 4 | 88000 | 0 | 88000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-Gr Fl GF Electric Meter Liasening Charges | Labour Lumpsum | No. | 1 | 22000 | 22000 | 0 | 22000 | 0 | 1 | 22000 | 0 | 22000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-1st Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 9 | 2000 | 18000 | 0 | 18000 | 0 | 9 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 2 | 10000 | 20000 | 0 | 20000 | 0 | 2 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Meter NOC (PWD) | No. | 14 | 4000 | 56000 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Meter NOC (PWD) | No. | 19 | 2500 | 47500 | 0 | 47500 | 0 | 0 | 0 | 0 | 0 | 19 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - 3rd Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-Gr Fl GF Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 237 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Meter NOC (PWD) | No. | 3 | 4000 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-1st Fl Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 7 | 6000 | 42000 | 0 | 42000 | 0 | 7 | 42000 | 0 | 42000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 237 | 1 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP-Gr Fl GF Electric Meter Liasening Charges | Electrical Meter Liasoning Charges | No. | 9 | 2000 | 18000 | 0 | 18000 | 0 | 9 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 | Load 90 KW. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 | Load 90 KW. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Deposit Charges | No. | 1 | 10300 | 10300 | 0 | 10300 | 0 | 1 | 10300 | 0 | 10300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 | Load 25 KW. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 238 | 0 | 09 Jan 2023 | CHETAN ELECTRICAL | KEP - Electrical Meter Sanction (Liaison) work | Electrical Meter Liasoning Charges | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 | Load 90 KW. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Gas Charging (L) | No. | 1 | 12000 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Drain Piping 32mm (L) | Mtrs | 30 | 25 | 750 | 135 | 885 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Drain Piping 25mm (L) | Mtrs | 40 | 20 | 800 | 144 | 944 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Control Cabling (L) | Mtrs | 170 | 20 | 3400 | 612 | 4012 | 2.5 | 0 | 0 | 0 | 0 | 170 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Refnets (Joints for Indoor Units) (L) | No. | 6 | 200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Cassette Unit 4 Way - 3.0 TR | No. | 2 | 3750 | 7500 | 1350 | 8850 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Cassette Type 1.6Tr (L) | No. | 5 | 3750 | 18750 | 3375 | 22125 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Pressure Testing, Vaccumising, Refrigerant Copper piping (L) | Mtrs | 130 | 15 | 1950 | 351 | 2301 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Outdoor Units- 14 HP | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved | DUSHANT GORE | 14 Jan 2023
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Refrigerant Piping (L) | Mtrs | 130 | 220 | 28600 | 5148 | 33748 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 239 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 3rd Floor - Gardian Office Air Conditioning | Stand for ODU unit (L) | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Drain Piping 25mm (L) | Mtrs | 100 | 20 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Control Cabling (L) | Mtrs | 300 | 20 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 300 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Outdoor Unit-36 HP | No. | 1 | 24000 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Internal Finishing Itmes | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | PVC Conduit Piping (L) | Mtrs | 300 | 8 | 2400 | 432 | 2832 | 2.5 | 0 | 0 | 0 | 0 | 300 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Refrigerant Piping (L) | Mtrs | 200 | 200 | 40000 | 7200 | 47200 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | 4TR Ductable Unit | No. | 9 | 3750 | 33750 | 6075 | 39825 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Internal Finishing Itmes | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Ductable Nozzle type Plenum unit (L) | No. | 9 | 1500 | 13500 | 2430 | 15930 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Pressure Testing, Vaccumising, Refrigerant Copper piping (L) | Mtrs | 200 | 15 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Stand for ODU unit (L) | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Gas Charging (L) | No. | 1 | 30000 | 30000 | 5400 | 35400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Refnets (Joints for Indoor Units) (L) | No. | 8 | 200 | 1600 | 288 | 1888 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Shifting Work BCE | No. | 1 | 14000 | 14000 | 2520 | 16520 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Internal Finishing Itmes | Un-Approved
EAST POINT MARKET | 240 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Drain Piping 32mm (L) | Mtrs | 150 | 25 | 3750 | 675 | 4425 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Un-Approved
EAST POINT MARKET | 241 | 0 | 14 Jan 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-Ventilation 2nd Floor Air Conditioning System | Refnets (Joints for Indoor Units) (M) | No. | 8 | 5000 | 40000 | 7200 | 47200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
EAST POINT MARKET | 242 | 0 | 17 Jan 2023 | NAGAUR STONES | 3rd Floor Atrium Passage side Granite work | Granite Flooring | Sq.Ft | 250.952 | 55 | 13802.36 | 2484.42 | 16286.78 | 2.5 | 250.9517 | 13802.34 | 2484.42 | 16286.76 | 0.0003 | 0.02 |  | 99.9999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 242 | 0 | 17 Jan 2023 | NAGAUR STONES | KEP - 4th Floor Lift Lobby (Railway & Fatima Side) | Granite Flooring | Sq.Ft | 104.72 | 55 | 5759.6 | 1036.72 | 6796.32 | 2.5 | 104.72 | 5759.6 | 1036.72 | 6796.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 242 | 0 | 17 Jan 2023 | NAGAUR STONES | KEP- 2nd Floor Atrium Passage side Granite Work | Granite Flooring | Sq.Ft | 266.34 | 55 | 14648.7 | 2636.76 | 17285.46 | 2.5 | 266.34 | 14648.7 | 2636.76 | 17285.46 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 242 | 0 | 17 Jan 2023 | NAGAUR STONES | KEP - 1st Floor Atrium Passage side Granite Work | Granite Flooring | Sq.Ft | 330.325 | 55 | 18167.88 | 3270.22 | 21438.1 | 2.5 | 330.325 | 18167.88 | 3270.22 | 21438.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 242 | 0 | 17 Jan 2023 | NAGAUR STONES | KEP - 4th Floor Lift Lobby (Railway & Fatima Side) | Granite Skirting | R.Ft | 34.833 | 55 | 1915.82 | 344.84 | 2260.66 | 2.5 | 34.833 | 1915.82 | 344.84 | 2260.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 242 | 0 | 17 Jan 2023 | NAGAUR STONES | KEP - 4th Floor Atrium Passage side Granite work | Granite Flooring | Sq.Ft | 307.732 | 55 | 16925.26 | 3046.54 | 19971.8 | 2.5 | 307.732 | 16925.26 | 3046.54 | 19971.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-1st Fl Door Shutter&Fitting Toilet Main Door | Carpentry work (m+l) | No. | 0.1 | 8480 | 848 | 152.64 | 1000.64 | 2.5 | 0.1 | 848 | 152.64 | 1000.64 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-2nd Fl Toilet SS Patta Fixing 75mm Mirror Finish | S.S. Patta (m+l) | R.Ft | 25.6 | 197.08 | 5045.25 | 908.14 | 5953.39 | 2.5 | 25.6 | 5045.25 | 908.14 | 5953.39 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-3rd Fl Door Shutter&Fitting Toilet Main Door | Carpentry work (m+l) | No. | 0.2 | 25480 | 5096 | 917.28 | 6013.28 | 2.5 | 0.2 | 5096 | 917.28 | 6013.28 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-2nd Fl Toilet Mirror Fixing (M+L) | Mirror fixing.. | Sq.Ft | 29.77 | 286.67 | 8534.17 | 1536.16 | 10070.33 | 2.5 | 29.77 | 8534.17 | 1536.16 | 10070.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-1st Fl Toilet Mirror Fixing (M+L) | Mirror fixing.. | Sq.Ft | 27.82 | 286.67 | 7975.16 | 1435.52 | 9410.68 | 2.5 | 27.82 | 7975.16 | 1435.52 | 9410.68 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-3rd Fl Toilet SS Patta Fixing 75mm Mirror Finish | S.S. Patta (m+l) | R.Ft | 25.6 | 197.08 | 5045.25 | 908.14 | 5953.39 | 2.5 | 25.6 | 5045.25 | 908.14 | 5953.39 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-1st Fl Toilet SS Patta Fixing 75mm Mirror Finish | S.S. Patta (m+l) | R.Ft | 25.83 | 197.08 | 5090.58 | 916.3 | 6006.88 | 2.5 | 25.83 | 5090.58 | 916.3 | 6006.88 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-3rd Fl Toilet Mirror Fixing (M+L) | Mirror fixing.. | Sq.Ft | 29.77 | 286.67 | 8534.17 | 1536.16 | 10070.33 | 2.5 | 29.77 | 8534.17 | 1536.16 | 10070.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-2nd Fl Door Shutter&Fitting Toilet Main Door | Carpentry work (m+l) | No. | 0.2 | 25480 | 5096 | 917.28 | 6013.28 | 2.5 | 0.2 | 5096 | 917.28 | 6013.28 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 243 | 0 | 17 Jan 2023 | RAMDEVRA INTERIORS | KEP-1st Fl Door Extra Work Shutter&Fitting Toilet Door Work | Door Fixing Charges-Toilet Door-BC | No. | 0.4 | 10302 | 4120.8 | 741.74 | 4862.54 | 2.5 | 0.4 | 4120.8 | 741.74 | 4862.54 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 0 | 24 Jan 2023 | KHAN KAMAR ALAM | 3rd Floor Food Court Seating area Grid Ceiling | Grid False Ceiling (M) | Sq.Ft | 2286.392 | 75 | 171479.4 | 0 | 171479.4 | 0 | 0 | 0 | 0 | 0 | 2286.392 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 1 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP-First FL Staircase Wall Plaster(Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 400.21 | 9.5 | 3802 | 0 | 3802 | 0 | 0 | 0 | 0 | 0 | 400.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 1 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP-Third FL Staircase Wall Plaster(Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 441.1 | 9.5 | 4190.45 | 0 | 4190.45 | 0 | 0 | 0 | 0 | 0 | 441.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 0 | 24 Jan 2023 | KHAN KAMAR ALAM | 3rd Floor Food Court Seating area Grid Ceiling | Grid False Ceiling (M) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA CHOUGULE | 24 Jan 2023
EAST POINT MARKET | 244 | 1 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP-Fourth FL Staircase Wall Plaster(Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 345.09 | 9.5 | 3278.36 | 0 | 3278.36 | 0 | 0 | 0 | 0 | 0 | 345.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 1 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP-Second FL Staircase Wall Plaster(Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 400.21 | 9.5 | 3802 | 0 | 3802 | 0 | 0 | 0 | 0 | 0 | 400.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 1 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP-Ground FL Staircase Wall Plaster(Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 400.21 | 9.5 | 3802 | 0 | 3802 | 0 | 0 | 0 | 0 | 0 | 400.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 244 | 1 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP-Basement FL Staircase Wall Plaster(Tikki Dhada) | Tikki Dhada (M) | Sq.Ft | 845.61 | 9.5 | 8033.3 | 0 | 8033.3 | 0 | 0 | 0 | 0 | 0 | 845.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 245 | 0 | 24 Jan 2023 | KHAN KAMAR ALAM | 3rd Floor Food Court Seating area Grid Ceiling | Grid False Ceiling (L) | Sq.Ft | 2286.392 | 15 | 34295.88 | 0 | 34295.88 | 2.5 | 0 | 0 | 0 | 0 | 2286.392 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 245 | 0 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP - 4th Floor Toilet wall gypsum | Groove in Plaster- DSP | R.Ft | 144 | 10 | 1440 | 0 | 1440 | 2.5 | 144 | 1440 | 0 | 1440 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Jan 2023 |  | DEV. Swimming Pool | Approved | Swapnil Erande
EAST POINT MARKET | 245 | 0 | 24 Jan 2023 | KHAN KAMAR ALAM | 3rd Floor Food Court Seating area Grid Ceiling | Gypsum Patta (M+L) | R.Ft | 934.209 | 45 | 42039.41 | 0 | 42039.41 | 2.5 | 934.209 | 42039.41 | 0 | 42039.41 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Jan 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 245 | 0 | 24 Jan 2023 | KHAN KAMAR ALAM | KEP - 4th Floor Toilet wall gypsum | Gypsum on Wall (L) | Sq.Ft | 260 | 15 | 3900 | 0 | 3900 | 2.5 | 260 | 3900 | 0 | 3900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Jan 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 246 | 0 | 02 Feb 2023 | EMRG SOLUTIONS | Media BRANDING | Event Expenses | No. | 1 | 288452 | 288452 | 51921.36 | 340373.36 | 0 | 1 | 288452 | 51921.36 | 340373.36 | 0 | 0 | EAST POINT KURLA BRANDING WORK AT KURLA SITE (GROUND FLOOR- PORCH AREA, 2ND FLOOR AREA FLEX PRINT WITH MS FRAME MAKING PASTING INSTALLATION ETC. CHOKAR BACK DROUPGATE ENTRANCE ARCH(BOX TYPE) COMPOUND WALL PANEL TRANSPORT + LABOUR ETC. FEB. 2022 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 13 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 247 | 0 | 02 Feb 2023 | EMRG SOLUTIONS | Media BRANDING | Event Expenses | No. | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 | EAST POINT MARKET- KURLA EVENT LAUNCH DTD. 19- 20 FEB. 22 ( VENUE BOOKING, GONG WITH METAL STAND WITH STICK, SPEAKERS WITH CORDLESS MIKE, ANCHOR, TRANSPORT, RECEPTION DESK, TABLE, CHAIR, STAGE, BACKDROP, LIGHTS,LED CAN ETC. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 13 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 248 | 0 | 18 Feb 2023 | FUTE SERVICES | 3D Exterior Views | Exterior Views | No. | 5 | 18000 | 90000 | 16200 | 106200 | 0 | 2.5 | 45000 | 8100 | 53100 | 2.5 | 53100 | Charges for 3D Exterior View | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 249 | 0 | 04 Mar 2023 | PRITESH SURESH BANSAL | Professional Fees | Internal Audit Fees -AIE- | Month | 12 | 25000 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Mar 2023 |  | Admin. Indirect Expenses | Un-Approved
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | Gas Solenoid Valve 2 inch (M+L) | No. | 2 | 28060 | 56120 | 10101.6 | 66221.6 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 0 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas Detector System | Siren | No. | 3 | 874 | 2622 | 471.96 | 3093.96 | 2.5 | 3 | 2622 | 471.96 | 3093.96 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | MS Bracket (M+L) | No. | 0 | 322 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Mar 2023 |  | No category | Cancelled | DUSHANT.GORE | 18 Oct 2023
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | Gas Solenoid Valve 1.5 inch (M+L) | No. | 1 | 23690 | 23690 | 4264.2 | 27954.2 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | 2'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 12 | 414 | 4968 | 894.24 | 5862.24 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 0 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas Detector System | Gas Alarm Panel | No. | 3 | 14260 | 42780 | 7700.4 | 50480.4 | 2.5 | 3 | 42780 | 7700.4 | 50480.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | MS Bracket (M+L) | No. | 8 | 322 | 2576 | 463.68 | 3039.68 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 0 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas Detector System | Labour lumpsum | No. | 1 | 23000 | 23000 | 4140 | 27140 | 2.5 | 1 | 23000 | 4140 | 27140 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | Fabrication Work-Lumsum-DCH | No. | 3 | 7820 | 23460 | 4222.8 | 27682.8 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | DEV. Club House | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | 1.5'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 4 | 322 | 1288 | 231.84 | 1519.84 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 0 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas Detector System | Gas Detector Point | No. | 24 | 12420 | 298080 | 53654.4 | 351734.4 | 2.5 | 24 | 298080 | 53654.4 | 351734.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 0 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas Detector System | 1.5 Sq.mm x 4C Cu Arm.Cable(M+L) | Mtrs | 400 | 142.6 | 57040 | 10267.2 | 67307.2 | 2.5 | 400 | 57040 | 10267.2 | 67307.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | 1.5'' Ball Valve (M+L) | No. | 2 | 3542 | 7084 | 1275.12 | 8359.12 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 250 | 1 | 20 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Gas Solenoid Valve system | 2'' Ball Valve (M+L) | No. | 6 | 5060 | 30360 | 5464.8 | 35824.8 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Service Passage Granite Patti | Granite Patti Fixing- SM | R.Ft | 137.33 | 55 | 7553.15 | 0 | 7553.15 | 2.5 | 137.33 | 7553.15 | 0 | 7553.15 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 17 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 396.97 | 28 | 11115.16 | 0 | 11115.16 | 2.5 | 0 | 0 | 0 | 0 | 396.97 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor Service Passage Granite Patti | Granite Patti Fixing- SM | R.Ft | 152.004 | 55 | 8360.22 | 0 | 8360.22 | 2.5 | 152.004 | 8360.22 | 0 | 8360.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 19 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 64.68 | 28 | 1811.04 | 0 | 1811.04 | 2.5 | 0 | 0 | 0 | 0 | 64.68 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 21 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 372 | 28 | 10416 | 0 | 10416 | 2.5 | 0 | 0 | 0 | 0 | 372 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 20 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 384 | 28 | 10752 | 0 | 10752 | 2.5 | 0 | 0 | 0 | 0 | 384 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 15 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 63.63 | 28 | 1781.64 | 0 | 1781.64 | 2.5 | 0 | 0 | 0 | 0 | 63.63 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor R2 flooring | Vitrified Flooring 800x800- BC | Sq.Ft | 1615.187 | 28 | 45225.24 | 0 | 45225.24 | 2.5 | 1615.187 | 45225.24 | 0 | 45225.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 4th floor passage Flooring Work. | Granite Flooring (L)- BCE | Sq.Ft | 482.87 | 55 | 26557.85 | 0 | 26557.85 | 2.5 | 289.52 | 15923.6 | 0 | 15923.6 | 193.35 | 10634.25 |  | 59.9582 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Elevation Features | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 20 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 66.78 | 28 | 1869.84 | 0 | 1869.84 | 2.5 | 0 | 0 | 0 | 0 | 66.78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 19 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 329.37 | 28 | 9222.36 | 0 | 9222.36 | 2.5 | 0 | 0 | 0 | 0 | 329.37 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 4th Floor Sample Office Misc Work | Granite Champher/ Polish- BCE | R.Ft | 31.16 | 20 | 623.2 | 0 | 623.2 | 2.5 | 31.16 | 623.2 | 0 | 623.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Elevation Features | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 4th floor passage Flooring Work. | Granite Patti - BCE | R.Ft | 590.1 | 55 | 32455.5 | 0 | 32455.5 | 2.5 | 590.1 | 32455.5 | 0 | 32455.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Elevation Features | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 21 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 68.74 | 28 | 1924.72 | 0 | 1924.72 | 2.5 | 0 | 0 | 0 | 0 | 68.74 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor R2 flooring | Vitrified Skirting 800x800- BCV | R.Ft | 251.412 | 28 | 7039.54 | 0 | 7039.54 | 2.5 | 251.412 | 7039.54 | 0 | 7039.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 16 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 67.27 | 28 | 1883.56 | 0 | 1883.56 | 2.5 | 0 | 0 | 0 | 0 | 67.27 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 18 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 313.26 | 28 | 8771.28 | 0 | 8771.28 | 2.5 | 0 | 0 | 0 | 0 | 313.26 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 17 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 67.27 | 28 | 1883.56 | 0 | 1883.56 | 2.5 | 0 | 0 | 0 | 0 | 67.27 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-Basement Floor toilet Granite Door edge polish | Granite Edge Polish | R.Ft | 91.22 | 10 | 912.2 | 0 | 912.2 | 2.5 | 91.22 | 912.2 | 0 | 912.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 15 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 242.674 | 28 | 6794.87 | 0 | 6794.87 | 2.5 | 0 | 0 | 0 | 0 | 242.674 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 4th Floor Sample Office Misc Work | Granite Edge Polish | R.Ft | 93.48 | 10 | 934.8 | 0 | 934.8 | 2.5 | 93.48 | 934.8 | 0 | 934.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 4th floor passage Flooring Work. | Vitrified Flooring - MKT - Sq.Ft | Sq.Ft | 1269.29 | 28 | 35540.12 | 0 | 35540.12 | 2.5 | 1269.29 | 35540.12 | 0 | 35540.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Floor R2 flooring | Vitrified Flooring 800x800- BC | Sq.Ft | 0 | 28 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 21 Mar 2023
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 18 Vitrified Tile Skirting | Vitrified Skirting BC | R.Ft | 64.05 | 28 | 1793.4 | 0 | 1793.4 | 2.5 | 0 | 0 | 0 | 0 | 64.05 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 1 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Shop 16 Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 341.54 | 28 | 9563.12 | 0 | 9563.12 | 2.5 | 0 | 0 | 0 | 0 | 341.54 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 251 | 0 | 20 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 4th Floor Sample Office Misc Work | Granite Ledge Wall Top - Mkt | R.Ft | 5.379 | 55 | 295.85 | 0 | 295.85 | 2.5 | 5.379 | 295.85 | 0 | 295.85 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 252 | 0 | 22 Mar 2023 | MD JAFAR IMAM | 3rd Floor ST.Landing Slab Cutting For Electrical Duct - 1 | Labour Lumpsum - BCo | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 253 | 0 | 22 Mar 2023 | MD JAFAR IMAM | Building Debris Shifting out side by truck | Debris Shifting Work | Brass. | 30 | 2500 | 75000 | 0 | 75000 | 0 | 16.92 | 42300 | 0 | 42300 | 13.08 | 32700 |  | 56.4 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 254 | 0 | 22 Mar 2023 | SAHARA ENGINEERING | External Facade Glass Changing - 1 No. | Glass work- Mkt | No. | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Mar 2023
EAST POINT MARKET | 254 | 0 | 22 Mar 2023 | SAHARA ENGINEERING | External Facade Glass Changing - 1 No. | Glass work- Mkt | No. | 3 | 10000 | 30000 | 5400 | 35400 | 0 | 3 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 254 | 0 | 22 Mar 2023 | SAHARA ENGINEERING | External Facade Glass Changing - 1 No. | Labour Lumpsum | No. | 1 | 120000 | 120000 | 21600 | 141600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 500 | 500 | 90 | 590 | 0 | 1 | 500 | 90 | 590 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 7000 | 7000 | 1260 | 8260 | 2.5 | 1 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 0 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | MS Work for Air Curtain at 2nd and 3rd - 1 Job | Fabrication work (L) No. | No. | 4 | 8000 | 32000 | 5760 | 37760 | 2.5 | 4 | 32000 | 5760 | 37760 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 0.5 | 2000 | 360 | 2360 | 0.5 | 2360 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 255 | 1 | 22 Mar 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP Misc Fabrication work | Fabrication Work. | No. | 1 | 12000 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Chemical Waterproofing (L) | Sq.Ft | 7100 | 21.6 | 153360 | 27604.8 | 180964.8 | 10 | 0 | 0 | 0 | 0 | 7100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Chemical Waterproofing work (m+l) | R.Ft | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 06 WATERPROOFING WORK | Cancelled | ADITYA CHOUGULE | 23 Mar 2023
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Brickbat W/P | Sq.Ft | 250 | 80 | 20000 | 3600 | 23600 | 10 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 1 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | KEP-Terrace Floor 5th floor expansion joint treatment | Expansion Joint Waterproofing treatment | R.Ft | 200 | 1250 | 250000 | 45000 | 295000 | 10 | 195.3333 | 244166.63 | 43950 | 288116.63 | 4.6667 | 6883.38 |  | 97.6667 |  | DUSHANT GORE | chetan jewalikar | construction open |  |  | 06 WATERPROOFING WORK | Approved | chetan jewalikar
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Crack Filling Mkt | R.Ft | 700 | 28 | 19600 | 3528 | 23128 | 2.5 | 0 | 0 | 0 | 0 | 700 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Breaking Work -DPo | Sq.Ft | 250 | 27 | 6750 | 1215 | 7965 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Podium | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Chemical Waterproofing (M+L).Sq.ft | Sq.Ft | 185 | 32 | 5920 | 1065.6 | 6985.6 | 10 | 0 | 0 | 0 | 0 | 185 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Breaking work (R.ft) | R.Ft | 115 | 27 | 3105 | 558.9 | 3663.9 | 0 | 0 | 0 | 0 | 0 | 115 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Chemical Waterproofing (L) | Sq.Ft | 7100 | 8.1 | 57510 | 10351.8 | 67861.8 | 10 | 0 | 0 | 0 | 0 | 7100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 256 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Ponding | R.Ft | 115 | 120 | 13800 | 2484 | 16284 | 2.5 | 0 | 0 | 0 | 0 | 115 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 12 MASONARY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 257 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Chemical Waterproofing (M) | Sq.Ft | 7100 | 50.4 | 357840 | 64411.2 | 422251.2 | 0 | 0 | 0 | 0 | 0 | 7100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 257 | 0 | 23 Mar 2023 | THE FAMOUS INDIA ENTERPRISES | 5th floor Sloping Terrce Repairing & W/P Coating - 1 No. | Chemical Waterproofing (M) | Sq.Ft | 7100 | 18.9 | 134190 | 24154.2 | 158344.2 | 0 | 0 | 0 | 0 | 0 | 7100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-6 size Gas Meter diaphragm Rate Diff.(L) | No. | 12 | 546.48 | 6557.76 | 1180.4 | 7738.16 | 2.5 | 4 | 2185.92 | 393.46 | 2579.38 | 8 | 5158.78 |  | 33.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Adaptor Rate Diff. (L) | No. | 58 | 26.49 | 1536.42 | 276.56 | 1812.98 | 2.5 | 12 | 317.88 | 57.22 | 375.1 | 46 | 1437.88 |  | 20.6897 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Adaptor (L) | No. | 58 | 220.8 | 12806.4 | 2305.16 | 15111.56 | 2.5 | 12 | 2649.6 | 476.92 | 3126.52 | 46 | 11985.04 |  | 20.6897 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-6 size Gas Meter diaphragm (L) | No. | 12 | 4554 | 54648 | 9836.64 | 64484.64 | 2.5 | 4 | 18216 | 3278.88 | 21494.88 | 8 | 42989.76 |  | 33.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-16 size Gas Meter diaphragm (L) | No. | 1 | 10971 | 10971 | 1974.78 | 12945.78 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-16 size Gas Meter diaphragm Rate Diff.(L) | No. | 1 | 1316.52 | 1316.52 | 236.98 | 1553.5 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-10 size Gas Meter diaphragm (L) | No. | 4 | 10419 | 41676 | 7501.68 | 49177.68 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-4 size Gas Meter diaphragm (L) | No. | 12 | 2111.4 | 25336.8 | 4560.62 | 29897.42 | 2.5 | 2 | 4222.8 | 760.1 | 4982.9 | 10 | 24914.52 |  | 16.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-10 size Gas Meter diaphragm Rate Diff.(L) | No. | 4 | 1250.28 | 5001.12 | 900.2 | 5901.32 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Support (L) | No. | 40 | 69 | 2760 | 496.8 | 3256.8 | 2.5 | 18 | 1242 | 223.56 | 1465.56 | 22 | 1791.24 |  | 45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-4 size Gas Meter diaphragm Rate Diff.(L) | No. | 12 | 253.33 | 3039.96 | 547.2 | 3587.16 | 2.5 | 2 | 506.66 | 91.2 | 597.86 | 10 | 2989.3 |  | 16.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 258 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Support Rate Diff. (L) | No. | 40 | 8.28 | 331.2 | 59.62 | 390.82 | 2.5 | 18 | 149.04 | 26.82 | 175.86 | 22 | 214.96 |  | 45 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Support Rate Diff. (M) | No. | 40 | 19.32 | 772.8 | 139.1 | 911.9 | 0 | 18 | 347.76 | 62.6 | 410.36 | 22 | 501.54 |  | 45 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-6 size Gas Meter diaphragm Rate Diff.(M) | No. | 12 | 1275.12 | 15301.44 | 2754.26 | 18055.7 | 0 | 4 | 5100.48 | 918.08 | 6018.56 | 8 | 12037.14 |  | 33.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Adaptor Rate Diff. (M) | No. | 58 | 61.82 | 3585.56 | 645.4 | 4230.96 | 0 | 12 | 741.84 | 133.54 | 875.38 | 46 | 3355.58 |  | 20.6897 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-10 size Gas Meter diaphragm Rate Diff.(M) | No. | 4 | 2917.32 | 11669.28 | 2100.48 | 13769.76 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Support (M) | No. | 40 | 161 | 6440 | 1159.2 | 7599.2 | 0 | 18 | 2898 | 521.64 | 3419.64 | 22 | 4179.56 |  | 45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-10 size Gas Meter diaphragm (M) | No. | 4 | 24311 | 97244 | 17503.92 | 114747.92 | 0 | 1 | 24311 | 4375.98 | 28686.98 | 3 | 86060.94 |  | 25 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Transportaion - No. | No. | 1 | 14260 | 14260 | 2566.8 | 16826.8 | 0 | 0.35 | 4991 | 898.38 | 5889.38 | 0.65 | 10937.42 |  | 35 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Media | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-16 size Gas Meter diaphragm Rate Diff.(M) | No. | 1 | 3071.88 | 3071.88 | 552.94 | 3624.82 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-4 size Gas Meter diaphragm (M) | No. | 12 | 4926.6 | 59119.2 | 10641.46 | 69760.66 | 0 | 2 | 9853.2 | 1773.58 | 11626.78 | 10 | 58133.88 |  | 16.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | Gas Meter Adaptor (M) | No. | 58 | 515.2 | 29881.6 | 5378.68 | 35260.28 | 0 | 14 | 7212.8 | 1298.32 | 8511.12 | 44 | 26749.16 |  | 24.1379 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-6 size Gas Meter diaphragm (M) | No. | 12 | 10626 | 127512 | 22952.16 | 150464.16 | 0 | 4 | 42504 | 7650.72 | 50154.72 | 8 | 100309.44 |  | 33.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 1 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-4 size Gas Meter diaphragm Rate Diff.(M) | No. | 12 | 591.1 | 7093.2 | 1276.78 | 8369.98 | 0 | 2 | 1182.2 | 212.8 | 1395 | 10 | 6974.98 |  | 16.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 259 | 0 | 25 Mar 2023 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court GAS Meter Work - 1 No. | G-16 size Gas Meter diaphragm (M) | No. | 1 | 25599 | 25599 | 4607.82 | 30206.82 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 0 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling 2nd Floor Granite Flooring | Granite Flooring | Sq.Ft | 822 | 55 | 45210 | 0 | 45210 | 2.5 | 484.3 | 26636.5 | 0 | 26636.5 | 337.7 | 18573.5 |  | 58.9173 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 2 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Arif Bhai - New Service passage Tile Fixing | Tile Fixing Work-DER | Sq.Ft | 130 | 28 | 3640 | 0 | 3640 | 2.5 | 130 | 3640 | 0 | 3640 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 2 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling 3rd floor service passage Dado work | Dado BC | Sq.Ft | 371 | 28 | 10388 | 0 | 10388 | 2.5 | 371 | 10388 | 0 | 10388 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 0 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling 3rd floor service passage side patt | Edge Polish - BCE | R.Ft | 274.66 | 10 | 2746.6 | 0 | 2746.6 | 2.5 | 274.66 | 2746.6 | 0 | 2746.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Elevation Features | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 0 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Fl Flooring & Tiling 3rd floor service passage Dado work | Dado BC | Sq.Ft | 2541 | 28 | 71148 | 0 | 71148 | 2.5 | 2540.9999 | 71148 | 0 | 71148 | 0.0001 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 2 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Arif bhai - New service passage granite patta work-R.Ft | Granite Patta -H - BCo | R.Ft | 34 | 55 | 1870 | 0 | 1870 | 2.5 | 34 | 1870 | 0 | 1870 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 1 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling 2nd Floor Steel Grey granite patt | Granite Patta -H - BCo | R.Ft | 90.844 | 55 | 4996.42 | 0 | 4996.42 | 2.5 | 90.8364 | 4996 | 0 | 4996 | 0.0076 | 0.42 |  | 99.9916 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | raviraj agarwal
EAST POINT MARKET | 260 | 1 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling Vitrified Tile Flooring | Vitrified Flooring -BC | Sq.Ft | 213.39 | 28 | 5974.92 | 0 | 5974.92 | 2.5 | 213.3571 | 5974 | 0 | 5974 | 0.0329 | 0.92 |  | 99.9846 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 30 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | raviraj agarwal
EAST POINT MARKET | 260 | 2 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Janitor Room Granite cupboard work-No. | Granite Cupboard | No. | 4 | 2000 | 8000 | 0 | 8000 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 11 TILING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 2 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | 3rd Service passage 3 Inch Granite Patta-No. | Granite Patta -H - BCo | R.Ft | 416 | 55 | 22880 | 0 | 22880 | 2.5 | 416 | 22880 | 0 | 22880 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 260 | 1 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling Vitrified Tile Flooring | Department Labour - DEn | No. | 50 | 2200 | 110000 | 0 | 110000 | 2.5 | 49.75 | 109450 | 0 | 109450 | 0.25 | 550 |  | 99.5 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 30 Mar 2023 |  | DEV. Entrance Gate | Approved | raviraj agarwal
EAST POINT MARKET | 260 | 0 | 25 Mar 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Fl Flooring&Tiling 2nd Floor Steel Grey granite patt | Granite Patta -H - BCo | R.Ft | 305.75 | 55 | 16816.25 | 0 | 16816.25 | 2.5 | 237.53 | 13064.15 | 0 | 13064.15 | 68.22 | 3752.1 |  | 77.6877 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 261 | 0 | 27 Mar 2023 | OASIS CONSULTANT | Consultancy RCC Consultancy | RCC Consultancy | Sq.Ft | 19373.454 | 12 | 232481.45 | 41846.66 | 274328.11 | 0 | 19373.454 | 232481.45 | 0 | 232481.45 | 0 | 41846.66 |  | 100 |  | DUSHANT GORE | Swapnil Erande | consultancy | 27 Mar 2023 |  | Consultacy RCC | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 102 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 56.51 | 1.5 | 84.77 | 0 | 84.77 | 2.5 | 52.6667 | 79 | 14.22 | 93.22 | 3.8433 | -8.46 |  | 93.1989 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.22 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 716.58 | 1.5 | 1074.87 | 0 | 1074.87 | 2.5 | 0 | 0 | 0 | 0 | 716.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 81 | 1st coat Premium Emulsion on wall | Sq.Ft | 236.56 | 1.5 | 354.84 | 0 | 354.84 | 2.5 | 236.5 | 354.75 | 0 | 354.75 | 0.06 | 0.09 |  | 99.9746 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.96 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 454.22 | 1.5 | 681.33 | 0 | 681.33 | 2.5 | 452.6667 | 679 | 122.22 | 801.22 | 1.5533 | -119.89 |  | 99.658 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 02 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 76.6667 | 115 | 0 | 115 | 0.6193 | 0.93 |  | 99.1987 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 71 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 123.78 | 1.5 | 185.67 | 0 | 185.67 | 2.5 | 123.3333 | 185 | 0 | 185 | 0.4467 | 0.67 |  | 99.6391 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.66 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 687.8 | 1.5 | 1031.7 | 0 | 1031.7 | 2.5 | 0 | 0 | 0 | 0 | 687.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.99 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 328.67 | 1.5 | 493.01 | 0 | 493.01 | 2.5 | 328.6667 | 493 | 0 | 493 | 0.0033 | 0 |  | 99.999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 06 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 180.665 | 1.5 | 271 | 0 | 271 | 2.5 | 0 | 0 | 0 | 0 | 180.665 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 53 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 96.6667 | 145 | 26.1 | 171.1 | 0.2033 | -25.8 |  | 99.7901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 21 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 175.13 | 1.5 | 262.7 | 0 | 262.7 | 2.5 | 169.3333 | 254 | 45.72 | 299.72 | 5.7967 | -37.03 |  | 96.6901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.107 wall paint | 1st Coat Wall Putty - | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 0 | 483 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 83 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 98.16 | 1.5 | 147.24 | 0 | 147.24 | 2.5 | 98.16 | 147.24 | 0 | 147.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 92 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 106.6667 | 160 | 28.8 | 188.8 | 4.3033 | -22.35 |  | 96.1221 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | 2nd floor shops passage ceiling painting - 5434.84 Sq.Ft | 2nd Coat Ceiling Putty | Sq.Ft | 5434.84 | 1.5 | 8152.26 | 0 | 8152.26 | 2.5 | 0 | 0 | 0 | 0 | 5434.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.96 wall paint | 1st Coat Wall Putty - | Sq.Ft | 454.22 | 1.5 | 681.33 | 0 | 681.33 | 2.5 | 452.6667 | 679 | 122.22 | 801.22 | 1.5533 | -119.89 |  | 99.658 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.84 wall paint | 1st Coat Wall Putty - | Sq.Ft | 243.58 | 1.5 | 365.37 | 0 | 365.37 | 2.5 | 243.58 | 365.37 | 0 | 365.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 65 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 110.33 | 1.5 | 165.5 | 0 | 165.5 | 2.5 | 0 | 0 | 0 | 0 | 110.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.101 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 446.71 | 1.5 | 670.07 | 0 | 670.07 | 2.5 | 446.6667 | 670 | 120.6 | 790.6 | 0.0433 | -120.54 |  | 99.9903 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 09 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 100.85 | 1.5 | 151.28 | 0 | 151.28 | 2.5 | 0 | 0 | 0 | 0 | 100.85 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 19 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 169.85 | 1.5 | 254.78 | 0 | 254.78 | 2.5 | 0 | 0 | 0 | 0 | 169.85 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 67 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 38.75 | 1.5 | 58.13 | 0 | 58.13 | 2.5 | 38.6667 | 58 | 0 | 58 | 0.0833 | 0.12 |  | 99.785 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.51 wall paint | 1st Coat Wall Putty - | Sq.Ft | 419.6 | 1.5 | 629.4 | 0 | 629.4 | 2.5 | 410.6667 | 616 | 110.88 | 726.88 | 8.9333 | -97.48 |  | 97.871 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.109 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 578.52 | 1.5 | 867.78 | 0 | 867.78 | 2.5 | 564 | 846 | 152.28 | 998.28 | 14.52 | -130.5 |  | 97.4901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 97 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 85.78 | 1.5 | 128.67 | 0 | 128.67 | 2.5 | 85.3333 | 128 | 0 | 128 | 0.4467 | 0.67 |  | 99.4792 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 36 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 97 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 85.78 | 1.5 | 128.67 | 0 | 128.67 | 2.5 | 85.3333 | 128 | 0 | 128 | 0.4467 | 0.67 |  | 99.4792 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.45 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 29 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 99.02 | 1.5 | 148.53 | 0 | 148.53 | 2.5 | 0 | 0 | 0 | 0 | 99.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.30 wall paint | 1st Coat Wall Putty - | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.25 wall paint | 1st Coat Wall Putty - | Sq.Ft | 772.06 | 1.5 | 1158.09 | 0 | 1158.09 | 2.5 | 0 | 0 | 0 | 0 | 772.06 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 103 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 52.85 | 1.5 | 79.28 | 0 | 79.28 | 2.5 | 52.6667 | 79 | 0 | 79 | 0.1833 | 0.27 |  | 99.6532 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 14 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 127.63 | 1.5 | 191.45 | 0 | 191.45 | 2.5 | 127.3333 | 191 | 0 | 191 | 0.2967 | 0.45 |  | 99.7675 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.14 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382.4 | 573.6 | 0 | 573.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 20 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 172.224 | 1.5 | 258.34 | 0 | 258.34 | 2.5 | 0 | 0 | 0 | 0 | 172.224 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.47 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 436.7 | 1.5 | 655.05 | 0 | 655.05 | 2.5 | 0 | 0 | 0 | 0 | 436.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 05 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 115 | 1.5 | 172.5 | 0 | 172.5 | 2.5 | 0 | 0 | 0 | 0 | 115 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.37 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 562.25 | 1.5 | 843.38 | 0 | 843.38 | 2.5 | 0 | 0 | 0 | 0 | 562.25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 18 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 116.251 | 1.5 | 174.38 | 0 | 174.38 | 2.5 | 0 | 0 | 0 | 0 | 116.251 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 31 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 55.11 | 1.5 | 82.67 | 0 | 82.67 | 2.5 | 54.6667 | 82 | 0 | 82 | 0.4433 | 0.66 |  | 99.1956 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 04 ceiling paint - | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 70.289 | 1.5 | 105.43 | 0 | 105.43 | 2.5 | 70 | 105 | 0 | 105 | 0.289 | 0.43 |  | 99.5888 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.115 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 540.56 | 1.5 | 810.84 | 0 | 810.84 | 2.5 | 0 | 0 | 0 | 0 | 540.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.50 wall paint | 1st Coat Wall Putty - | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 410.6667 | 616 | 110.88 | 726.88 | 7.2633 | -99.99 |  | 98.2621 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.48 wall paint | 1st Coat Wall Putty - | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.39 wall paint | 1st Coat Wall Putty - | Sq.Ft | 362.04 | 1.5 | 543.06 | 0 | 543.06 | 2.5 | 0 | 0 | 0 | 0 | 362.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.26 wall paint | 1st Coat Wall Putty - | Sq.Ft | 744.11 | 1.5 | 1116.17 | 0 | 1116.17 | 2.5 | 0 | 0 | 0 | 0 | 744.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 46 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 74.81 | 1.5 | 112.22 | 0 | 112.22 | 2.5 | 0 | 0 | 0 | 0 | 74.81 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 99 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 67.81 | 1.5 | 101.72 | 0 | 101.72 | 2.5 | 67.3333 | 101 | 0 | 101 | 0.4767 | 0.72 |  | 99.297 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.59 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 222.31 | 1.5 | 333.47 | 0 | 333.47 | 2.5 | 222.31 | 333.47 | 0 | 333.47 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 16 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 108.46 | 1.5 | 162.69 | 0 | 162.69 | 2.5 | 108.46 | 162.69 | 0 | 162.69 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 36 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 130.55 | 1.5 | 195.83 | 0 | 195.83 | 2.5 | 0 | 0 | 0 | 0 | 130.55 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.28 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 539.31 | 1.5 | 808.97 | 0 | 808.97 | 2.5 | 0 | 0 | 0 | 0 | 539.31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.27 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 537.64 | 1.5 | 806.46 | 0 | 806.46 | 2.5 | 0 | 0 | 0 | 0 | 537.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.15 wall paint | 1st Coat Wall Putty - | Sq.Ft | 325.59 | 1.5 | 488.39 | 0 | 488.39 | 2.5 | 325.3333 | 488 | 0 | 488 | 0.2567 | 0.39 |  | 99.9212 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.2 wall paint | 1st Coat Wall Putty - | Sq.Ft | 344.529 | 1.5 | 516.79 | 0 | 516.79 | 2.5 | 344 | 516 | 0 | 516 | 0.529 | 0.79 |  | 99.8465 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.100 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 487.17 | 1.5 | 730.76 | 0 | 730.76 | 2.5 | 487 | 730.5 | 0 | 730.5 | 0.17 | 0.26 |  | 99.9651 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.11 wall paint | Primer Water Base- Wall | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 422.11 | 633.17 | 0 | 633.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.34 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 780.4 | 1.5 | 1170.6 | 0 | 1170.6 | 2.5 | 0 | 0 | 0 | 0 | 780.4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.62 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 342.44 | 1.5 | 513.66 | 0 | 513.66 | 2.5 | 0 | 0 | 0 | 0 | 342.44 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.18 wall paint | 1st Coat Wall Putty - | Sq.Ft | 503.86 | 1.5 | 755.79 | 0 | 755.79 | 2.5 | 0 | 0 | 0 | 0 | 503.86 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.5 wall paint | 1st Coat Wall Putty - | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.29 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 445.88 | 1.5 | 668.82 | 0 | 668.82 | 2.5 | 0 | 0 | 0 | 0 | 445.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.45 wall paint | Primer Water Base- Wall | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.117 wall paint | Primer Water Base- Wall | Sq.Ft | 208.55 | 1.5 | 312.83 | 0 | 312.83 | 2.5 | 208.55 | 312.83 | 0 | 312.83 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 69 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 32.58 | 213.57 | 0 | -32.58 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.3 wall paint | 1st Coat Wall Putty - | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.60 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 388.74 | 1.5 | 583.11 | 0 | 583.11 | 2.5 | 388.74 | 583.11 | 0 | 583.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 19 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 169.85 | 1.5 | 254.78 | 0 | 254.78 | 2.5 | 0 | 0 | 0 | 0 | 169.85 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.50 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 410.6667 | 616 | 110.88 | 726.88 | 7.2633 | -99.99 |  | 98.2621 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.86 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 584.78 | 1.5 | 877.17 | 0 | 877.17 | 2.5 | 0 | 0 | 0 | 0 | 584.78 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 39 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 71.04 | 1.5 | 106.56 | 0 | 106.56 | 2.5 | 0 | 0 | 0 | 0 | 71.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 43 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.25 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 772.06 | 1.5 | 1158.09 | 0 | 1158.09 | 2.5 | 0 | 0 | 0 | 0 | 772.06 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.51 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 419.6 | 1.5 | 629.4 | 0 | 629.4 | 2.5 | 410.6667 | 616 | 110.88 | 726.88 | 8.9333 | -97.48 |  | 97.871 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.66 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 687.8 | 1.5 | 1031.7 | 0 | 1031.7 | 2.5 | 508.6667 | 763 | 137.34 | 900.34 | 179.1333 | 131.36 |  | 73.9556 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.107 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 0 | 483 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.70 wall paint | Primer Water Base- Wall | Sq.Ft | 573.51 | 1.5 | 860.27 | 0 | 860.27 | 2.5 | 0 | 0 | 0 | 0 | 573.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 41 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 113.02 | 1.5 | 169.53 | 0 | 169.53 | 2.5 | 0 | 0 | 0 | 0 | 113.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.63 wall paint | 1st Coat Wall Putty - | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 417.3333 | 626 | 112.68 | 738.68 | 14.3667 | -91.13 |  | 96.6721 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.100 wall paint | 1st Coat Wall Putty - | Sq.Ft | 487.17 | 1.5 | 730.76 | 0 | 730.76 | 2.5 | 487 | 730.5 | 0 | 730.5 | 0.17 | 0.26 |  | 99.9651 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 11 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 99.244 | 1.5 | 148.87 | 0 | 148.87 | 2.5 | 98.6667 | 148 | 0 | 148 | 0.5773 | 0.87 |  | 99.4183 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 59 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120 | 180 | 0 | 180 | 0.66 | 0.99 |  | 99.453 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 91 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 63.5 | 1.5 | 95.25 | 0 | 95.25 | 2.5 | 0 | 0 | 0 | 0 | 63.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.105 wall paint | 1st Coat Wall Putty - | Sq.Ft | 159.75 | 1.5 | 239.63 | 0 | 239.63 | 2.5 | 159.3333 | 239 | 0 | 239 | 0.4167 | 0.63 |  | 99.7392 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.52 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 418.35 | 1.5 | 627.53 | 0 | 627.53 | 2.5 | 0 | 0 | 0 | 0 | 418.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.55 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 425.03 | 1.5 | 637.55 | 0 | 637.55 | 2.5 | 0 | 0 | 0 | 0 | 425.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 34 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 181.69 | 1.5 | 272.54 | 0 | 272.54 | 2.5 | 0 | 0 | 0 | 0 | 181.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.8 wall paint | 1st Coat Wall Putty - | Sq.Ft | 469.24 | 1.5 | 703.86 | 0 | 703.86 | 2.5 | 340 | 510 | 91.8 | 601.8 | 129.24 | 102.06 |  | 72.4576 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.68 wall paint | 1st Coat Wall Putty - | Sq.Ft | 618.56 | 1.5 | 927.84 | 0 | 927.84 | 2.5 | 0 | 0 | 0 | 0 | 618.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 47 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 102.64 | 1.5 | 153.96 | 0 | 153.96 | 2.5 | 0 | 0 | 0 | 0 | 102.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 30 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 74.27 | 1.5 | 111.41 | 0 | 111.41 | 2.5 | 74.27 | 111.41 | 0 | 111.41 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.70 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 573.51 | 1.5 | 860.27 | 0 | 860.27 | 2.5 | 0 | 0 | 0 | 0 | 573.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.32 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 531.8 | 1.5 | 797.7 | 0 | 797.7 | 2.5 | 0 | 0 | 0 | 0 | 531.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.86 wall paint | Primer Water Base- Wall | Sq.Ft | 584.78 | 1.5 | 877.17 | 0 | 877.17 | 2.5 | 0 | 0 | 0 | 0 | 584.78 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.69 wall paint | Primer Water Base- Wall | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 456.6667 | 685 | 123.3 | 808.3 | 111.4233 | 43.83 |  | 80.3863 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 4 | 1st coat Premium Emulsion on wall | Sq.Ft | 193.63 | 1.5 | 290.45 | 0 | 290.45 | 2.5 | 193.3333 | 290 | 0 | 290 | 0.2967 | 0.45 |  | 99.8468 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.38 wall paint | Primer Water Base- Wall | Sq.Ft | 387.07 | 1.5 | 580.61 | 0 | 580.61 | 2.5 | 0 | 0 | 0 | 0 | 387.07 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 45 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 89.34 | 1.5 | 134.01 | 0 | 134.01 | 2.5 | 0 | 0 | 0 | 0 | 89.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 58 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 132.93 | 1.5 | 199.4 | 0 | 199.4 | 2.5 | 132.6667 | 199 | 35.82 | 234.82 | 0.2633 | -35.43 |  | 99.8019 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 81 | 2nd coat Premium Emulsion on wall | Sq.Ft | 236.56 | 1.5 | 354.84 | 0 | 354.84 | 2.5 | 236.5 | 354.75 | 0 | 354.75 | 0.06 | 0.09 |  | 99.9746 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 26 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 250.43 | 1.5 | 375.65 | 0 | 375.65 | 2.5 | 0 | 0 | 0 | 0 | 250.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.67 wall paint | 1st Coat Wall Putty - | Sq.Ft | 255.26 | 1.5 | 382.89 | 0 | 382.89 | 2.5 | 190.6667 | 286 | 0 | 286 | 64.5933 | 96.89 |  | 74.6951 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.104 wall paint | 1st Coat Wall Putty - | Sq.Ft | 285.3 | 1.5 | 427.95 | 0 | 427.95 | 2.5 | 283.3333 | 425 | 76.5 | 501.5 | 1.9667 | -73.55 |  | 99.3107 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 25 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 270 | 1.5 | 405 | 0 | 405 | 2.5 | 0 | 0 | 0 | 0 | 270 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.24 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 792.5 | 1.5 | 1188.75 | 0 | 1188.75 | 2.5 | 0 | 0 | 0 | 0 | 792.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 11 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 99.244 | 1.5 | 148.87 | 0 | 148.87 | 2.5 | 99.244 | 148.87 | 0 | 148.87 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 66 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 200.74 | 1.5 | 301.11 | 0 | 301.11 | 2.5 | 0 | 0 | 0 | 0 | 200.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 24 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 280 | 1.5 | 420 | 0 | 420 | 2.5 | 0 | 0 | 0 | 0 | 280 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.99 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 328.67 | 1.5 | 493.01 | 0 | 493.01 | 2.5 | 328.6667 | 493 | 0 | 493 | 0.0033 | 0 |  | 99.999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 78 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 62.53 | 1.5 | 93.8 | 0 | 93.8 | 2.5 | 62.53 | 93.8 | 0 | 93.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 98 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 47.68 | 1.5 | 71.52 | 0 | 71.52 | 2.5 | 47.68 | 71.52 | 12.88 | 84.4 | 0 | -12.88 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 57 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 87.94 | 1.5 | 131.91 | 0 | 131.91 | 2.5 | 87.94 | 131.91 | 0 | 131.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 48 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 52 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 90.95 | 1.5 | 136.43 | 0 | 136.43 | 2.5 | 0 | 0 | 0 | 0 | 90.95 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.12 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 485.92 | 1.5 | 728.88 | 0 | 728.88 | 2.5 | 485.92 | 728.88 | 0 | 728.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 86 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 166.84 | 1.5 | 250.26 | 0 | 250.26 | 2.5 | 0 | 0 | 0 | 0 | 166.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 42 | 1st coat Premium Emulsion on wall | Sq.Ft | 264.96 | 1.5 | 397.44 | 0 | 397.44 | 2.5 | 264.6667 | 397 | 0 | 397 | 0.2933 | 0.44 |  | 99.8893 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 51 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 89.87 | 1.5 | 134.81 | 0 | 134.81 | 2.5 | 88.6667 | 133 | 23.94 | 156.94 | 1.2033 | -22.14 |  | 98.6611 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 4 | 2nd coat Premium Emulsion on wall | Sq.Ft | 193.63 | 1.5 | 290.45 | 0 | 290.45 | 2.5 | 193.3333 | 290 | 0 | 290 | 0.2967 | 0.45 |  | 99.8468 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.101 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 446.71 | 1.5 | 670.07 | 0 | 670.07 | 2.5 | 446.6667 | 670 | 120.6 | 790.6 | 0.0433 | -120.54 |  | 99.9903 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 30 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 74.27 | 1.5 | 111.41 | 0 | 111.41 | 2.5 | 74.27 | 111.41 | 0 | 111.41 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.110 wall paint | 1st Coat Wall Putty - | Sq.Ft | 231.49 | 1.5 | 347.24 | 0 | 347.24 | 2.5 | 231.49 | 347.24 | 0 | 347.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.106 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 218.56 | 1.5 | 327.84 | 0 | 327.84 | 2.5 | 218.56 | 327.84 | 0 | 327.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 75 | 1st coat Premium Emulsion on wall | Sq.Ft | 183.14 | 1.5 | 274.71 | 0 | 274.71 | 2.5 | 183 | 274.5 | 0 | 274.5 | 0.14 | 0.21 |  | 99.9236 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 113 | 1st coat Premium Emulsion on wall | Sq.Ft | 231.05 | 1.5 | 346.58 | 0 | 346.58 | 2.5 | 231 | 346.5 | 0 | 346.5 | 0.05 | 0.08 |  | 99.9784 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 08 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 148.866 | 1.5 | 223.3 | 0 | 223.3 | 2.5 | 136.6667 | 205 | 36.9 | 241.9 | 12.1993 | -18.6 |  | 91.8052 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.67 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 255.26 | 1.5 | 382.89 | 0 | 382.89 | 2.5 | 190.6667 | 286 | 0 | 286 | 64.5933 | 96.89 |  | 74.6951 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 18 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 116.251 | 1.5 | 174.38 | 0 | 174.38 | 2.5 | 0 | 0 | 0 | 0 | 116.251 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 59 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 0 | 180.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 91 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 63.5 | 1.5 | 95.25 | 0 | 95.25 | 2.5 | 0 | 0 | 0 | 0 | 63.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 97 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 85.78 | 1.5 | 128.67 | 0 | 128.67 | 2.5 | 0 | 0 | 0 | 0 | 85.78 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.53 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 443.8 | 1.5 | 665.7 | 0 | 665.7 | 2.5 | 0 | 0 | 0 | 0 | 443.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 68 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 129.16 | 1.5 | 193.74 | 0 | 193.74 | 2.5 | 0 | 0 | 0 | 0 | 129.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.24 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 792.5 | 1.5 | 1188.75 | 0 | 1188.75 | 2.5 | 0 | 0 | 0 | 0 | 792.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 108 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 163.82 | 1.5 | 245.73 | 0 | 245.73 | 2.5 | 160 | 240 | 43.2 | 283.2 | 3.82 | -37.47 |  | 97.6682 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.85 wall paint | Primer Water Base- Wall | Sq.Ft | 592.7 | 1.5 | 889.05 | 0 | 889.05 | 2.5 | 0 | 0 | 0 | 0 | 592.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.43 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 404.59 | 1.5 | 606.89 | 0 | 606.89 | 2.5 | 0 | 0 | 0 | 0 | 404.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.57 wall paint | Primer Water Base- Wall | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 110 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 82.56 | 1.5 | 123.84 | 0 | 123.84 | 2.5 | 82.56 | 123.84 | 0 | 123.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.108 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 564 | 846 | 152.28 | 998.28 | 4.09 | -146.15 |  | 99.28 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 72 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 133.36 | 1.5 | 200.04 | 0 | 200.04 | 2.5 | 0 | 0 | 0 | 0 | 133.36 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 47 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 102 | 1.5 | 153 | 0 | 153 | 2.5 | 0 | 0 | 0 | 0 | 102 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 63 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.19 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 608.97 | 1.5 | 913.46 | 0 | 913.46 | 2.5 | 0 | 0 | 0 | 0 | 608.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.74 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 294.05 | 1.5 | 441.08 | 0 | 441.08 | 2.5 | 294.05 | 441.08 | 0 | 441.08 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 95 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 61.03 | 1.5 | 91.55 | 0 | 91.55 | 2.5 | 60 | 90 | 16.2 | 106.2 | 1.03 | -14.66 |  | 98.3123 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 37 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 126.69 | 1.5 | 190.04 | 0 | 190.04 | 2.5 | 0 | 0 | 0 | 0 | 126.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.54 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 432.53 | 1.5 | 648.8 | 0 | 648.8 | 2.5 | 0 | 0 | 0 | 0 | 432.53 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.74 wall paint | Primer Water Base- Wall | Sq.Ft | 294.05 | 1.5 | 441.08 | 0 | 441.08 | 2.5 | 294.05 | 441.08 | 0 | 441.08 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 30 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 74.27 | 1.5 | 111.41 | 0 | 111.41 | 2.5 | 74.27 | 111.41 | 0 | 111.41 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.76 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 275.28 | 1.5 | 412.92 | 0 | 412.92 | 2.5 | 274.6667 | 412 | 0 | 412 | 0.6133 | 0.92 |  | 99.7772 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.81 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 17 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 109.72 | 1.5 | 164.58 | 0 | 164.58 | 2.5 | 109.72 | 164.58 | 0 | 164.58 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 12 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 127.661 | 1.5 | 191.49 | 0 | 191.49 | 2.5 | 127.661 | 191.49 | 0 | 191.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.37 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 562.25 | 1.5 | 843.38 | 0 | 843.38 | 2.5 | 0 | 0 | 0 | 0 | 562.25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.72 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 577.69 | 1.5 | 866.54 | 0 | 866.54 | 2.5 | 0 | 0 | 0 | 0 | 577.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.80 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 472 | 708 | 127.44 | 835.44 | 27.69 | -85.91 |  | 94.4586 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.22 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 716.58 | 1.5 | 1074.87 | 0 | 1074.87 | 2.5 | 515.3333 | 773 | 139.14 | 912.14 | 201.2467 | 162.73 |  | 71.9157 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 10 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 102.473 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.473 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 27 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 174.91 | 1.5 | 262.37 | 0 | 262.37 | 2.5 | 0 | 0 | 0 | 0 | 174.91 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.74 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 294.05 | 1.5 | 441.08 | 0 | 441.08 | 2.5 | 294 | 441 | 0 | 441 | 0.05 | 0.08 |  | 99.983 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.77 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 214.8 | 1.5 | 322.2 | 0 | 322.2 | 2.5 | 214 | 321 | 0 | 321 | 0.8 | 1.2 |  | 99.6276 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 111 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 83.95 | 1.5 | 125.93 | 0 | 125.93 | 2.5 | 83.95 | 125.93 | 0 | 125.93 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 02 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 76.6667 | 115 | 0 | 115 | 0.6193 | 0.93 |  | 99.1987 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.1 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 345.029 | 1.5 | 517.54 | 0 | 517.54 | 2.5 | 0 | 0 | 0 | 0 | 345.029 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.48 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 33 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 0 | 0 | 0 | 0 | 78.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.45 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.115 wall paint | 1st Coat Wall Putty - | Sq.Ft | 540.56 | 1.5 | 810.84 | 0 | 810.84 | 2.5 | 0 | 0 | 0 | 0 | 540.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.61 wall paint | Primer Water Base- Wall | Sq.Ft | 492.6 | 1.5 | 738.9 | 0 | 738.9 | 2.5 | 492 | 738 | 132.84 | 870.84 | 0.6 | -131.94 |  | 99.8782 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.84 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 243.58 | 1.5 | 365.37 | 0 | 365.37 | 2.5 | 243.58 | 365.37 | 0 | 365.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.29 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 445.88 | 1.5 | 668.82 | 0 | 668.82 | 2.5 | 0 | 0 | 0 | 0 | 445.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 43 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.36 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 679.88 | 1.5 | 1019.82 | 0 | 1019.82 | 2.5 | 0 | 0 | 0 | 0 | 679.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.60 wall paint | 1st Coat Wall Putty - | Sq.Ft | 388.74 | 1.5 | 583.11 | 0 | 583.11 | 2.5 | 388.74 | 583.11 | 0 | 583.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 73 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 189.01 | 1.5 | 283.52 | 0 | 283.52 | 2.5 | 0 | 0 | 0 | 0 | 189.01 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 117 | 2nd coat Premium Emulsion on wall | Sq.Ft | 211.97 | 1.5 | 317.96 | 0 | 317.96 | 2.5 | 211.9 | 317.85 | 0 | 317.85 | 0.07 | 0.11 |  | 99.967 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.72 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 577.69 | 1.5 | 866.54 | 0 | 866.54 | 2.5 | 0 | 0 | 0 | 0 | 577.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 68 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 129.16 | 1.5 | 193.74 | 0 | 193.74 | 2.5 | 0 | 0 | 0 | 0 | 129.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.85 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 592.7 | 1.5 | 889.05 | 0 | 889.05 | 2.5 | 0 | 0 | 0 | 0 | 592.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.56 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 307.82 | 1.5 | 461.73 | 0 | 461.73 | 2.5 | 0 | 0 | 0 | 0 | 307.82 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.27 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 537.64 | 1.5 | 806.46 | 0 | 806.46 | 2.5 | 0 | 0 | 0 | 0 | 537.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 35 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 220 | 1.5 | 330 | 0 | 330 | 2.5 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.87 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 378.73 | 1.5 | 568.1 | 0 | 568.1 | 2.5 | 378.73 | 568.1 | 0 | 568.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 74 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 45.31 | 1.5 | 67.97 | 0 | 67.97 | 2.5 | 45.31 | 67.97 | 0 | 67.97 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.31 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 291.97 | 1.5 | 437.96 | 0 | 437.96 | 2.5 | 291.3333 | 437 | 0 | 437 | 0.6367 | 0.96 |  | 99.7819 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.93 wall paint | Primer Water Base- Wall | Sq.Ft | 505.94 | 1.5 | 758.91 | 0 | 758.91 | 2.5 | 500 | 750 | 0 | 750 | 5.94 | 8.91 |  | 98.8259 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 03 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 70.504 | 1.5 | 105.76 | 0 | 105.76 | 2.5 | 70 | 105 | 0 | 105 | 0.504 | 0.76 |  | 99.2851 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.28 wall paint | 1st Coat Wall Putty - | Sq.Ft | 539.31 | 1.5 | 808.97 | 0 | 808.97 | 2.5 | 0 | 0 | 0 | 0 | 539.31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.80 wall paint | 1st Coat Wall Putty - | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 472 | 708 | 127.44 | 835.44 | 27.69 | -85.91 |  | 94.4586 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.63 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 417.3333 | 626 | 112.68 | 738.68 | 14.3667 | -91.13 |  | 96.6721 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.78 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 346.19 | 1.5 | 519.29 | 0 | 519.29 | 2.5 | 346.19 | 519.29 | 0 | 519.29 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.34 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 780.4 | 1.5 | 1170.6 | 0 | 1170.6 | 2.5 | 0 | 0 | 0 | 0 | 780.4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 08 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 148.866 | 1.5 | 223.3 | 0 | 223.3 | 2.5 | 0 | 0 | 0 | 0 | 148.866 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 27 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 174.91 | 1.5 | 262.37 | 0 | 262.37 | 2.5 | 0 | 0 | 0 | 0 | 174.91 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.96 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 454.22 | 1.5 | 681.33 | 0 | 681.33 | 2.5 | 452.6667 | 679 | 122.22 | 801.22 | 1.5533 | -119.89 |  | 99.658 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.73 wall paint | Primer Water Base- Wall | Sq.Ft | 811.26 | 1.5 | 1216.89 | 0 | 1216.89 | 2.5 | 0 | 0 | 0 | 0 | 811.26 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.23 wall paint | Primer Water Base- Wall | Sq.Ft | 724.92 | 1.5 | 1087.38 | 0 | 1087.38 | 2.5 | 0 | 0 | 0 | 0 | 724.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.48 wall paint | Primer Water Base- Wall | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 03 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 70.504 | 1.5 | 105.76 | 0 | 105.76 | 2.5 | 70 | 105 | 0 | 105 | 0.504 | 0.76 |  | 99.2851 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 06 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 180 | 1.5 | 270 | 0 | 270 | 2.5 | 0 | 0 | 0 | 0 | 180 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.41 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 446.3 | 1.5 | 669.45 | 0 | 669.45 | 2.5 | 439.3333 | 659 | 0 | 659 | 6.9667 | 10.45 |  | 98.439 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.116 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 311.99 | 1.5 | 467.99 | 0 | 467.99 | 2.5 | 311.99 | 467.99 | 0 | 467.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.87 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 378.73 | 1.5 | 568.1 | 0 | 568.1 | 2.5 | 378.6667 | 568 | 0 | 568 | 0.0633 | 0.09 |  | 99.9833 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 26 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 41 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 113.02 | 1.5 | 169.53 | 0 | 169.53 | 2.5 | 0 | 0 | 0 | 0 | 113.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.105 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 159.75 | 1.5 | 239.63 | 0 | 239.63 | 2.5 | 159.3333 | 239 | 0 | 239 | 0.4167 | 0.63 |  | 99.7392 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 89 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 109.3333 | 164 | 29.52 | 193.52 | 1.6367 | -27.07 |  | 98.5251 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 15 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 102.47 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.47 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 63 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 95.3333 | 143 | 25.74 | 168.74 | 1.5367 | -23.44 |  | 98.4136 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.44 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 435.87 | 1.5 | 653.81 | 0 | 653.81 | 2.5 | 0 | 0 | 0 | 0 | 435.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.90 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 258.18 | 1.5 | 387.27 | 0 | 387.27 | 2.5 | 0 | 0 | 0 | 0 | 258.18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.14 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382.4 | 573.6 | 0 | 573.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.88 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.53 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 443.8 | 1.5 | 665.7 | 0 | 665.7 | 2.5 | 440 | 660 | 118.8 | 778.8 | 3.8 | -113.1 |  | 99.1438 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.68 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 618.56 | 1.5 | 927.84 | 0 | 927.84 | 2.5 | 0 | 0 | 0 | 0 | 618.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.33 wall paint | Primer Water Base- Wall | Sq.Ft | 410.43 | 1.5 | 615.65 | 0 | 615.65 | 2.5 | 0 | 0 | 0 | 0 | 410.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 11 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 99.244 | 1.5 | 148.87 | 0 | 148.87 | 2.5 | 99.244 | 148.87 | 0 | 148.87 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.40 wall paint | 1st Coat Wall Putty - | Sq.Ft | 554.75 | 1.5 | 832.13 | 0 | 832.13 | 2.5 | 0 | 0 | 0 | 0 | 554.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 49 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 91.49 | 1.5 | 137.24 | 0 | 137.24 | 2.5 | 0 | 0 | 0 | 0 | 91.49 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 30 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 74.27 | 1.5 | 111.41 | 0 | 111.41 | 2.5 | 74.27 | 111.41 | 0 | 111.41 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.38 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 387.07 | 1.5 | 580.61 | 0 | 580.61 | 2.5 | 0 | 0 | 0 | 0 | 387.07 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 02 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 76.6667 | 115 | 0 | 115 | 0.6193 | 0.93 |  | 99.1987 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 12 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 127.661 | 1.5 | 191.49 | 0 | 191.49 | 2.5 | 127.661 | 191.49 | 0 | 191.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 01 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 0 | 0 | 0 | 0 | 77.286 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.79 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 492.18 | 1.5 | 738.27 | 0 | 738.27 | 2.5 | 486 | 729 | 131.22 | 860.22 | 6.18 | -121.95 |  | 98.7444 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 37 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 126.69 | 1.5 | 190.04 | 0 | 190.04 | 2.5 | 0 | 0 | 0 | 0 | 126.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.56 wall paint | Primer Water Base- Wall | Sq.Ft | 307.82 | 1.5 | 461.73 | 0 | 461.73 | 2.5 | 0 | 0 | 0 | 0 | 307.82 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 17 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 109.72 | 1.5 | 164.58 | 0 | 164.58 | 2.5 | 109.72 | 164.58 | 0 | 164.58 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.43 wall paint | Primer Water Base- Wall | Sq.Ft | 404.59 | 1.5 | 606.89 | 0 | 606.89 | 2.5 | 0 | 0 | 0 | 0 | 404.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 39 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 71.04 | 1.5 | 106.56 | 0 | 106.56 | 2.5 | 0 | 0 | 0 | 0 | 71.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 23 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 264 | 1.5 | 396 | 0 | 396 | 2.5 | 0 | 0 | 0 | 0 | 264 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.92 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 488 | 1.5 | 732 | 0 | 732 | 2.5 | 480.6667 | 721 | 129.78 | 850.78 | 7.3333 | -118.78 |  | 98.4973 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.17 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 419.7 | 1.5 | 629.55 | 0 | 629.55 | 2.5 | 419.7 | 629.55 | 0 | 629.55 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.21 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 616.89 | 1.5 | 925.34 | 0 | 925.34 | 2.5 | 0 | 0 | 0 | 0 | 616.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 42 | 2nd coat Premium Emulsion on wall | Sq.Ft | 264.96 | 1.5 | 397.44 | 0 | 397.44 | 2.5 | 264.6667 | 397 | 0 | 397 | 0.2933 | 0.44 |  | 99.8893 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.36 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 679.88 | 1.5 | 1019.82 | 0 | 1019.82 | 2.5 | 0 | 0 | 0 | 0 | 679.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.39 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 362.04 | 1.5 | 543.06 | 0 | 543.06 | 2.5 | 0 | 0 | 0 | 0 | 362.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 19 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 169.85 | 1.5 | 254.78 | 0 | 254.78 | 2.5 | 0 | 0 | 0 | 0 | 169.85 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.24 wall paint | Primer Water Base- Wall | Sq.Ft | 792.5 | 1.5 | 1188.75 | 0 | 1188.75 | 2.5 | 0 | 0 | 0 | 0 | 792.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 67 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 38.75 | 1.5 | 58.13 | 0 | 58.13 | 2.5 | 38.6667 | 58 | 0 | 58 | 0.0833 | 0.12 |  | 99.785 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.61 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 492.6 | 1.5 | 738.9 | 0 | 738.9 | 2.5 | 492 | 738 | 132.84 | 870.84 | 0.6 | -131.94 |  | 99.8782 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.6 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 523.05 | 1.5 | 784.58 | 0 | 784.58 | 2.5 | 0 | 0 | 0 | 0 | 523.05 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 12 | 1st coat Premium Emulsion on wall | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382 | 573 | 0 | 573 | 0.4 | 0.6 |  | 99.8954 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.18 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 503.86 | 1.5 | 755.79 | 0 | 755.79 | 2.5 | 0 | 0 | 0 | 0 | 503.86 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 37 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 126.69 | 1.5 | 190.04 | 0 | 190.04 | 2.5 | 0 | 0 | 0 | 0 | 126.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 117 | 1st coat Premium Emulsion on wall | Sq.Ft | 211.97 | 1.5 | 317.96 | 0 | 317.96 | 2.5 | 211.3333 | 317 | 0 | 317 | 0.6367 | 0.96 |  | 99.6996 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.48 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.83 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 386.23 | 1.5 | 579.35 | 0 | 579.35 | 2.5 | 386.23 | 579.35 | 0 | 579.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 105 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 75.13 | 1.5 | 112.7 | 0 | 112.7 | 2.5 | 74 | 111 | 0 | 111 | 1.13 | 1.7 |  | 98.4959 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.17 wall paint | Primer Water Base- Wall | Sq.Ft | 419.7 | 1.5 | 629.55 | 0 | 629.55 | 2.5 | 419.7 | 629.55 | 0 | 629.55 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 28 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 178.58 | 1.5 | 267.87 | 0 | 267.87 | 2.5 | 0 | 0 | 0 | 0 | 178.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 40 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 112.48 | 1.5 | 168.72 | 0 | 168.72 | 2.5 | 0 | 0 | 0 | 0 | 112.48 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.3 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 28 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 178.58 | 1.5 | 267.87 | 0 | 267.87 | 2.5 | 0 | 0 | 0 | 0 | 178.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.12 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 485.92 | 1.5 | 728.88 | 0 | 728.88 | 2.5 | 485.3333 | 728 | 0 | 728 | 0.5867 | 0.88 |  | 99.8793 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 60 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 82.23 | 1.5 | 123.35 | 0 | 123.35 | 2.5 | 82.23 | 123.35 | 0 | 123.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 83 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 98.16 | 1.5 | 147.24 | 0 | 147.24 | 2.5 | 98.16 | 147.24 | 0 | 147.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.9 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 322 | 483 | 0 | 483 | 100.11 | 150.17 |  | 76.2834 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.116 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 311.99 | 1.5 | 467.99 | 0 | 467.99 | 2.5 | 311.3333 | 467 | 0 | 467 | 0.6567 | 0.99 |  | 99.7895 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 32 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 13 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 126.17 | 1.5 | 189.26 | 0 | 189.26 | 2.5 | 126 | 189 | 0 | 189 | 0.17 | 0.26 |  | 99.8653 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.38 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 387.07 | 1.5 | 580.61 | 0 | 580.61 | 2.5 | 0 | 0 | 0 | 0 | 387.07 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.5 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 114 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 165.98 | 1.5 | 248.97 | 0 | 248.97 | 2.5 | 0 | 0 | 0 | 0 | 165.98 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.19 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 608.97 | 1.5 | 913.46 | 0 | 913.46 | 2.5 | 0 | 0 | 0 | 0 | 608.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 79 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 133.79 | 1.5 | 200.69 | 0 | 200.69 | 2.5 | 132 | 198 | 35.64 | 233.64 | 1.79 | -32.96 |  | 98.6621 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 18 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 116.251 | 1.5 | 174.38 | 0 | 174.38 | 2.5 | 0 | 0 | 0 | 0 | 116.251 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 80 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 139.93 | 1.5 | 209.9 | 0 | 209.9 | 2.5 | 0 | 0 | 0 | 0 | 139.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 60 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 82.23 | 1.5 | 123.35 | 0 | 123.35 | 2.5 | 82.23 | 123.35 | 0 | 123.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 53 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 64 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 164.15 | 1.5 | 246.23 | 0 | 246.23 | 2.5 | 0 | 0 | 0 | 0 | 164.15 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 83 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 98.16 | 1.5 | 147.24 | 0 | 147.24 | 2.5 | 98 | 147 | 0 | 147 | 0.16 | 0.24 |  | 99.837 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 88 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 80.83 | 1.5 | 121.25 | 0 | 121.25 | 2.5 | 80.83 | 121.25 | 0 | 121.25 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 51 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 89.87 | 1.5 | 134.81 | 0 | 134.81 | 2.5 | 88.6667 | 133 | 23.94 | 156.94 | 1.2033 | -22.14 |  | 98.6611 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.35 wall paint | Primer Water Base- Wall | Sq.Ft | 561.84 | 1.5 | 842.76 | 0 | 842.76 | 2.5 | 0 | 0 | 0 | 0 | 561.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 67 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 38.75 | 1.5 | 58.13 | 0 | 58.13 | 2.5 | 38.6667 | 58 | 0 | 58 | 0.0833 | 0.12 |  | 99.785 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 88 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 80.83 | 1.5 | 121.25 | 0 | 121.25 | 2.5 | 80.83 | 121.25 | 0 | 121.25 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 110 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 82.56 | 1.5 | 123.84 | 0 | 123.84 | 2.5 | 82 | 123 | 0 | 123 | 0.56 | 0.84 |  | 99.3217 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.102 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 296.97 | 1.5 | 445.46 | 0 | 445.46 | 2.5 | 293.3333 | 440 | 79.2 | 519.2 | 3.6367 | -73.75 |  | 98.7754 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.87 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 378.73 | 1.5 | 568.1 | 0 | 568.1 | 2.5 | 378.73 | 568.1 | 0 | 568.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 113 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 79.33 | 1.5 | 119 | 0 | 119 | 2.5 | 79.33 | 119 | 0 | 119 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 100 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 119.02 | 1.5 | 178.53 | 0 | 178.53 | 2.5 | 118.6667 | 178 | 0 | 178 | 0.3533 | 0.53 |  | 99.7032 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 105 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 75.13 | 1.5 | 112.7 | 0 | 112.7 | 2.5 | 74 | 111 | 0 | 111 | 1.13 | 1.7 |  | 98.4959 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.52 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 418.35 | 1.5 | 627.53 | 0 | 627.53 | 2.5 | 417.3333 | 626 | 112.68 | 738.68 | 1.0167 | -111.16 |  | 99.757 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 11 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 99.244 | 1.5 | 148.87 | 0 | 148.87 | 2.5 | 99.244 | 148.87 | 0 | 148.87 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 63 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 50 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 90.41 | 1.5 | 135.62 | 0 | 135.62 | 2.5 | 0 | 0 | 0 | 0 | 90.41 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 81 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 78.79 | 1.5 | 118.19 | 0 | 118.19 | 2.5 | 78.79 | 118.19 | 0 | 118.19 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 20 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 172.224 | 1.5 | 258.34 | 0 | 258.34 | 2.5 | 158.6667 | 238 | 42.84 | 280.84 | 13.5573 | -22.5 |  | 92.1281 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.105 wall paint | Primer Water Base- Wall | Sq.Ft | 159.75 | 1.5 | 239.63 | 0 | 239.63 | 2.5 | 159.3333 | 239 | 0 | 239 | 0.4167 | 0.63 |  | 99.7392 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 40 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 112.48 | 1.5 | 168.72 | 0 | 168.72 | 2.5 | 0 | 0 | 0 | 0 | 112.48 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.46 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 403.34 | 1.5 | 605.01 | 0 | 605.01 | 2.5 | 0 | 0 | 0 | 0 | 403.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.111 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 358.71 | 1.5 | 538.07 | 0 | 538.07 | 2.5 | 358.71 | 538.07 | 0 | 538.07 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 116 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 66.41 | 1.5 | 99.62 | 0 | 99.62 | 2.5 | 66.41 | 99.62 | 0 | 99.62 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.93 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 505.94 | 1.5 | 758.91 | 0 | 758.91 | 2.5 | 500 | 750 | 0 | 750 | 5.94 | 8.91 |  | 98.8259 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.51 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 419.6 | 1.5 | 629.4 | 0 | 629.4 | 2.5 | 0 | 0 | 0 | 0 | 419.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 86 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 166.84 | 1.5 | 250.26 | 0 | 250.26 | 2.5 | 0 | 0 | 0 | 0 | 166.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 96 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 104.62 | 1.5 | 156.93 | 0 | 156.93 | 2.5 | 103.3333 | 155 | 27.9 | 182.9 | 1.2867 | -25.97 |  | 98.7701 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 92 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 106.6667 | 160 | 28.8 | 188.8 | 4.3033 | -22.35 |  | 96.1221 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 28 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 178.58 | 1.5 | 267.87 | 0 | 267.87 | 2.5 | 0 | 0 | 0 | 0 | 178.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.89 wall paint | Primer Water Base- Wall | Sq.Ft | 485.51 | 1.5 | 728.27 | 0 | 728.27 | 2.5 | 329.3333 | 494 | 88.92 | 582.92 | 156.1767 | 145.35 |  | 67.8324 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.41 wall paint | Primer Water Base- Wall | Sq.Ft | 446.3 | 1.5 | 669.45 | 0 | 669.45 | 2.5 | 0 | 0 | 0 | 0 | 446.3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 39 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 71.04 | 1.5 | 106.56 | 0 | 106.56 | 2.5 | 0 | 0 | 0 | 0 | 71.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.32 wall paint | Primer Water Base- Wall | Sq.Ft | 531.8 | 1.5 | 797.7 | 0 | 797.7 | 2.5 | 0 | 0 | 0 | 0 | 531.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.79 wall paint | Primer Water Base- Wall | Sq.Ft | 492.18 | 1.5 | 738.27 | 0 | 738.27 | 2.5 | 0 | 0 | 0 | 0 | 492.18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | 2nd floor shops passage ceiling painting - 5434.84 Sq.Ft | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 5434.84 | 1.5 | 8152.26 | 0 | 8152.26 | 2.5 | 0 | 0 | 0 | 0 | 5434.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.113 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 227.32 | 1.5 | 340.98 | 0 | 340.98 | 2.5 | 227.32 | 340.98 | 0 | 340.98 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.73 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 811.26 | 1.5 | 1216.89 | 0 | 1216.89 | 2.5 | 0 | 0 | 0 | 0 | 811.26 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 48 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 51 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 89.87 | 1.5 | 134.81 | 0 | 134.81 | 2.5 | 0 | 0 | 0 | 0 | 89.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 17 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 109.72 | 1.5 | 164.58 | 0 | 164.58 | 2.5 | 109.72 | 164.58 | 0 | 164.58 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.78 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 346.19 | 1.5 | 519.29 | 0 | 519.29 | 2.5 | 346.19 | 519.29 | 0 | 519.29 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 57 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 87.94 | 1.5 | 131.91 | 0 | 131.91 | 2.5 | 87.94 | 131.91 | 0 | 131.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 54 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.65 wall paint | Primer Water Base- Wall | Sq.Ft | 437.12 | 1.5 | 655.68 | 0 | 655.68 | 2.5 | 0 | 0 | 0 | 0 | 437.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.82 wall paint | Primer Water Base- Wall | Sq.Ft | 354.53 | 1.5 | 531.8 | 0 | 531.8 | 2.5 | 354.4945 | 531.74 | 0 | 531.74 | 0.0355 | 0.05 |  | 99.99 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 85 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 0 | 0 | 0 | 0 | 176.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.10 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 423.77 | 1.5 | 635.66 | 0 | 635.66 | 2.5 | 423.3333 | 635 | 0 | 635 | 0.4367 | 0.66 |  | 99.8969 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 86 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 166.84 | 1.5 | 250.26 | 0 | 250.26 | 2.5 | 0 | 0 | 0 | 0 | 166.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.4 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.95 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 303.65 | 1.5 | 455.48 | 0 | 455.48 | 2.5 | 299.3333 | 449 | 0 | 449 | 4.3167 | 6.48 |  | 98.5784 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 66 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 200.74 | 1.5 | 301.11 | 0 | 301.11 | 2.5 | 0 | 0 | 0 | 0 | 200.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 73 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 189.01 | 1.5 | 283.52 | 0 | 283.52 | 2.5 | 0 | 0 | 0 | 0 | 189.01 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.22 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 716.58 | 1.5 | 1074.87 | 0 | 1074.87 | 2.5 | 0 | 0 | 0 | 0 | 716.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 44 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 98.38 | 1.5 | 147.57 | 0 | 147.57 | 2.5 | 0 | 0 | 0 | 0 | 98.38 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 104 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 56.08 | 1.5 | 84.12 | 0 | 84.12 | 2.5 | 56 | 84 | 15.12 | 99.12 | 0.08 | -15 |  | 99.8573 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 98 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 47.68 | 1.5 | 71.52 | 0 | 71.52 | 2.5 | 47.68 | 71.52 | 12.88 | 84.4 | 0 | -12.88 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 62 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 115.71 | 1.5 | 173.57 | 0 | 173.57 | 2.5 | 0 | 0 | 0 | 0 | 115.71 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 87 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86.11 | 129.17 | 0 | 129.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 109 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 175.3333 | 263 | 47.34 | 310.34 | 1.4067 | -45.23 |  | 99.2041 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 45 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 89.34 | 1.5 | 134.01 | 0 | 134.01 | 2.5 | 0 | 0 | 0 | 0 | 89.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 14 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 127.63 | 1.5 | 191.45 | 0 | 191.45 | 2.5 | 127.3333 | 191 | 0 | 191 | 0.2967 | 0.45 |  | 99.7675 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 42 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 101.28 | 1.5 | 151.92 | 0 | 151.92 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.6133 | 0.92 |  | 99.3945 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.103 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 208.13 | 1.5 | 312.2 | 0 | 312.2 | 2.5 | 194 | 291 | 0 | 291 | 14.13 | 21.2 |  | 93.211 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 83 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 98.16 | 1.5 | 147.24 | 0 | 147.24 | 2.5 | 98.16 | 147.24 | 0 | 147.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 47 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 102 | 1.5 | 153 | 0 | 153 | 2.5 | 0 | 0 | 0 | 0 | 102 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 25 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 270.02 | 1.5 | 405.03 | 0 | 405.03 | 2.5 | 0 | 0 | 0 | 0 | 270.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.7 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 703.65 | 1.5 | 1055.48 | 0 | 1055.48 | 2.5 | 0 | 0 | 0 | 0 | 703.65 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.12 wall paint | Primer Water Base- Wall | Sq.Ft | 485.92 | 1.5 | 728.88 | 0 | 728.88 | 2.5 | 485.92 | 728.88 | 0 | 728.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.40 wall paint | Primer Water Base- Wall | Sq.Ft | 554.75 | 1.5 | 832.13 | 0 | 832.13 | 2.5 | 0 | 0 | 0 | 0 | 554.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.115 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 540.56 | 1.5 | 810.84 | 0 | 810.84 | 2.5 | 0 | 0 | 0 | 0 | 540.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.20 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 615.23 | 1.5 | 922.85 | 0 | 922.85 | 2.5 | 0 | 0 | 0 | 0 | 615.23 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 75 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 39.18 | 1.5 | 58.77 | 0 | 58.77 | 2.5 | 39.18 | 58.77 | 0 | 58.77 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 29 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 99.02 | 1.5 | 148.53 | 0 | 148.53 | 2.5 | 0 | 0 | 0 | 0 | 99.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.1 wall paint | Primer Water Base- Wall | Sq.Ft | 345.029 | 1.5 | 517.54 | 0 | 517.54 | 2.5 | 0 | 0 | 0 | 0 | 345.029 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.94 wall paint | Primer Water Base- Wall | Sq.Ft | 335.35 | 1.5 | 503.03 | 0 | 503.03 | 2.5 | 0 | 0 | 0 | 0 | 335.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 80 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 139.93 | 1.5 | 209.9 | 0 | 209.9 | 2.5 | 0 | 0 | 0 | 0 | 139.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.114 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 550.16 | 1.5 | 825.24 | 0 | 825.24 | 2.5 | 0 | 0 | 0 | 0 | 550.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 32 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.4 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.102 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 296.97 | 1.5 | 445.46 | 0 | 445.46 | 2.5 | 293.3333 | 440 | 79.2 | 519.2 | 3.6367 | -73.75 |  | 98.7754 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 104 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 56.08 | 1.5 | 84.12 | 0 | 84.12 | 2.5 | 56 | 84 | 15.12 | 99.12 | 0.08 | -15 |  | 99.8573 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 101 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 94.6667 | 142 | 25.56 | 167.56 | 2.2033 | -22.26 |  | 97.7255 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 116 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 66.41 | 1.5 | 99.62 | 0 | 99.62 | 2.5 | 66 | 99 | 0 | 99 | 0.41 | 0.62 |  | 99.3826 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.109 wall paint | 1st Coat Wall Putty - | Sq.Ft | 578.52 | 1.5 | 867.78 | 0 | 867.78 | 2.5 | 564 | 846 | 152.28 | 998.28 | 14.52 | -130.5 |  | 97.4901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.87 wall paint | 1st Coat Wall Putty - | Sq.Ft | 378.73 | 1.5 | 568.1 | 0 | 568.1 | 2.5 | 378.73 | 568.1 | 0 | 568.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.1 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 345.029 | 1.5 | 517.54 | 0 | 517.54 | 2.5 | 0 | 0 | 0 | 0 | 345.029 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.23 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 724.92 | 1.5 | 1087.38 | 0 | 1087.38 | 2.5 | 0 | 0 | 0 | 0 | 724.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.20 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 615.23 | 1.5 | 922.85 | 0 | 922.85 | 2.5 | 0 | 0 | 0 | 0 | 615.23 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 87 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86.11 | 129.17 | 0 | 129.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 55 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 95.47 | 1.5 | 143.21 | 0 | 143.21 | 2.5 | 0 | 0 | 0 | 0 | 95.47 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 84 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 90.74 | 1.5 | 136.11 | 0 | 136.11 | 2.5 | 90.74 | 136.11 | 0 | 136.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 101 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 94.6667 | 142 | 25.56 | 167.56 | 2.2033 | -22.26 |  | 97.7255 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 90 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 96 | 144 | 25.92 | 169.92 | 0.87 | -24.62 |  | 99.1019 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 35 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 220 | 1.5 | 330 | 0 | 330 | 2.5 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 113 | 2nd coat Premium Emulsion on wall | Sq.Ft | 231.05 | 1.5 | 346.58 | 0 | 346.58 | 2.5 | 231 | 346.5 | 0 | 346.5 | 0.05 | 0.08 |  | 99.9784 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 108 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 163.82 | 1.5 | 245.73 | 0 | 245.73 | 2.5 | 160 | 240 | 43.2 | 283.2 | 3.82 | -37.47 |  | 97.6682 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 112 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 78 | 117 | 0 | 117 | 0.03 | 0.05 |  | 99.9616 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.39 wall paint | Primer Water Base- Wall | Sq.Ft | 362.04 | 1.5 | 543.06 | 0 | 543.06 | 2.5 | 0 | 0 | 0 | 0 | 362.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.108 wall paint | Primer Water Base- Wall | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 564 | 846 | 0 | 846 | 4.09 | 6.14 |  | 99.28 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.21 wall paint | Primer Water Base- Wall | Sq.Ft | 616.89 | 1.5 | 925.34 | 0 | 925.34 | 2.5 | 0 | 0 | 0 | 0 | 616.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 98 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 47.68 | 1.5 | 71.52 | 0 | 71.52 | 2.5 | 47.68 | 71.52 | 12.88 | 84.4 | 0 | -12.88 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 43 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 61 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 109.47 | 1.5 | 164.21 | 0 | 164.21 | 2.5 | 0 | 0 | 0 | 0 | 109.47 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 53 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 96.6667 | 145 | 26.1 | 171.1 | 0.2033 | -25.8 |  | 99.7901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 26 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 250.43 | 1.5 | 375.65 | 0 | 375.65 | 2.5 | 0 | 0 | 0 | 0 | 250.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 97 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 85.78 | 1.5 | 128.67 | 0 | 128.67 | 2.5 | 85.69 | 128.54 | 0 | 128.54 | 0.09 | 0.14 |  | 99.8951 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 55 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 95.47 | 1.5 | 143.21 | 0 | 143.21 | 2.5 | 0 | 0 | 0 | 0 | 95.47 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 17 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 109.72 | 1.5 | 164.58 | 0 | 164.58 | 2.5 | 109.72 | 164.58 | 0 | 164.58 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.11 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 422.11 | 633.17 | 0 | 633.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 43 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 42 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 101.28 | 1.5 | 151.92 | 0 | 151.92 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.6133 | 0.92 |  | 99.3945 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 64 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 164.15 | 1.5 | 246.23 | 0 | 246.23 | 2.5 | 158.6667 | 238 | 42.84 | 280.84 | 5.4833 | -34.62 |  | 96.6596 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.39 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 362.04 | 1.5 | 543.06 | 0 | 543.06 | 2.5 | 0 | 0 | 0 | 0 | 362.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.44 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 435.87 | 1.5 | 653.81 | 0 | 653.81 | 2.5 | 0 | 0 | 0 | 0 | 435.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 47 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 102 | 1.5 | 153 | 0 | 153 | 2.5 | 0 | 0 | 0 | 0 | 102 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 107 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 71.58 | 1.5 | 107.37 | 0 | 107.37 | 2.5 | 71.3333 | 107 | 0 | 107 | 0.2467 | 0.37 |  | 99.6554 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 69 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 32.58 | 213.57 | 0 | -32.58 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 84 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 90.74 | 1.5 | 136.11 | 0 | 136.11 | 2.5 | 90.74 | 136.11 | 0 | 136.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 107 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 71.58 | 1.5 | 107.37 | 0 | 107.37 | 2.5 | 71.58 | 107.37 | 0 | 107.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.2 wall paint | Primer Water Base- Wall | Sq.Ft | 344.529 | 1.5 | 516.79 | 0 | 516.79 | 2.5 | 344 | 516 | 0 | 516 | 0.529 | 0.79 |  | 99.8465 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 105 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 75.13 | 1.5 | 112.7 | 0 | 112.7 | 2.5 | 74 | 111 | 0 | 111 | 1.13 | 1.7 |  | 98.4959 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.56 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 307.82 | 1.5 | 461.73 | 0 | 461.73 | 2.5 | 0 | 0 | 0 | 0 | 307.82 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 112 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 78.03 | 117.05 | 0 | 117.05 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.9 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 322 | 483 | 0 | 483 | 100.11 | 150.17 |  | 76.2834 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.21 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 616.89 | 1.5 | 925.34 | 0 | 925.34 | 2.5 | 0 | 0 | 0 | 0 | 616.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.117 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 208.55 | 1.5 | 312.83 | 0 | 312.83 | 2.5 | 208.55 | 312.83 | 0 | 312.83 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.1 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 345.029 | 1.5 | 517.54 | 0 | 517.54 | 2.5 | 340 | 510 | 91.8 | 601.8 | 5.029 | -84.26 |  | 98.5424 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.10 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 423.77 | 1.5 | 635.66 | 0 | 635.66 | 2.5 | 423.77 | 635.66 | 0 | 635.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.79 wall paint | 1st Coat Wall Putty - | Sq.Ft | 492.18 | 1.5 | 738.27 | 0 | 738.27 | 2.5 | 486 | 729 | 131.22 | 860.22 | 6.18 | -121.95 |  | 98.7444 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.112 wall paint | 1st Coat Wall Putty - | Sq.Ft | 350.36 | 1.5 | 525.54 | 0 | 525.54 | 2.5 | 350.36 | 525.54 | 0 | 525.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.93 wall paint | 1st Coat Wall Putty - | Sq.Ft | 505.94 | 1.5 | 758.91 | 0 | 758.91 | 2.5 | 500 | 750 | 0 | 750 | 5.94 | 8.91 |  | 98.8259 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.114 wall paint | Primer Water Base- Wall | Sq.Ft | 550.16 | 1.5 | 825.24 | 0 | 825.24 | 2.5 | 0 | 0 | 0 | 0 | 550.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.10 wall paint | Primer Water Base- Wall | Sq.Ft | 423.77 | 1.5 | 635.66 | 0 | 635.66 | 2.5 | 423.77 | 635.66 | 0 | 635.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.73 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 811.26 | 1.5 | 1216.89 | 0 | 1216.89 | 2.5 | 0 | 0 | 0 | 0 | 811.26 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 22 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.36 wall paint | Primer Water Base- Wall | Sq.Ft | 679.88 | 1.5 | 1019.82 | 0 | 1019.82 | 2.5 | 0 | 0 | 0 | 0 | 679.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.43 wall paint | 1st Coat Wall Putty - | Sq.Ft | 404.59 | 1.5 | 606.89 | 0 | 606.89 | 2.5 | 0 | 0 | 0 | 0 | 404.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.103 wall paint | 1st Coat Wall Putty - | Sq.Ft | 208.13 | 1.5 | 312.2 | 0 | 312.2 | 2.5 | 194 | 291 | 0 | 291 | 14.13 | 21.2 |  | 93.211 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.34 wall paint | 1st Coat Wall Putty - | Sq.Ft | 780.4 | 1.5 | 1170.6 | 0 | 1170.6 | 2.5 | 0 | 0 | 0 | 0 | 780.4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 82 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 70.82 | 1.5 | 106.23 | 0 | 106.23 | 2.5 | 70.6667 | 106 | 0 | 106 | 0.1533 | 0.23 |  | 99.7835 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.26 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 744.11 | 1.5 | 1116.17 | 0 | 1116.17 | 2.5 | 0 | 0 | 0 | 0 | 744.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.107 wall paint | Primer Water Base- Wall | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 0 | 483 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 79 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 133.79 | 1.5 | 200.69 | 0 | 200.69 | 2.5 | 0 | 0 | 0 | 0 | 133.79 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 05 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 115 | 1.5 | 172.5 | 0 | 172.5 | 2.5 | 0 | 0 | 0 | 0 | 115 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 15 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 102.47 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.47 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 24 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 280 | 1.5 | 420 | 0 | 420 | 2.5 | 0 | 0 | 0 | 0 | 280 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.30 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 0 | 0 | 0 | 0 | 245.67 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 12 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 127.661 | 1.5 | 191.49 | 0 | 191.49 | 2.5 | 127.661 | 191.49 | 0 | 191.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.110 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 231.49 | 1.5 | 347.24 | 0 | 347.24 | 2.5 | 231.49 | 347.24 | 0 | 347.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 14 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 127.63 | 1.5 | 191.45 | 0 | 191.45 | 2.5 | 127.3333 | 191 | 0 | 191 | 0.2967 | 0.45 |  | 99.7675 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 18 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 116.251 | 1.5 | 174.38 | 0 | 174.38 | 2.5 | 0 | 0 | 0 | 0 | 116.251 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.14 wall paint | 1st Coat Wall Putty - | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382.4 | 573.6 | 0 | 573.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.91 wall paint | 1st Coat Wall Putty - | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 86.94 | 569.94 | 0 | -86.94 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 25 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 270 | 1.5 | 405 | 0 | 405 | 2.5 | 0 | 0 | 0 | 0 | 270 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 44 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 98.38 | 1.5 | 147.57 | 0 | 147.57 | 2.5 | 0 | 0 | 0 | 0 | 98.38 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.105 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 159.75 | 1.5 | 239.63 | 0 | 239.63 | 2.5 | 159.3333 | 239 | 0 | 239 | 0.4167 | 0.63 |  | 99.7392 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 107 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 71.58 | 1.5 | 107.37 | 0 | 107.37 | 2.5 | 71.58 | 107.37 | 0 | 107.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.66 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 687.8 | 1.5 | 1031.7 | 0 | 1031.7 | 2.5 | 0 | 0 | 0 | 0 | 687.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 14 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 127.63 | 1.5 | 191.45 | 0 | 191.45 | 2.5 | 127.3333 | 191 | 0 | 191 | 0.2967 | 0.45 |  | 99.7675 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.16 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 423.1 | 1.5 | 634.65 | 0 | 634.65 | 2.5 | 423.1 | 634.65 | 0 | 634.65 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 38 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 85.03 | 1.5 | 127.55 | 0 | 127.55 | 2.5 | 0 | 0 | 0 | 0 | 85.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.110 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 231.49 | 1.5 | 347.24 | 0 | 347.24 | 2.5 | 231.49 | 347.24 | 0 | 347.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 96 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 104.62 | 1.5 | 156.93 | 0 | 156.93 | 2.5 | 103.3333 | 155 | 27.9 | 182.9 | 1.2867 | -25.97 |  | 98.7701 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 32 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 23 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 264 | 1.5 | 396 | 0 | 396 | 2.5 | 0 | 0 | 0 | 0 | 264 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.61 wall paint | 1st Coat Wall Putty - | Sq.Ft | 492.6 | 1.5 | 738.9 | 0 | 738.9 | 2.5 | 492 | 738 | 132.84 | 870.84 | 0.6 | -131.94 |  | 99.8782 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 87 | 1st coat Premium Emulsion on wall | Sq.Ft | 363.32 | 1.5 | 544.98 | 0 | 544.98 | 2.5 | 363 | 544.5 | 0 | 544.5 | 0.32 | 0.48 |  | 99.9119 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.33 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 410.43 | 1.5 | 615.65 | 0 | 615.65 | 2.5 | 0 | 0 | 0 | 0 | 410.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 60 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 82.23 | 1.5 | 123.35 | 0 | 123.35 | 2.5 | 49.338 | 74.01 | 0 | 74.01 | 32.892 | 49.34 |  | 60 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 106 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 74.37 | 1.5 | 111.56 | 0 | 111.56 | 2.5 | 74.37 | 111.56 | 0 | 111.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 91 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 63.5 | 1.5 | 95.25 | 0 | 95.25 | 2.5 | 0 | 0 | 0 | 0 | 63.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 23 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 264 | 1.5 | 396 | 0 | 396 | 2.5 | 0 | 0 | 0 | 0 | 264 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.46 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 403.34 | 1.5 | 605.01 | 0 | 605.01 | 2.5 | 0 | 0 | 0 | 0 | 403.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 06 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 180.665 | 1.5 | 271 | 0 | 271 | 2.5 | 0 | 0 | 0 | 0 | 180.665 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.62 wall paint | 1st Coat Wall Putty - | Sq.Ft | 342.44 | 1.5 | 513.66 | 0 | 513.66 | 2.5 | 0 | 0 | 0 | 0 | 342.44 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 109 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 175.3333 | 263 | 47.34 | 310.34 | 1.4067 | -45.23 |  | 99.2041 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.62 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 342.44 | 1.5 | 513.66 | 0 | 513.66 | 2.5 | 0 | 0 | 0 | 0 | 342.44 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 31 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 55.11 | 1.5 | 82.67 | 0 | 82.67 | 2.5 | 54.6667 | 82 | 0 | 82 | 0.4433 | 0.66 |  | 99.1956 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 25 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 270 | 1.5 | 405 | 0 | 405 | 2.5 | 0 | 0 | 0 | 0 | 270 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.57 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.48 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.75 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 292.8 | 1.5 | 439.2 | 0 | 439.2 | 2.5 | 292.8 | 439.2 | 0 | 439.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | 2nd floor shops passage ceiling painting - 5434.84 Sq.Ft | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 5434.84 | 1.5 | 8152.26 | 0 | 8152.26 | 2.5 | 0 | 0 | 0 | 0 | 5434.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.100 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 487.17 | 1.5 | 730.76 | 0 | 730.76 | 2.5 | 487 | 730.5 | 0 | 730.5 | 0.17 | 0.26 |  | 99.9651 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 57 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 87.94 | 1.5 | 131.91 | 0 | 131.91 | 2.5 | 87.94 | 131.91 | 0 | 131.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.16 wall paint | Primer Water Base- Wall | Sq.Ft | 423.1 | 1.5 | 634.65 | 0 | 634.65 | 2.5 | 423.1 | 634.65 | 0 | 634.65 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.55 wall paint | Primer Water Base- Wall | Sq.Ft | 425.03 | 1.5 | 637.55 | 0 | 637.55 | 2.5 | 0 | 0 | 0 | 0 | 425.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.33 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 410.43 | 1.5 | 615.65 | 0 | 615.65 | 2.5 | 0 | 0 | 0 | 0 | 410.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.16 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 423.1 | 1.5 | 634.65 | 0 | 634.65 | 2.5 | 423.1 | 634.65 | 0 | 634.65 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 38 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 85.03 | 1.5 | 127.55 | 0 | 127.55 | 2.5 | 0 | 0 | 0 | 0 | 85.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 108 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 163.82 | 1.5 | 245.73 | 0 | 245.73 | 2.5 | 163.3333 | 245 | 0 | 245 | 0.4867 | 0.73 |  | 99.7029 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 15 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 102.47 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.47 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.56 wall paint | 1st Coat Wall Putty - | Sq.Ft | 307.82 | 1.5 | 461.73 | 0 | 461.73 | 2.5 | 0 | 0 | 0 | 0 | 307.82 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.113 wall paint | 1st Coat Wall Putty - | Sq.Ft | 227.32 | 1.5 | 340.98 | 0 | 340.98 | 2.5 | 227.32 | 340.98 | 0 | 340.98 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.71 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 545.99 | 1.5 | 818.99 | 0 | 818.99 | 2.5 | 545.99 | 818.99 | 0 | 818.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 16 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 108.46 | 1.5 | 162.69 | 0 | 162.69 | 2.5 | 108.46 | 162.69 | 0 | 162.69 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 54 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.29 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 445.88 | 1.5 | 668.82 | 0 | 668.82 | 2.5 | 0 | 0 | 0 | 0 | 445.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 10 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 102.473 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.473 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.73 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 811.26 | 1.5 | 1216.89 | 0 | 1216.89 | 2.5 | 0 | 0 | 0 | 0 | 811.26 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 07 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 61 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 109.47 | 1.5 | 164.21 | 0 | 164.21 | 2.5 | 109.3333 | 164 | 29.52 | 193.52 | 0.1367 | -29.32 |  | 99.8751 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.117 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 208.55 | 1.5 | 312.83 | 0 | 312.83 | 2.5 | 208.55 | 312.83 | 0 | 312.83 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 16 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 108.46 | 1.5 | 162.69 | 0 | 162.69 | 2.5 | 108.46 | 162.69 | 0 | 162.69 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 09 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 100.85 | 1.5 | 151.28 | 0 | 151.28 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.1833 | 0.27 |  | 99.8182 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 113 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 79.33 | 1.5 | 119 | 0 | 119 | 2.5 | 79.33 | 119 | 0 | 119 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.84 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 243.58 | 1.5 | 365.37 | 0 | 365.37 | 2.5 | 243.3333 | 365 | 0 | 365 | 0.2467 | 0.37 |  | 99.8987 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 05 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 115 | 1.5 | 172.5 | 0 | 172.5 | 2.5 | 0 | 0 | 0 | 0 | 115 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.84 wall paint | Primer Water Base- Wall | Sq.Ft | 243.58 | 1.5 | 365.37 | 0 | 365.37 | 2.5 | 243.58 | 365.37 | 0 | 365.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | 2nd floor shops passage ceiling painting - 5434.84 Sq.Ft | 1st Coat Ceiling Putty | Sq.Ft | 5434.84 | 1.5 | 8152.26 | 0 | 8152.26 | 2.5 | 0 | 0 | 0 | 0 | 5434.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.17 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 419.7 | 1.5 | 629.55 | 0 | 629.55 | 2.5 | 419.7 | 629.55 | 0 | 629.55 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.94 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 335.35 | 1.5 | 503.03 | 0 | 503.03 | 2.5 | 0 | 0 | 0 | 0 | 335.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.44 wall paint | Primer Water Base- Wall | Sq.Ft | 435.87 | 1.5 | 653.81 | 0 | 653.81 | 2.5 | 0 | 0 | 0 | 0 | 435.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.59 wall paint | Primer Water Base- Wall | Sq.Ft | 222.31 | 1.5 | 333.47 | 0 | 333.47 | 2.5 | 222.31 | 333.47 | 0 | 333.47 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.62 wall paint | Primer Water Base- Wall | Sq.Ft | 342.44 | 1.5 | 513.66 | 0 | 513.66 | 2.5 | 0 | 0 | 0 | 0 | 342.44 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.27 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 537.64 | 1.5 | 806.46 | 0 | 806.46 | 2.5 | 0 | 0 | 0 | 0 | 537.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 24 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 280.89 | 1.5 | 421.34 | 0 | 421.34 | 2.5 | 0 | 0 | 0 | 0 | 280.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.60 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 388.74 | 1.5 | 583.11 | 0 | 583.11 | 2.5 | 388.6667 | 583 | 0 | 583 | 0.0733 | 0.11 |  | 99.9811 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.116 wall paint | 1st Coat Wall Putty - | Sq.Ft | 311.99 | 1.5 | 467.99 | 0 | 467.99 | 2.5 | 311.99 | 467.99 | 0 | 467.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 43 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 130.79 | 1.5 | 196.19 | 0 | 196.19 | 2.5 | 0 | 0 | 0 | 0 | 130.79 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 50 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 90.41 | 1.5 | 135.62 | 0 | 135.62 | 2.5 | 88 | 132 | 23.76 | 155.76 | 2.41 | -20.15 |  | 97.3344 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 37 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 126.69 | 1.5 | 190.04 | 0 | 190.04 | 2.5 | 0 | 0 | 0 | 0 | 126.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.36 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 679.88 | 1.5 | 1019.82 | 0 | 1019.82 | 2.5 | 0 | 0 | 0 | 0 | 679.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.98 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 298.23 | 1.5 | 447.35 | 0 | 447.35 | 2.5 | 290 | 435 | 78.3 | 513.3 | 8.23 | -65.96 |  | 97.2404 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.34 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 780.4 | 1.5 | 1170.6 | 0 | 1170.6 | 2.5 | 0 | 0 | 0 | 0 | 780.4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.74 wall paint | 1st Coat Wall Putty - | Sq.Ft | 294.05 | 1.5 | 441.08 | 0 | 441.08 | 2.5 | 294.05 | 441.08 | 0 | 441.08 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.88 wall paint | Primer Water Base- Wall | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.41 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 446.3 | 1.5 | 669.45 | 0 | 669.45 | 2.5 | 0 | 0 | 0 | 0 | 446.3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.35 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 561.84 | 1.5 | 842.76 | 0 | 842.76 | 2.5 | 0 | 0 | 0 | 0 | 561.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.88 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 0 | 0 | 0 | 0 | 228.99 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.100 wall paint | Primer Water Base- Wall | Sq.Ft | 487.17 | 1.5 | 730.76 | 0 | 730.76 | 2.5 | 487 | 730.5 | 0 | 730.5 | 0.17 | 0.26 |  | 99.9651 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.103 wall paint | Primer Water Base- Wall | Sq.Ft | 208.13 | 1.5 | 312.2 | 0 | 312.2 | 2.5 | 194 | 291 | 0 | 291 | 14.13 | 21.2 |  | 93.211 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 83 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 98.16 | 1.5 | 147.24 | 0 | 147.24 | 2.5 | 98.16 | 147.24 | 0 | 147.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 46 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 74.81 | 1.5 | 112.22 | 0 | 112.22 | 2.5 | 0 | 0 | 0 | 0 | 74.81 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 49 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 91.49 | 1.5 | 137.24 | 0 | 137.24 | 2.5 | 88 | 132 | 23.76 | 155.76 | 3.49 | -18.53 |  | 96.1854 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.30 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.63 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.72 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 577.69 | 1.5 | 866.54 | 0 | 866.54 | 2.5 | 0 | 0 | 0 | 0 | 577.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.81 wall paint | 1st Coat Wall Putty - | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.85 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 592.7 | 1.5 | 889.05 | 0 | 889.05 | 2.5 | 0 | 0 | 0 | 0 | 592.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 38 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 85.03 | 1.5 | 127.55 | 0 | 127.55 | 2.5 | 0 | 0 | 0 | 0 | 85.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.39 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 362.04 | 1.5 | 543.06 | 0 | 543.06 | 2.5 | 0 | 0 | 0 | 0 | 362.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 55 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 95.47 | 1.5 | 143.21 | 0 | 143.21 | 2.5 | 94 | 141 | 25.38 | 166.38 | 1.47 | -23.18 |  | 98.4602 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 52 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 90.95 | 1.5 | 136.43 | 0 | 136.43 | 2.5 | 87.3333 | 131 | 23.58 | 154.58 | 3.6167 | -18.16 |  | 96.0234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.71 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 545.99 | 1.5 | 818.99 | 0 | 818.99 | 2.5 | 545.3333 | 818 | 0 | 818 | 0.6567 | 0.99 |  | 99.8797 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.45 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 16 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 108.46 | 1.5 | 162.69 | 0 | 162.69 | 2.5 | 108.46 | 162.69 | 0 | 162.69 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 108 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 163.82 | 1.5 | 245.73 | 0 | 245.73 | 2.5 | 0 | 0 | 0 | 0 | 163.82 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.31 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 291.97 | 1.5 | 437.96 | 0 | 437.96 | 2.5 | 291.3333 | 437 | 0 | 437 | 0.6367 | 0.96 |  | 99.7819 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 56 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 110.31 | 1.5 | 165.47 | 0 | 165.47 | 2.5 | 0 | 0 | 0 | 0 | 110.31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 76 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 49.51 | 1.5 | 74.27 | 0 | 74.27 | 2.5 | 49.3333 | 74 | 0 | 74 | 0.1767 | 0.27 |  | 99.6431 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 101 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 94.6667 | 142 | 25.56 | 167.56 | 2.2033 | -22.26 |  | 97.7255 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 79 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 133.79 | 1.5 | 200.69 | 0 | 200.69 | 2.5 | 0 | 0 | 0 | 0 | 133.79 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 34 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 181.69 | 1.5 | 272.54 | 0 | 272.54 | 2.5 | 0 | 0 | 0 | 0 | 181.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.64 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 490.93 | 1.5 | 736.4 | 0 | 736.4 | 2.5 | 482 | 723 | 130.14 | 853.14 | 8.93 | -116.75 |  | 98.181 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.54 wall paint | Primer Water Base- Wall | Sq.Ft | 432.53 | 1.5 | 648.8 | 0 | 648.8 | 2.5 | 0 | 0 | 0 | 0 | 432.53 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.30 wall paint | Primer Water Base- Wall | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 59 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 0 | 180.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.98 wall paint | Primer Water Base- Wall | Sq.Ft | 298.23 | 1.5 | 447.35 | 0 | 447.35 | 2.5 | 290 | 435 | 78.3 | 513.3 | 8.23 | -65.96 |  | 97.2404 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 42 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 101.28 | 1.5 | 151.92 | 0 | 151.92 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.6133 | 0.92 |  | 99.3945 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.64 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 490.93 | 1.5 | 736.4 | 0 | 736.4 | 2.5 | 0 | 0 | 0 | 0 | 490.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.79 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 492.18 | 1.5 | 738.27 | 0 | 738.27 | 2.5 | 0 | 0 | 0 | 0 | 492.18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.102 wall paint | 1st Coat Wall Putty - | Sq.Ft | 296.97 | 1.5 | 445.46 | 0 | 445.46 | 2.5 | 293.3333 | 440 | 79.2 | 519.2 | 3.6367 | -73.75 |  | 98.7754 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.86 wall paint | 1st Coat Wall Putty - | Sq.Ft | 584.78 | 1.5 | 877.17 | 0 | 877.17 | 2.5 | 0 | 0 | 0 | 0 | 584.78 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 23 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 264.02 | 1.5 | 396.03 | 0 | 396.03 | 2.5 | 0 | 0 | 0 | 0 | 264.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.111 wall paint | Primer Water Base- Wall | Sq.Ft | 358.71 | 1.5 | 538.07 | 0 | 538.07 | 2.5 | 358.71 | 538.07 | 0 | 538.07 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.79 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 492.18 | 1.5 | 738.27 | 0 | 738.27 | 2.5 | 0 | 0 | 0 | 0 | 492.18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 87 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86 | 129 | 0 | 129 | 0.11 | 0.17 |  | 99.8723 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 29 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 99.02 | 1.5 | 148.53 | 0 | 148.53 | 2.5 | 0 | 0 | 0 | 0 | 99.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 44 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 98.38 | 1.5 | 147.57 | 0 | 147.57 | 2.5 | 0 | 0 | 0 | 0 | 98.38 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 36 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.89 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 485.51 | 1.5 | 728.27 | 0 | 728.27 | 2.5 | 0 | 0 | 0 | 0 | 485.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 20 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 172.224 | 1.5 | 258.34 | 0 | 258.34 | 2.5 | 158.6667 | 238 | 42.84 | 280.84 | 13.5573 | -22.5 |  | 92.1281 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 95 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 61.03 | 1.5 | 91.55 | 0 | 91.55 | 2.5 | 60 | 90 | 16.2 | 106.2 | 1.03 | -14.66 |  | 98.3123 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 73 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 189.01 | 1.5 | 283.52 | 0 | 283.52 | 2.5 | 0 | 0 | 0 | 0 | 189.01 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 93 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 110.65 | 1.5 | 165.98 | 0 | 165.98 | 2.5 | 110 | 165 | 0 | 165 | 0.65 | 0.98 |  | 99.4126 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.88 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 58 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 132.93 | 1.5 | 199.4 | 0 | 199.4 | 2.5 | 0 | 0 | 0 | 0 | 132.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 40 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 112.48 | 1.5 | 168.72 | 0 | 168.72 | 2.5 | 0 | 0 | 0 | 0 | 112.48 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 22 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 250.16 | 1.5 | 375.24 | 0 | 375.24 | 2.5 | 172.6667 | 259 | 46.62 | 305.62 | 77.4933 | 69.62 |  | 69.0225 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 08 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 148.866 | 1.5 | 223.3 | 0 | 223.3 | 2.5 | 0 | 0 | 0 | 0 | 148.866 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 04 ceiling paint - | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 70.289 | 1.5 | 105.43 | 0 | 105.43 | 2.5 | 70 | 105 | 0 | 105 | 0.289 | 0.43 |  | 99.5888 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.106 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 218.56 | 1.5 | 327.84 | 0 | 327.84 | 2.5 | 218.56 | 327.84 | 0 | 327.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.112 wall paint | Primer Water Base- Wall | Sq.Ft | 350.36 | 1.5 | 525.54 | 0 | 525.54 | 2.5 | 350.36 | 525.54 | 0 | 525.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.104 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 285.3 | 1.5 | 427.95 | 0 | 427.95 | 2.5 | 283.3333 | 425 | 76.5 | 501.5 | 1.9667 | -73.55 |  | 99.3107 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.63 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.42 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 269.86 | 1.5 | 404.79 | 0 | 404.79 | 2.5 | 264.6667 | 397 | 0 | 397 | 5.1933 | 7.79 |  | 98.0756 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 28 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 178.58 | 1.5 | 267.87 | 0 | 267.87 | 2.5 | 0 | 0 | 0 | 0 | 178.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 73 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 189.01 | 1.5 | 283.52 | 0 | 283.52 | 2.5 | 0 | 0 | 0 | 0 | 189.01 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 19 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 169.85 | 1.5 | 254.78 | 0 | 254.78 | 2.5 | 0 | 0 | 0 | 0 | 169.85 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 87 | 2nd coat Premium Emulsion on wall | Sq.Ft | 363.32 | 1.5 | 544.98 | 0 | 544.98 | 2.5 | 363.3 | 544.95 | 0 | 544.95 | 0.02 | 0.03 |  | 99.9945 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 70 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 119.58 | 1.5 | 179.37 | 0 | 179.37 | 2.5 | 0 | 0 | 0 | 0 | 119.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.77 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 214.8 | 1.5 | 322.2 | 0 | 322.2 | 2.5 | 214.8 | 322.2 | 0 | 322.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.91 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 86.94 | 569.94 | 0 | -86.94 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.57 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.3333 | 368 | 0 | 368 | 0.3367 | 0.51 |  | 99.8629 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 32 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 117 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 67.27 | 1.5 | 100.91 | 0 | 100.91 | 2.5 | 66.6667 | 100 | 0 | 100 | 0.6033 | 0.9 |  | 99.1032 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 45 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 89.34 | 1.5 | 134.01 | 0 | 134.01 | 2.5 | 0 | 0 | 0 | 0 | 89.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.114 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 550.16 | 1.5 | 825.24 | 0 | 825.24 | 2.5 | 0 | 0 | 0 | 0 | 550.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.78 wall paint | 1st Coat Wall Putty - | Sq.Ft | 346.19 | 1.5 | 519.29 | 0 | 519.29 | 2.5 | 346.19 | 519.29 | 0 | 519.29 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.117 wall paint | 1st Coat Wall Putty - | Sq.Ft | 208.55 | 1.5 | 312.83 | 0 | 312.83 | 2.5 | 208.55 | 312.83 | 0 | 312.83 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.76 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 275.28 | 1.5 | 412.92 | 0 | 412.92 | 2.5 | 274.6667 | 412 | 0 | 412 | 0.6133 | 0.92 |  | 99.7772 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.64 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 490.93 | 1.5 | 736.4 | 0 | 736.4 | 2.5 | 0 | 0 | 0 | 0 | 490.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.97 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 450.05 | 1.5 | 675.08 | 0 | 675.08 | 2.5 | 450 | 675 | 0 | 675 | 0.05 | 0.08 |  | 99.9889 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 10 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 102.473 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102 | 153 | 0 | 153 | 0.473 | 0.71 |  | 99.5384 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 58 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 132.93 | 1.5 | 199.4 | 0 | 199.4 | 2.5 | 0 | 0 | 0 | 0 | 132.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 114 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 165.98 | 1.5 | 248.97 | 0 | 248.97 | 2.5 | 0 | 0 | 0 | 0 | 165.98 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 05 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 115.404 | 1.5 | 173.11 | 0 | 173.11 | 2.5 | 0 | 0 | 0 | 0 | 115.404 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.42 wall paint | Primer Water Base- Wall | Sq.Ft | 269.86 | 1.5 | 404.79 | 0 | 404.79 | 2.5 | 264.6667 | 397 | 0 | 397 | 5.1933 | 7.79 |  | 98.0756 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.24 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 792.5 | 1.5 | 1188.75 | 0 | 1188.75 | 2.5 | 0 | 0 | 0 | 0 | 792.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.22 wall paint | 1st Coat Wall Putty - | Sq.Ft | 716.58 | 1.5 | 1074.87 | 0 | 1074.87 | 2.5 | 515.3333 | 773 | 139.14 | 912.14 | 201.2467 | 162.73 |  | 71.9157 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.19 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 608.97 | 1.5 | 913.46 | 0 | 913.46 | 2.5 | 0 | 0 | 0 | 0 | 608.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.50 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.55 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 425.03 | 1.5 | 637.55 | 0 | 637.55 | 2.5 | 420 | 630 | 113.4 | 743.4 | 5.03 | -105.86 |  | 98.8166 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.35 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 561.84 | 1.5 | 842.76 | 0 | 842.76 | 2.5 | 0 | 0 | 0 | 0 | 561.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.90 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 258.18 | 1.5 | 387.27 | 0 | 387.27 | 2.5 | 255.3333 | 383 | 68.94 | 451.94 | 2.8467 | -64.67 |  | 98.8974 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 85 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 0 | 0 | 0 | 0 | 176.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.81 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 53 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.68 wall paint | Primer Water Base- Wall | Sq.Ft | 618.56 | 1.5 | 927.84 | 0 | 927.84 | 2.5 | 0 | 0 | 0 | 0 | 618.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.23 wall paint | 1st Coat Wall Putty - | Sq.Ft | 724.92 | 1.5 | 1087.38 | 0 | 1087.38 | 2.5 | 0 | 0 | 0 | 0 | 724.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 113 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 79.33 | 1.5 | 119 | 0 | 119 | 2.5 | 79.3 | 118.95 | 0 | 118.95 | 0.03 | 0.05 |  | 99.9622 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 115 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 153.92 | 1.5 | 230.88 | 0 | 230.88 | 2.5 | 0 | 0 | 0 | 0 | 153.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.43 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 404.59 | 1.5 | 606.89 | 0 | 606.89 | 2.5 | 0 | 0 | 0 | 0 | 404.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.76 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 275.28 | 1.5 | 412.92 | 0 | 412.92 | 2.5 | 274.6667 | 412 | 0 | 412 | 0.6133 | 0.92 |  | 99.7772 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.50 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.53 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 443.8 | 1.5 | 665.7 | 0 | 665.7 | 2.5 | 0 | 0 | 0 | 0 | 443.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 09 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 100.85 | 1.5 | 151.28 | 0 | 151.28 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.1833 | 0.27 |  | 99.8182 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 77 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 70.5 | 1.5 | 105.75 | 0 | 105.75 | 2.5 | 70 | 105 | 0 | 105 | 0.5 | 0.75 |  | 99.2908 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 96 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 104.62 | 1.5 | 156.93 | 0 | 156.93 | 2.5 | 103.3333 | 155 | 27.9 | 182.9 | 1.2867 | -25.97 |  | 98.7701 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.42 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 269.86 | 1.5 | 404.79 | 0 | 404.79 | 2.5 | 264.6667 | 397 | 0 | 397 | 5.1933 | 7.79 |  | 98.0756 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.77 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 214.8 | 1.5 | 322.2 | 0 | 322.2 | 2.5 | 214.8 | 322.2 | 0 | 322.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.89 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 485.51 | 1.5 | 728.27 | 0 | 728.27 | 2.5 | 0 | 0 | 0 | 0 | 485.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.108 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 564 | 846 | 0 | 846 | 4.09 | 6.14 |  | 99.28 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 72 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 133.36 | 1.5 | 200.04 | 0 | 200.04 | 2.5 | 0 | 0 | 0 | 0 | 133.36 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 75 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 39.18 | 1.5 | 58.77 | 0 | 58.77 | 2.5 | 38.6667 | 58 | 0 | 58 | 0.5133 | 0.77 |  | 98.6899 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 115 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 153.92 | 1.5 | 230.88 | 0 | 230.88 | 2.5 | 0 | 0 | 0 | 0 | 153.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 68 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 129.16 | 1.5 | 193.74 | 0 | 193.74 | 2.5 | 0 | 0 | 0 | 0 | 129.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 62 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 115.71 | 1.5 | 173.57 | 0 | 173.57 | 2.5 | 0 | 0 | 0 | 0 | 115.71 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 56 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 110 | 1.5 | 165 | 0 | 165 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 53 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 24 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 280 | 1.5 | 420 | 0 | 420 | 2.5 | 0 | 0 | 0 | 0 | 280 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.9 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 322 | 483 | 0 | 483 | 100.11 | 150.17 |  | 76.2834 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 49 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 91.49 | 1.5 | 137.24 | 0 | 137.24 | 2.5 | 0 | 0 | 0 | 0 | 91.49 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.54 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 432.53 | 1.5 | 648.8 | 0 | 648.8 | 2.5 | 0 | 0 | 0 | 0 | 432.53 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.109 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 578.52 | 1.5 | 867.78 | 0 | 867.78 | 2.5 | 564 | 846 | 152.28 | 998.28 | 14.52 | -130.5 |  | 97.4901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 27 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 174.91 | 1.5 | 262.37 | 0 | 262.37 | 2.5 | 0 | 0 | 0 | 0 | 174.91 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 40 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 112.48 | 1.5 | 168.72 | 0 | 168.72 | 2.5 | 0 | 0 | 0 | 0 | 112.48 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 112 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 78.03 | 117.05 | 0 | 117.05 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.110 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 231.49 | 1.5 | 347.24 | 0 | 347.24 | 2.5 | 231.3333 | 347 | 0 | 347 | 0.1567 | 0.24 |  | 99.9323 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.31 wall paint | 1st Coat Wall Putty - | Sq.Ft | 291.97 | 1.5 | 437.96 | 0 | 437.96 | 2.5 | 291.3333 | 437 | 0 | 437 | 0.6367 | 0.96 |  | 99.7819 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.58 wall paint | 1st Coat Wall Putty - | Sq.Ft | 455.89 | 1.5 | 683.84 | 0 | 683.84 | 2.5 | 455.3333 | 683 | 122.94 | 805.94 | 0.5567 | -122.11 |  | 99.8779 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.46 wall paint | 1st Coat Wall Putty - | Sq.Ft | 403.34 | 1.5 | 605.01 | 0 | 605.01 | 2.5 | 0 | 0 | 0 | 0 | 403.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.75 wall paint | 1st Coat Wall Putty - | Sq.Ft | 292.8 | 1.5 | 439.2 | 0 | 439.2 | 2.5 | 292.8 | 439.2 | 0 | 439.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 105 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 75.13 | 1.5 | 112.7 | 0 | 112.7 | 2.5 | 74 | 111 | 0 | 111 | 1.13 | 1.7 |  | 98.4959 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.92 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 488 | 1.5 | 732 | 0 | 732 | 2.5 | 480.6667 | 721 | 129.78 | 850.78 | 7.3333 | -118.78 |  | 98.4973 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.84 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 243.58 | 1.5 | 365.37 | 0 | 365.37 | 2.5 | 243.58 | 365.37 | 0 | 365.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.92 wall paint | Primer Water Base- Wall | Sq.Ft | 488 | 1.5 | 732 | 0 | 732 | 2.5 | 480.6667 | 721 | 129.78 | 850.78 | 7.3333 | -118.78 |  | 98.4973 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.100 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 487.17 | 1.5 | 730.76 | 0 | 730.76 | 2.5 | 487 | 730.5 | 0 | 730.5 | 0.17 | 0.26 |  | 99.9651 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 41 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 113.02 | 1.5 | 169.53 | 0 | 169.53 | 2.5 | 112.6667 | 169 | 0 | 169 | 0.3533 | 0.53 |  | 99.6874 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.112 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 350.36 | 1.5 | 525.54 | 0 | 525.54 | 2.5 | 350 | 525 | 0 | 525 | 0.36 | 0.54 |  | 99.8972 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 99 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 67.81 | 1.5 | 101.72 | 0 | 101.72 | 2.5 | 67.3333 | 101 | 0 | 101 | 0.4767 | 0.72 |  | 99.297 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.85 wall paint | 1st Coat Wall Putty - | Sq.Ft | 592.7 | 1.5 | 889.05 | 0 | 889.05 | 2.5 | 0 | 0 | 0 | 0 | 592.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.90 wall paint | 1st Coat Wall Putty - | Sq.Ft | 258.18 | 1.5 | 387.27 | 0 | 387.27 | 2.5 | 255.3333 | 383 | 68.94 | 451.94 | 2.8467 | -64.67 |  | 98.8974 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 116 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 66.41 | 1.5 | 99.62 | 0 | 99.62 | 2.5 | 66.41 | 99.62 | 0 | 99.62 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 79 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 133.79 | 1.5 | 200.69 | 0 | 200.69 | 2.5 | 0 | 0 | 0 | 0 | 133.79 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 101 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 94.6667 | 142 | 25.56 | 167.56 | 2.2033 | -22.26 |  | 97.7255 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.52 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 418.35 | 1.5 | 627.53 | 0 | 627.53 | 2.5 | 0 | 0 | 0 | 0 | 418.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.23 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 724.92 | 1.5 | 1087.38 | 0 | 1087.38 | 2.5 | 0 | 0 | 0 | 0 | 724.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.61 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 492.6 | 1.5 | 738.9 | 0 | 738.9 | 2.5 | 0 | 0 | 0 | 0 | 492.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 27 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 174.91 | 1.5 | 262.37 | 0 | 262.37 | 2.5 | 0 | 0 | 0 | 0 | 174.91 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.58 wall paint | Primer Water Base- Wall | Sq.Ft | 455.89 | 1.5 | 683.84 | 0 | 683.84 | 2.5 | 0 | 0 | 0 | 0 | 455.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 09 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 100.85 | 1.5 | 151.28 | 0 | 151.28 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.1833 | 0.27 |  | 99.8182 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 44 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 98.38 | 1.5 | 147.57 | 0 | 147.57 | 2.5 | 0 | 0 | 0 | 0 | 98.38 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.114 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 550.16 | 1.5 | 825.24 | 0 | 825.24 | 2.5 | 0 | 0 | 0 | 0 | 550.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 65 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 110.33 | 1.5 | 165.5 | 0 | 165.5 | 2.5 | 0 | 0 | 0 | 0 | 110.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.2 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 344.529 | 1.5 | 516.79 | 0 | 516.79 | 2.5 | 344 | 516 | 0 | 516 | 0.529 | 0.79 |  | 99.8465 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.67 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 255.26 | 1.5 | 382.89 | 0 | 382.89 | 2.5 | 190.6667 | 286 | 0 | 286 | 64.5933 | 96.89 |  | 74.6951 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 54 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86 | 129 | 23.22 | 152.22 | 0.11 | -23.06 |  | 99.8723 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.2 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 344.529 | 1.5 | 516.79 | 0 | 516.79 | 2.5 | 344 | 516 | 0 | 516 | 0.529 | 0.79 |  | 99.8465 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.58 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 455.89 | 1.5 | 683.84 | 0 | 683.84 | 2.5 | 0 | 0 | 0 | 0 | 455.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.80 wall paint | Primer Water Base- Wall | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.110 wall paint | Primer Water Base- Wall | Sq.Ft | 231.49 | 1.5 | 347.24 | 0 | 347.24 | 2.5 | 231.49 | 347.24 | 0 | 347.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 109 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 175.3333 | 263 | 47.34 | 310.34 | 1.4067 | -45.23 |  | 99.2041 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 85 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 0 | 0 | 0 | 0 | 176.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.80 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.98 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 298.23 | 1.5 | 447.35 | 0 | 447.35 | 2.5 | 290 | 435 | 78.3 | 513.3 | 8.23 | -65.96 |  | 97.2404 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.87 wall paint | Primer Water Base- Wall | Sq.Ft | 378.73 | 1.5 | 568.1 | 0 | 568.1 | 2.5 | 378.73 | 568.1 | 0 | 568.1 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.26 wall paint | Primer Water Base- Wall | Sq.Ft | 744.11 | 1.5 | 1116.17 | 0 | 1116.17 | 2.5 | 0 | 0 | 0 | 0 | 744.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.97 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 450.05 | 1.5 | 675.08 | 0 | 675.08 | 2.5 | 450 | 675 | 0 | 675 | 0.05 | 0.08 |  | 99.9889 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.75 wall paint | Primer Water Base- Wall | Sq.Ft | 292.8 | 1.5 | 439.2 | 0 | 439.2 | 2.5 | 292.8 | 439.2 | 0 | 439.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 109 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 175.3333 | 263 | 47.34 | 310.34 | 1.4067 | -45.23 |  | 99.2041 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 81 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 78.79 | 1.5 | 118.19 | 0 | 118.19 | 2.5 | 78.79 | 118.19 | 0 | 118.19 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 94 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 63.35 | 1.5 | 95.03 | 0 | 95.03 | 2.5 | 0 | 0 | 0 | 0 | 63.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.75 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 292.8 | 1.5 | 439.2 | 0 | 439.2 | 2.5 | 292.8 | 439.2 | 0 | 439.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.26 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 744.11 | 1.5 | 1116.17 | 0 | 1116.17 | 2.5 | 0 | 0 | 0 | 0 | 744.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.28 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 539.31 | 1.5 | 808.97 | 0 | 808.97 | 2.5 | 0 | 0 | 0 | 0 | 539.31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.42 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 269.86 | 1.5 | 404.79 | 0 | 404.79 | 2.5 | 264.6667 | 397 | 0 | 397 | 5.1933 | 7.79 |  | 98.0756 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.69 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 456.6667 | 685 | 123.3 | 808.3 | 111.4233 | 43.83 |  | 80.3863 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 74 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 45.31 | 1.5 | 67.97 | 0 | 67.97 | 2.5 | 44.6667 | 67 | 0 | 67 | 0.6433 | 0.96 |  | 98.5802 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.95 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 303.65 | 1.5 | 455.48 | 0 | 455.48 | 2.5 | 299.3333 | 449 | 0 | 449 | 4.3167 | 6.48 |  | 98.5784 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.92 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 488 | 1.5 | 732 | 0 | 732 | 2.5 | 480.6667 | 721 | 129.78 | 850.78 | 7.3333 | -118.78 |  | 98.4973 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 08 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 148.866 | 1.5 | 223.3 | 0 | 223.3 | 2.5 | 136.6667 | 205 | 36.9 | 241.9 | 12.1993 | -18.6 |  | 91.8052 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 34 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 181.69 | 1.5 | 272.54 | 0 | 272.54 | 2.5 | 0 | 0 | 0 | 0 | 181.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 01 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 77 | 115.5 | 20.8 | 136.3 | 0.286 | -20.37 |  | 99.6299 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.11 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 422 | 633 | 0 | 633 | 0.11 | 0.17 |  | 99.9739 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 111 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 83.95 | 1.5 | 125.93 | 0 | 125.93 | 2.5 | 83.95 | 125.93 | 0 | 125.93 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 01 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 0 | 0 | 0 | 0 | 77.286 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.115 wall paint | Primer Water Base- Wall | Sq.Ft | 540.56 | 1.5 | 810.84 | 0 | 810.84 | 2.5 | 0 | 0 | 0 | 0 | 540.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 104 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 56.08 | 1.5 | 84.12 | 0 | 84.12 | 2.5 | 56 | 84 | 15.12 | 99.12 | 0.08 | -15 |  | 99.8573 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 41 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 113.02 | 1.5 | 169.53 | 0 | 169.53 | 2.5 | 113 | 169.5 | 0 | 169.5 | 0.02 | 0.03 |  | 99.9823 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 38 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 85.03 | 1.5 | 127.55 | 0 | 127.55 | 2.5 | 0 | 0 | 0 | 0 | 85.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 30 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 74.27 | 1.5 | 111.41 | 0 | 111.41 | 2.5 | 0 | 0 | 0 | 0 | 74.27 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 46 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 74.81 | 1.5 | 112.22 | 0 | 112.22 | 2.5 | 0 | 0 | 0 | 0 | 74.81 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 56 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 110 | 1.5 | 165 | 0 | 165 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 75 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 39.18 | 1.5 | 58.77 | 0 | 58.77 | 2.5 | 39.18 | 58.77 | 0 | 58.77 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 100 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 119.02 | 1.5 | 178.53 | 0 | 178.53 | 2.5 | 118.6667 | 178 | 0 | 178 | 0.3533 | 0.53 |  | 99.7032 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.82 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 354.53 | 1.5 | 531.8 | 0 | 531.8 | 2.5 | 354.4945 | 531.74 | 0 | 531.74 | 0.0355 | 0.05 |  | 99.99 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 21 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 175.13 | 1.5 | 262.7 | 0 | 262.7 | 2.5 | 169.3333 | 254 | 45.72 | 299.72 | 5.7967 | -37.03 |  | 96.6901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.7 wall paint | Primer Water Base- Wall | Sq.Ft | 703.65 | 1.5 | 1055.48 | 0 | 1055.48 | 2.5 | 0 | 0 | 0 | 0 | 703.65 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.98 wall paint | 1st Coat Wall Putty - | Sq.Ft | 298.23 | 1.5 | 447.35 | 0 | 447.35 | 2.5 | 290 | 435 | 78.3 | 513.3 | 8.23 | -65.96 |  | 97.2404 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.66 wall paint | 1st Coat Wall Putty - | Sq.Ft | 687.8 | 1.5 | 1031.7 | 0 | 1031.7 | 2.5 | 508.6667 | 763 | 137.34 | 900.34 | 179.1333 | 131.36 |  | 73.9556 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.92 wall paint | 1st Coat Wall Putty - | Sq.Ft | 488 | 1.5 | 732 | 0 | 732 | 2.5 | 480.6667 | 721 | 129.78 | 850.78 | 7.3333 | -118.78 |  | 98.4973 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 33 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 0 | 0 | 0 | 0 | 78.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 85 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 0 | 0 | 0 | 0 | 176.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 98 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 47.68 | 1.5 | 71.52 | 0 | 71.52 | 2.5 | 47.68 | 71.52 | 12.88 | 84.4 | 0 | -12.88 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 100 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 119.02 | 1.5 | 178.53 | 0 | 178.53 | 2.5 | 118.6667 | 178 | 0 | 178 | 0.3533 | 0.53 |  | 99.7032 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.64 wall paint | Primer Water Base- Wall | Sq.Ft | 490.93 | 1.5 | 736.4 | 0 | 736.4 | 2.5 | 0 | 0 | 0 | 0 | 490.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 70 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 119.58 | 1.5 | 179.37 | 0 | 179.37 | 2.5 | 0 | 0 | 0 | 0 | 119.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 22 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 102 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 56.51 | 1.5 | 84.77 | 0 | 84.77 | 2.5 | 52.6667 | 79 | 14.22 | 93.22 | 3.8433 | -8.46 |  | 93.1989 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 15 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 102.47 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.47 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 56 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 110 | 1.5 | 165 | 0 | 165 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 64 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 164.15 | 1.5 | 246.23 | 0 | 246.23 | 2.5 | 0 | 0 | 0 | 0 | 164.15 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.58 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 455.89 | 1.5 | 683.84 | 0 | 683.84 | 2.5 | 0 | 0 | 0 | 0 | 455.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.43 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 404.59 | 1.5 | 606.89 | 0 | 606.89 | 2.5 | 0 | 0 | 0 | 0 | 404.59 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 44 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 98.38 | 1.5 | 147.57 | 0 | 147.57 | 2.5 | 0 | 0 | 0 | 0 | 98.38 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 89 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 109.3333 | 164 | 29.52 | 193.52 | 1.6367 | -27.07 |  | 98.5251 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.1 wall paint | 1st Coat Wall Putty - | Sq.Ft | 345.029 | 1.5 | 517.54 | 0 | 517.54 | 2.5 | 340 | 510 | 91.8 | 601.8 | 5.029 | -84.26 |  | 98.5424 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.29 wall paint | 1st Coat Wall Putty - | Sq.Ft | 445.88 | 1.5 | 668.82 | 0 | 668.82 | 2.5 | 0 | 0 | 0 | 0 | 445.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 88 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 80.83 | 1.5 | 121.25 | 0 | 121.25 | 2.5 | 0 | 0 | 0 | 0 | 80.83 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.90 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 258.18 | 1.5 | 387.27 | 0 | 387.27 | 2.5 | 0 | 0 | 0 | 0 | 258.18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 93 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 110.65 | 1.5 | 165.98 | 0 | 165.98 | 2.5 | 110.6 | 165.9 | 0 | 165.9 | 0.05 | 0.08 |  | 99.9548 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 29 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 99.02 | 1.5 | 148.53 | 0 | 148.53 | 2.5 | 0 | 0 | 0 | 0 | 99.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.104 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 285.3 | 1.5 | 427.95 | 0 | 427.95 | 2.5 | 283.3333 | 425 | 76.5 | 501.5 | 1.9667 | -73.55 |  | 99.3107 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.101 wall paint | 1st Coat Wall Putty - | Sq.Ft | 446.71 | 1.5 | 670.07 | 0 | 670.07 | 2.5 | 446.6667 | 670 | 120.6 | 790.6 | 0.0433 | -120.54 |  | 99.9903 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 20 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 172.224 | 1.5 | 258.34 | 0 | 258.34 | 2.5 | 0 | 0 | 0 | 0 | 172.224 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.37 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 562.25 | 1.5 | 843.38 | 0 | 843.38 | 2.5 | 0 | 0 | 0 | 0 | 562.25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.25 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 772.06 | 1.5 | 1158.09 | 0 | 1158.09 | 2.5 | 0 | 0 | 0 | 0 | 772.06 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.30 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.33 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 410.43 | 1.5 | 615.65 | 0 | 615.65 | 2.5 | 0 | 0 | 0 | 0 | 410.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.15 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 325.59 | 1.5 | 488.39 | 0 | 488.39 | 2.5 | 325.3333 | 488 | 0 | 488 | 0.2567 | 0.39 |  | 99.9212 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.67 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 255.26 | 1.5 | 382.89 | 0 | 382.89 | 2.5 | 190.6667 | 286 | 0 | 286 | 64.5933 | 96.89 |  | 74.6951 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.9 wall paint | Primer Water Base- Wall | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 322 | 483 | 0 | 483 | 100.11 | 150.17 |  | 76.2834 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.113 wall paint | Primer Water Base- Wall | Sq.Ft | 227.32 | 1.5 | 340.98 | 0 | 340.98 | 2.5 | 227.32 | 340.98 | 0 | 340.98 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 70 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 119.58 | 1.5 | 179.37 | 0 | 179.37 | 2.5 | 0 | 0 | 0 | 0 | 119.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 100 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 119.02 | 1.5 | 178.53 | 0 | 178.53 | 2.5 | 118.6667 | 178 | 0 | 178 | 0.3533 | 0.53 |  | 99.7032 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 31 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 55.11 | 1.5 | 82.67 | 0 | 82.67 | 2.5 | 54.6667 | 82 | 0 | 82 | 0.4433 | 0.66 |  | 99.1956 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 110 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 82.56 | 1.5 | 123.84 | 0 | 123.84 | 2.5 | 82.56 | 123.84 | 0 | 123.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.19 wall paint | Primer Water Base- Wall | Sq.Ft | 608.97 | 1.5 | 913.46 | 0 | 913.46 | 2.5 | 0 | 0 | 0 | 0 | 608.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.27 wall paint | Primer Water Base- Wall | Sq.Ft | 537.64 | 1.5 | 806.46 | 0 | 806.46 | 2.5 | 0 | 0 | 0 | 0 | 537.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.20 wall paint | 1st Coat Wall Putty - | Sq.Ft | 615.23 | 1.5 | 922.85 | 0 | 922.85 | 2.5 | 498 | 747 | 134.46 | 881.46 | 117.23 | 41.39 |  | 80.9453 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 89 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 109.3333 | 164 | 29.52 | 193.52 | 1.6367 | -27.07 |  | 98.5251 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.10 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 423.77 | 1.5 | 635.66 | 0 | 635.66 | 2.5 | 423.77 | 635.66 | 0 | 635.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.102 wall paint | Primer Water Base- Wall | Sq.Ft | 296.97 | 1.5 | 445.46 | 0 | 445.46 | 2.5 | 293.3333 | 440 | 79.2 | 519.2 | 3.6367 | -73.75 |  | 98.7754 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.14 wall paint | Primer Water Base- Wall | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382.4 | 573.6 | 0 | 573.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.22 wall paint | Primer Water Base- Wall | Sq.Ft | 716.58 | 1.5 | 1074.87 | 0 | 1074.87 | 2.5 | 0 | 0 | 0 | 0 | 716.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.21 wall paint | 1st Coat Wall Putty - | Sq.Ft | 616.89 | 1.5 | 925.34 | 0 | 925.34 | 2.5 | 502 | 753 | 135.54 | 888.54 | 114.89 | 36.8 |  | 81.3759 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 77 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 70.5 | 1.5 | 105.75 | 0 | 105.75 | 2.5 | 70.5 | 105.75 | 0 | 105.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 80 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 139.93 | 1.5 | 209.9 | 0 | 209.9 | 2.5 | 121.3333 | 182 | 32.76 | 214.76 | 18.5967 | -4.87 |  | 86.71 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 91 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 63.5 | 1.5 | 95.25 | 0 | 95.25 | 2.5 | 61.3333 | 92 | 16.56 | 108.56 | 2.1667 | -13.31 |  | 96.5879 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 103 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 52.85 | 1.5 | 79.28 | 0 | 79.28 | 2.5 | 52.6667 | 79 | 0 | 79 | 0.1833 | 0.27 |  | 99.6532 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 56 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 110 | 1.5 | 165 | 0 | 165 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 103 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 52.85 | 1.5 | 79.28 | 0 | 79.28 | 2.5 | 52.6667 | 79 | 0 | 79 | 0.1833 | 0.27 |  | 99.6532 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.5 wall paint | Primer Water Base- Wall | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 114 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 165.98 | 1.5 | 248.97 | 0 | 248.97 | 2.5 | 0 | 0 | 0 | 0 | 165.98 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 76 | 1st coat Premium Emulsion on wall | Sq.Ft | 279.8 | 1.5 | 419.7 | 0 | 419.7 | 2.5 | 279.8 | 419.7 | 0 | 419.7 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.18 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 503.86 | 1.5 | 755.79 | 0 | 755.79 | 2.5 | 0 | 0 | 0 | 0 | 503.86 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.116 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 311.99 | 1.5 | 467.99 | 0 | 467.99 | 2.5 | 311.99 | 467.99 | 0 | 467.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 72 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 133.36 | 1.5 | 200.04 | 0 | 200.04 | 2.5 | 0 | 0 | 0 | 0 | 133.36 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 103 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 52.85 | 1.5 | 79.28 | 0 | 79.28 | 2.5 | 52.6668 | 79 | 0 | 79 | 0.1832 | 0.27 |  | 99.6534 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 03 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 70.504 | 1.5 | 105.76 | 0 | 105.76 | 2.5 | 70 | 105 | 0 | 105 | 0.504 | 0.76 |  | 99.2851 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.97 wall paint | 1st Coat Wall Putty - | Sq.Ft | 450.05 | 1.5 | 675.08 | 0 | 675.08 | 2.5 | 450 | 675 | 0 | 675 | 0.05 | 0.08 |  | 99.9889 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.65 wall paint | 1st Coat Wall Putty - | Sq.Ft | 437.12 | 1.5 | 655.68 | 0 | 655.68 | 2.5 | 426 | 639 | 115.02 | 754.02 | 11.12 | -98.34 |  | 97.4561 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.91 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 0 | 0 | 0 | 0 | 322 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 84 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 90.74 | 1.5 | 136.11 | 0 | 136.11 | 2.5 | 90.74 | 136.11 | 0 | 136.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 62 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 115.71 | 1.5 | 173.57 | 0 | 173.57 | 2.5 | 0 | 0 | 0 | 0 | 115.71 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.97 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 450.05 | 1.5 | 675.08 | 0 | 675.08 | 2.5 | 450 | 675 | 0 | 675 | 0.05 | 0.08 |  | 99.9889 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.56 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 307.82 | 1.5 | 461.73 | 0 | 461.73 | 2.5 | 0 | 0 | 0 | 0 | 307.82 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 76 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 49.51 | 1.5 | 74.27 | 0 | 74.27 | 2.5 | 49.3333 | 74 | 0 | 74 | 0.1767 | 0.27 |  | 99.6431 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.16 wall paint | 1st Coat Wall Putty - | Sq.Ft | 423.1 | 1.5 | 634.65 | 0 | 634.65 | 2.5 | 423.1 | 634.65 | 0 | 634.65 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.11 wall paint | 1st Coat Wall Putty - | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 422.11 | 633.17 | 0 | 633.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 92 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 106.6667 | 160 | 28.8 | 188.8 | 4.3033 | -22.35 |  | 96.1221 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.50 wall paint | Primer Water Base- Wall | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 04 ceiling paint - | Primer Water Base- Ceiling | Sq.Ft | 70.289 | 1.5 | 105.43 | 0 | 105.43 | 2.5 | 70 | 105 | 0 | 105 | 0.289 | 0.43 |  | 99.5888 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 117 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 67.27 | 1.5 | 100.91 | 0 | 100.91 | 2.5 | 67.27 | 100.91 | 0 | 100.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.18 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 503.86 | 1.5 | 755.79 | 0 | 755.79 | 2.5 | 0 | 0 | 0 | 0 | 503.86 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.26 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 744.11 | 1.5 | 1116.17 | 0 | 1116.17 | 2.5 | 0 | 0 | 0 | 0 | 744.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.60 wall paint | Primer Water Base- Wall | Sq.Ft | 388.74 | 1.5 | 583.11 | 0 | 583.11 | 2.5 | 388.74 | 583.11 | 0 | 583.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 90 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 96 | 144 | 25.92 | 169.92 | 0.87 | -24.62 |  | 99.1019 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 110 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 82.56 | 1.5 | 123.84 | 0 | 123.84 | 2.5 | 82.56 | 123.84 | 0 | 123.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 58 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 132.93 | 1.5 | 199.4 | 0 | 199.4 | 2.5 | 132.6667 | 199 | 35.82 | 234.82 | 0.2633 | -35.43 |  | 99.8019 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 20 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 172.224 | 1.5 | 258.34 | 0 | 258.34 | 2.5 | 0 | 0 | 0 | 0 | 172.224 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 07 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.5 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 77 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 70.5 | 1.5 | 105.75 | 0 | 105.75 | 2.5 | 70.5 | 105.75 | 0 | 105.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.11 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 422.11 | 633.17 | 0 | 633.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 68 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 129.16 | 1.5 | 193.74 | 0 | 193.74 | 2.5 | 0 | 0 | 0 | 0 | 129.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.60 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 388.74 | 1.5 | 583.11 | 0 | 583.11 | 2.5 | 388.74 | 583.11 | 0 | 583.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 13 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 126.17 | 1.5 | 189.26 | 0 | 189.26 | 2.5 | 126 | 189 | 0 | 189 | 0.17 | 0.26 |  | 99.8653 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.95 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 303.65 | 1.5 | 455.48 | 0 | 455.48 | 2.5 | 299.3333 | 449 | 80.82 | 529.82 | 4.3167 | -74.35 |  | 98.5784 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 19 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 169.85 | 1.5 | 254.78 | 0 | 254.78 | 2.5 | 0 | 0 | 0 | 0 | 169.85 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 78 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 62.53 | 1.5 | 93.8 | 0 | 93.8 | 2.5 | 62 | 93 | 0 | 93 | 0.53 | 0.8 |  | 99.1524 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.49 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 421.69 | 1.5 | 632.54 | 0 | 632.54 | 2.5 | 421.3333 | 632 | 113.76 | 745.76 | 0.3567 | -113.23 |  | 99.9154 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 59 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 0 | 180.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 113 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 79.33 | 1.5 | 119 | 0 | 119 | 2.5 | 79.3299 | 118.99 | 0 | 118.99 | 0.0001 | 0 |  | 99.9999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 95 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 61.03 | 1.5 | 91.55 | 0 | 91.55 | 2.5 | 60 | 90 | 0 | 90 | 1.03 | 1.55 |  | 98.3123 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 02 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 0 | 0 | 0 | 0 | 77.286 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.86 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 584.78 | 1.5 | 877.17 | 0 | 877.17 | 2.5 | 0 | 0 | 0 | 0 | 584.78 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 26 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 117 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 67.27 | 1.5 | 100.91 | 0 | 100.91 | 2.5 | 67.27 | 100.91 | 0 | 100.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.96 wall paint | Primer Water Base- Wall | Sq.Ft | 454.22 | 1.5 | 681.33 | 0 | 681.33 | 2.5 | 452.6667 | 679 | 122.22 | 801.22 | 1.5533 | -119.89 |  | 99.658 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 45 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 89.34 | 1.5 | 134.01 | 0 | 134.01 | 2.5 | 0 | 0 | 0 | 0 | 89.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 71 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 123.78 | 1.5 | 185.67 | 0 | 185.67 | 2.5 | 123.78 | 185.67 | 0 | 185.67 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 55 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 95.47 | 1.5 | 143.21 | 0 | 143.21 | 2.5 | 94 | 141 | 25.38 | 166.38 | 1.47 | -23.18 |  | 98.4602 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.62 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 342.44 | 1.5 | 513.66 | 0 | 513.66 | 2.5 | 0 | 0 | 0 | 0 | 342.44 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 78 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 62.53 | 1.5 | 93.8 | 0 | 93.8 | 2.5 | 62.53 | 93.8 | 0 | 93.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 112 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 78.03 | 117.05 | 0 | 117.05 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 108 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 163.82 | 1.5 | 245.73 | 0 | 245.73 | 2.5 | 163.3333 | 245 | 0 | 245 | 0.4867 | 0.73 |  | 99.7029 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 76 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 49.51 | 1.5 | 74.27 | 0 | 74.27 | 2.5 | 49.3333 | 74 | 0 | 74 | 0.1767 | 0.27 |  | 99.6431 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 69 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 32.58 | 213.57 | 0 | -32.58 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.51 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 419.6 | 1.5 | 629.4 | 0 | 629.4 | 2.5 | 0 | 0 | 0 | 0 | 419.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.83 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 386.23 | 1.5 | 579.35 | 0 | 579.35 | 2.5 | 386 | 579 | 0 | 579 | 0.23 | 0.35 |  | 99.9404 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.2 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 344.529 | 1.5 | 516.79 | 0 | 516.79 | 2.5 | 344 | 516 | 0 | 516 | 0.529 | 0.79 |  | 99.8465 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 63 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 95.3333 | 143 | 25.74 | 168.74 | 1.5367 | -23.44 |  | 98.4136 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 70 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 119.58 | 1.5 | 179.37 | 0 | 179.37 | 2.5 | 0 | 0 | 0 | 0 | 119.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 76 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 49.51 | 1.5 | 74.27 | 0 | 74.27 | 2.5 | 49.3333 | 74 | 0 | 74 | 0.1767 | 0.27 |  | 99.6431 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.51 wall paint | Primer Water Base- Wall | Sq.Ft | 419.6 | 1.5 | 629.4 | 0 | 629.4 | 2.5 | 0 | 0 | 0 | 0 | 419.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 78 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 62.53 | 1.5 | 93.8 | 0 | 93.8 | 2.5 | 62.53 | 93.8 | 0 | 93.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 102 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 56.51 | 1.5 | 84.77 | 0 | 84.77 | 2.5 | 52.6667 | 79 | 14.22 | 93.22 | 3.8433 | -8.46 |  | 93.1989 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.55 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 425.03 | 1.5 | 637.55 | 0 | 637.55 | 2.5 | 0 | 0 | 0 | 0 | 425.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 114 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 165.98 | 1.5 | 248.97 | 0 | 248.97 | 2.5 | 0 | 0 | 0 | 0 | 165.98 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 103 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 52.85 | 1.5 | 79.28 | 0 | 79.28 | 2.5 | 52.6667 | 79 | 0 | 79 | 0.1833 | 0.27 |  | 99.6532 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.59 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 222.31 | 1.5 | 333.47 | 0 | 333.47 | 2.5 | 222.31 | 333.47 | 0 | 333.47 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 95 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 61.03 | 1.5 | 91.55 | 0 | 91.55 | 2.5 | 60 | 90 | 0 | 90 | 1.03 | 1.55 |  | 98.3123 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.9 wall paint | 1st Coat Wall Putty - | Sq.Ft | 422.11 | 1.5 | 633.17 | 0 | 633.17 | 2.5 | 322 | 483 | 0 | 483 | 100.11 | 150.17 |  | 76.2834 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.93 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 505.94 | 1.5 | 758.91 | 0 | 758.91 | 2.5 | 500 | 750 | 0 | 750 | 5.94 | 8.91 |  | 98.8259 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 112 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 78.03 | 117.05 | 0 | 117.05 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.83 wall paint | Primer Water Base- Wall | Sq.Ft | 386.23 | 1.5 | 579.35 | 0 | 579.35 | 2.5 | 386.23 | 579.35 | 0 | 579.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 33 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 0 | 0 | 0 | 0 | 78.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 77 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 70.5 | 1.5 | 105.75 | 0 | 105.75 | 2.5 | 70.5 | 105.75 | 0 | 105.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 58 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 132.93 | 1.5 | 199.4 | 0 | 199.4 | 2.5 | 0 | 0 | 0 | 0 | 132.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 74 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 45.31 | 1.5 | 67.97 | 0 | 67.97 | 2.5 | 45.31 | 67.97 | 0 | 67.97 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 82 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 70.82 | 1.5 | 106.23 | 0 | 106.23 | 2.5 | 70.82 | 106.23 | 0 | 106.23 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 94 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 63.35 | 1.5 | 95.03 | 0 | 95.03 | 2.5 | 0 | 0 | 0 | 0 | 63.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 109 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 175.3333 | 263 | 47.34 | 310.34 | 1.4067 | -45.23 |  | 99.2041 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 49 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 91.49 | 1.5 | 137.24 | 0 | 137.24 | 2.5 | 88 | 132 | 23.76 | 155.76 | 3.49 | -18.53 |  | 96.1854 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.7 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 703.65 | 1.5 | 1055.48 | 0 | 1055.48 | 2.5 | 472.6667 | 709 | 127.62 | 836.62 | 230.9833 | 218.85 |  | 67.1736 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.12 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 485.92 | 1.5 | 728.88 | 0 | 728.88 | 2.5 | 485.92 | 728.88 | 0 | 728.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 66 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 200.74 | 1.5 | 301.11 | 0 | 301.11 | 2.5 | 0 | 0 | 0 | 0 | 200.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.86 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 584.78 | 1.5 | 877.17 | 0 | 877.17 | 2.5 | 0 | 0 | 0 | 0 | 584.78 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 91 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 63.5 | 1.5 | 95.25 | 0 | 95.25 | 2.5 | 61.3333 | 92 | 16.56 | 108.56 | 2.1667 | -13.31 |  | 96.5879 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 48 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.78 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 346.19 | 1.5 | 519.29 | 0 | 519.29 | 2.5 | 346 | 519 | 0 | 519 | 0.19 | 0.29 |  | 99.9451 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 57 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 87.94 | 1.5 | 131.91 | 0 | 131.91 | 2.5 | 87.94 | 131.91 | 0 | 131.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 31 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 55.11 | 1.5 | 82.67 | 0 | 82.67 | 2.5 | 54.6667 | 82 | 0 | 82 | 0.4433 | 0.66 |  | 99.1956 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 61 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 109.47 | 1.5 | 164.21 | 0 | 164.21 | 2.5 | 109.3333 | 164 | 29.52 | 193.52 | 0.1367 | -29.32 |  | 99.8751 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.4 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.111 wall paint | 1st Coat Wall Putty - | Sq.Ft | 358.71 | 1.5 | 538.07 | 0 | 538.07 | 2.5 | 358.71 | 538.07 | 0 | 538.07 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 114 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 165.98 | 1.5 | 248.97 | 0 | 248.97 | 2.5 | 0 | 0 | 0 | 0 | 165.98 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.97 wall paint | Primer Water Base- Wall | Sq.Ft | 450.05 | 1.5 | 675.08 | 0 | 675.08 | 2.5 | 450 | 675 | 0 | 675 | 0.05 | 0.08 |  | 99.9889 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 73 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 189.01 | 1.5 | 283.52 | 0 | 283.52 | 2.5 | 0 | 0 | 0 | 0 | 189.01 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.99 wall paint | 1st Coat Wall Putty - | Sq.Ft | 328.67 | 1.5 | 493.01 | 0 | 493.01 | 2.5 | 328.6667 | 493 | 0 | 493 | 0.0033 | 0 |  | 99.999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 72 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 133.36 | 1.5 | 200.04 | 0 | 200.04 | 2.5 | 0 | 0 | 0 | 0 | 133.36 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 88 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 80.83 | 1.5 | 121.25 | 0 | 121.25 | 2.5 | 80.83 | 121.25 | 0 | 121.25 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 27 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 174.91 | 1.5 | 262.37 | 0 | 262.37 | 2.5 | 0 | 0 | 0 | 0 | 174.91 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.69 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 0 | 0 | 0 | 0 | 568.09 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.47 wall paint | 1st Coat Wall Putty - | Sq.Ft | 436.7 | 1.5 | 655.05 | 0 | 655.05 | 2.5 | 0 | 0 | 0 | 0 | 436.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.44 wall paint | 1st Coat Wall Putty - | Sq.Ft | 435.87 | 1.5 | 653.81 | 0 | 653.81 | 2.5 | 0 | 0 | 0 | 0 | 435.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.35 wall paint | 1st Coat Wall Putty - | Sq.Ft | 561.84 | 1.5 | 842.76 | 0 | 842.76 | 2.5 | 0 | 0 | 0 | 0 | 561.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 21 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 175.13 | 1.5 | 262.7 | 0 | 262.7 | 2.5 | 0 | 0 | 0 | 0 | 175.13 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.73 wall paint | 1st Coat Wall Putty - | Sq.Ft | 811.26 | 1.5 | 1216.89 | 0 | 1216.89 | 2.5 | 0 | 0 | 0 | 0 | 811.26 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 05 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 115.404 | 1.5 | 173.11 | 0 | 173.11 | 2.5 | 0 | 0 | 0 | 0 | 115.404 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.6 wall paint | Primer Water Base- Wall | Sq.Ft | 523.05 | 1.5 | 784.58 | 0 | 784.58 | 2.5 | 0 | 0 | 0 | 0 | 523.05 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 97 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 85.78 | 1.5 | 128.67 | 0 | 128.67 | 2.5 | 85.3333 | 128 | 0 | 128 | 0.4467 | 0.67 |  | 99.4792 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 94 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 63.35 | 1.5 | 95.03 | 0 | 95.03 | 2.5 | 0 | 0 | 0 | 0 | 63.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 06 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 180 | 1.5 | 270 | 0 | 270 | 2.5 | 0 | 0 | 0 | 0 | 180 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 22 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 116 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 66.41 | 1.5 | 99.62 | 0 | 99.62 | 2.5 | 66.41 | 99.62 | 0 | 99.62 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 61 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 109.47 | 1.5 | 164.21 | 0 | 164.21 | 2.5 | 109.3333 | 164 | 29.52 | 193.52 | 0.1367 | -29.32 |  | 99.8751 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 95 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 61.03 | 1.5 | 91.55 | 0 | 91.55 | 2.5 | 60 | 90 | 0 | 90 | 1.03 | 1.55 |  | 98.3123 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.12 wall paint | 1st Coat Wall Putty - | Sq.Ft | 485.92 | 1.5 | 728.88 | 0 | 728.88 | 2.5 | 485.92 | 728.88 | 0 | 728.88 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 40 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 112.48 | 1.5 | 168.72 | 0 | 168.72 | 2.5 | 0 | 0 | 0 | 0 | 112.48 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 08 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 148.866 | 1.5 | 223.3 | 0 | 223.3 | 2.5 | 0 | 0 | 0 | 0 | 148.866 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.91 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 0 | 0 | 0 | 0 | 322 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 92 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 106.6667 | 160 | 28.8 | 188.8 | 4.3033 | -22.35 |  | 96.1221 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.58 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 455.89 | 1.5 | 683.84 | 0 | 683.84 | 2.5 | 455.3333 | 683 | 122.94 | 805.94 | 0.5567 | -122.11 |  | 99.8779 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 03 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 70.504 | 1.5 | 105.76 | 0 | 105.76 | 2.5 | 70 | 105 | 0 | 105 | 0.504 | 0.76 |  | 99.2851 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.74 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 294.05 | 1.5 | 441.08 | 0 | 441.08 | 2.5 | 294.05 | 441.08 | 0 | 441.08 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 21 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 175.13 | 1.5 | 262.7 | 0 | 262.7 | 2.5 | 0 | 0 | 0 | 0 | 175.13 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 49 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 91.49 | 1.5 | 137.24 | 0 | 137.24 | 2.5 | 0 | 0 | 0 | 0 | 91.49 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.70 wall paint | 1st Coat Wall Putty - | Sq.Ft | 573.51 | 1.5 | 860.27 | 0 | 860.27 | 2.5 | 0 | 0 | 0 | 0 | 573.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.82 wall paint | 1st Coat Wall Putty - | Sq.Ft | 354.53 | 1.5 | 531.8 | 0 | 531.8 | 2.5 | 354.5296 | 531.79 | 0 | 531.79 | 0.0004 | 0 |  | 99.9999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 80 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 139.93 | 1.5 | 209.9 | 0 | 209.9 | 2.5 | 0 | 0 | 0 | 0 | 139.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 35 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 220 | 1.5 | 330 | 0 | 330 | 2.5 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 13 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 126.17 | 1.5 | 189.26 | 0 | 189.26 | 2.5 | 126 | 189 | 0 | 189 | 0.17 | 0.26 |  | 99.8653 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.36 wall paint | 1st Coat Wall Putty - | Sq.Ft | 679.88 | 1.5 | 1019.82 | 0 | 1019.82 | 2.5 | 0 | 0 | 0 | 0 | 679.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.94 wall paint | 1st Coat Wall Putty - | Sq.Ft | 335.35 | 1.5 | 503.03 | 0 | 503.03 | 2.5 | 325.3333 | 488 | 87.84 | 575.84 | 10.0167 | -72.82 |  | 97.0131 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.95 wall paint | Primer Water Base- Wall | Sq.Ft | 303.65 | 1.5 | 455.48 | 0 | 455.48 | 2.5 | 299.3333 | 449 | 0 | 449 | 4.3167 | 6.48 |  | 98.5784 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.78 wall paint | Primer Water Base- Wall | Sq.Ft | 346.19 | 1.5 | 519.29 | 0 | 519.29 | 2.5 | 346.19 | 519.29 | 0 | 519.29 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.96 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 454.22 | 1.5 | 681.33 | 0 | 681.33 | 2.5 | 452.6667 | 679 | 122.22 | 801.22 | 1.5533 | -119.89 |  | 99.658 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.38 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 387.07 | 1.5 | 580.61 | 0 | 580.61 | 2.5 | 0 | 0 | 0 | 0 | 387.07 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.15 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 325.59 | 1.5 | 488.39 | 0 | 488.39 | 2.5 | 325.3333 | 488 | 0 | 488 | 0.2567 | 0.39 |  | 99.9212 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 10 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 102.473 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.473 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 35 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 220 | 1.5 | 330 | 0 | 330 | 2.5 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 46 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 74.81 | 1.5 | 112.22 | 0 | 112.22 | 2.5 | 0 | 0 | 0 | 0 | 74.81 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.4 wall paint | 1st Coat Wall Putty - | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.69 wall paint | 1st Coat Wall Putty - | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 456.6667 | 685 | 123.3 | 808.3 | 111.4233 | 43.83 |  | 80.3863 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 01 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 0 | 0 | 0 | 0 | 77.286 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.54 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 432.53 | 1.5 | 648.8 | 0 | 648.8 | 2.5 | 432.36 | 648.54 | 116.74 | 765.28 | 0.17 | -116.49 |  | 99.9607 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 52 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 90.95 | 1.5 | 136.43 | 0 | 136.43 | 2.5 | 0 | 0 | 0 | 0 | 90.95 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 69 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 0 | 0 | 0 | 0 | 120.66 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 33 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 0 | 0 | 0 | 0 | 78.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 98 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 47.68 | 1.5 | 71.52 | 0 | 71.52 | 2.5 | 47.68 | 71.52 | 12.88 | 84.4 | 0 | -12.88 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 64 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 164.15 | 1.5 | 246.23 | 0 | 246.23 | 2.5 | 158.6667 | 238 | 42.84 | 280.84 | 5.4833 | -34.62 |  | 96.6596 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 84 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 90.74 | 1.5 | 136.11 | 0 | 136.11 | 2.5 | 90.74 | 136.11 | 0 | 136.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.15 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 325.59 | 1.5 | 488.39 | 0 | 488.39 | 2.5 | 325.3333 | 488 | 0 | 488 | 0.2567 | 0.39 |  | 99.9212 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.111 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 358.71 | 1.5 | 538.07 | 0 | 538.07 | 2.5 | 358.71 | 538.07 | 0 | 538.07 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 81 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 78.79 | 1.5 | 118.19 | 0 | 118.19 | 2.5 | 78.79 | 118.19 | 0 | 118.19 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 85 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 176.74 | 1.5 | 265.11 | 0 | 265.11 | 2.5 | 0 | 0 | 0 | 0 | 176.74 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.49 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 421.69 | 1.5 | 632.54 | 0 | 632.54 | 2.5 | 0 | 0 | 0 | 0 | 421.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.117 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 208.55 | 1.5 | 312.83 | 0 | 312.83 | 2.5 | 208 | 312 | 0 | 312 | 0.55 | 0.83 |  | 99.7363 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 76 | 2nd coat Premium Emulsion on wall | Sq.Ft | 279.8 | 1.5 | 419.7 | 0 | 419.7 | 2.5 | 279.8 | 419.7 | 0 | 419.7 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 04 ceiling paint - | 1st Coat Ceiling Putty | Sq.Ft | 70.289 | 1.5 | 105.43 | 0 | 105.43 | 2.5 | 0 | 0 | 0 | 0 | 70.289 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 78 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 62.53 | 1.5 | 93.8 | 0 | 93.8 | 2.5 | 62.53 | 93.8 | 0 | 93.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 67 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 38.75 | 1.5 | 58.13 | 0 | 58.13 | 2.5 | 38.6667 | 58 | 0 | 58 | 0.0833 | 0.12 |  | 99.785 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | 2nd floor shops passage ceiling painting - 5434.84 Sq.Ft | Primer Water Base- Ceiling | Sq.Ft | 5434.84 | 1.5 | 8152.26 | 0 | 8152.26 | 2.5 | 0 | 0 | 0 | 0 | 5434.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.6 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 523.05 | 1.5 | 784.58 | 0 | 784.58 | 2.5 | 0 | 0 | 0 | 0 | 523.05 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 42 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 101.28 | 1.5 | 151.92 | 0 | 151.92 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.6133 | 0.92 |  | 99.3945 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.25 wall paint | Primer Water Base- Wall | Sq.Ft | 772.06 | 1.5 | 1158.09 | 0 | 1158.09 | 2.5 | 0 | 0 | 0 | 0 | 772.06 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 111 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 83.95 | 1.5 | 125.93 | 0 | 125.93 | 2.5 | 83.95 | 125.93 | 0 | 125.93 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.21 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 616.89 | 1.5 | 925.34 | 0 | 925.34 | 2.5 | 502 | 753 | 135.54 | 888.54 | 114.89 | 36.8 |  | 81.3759 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.81 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.6667 | 343 | 0 | 343 | 0.3233 | 0.48 |  | 99.8588 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.31 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 291.97 | 1.5 | 437.96 | 0 | 437.96 | 2.5 | 291.3333 | 437 | 0 | 437 | 0.6367 | 0.96 |  | 99.7819 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 101 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 94.6667 | 142 | 25.56 | 167.56 | 2.2033 | -22.26 |  | 97.7255 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 24 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 280.89 | 1.5 | 421.34 | 0 | 421.34 | 2.5 | 0 | 0 | 0 | 0 | 280.89 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.69 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 0 | 0 | 0 | 0 | 568.09 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 50 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 90.41 | 1.5 | 135.62 | 0 | 135.62 | 2.5 | 88 | 132 | 23.76 | 155.76 | 2.41 | -20.15 |  | 97.3344 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 66 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 200.74 | 1.5 | 301.11 | 0 | 301.11 | 2.5 | 194.6667 | 292 | 52.56 | 344.56 | 6.0733 | -43.45 |  | 96.9745 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 82 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 70.82 | 1.5 | 106.23 | 0 | 106.23 | 2.5 | 70.82 | 106.23 | 0 | 106.23 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.47 wall paint | Primer Water Base- Wall | Sq.Ft | 436.7 | 1.5 | 655.05 | 0 | 655.05 | 2.5 | 0 | 0 | 0 | 0 | 436.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 88 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 80.83 | 1.5 | 121.25 | 0 | 121.25 | 2.5 | 80.83 | 121.25 | 0 | 121.25 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.112 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 350.36 | 1.5 | 525.54 | 0 | 525.54 | 2.5 | 350.36 | 525.54 | 0 | 525.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 15 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 102.47 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.47 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.7 wall paint | 1st Coat Wall Putty - | Sq.Ft | 703.65 | 1.5 | 1055.48 | 0 | 1055.48 | 2.5 | 472.6667 | 709 | 127.62 | 836.62 | 230.9833 | 218.85 |  | 67.1736 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 94 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 63.35 | 1.5 | 95.03 | 0 | 95.03 | 2.5 | 59.3333 | 89 | 16.02 | 105.02 | 4.0167 | -10 |  | 93.6595 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.17 wall paint | 1st Coat Wall Putty - | Sq.Ft | 419.7 | 1.5 | 629.55 | 0 | 629.55 | 2.5 | 419.7 | 629.55 | 0 | 629.55 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.37 wall paint | 1st Coat Wall Putty - | Sq.Ft | 562.25 | 1.5 | 843.38 | 0 | 843.38 | 2.5 | 0 | 0 | 0 | 0 | 562.25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.83 wall paint | 1st Coat Wall Putty - | Sq.Ft | 386.23 | 1.5 | 579.35 | 0 | 579.35 | 2.5 | 386.23 | 579.35 | 0 | 579.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 33 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 78.03 | 1.5 | 117.05 | 0 | 117.05 | 2.5 | 0 | 0 | 0 | 0 | 78.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.47 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 436.7 | 1.5 | 655.05 | 0 | 655.05 | 2.5 | 0 | 0 | 0 | 0 | 436.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 67 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 38.75 | 1.5 | 58.13 | 0 | 58.13 | 2.5 | 38.6667 | 58 | 0 | 58 | 0.0833 | 0.12 |  | 99.785 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.35 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 561.84 | 1.5 | 842.76 | 0 | 842.76 | 2.5 | 0 | 0 | 0 | 0 | 561.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 96 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 104.62 | 1.5 | 156.93 | 0 | 156.93 | 2.5 | 103.3333 | 155 | 27.9 | 182.9 | 1.2867 | -25.97 |  | 98.7701 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.45 wall paint | 1st Coat Wall Putty - | Sq.Ft | 417.93 | 1.5 | 626.9 | 0 | 626.9 | 2.5 | 0 | 0 | 0 | 0 | 417.93 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.115 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 540.56 | 1.5 | 810.84 | 0 | 810.84 | 2.5 | 0 | 0 | 0 | 0 | 540.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.105 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 159.75 | 1.5 | 239.63 | 0 | 239.63 | 2.5 | 159.3333 | 239 | 0 | 239 | 0.4167 | 0.63 |  | 99.7392 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.6 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 523.05 | 1.5 | 784.58 | 0 | 784.58 | 2.5 | 0 | 0 | 0 | 0 | 523.05 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 106 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 74.37 | 1.5 | 111.56 | 0 | 111.56 | 2.5 | 74.37 | 111.56 | 0 | 111.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.5 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 63 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.68 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 618.56 | 1.5 | 927.84 | 0 | 927.84 | 2.5 | 0 | 0 | 0 | 0 | 618.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.16 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 423.1 | 1.5 | 634.65 | 0 | 634.65 | 2.5 | 423.1 | 634.65 | 0 | 634.65 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 23 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 264.02 | 1.5 | 396.03 | 0 | 396.03 | 2.5 | 0 | 0 | 0 | 0 | 264.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 39 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 71.04 | 1.5 | 106.56 | 0 | 106.56 | 2.5 | 0 | 0 | 0 | 0 | 71.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 82 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 70.82 | 1.5 | 106.23 | 0 | 106.23 | 2.5 | 70.82 | 106.23 | 0 | 106.23 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 116 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 66.41 | 1.5 | 99.62 | 0 | 99.62 | 2.5 | 66.41 | 99.62 | 0 | 99.62 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.113 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 227.32 | 1.5 | 340.98 | 0 | 340.98 | 2.5 | 227.32 | 340.98 | 0 | 340.98 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 50 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 90.41 | 1.5 | 135.62 | 0 | 135.62 | 2.5 | 0 | 0 | 0 | 0 | 90.41 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.29 wall paint | Primer Water Base- Wall | Sq.Ft | 445.88 | 1.5 | 668.82 | 0 | 668.82 | 2.5 | 0 | 0 | 0 | 0 | 445.88 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 12 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 127.661 | 1.5 | 191.49 | 0 | 191.49 | 2.5 | 127.661 | 191.49 | 0 | 191.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 117 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 67.27 | 1.5 | 100.91 | 0 | 100.91 | 2.5 | 67.27 | 100.91 | 0 | 100.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.72 wall paint | Primer Water Base- Wall | Sq.Ft | 577.69 | 1.5 | 866.54 | 0 | 866.54 | 2.5 | 0 | 0 | 0 | 0 | 577.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.106 wall paint | Primer Water Base- Wall | Sq.Ft | 218.56 | 1.5 | 327.84 | 0 | 327.84 | 2.5 | 218.56 | 327.84 | 0 | 327.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 60 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 82.23 | 1.5 | 123.35 | 0 | 123.35 | 2.5 | 82.23 | 123.35 | 0 | 123.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 76 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 49.51 | 1.5 | 74.27 | 0 | 74.27 | 2.5 | 49.3333 | 74 | 0 | 74 | 0.1767 | 0.27 |  | 99.6431 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.68 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 618.56 | 1.5 | 927.84 | 0 | 927.84 | 2.5 | 0 | 0 | 0 | 0 | 618.56 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.107 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 0 | 483 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.61 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 492.6 | 1.5 | 738.9 | 0 | 738.9 | 2.5 | 0 | 0 | 0 | 0 | 492.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.82 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 354.53 | 1.5 | 531.8 | 0 | 531.8 | 2.5 | 354 | 531 | 0 | 531 | 0.53 | 0.8 |  | 99.8505 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 03 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 70.504 | 1.5 | 105.76 | 0 | 105.76 | 2.5 | 70 | 105 | 0 | 105 | 0.504 | 0.76 |  | 99.2851 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 51 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 89.87 | 1.5 | 134.81 | 0 | 134.81 | 2.5 | 0 | 0 | 0 | 0 | 89.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.57 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 54 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 34 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 181.69 | 1.5 | 272.54 | 0 | 272.54 | 2.5 | 0 | 0 | 0 | 0 | 181.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.3 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 71 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 123.78 | 1.5 | 185.67 | 0 | 185.67 | 2.5 | 123.78 | 185.67 | 0 | 185.67 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.83 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 386.23 | 1.5 | 579.35 | 0 | 579.35 | 2.5 | 386.23 | 579.35 | 0 | 579.35 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 51 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 89.87 | 1.5 | 134.81 | 0 | 134.81 | 2.5 | 0 | 0 | 0 | 0 | 89.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.108 wall paint | 1st Coat Wall Putty - | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 564 | 846 | 152.28 | 998.28 | 4.09 | -146.15 |  | 99.28 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.89 wall paint | 1st Coat Wall Putty - | Sq.Ft | 485.51 | 1.5 | 728.27 | 0 | 728.27 | 2.5 | 329.3333 | 494 | 88.92 | 582.92 | 156.1767 | 145.35 |  | 67.8324 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 52 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 90.95 | 1.5 | 136.43 | 0 | 136.43 | 2.5 | 87.3333 | 131 | 23.58 | 154.58 | 3.6167 | -18.16 |  | 96.0234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 106 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 74.37 | 1.5 | 111.56 | 0 | 111.56 | 2.5 | 74.37 | 111.56 | 0 | 111.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 50 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 90.41 | 1.5 | 135.62 | 0 | 135.62 | 2.5 | 0 | 0 | 0 | 0 | 90.41 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 99 | 1st coat Premium Emulsion on wall | Sq.Ft | 324.74 | 1.5 | 487.11 | 0 | 487.11 | 2.5 | 324.6667 | 487 | 0 | 487 | 0.0733 | 0.11 |  | 99.9774 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 14 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 127.63 | 1.5 | 191.45 | 0 | 191.45 | 2.5 | 127.3333 | 191 | 0 | 191 | 0.2967 | 0.45 |  | 99.7675 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.34 wall paint | Primer Water Base- Wall | Sq.Ft | 780.4 | 1.5 | 1170.6 | 0 | 1170.6 | 2.5 | 0 | 0 | 0 | 0 | 780.4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.49 wall paint | Primer Water Base- Wall | Sq.Ft | 421.69 | 1.5 | 632.54 | 0 | 632.54 | 2.5 | 0 | 0 | 0 | 0 | 421.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 54 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86 | 129 | 23.22 | 152.22 | 0.11 | -23.06 |  | 99.8723 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 70 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 119.58 | 1.5 | 179.37 | 0 | 179.37 | 2.5 | 0 | 0 | 0 | 0 | 119.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 87 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86.11 | 129.17 | 0 | 129.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.65 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 437.12 | 1.5 | 655.68 | 0 | 655.68 | 2.5 | 0 | 0 | 0 | 0 | 437.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 62 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 115.71 | 1.5 | 173.57 | 0 | 173.57 | 2.5 | 0 | 0 | 0 | 0 | 115.71 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 115 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 153.92 | 1.5 | 230.88 | 0 | 230.88 | 2.5 | 0 | 0 | 0 | 0 | 153.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 81 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 78.79 | 1.5 | 118.19 | 0 | 118.19 | 2.5 | 78.79 | 118.19 | 0 | 118.19 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 13 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 126.17 | 1.5 | 189.26 | 0 | 189.26 | 2.5 | 126 | 189 | 0 | 189 | 0.17 | 0.26 |  | 99.8653 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 93 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 110.65 | 1.5 | 165.98 | 0 | 165.98 | 2.5 | 110.59 | 165.89 | 0 | 165.89 | 0.06 | 0.09 |  | 99.9458 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 64 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 164.15 | 1.5 | 246.23 | 0 | 246.23 | 2.5 | 0 | 0 | 0 | 0 | 164.15 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 104 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 56.08 | 1.5 | 84.12 | 0 | 84.12 | 2.5 | 56 | 84 | 15.12 | 99.12 | 0.08 | -15 |  | 99.8573 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.85 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 592.7 | 1.5 | 889.05 | 0 | 889.05 | 2.5 | 0 | 0 | 0 | 0 | 592.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.59 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 222.31 | 1.5 | 333.47 | 0 | 333.47 | 2.5 | 222 | 333 | 0 | 333 | 0.31 | 0.47 |  | 99.8606 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.3 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 16 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 108.46 | 1.5 | 162.69 | 0 | 162.69 | 2.5 | 108.46 | 162.69 | 0 | 162.69 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.42 wall paint | 1st Coat Wall Putty - | Sq.Ft | 269.86 | 1.5 | 404.79 | 0 | 404.79 | 2.5 | 264.6667 | 397 | 0 | 397 | 5.1933 | 7.79 |  | 98.0756 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 61 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 109.47 | 1.5 | 164.21 | 0 | 164.21 | 2.5 | 0 | 0 | 0 | 0 | 109.47 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 105 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 75.13 | 1.5 | 112.7 | 0 | 112.7 | 2.5 | 74 | 111 | 0 | 111 | 1.13 | 1.7 |  | 98.4959 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.70 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 573.51 | 1.5 | 860.27 | 0 | 860.27 | 2.5 | 0 | 0 | 0 | 0 | 573.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.75 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 292.8 | 1.5 | 439.2 | 0 | 439.2 | 2.5 | 292.6667 | 439 | 0 | 439 | 0.1333 | 0.2 |  | 99.9545 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.102 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 296.97 | 1.5 | 445.46 | 0 | 445.46 | 2.5 | 293.3333 | 440 | 79.2 | 519.2 | 3.6367 | -73.75 |  | 98.7754 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.8 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 469.24 | 1.5 | 703.86 | 0 | 703.86 | 2.5 | 340 | 510 | 91.8 | 601.8 | 129.24 | 102.06 |  | 72.4576 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.101 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 446.71 | 1.5 | 670.07 | 0 | 670.07 | 2.5 | 446.6667 | 670 | 120.6 | 790.6 | 0.0433 | -120.54 |  | 99.9903 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 99 | 2nd coat Premium Emulsion on wall | Sq.Ft | 324.74 | 1.5 | 487.11 | 0 | 487.11 | 2.5 | 324.6667 | 487 | 0 | 487 | 0.0733 | 0.11 |  | 99.9774 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.80 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 499.69 | 1.5 | 749.54 | 0 | 749.54 | 2.5 | 0 | 0 | 0 | 0 | 499.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 47 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 102 | 1.5 | 153 | 0 | 153 | 2.5 | 0 | 0 | 0 | 0 | 102 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 52 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 90.95 | 1.5 | 136.43 | 0 | 136.43 | 2.5 | 0 | 0 | 0 | 0 | 90.95 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.7 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 703.65 | 1.5 | 1055.48 | 0 | 1055.48 | 2.5 | 0 | 0 | 0 | 0 | 703.65 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.112 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 350.36 | 1.5 | 525.54 | 0 | 525.54 | 2.5 | 350.36 | 525.54 | 0 | 525.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.93 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 505.94 | 1.5 | 758.91 | 0 | 758.91 | 2.5 | 500 | 750 | 0 | 750 | 5.94 | 8.91 |  | 98.8259 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.99 wall paint | Primer Water Base- Wall | Sq.Ft | 328.67 | 1.5 | 493.01 | 0 | 493.01 | 2.5 | 328.6667 | 493 | 0 | 493 | 0.0033 | 0 |  | 99.999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 12 | 2nd coat Premium Emulsion on wall | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382.4 | 573.6 | 0 | 573.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.106 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 218.56 | 1.5 | 327.84 | 0 | 327.84 | 2.5 | 218 | 327 | 0 | 327 | 0.56 | 0.84 |  | 99.7438 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 09 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 100.85 | 1.5 | 151.28 | 0 | 151.28 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.1833 | 0.27 |  | 99.8182 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 65 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 110.33 | 1.5 | 165.5 | 0 | 165.5 | 2.5 | 0 | 0 | 0 | 0 | 110.33 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 68 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 129.16 | 1.5 | 193.74 | 0 | 193.74 | 2.5 | 0 | 0 | 0 | 0 | 129.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 07 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 79 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 133.79 | 1.5 | 200.69 | 0 | 200.69 | 2.5 | 132 | 198 | 35.64 | 233.64 | 1.79 | -32.96 |  | 98.6621 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 106 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 74.37 | 1.5 | 111.56 | 0 | 111.56 | 2.5 | 74.37 | 111.56 | 0 | 111.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 86 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 166.84 | 1.5 | 250.26 | 0 | 250.26 | 2.5 | 0 | 0 | 0 | 0 | 166.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.77 wall paint | 1st Coat Wall Putty - | Sq.Ft | 214.8 | 1.5 | 322.2 | 0 | 322.2 | 2.5 | 214.8 | 322.2 | 0 | 322.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 106 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 74.37 | 1.5 | 111.56 | 0 | 111.56 | 2.5 | 74 | 111 | 0 | 111 | 0.37 | 0.56 |  | 99.5025 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 55 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 95.47 | 1.5 | 143.21 | 0 | 143.21 | 2.5 | 0 | 0 | 0 | 0 | 95.47 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 111 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 83.95 | 1.5 | 125.93 | 0 | 125.93 | 2.5 | 83.3333 | 125 | 0 | 125 | 0.6167 | 0.93 |  | 99.2654 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 45 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 89.34 | 1.5 | 134.01 | 0 | 134.01 | 2.5 | 0 | 0 | 0 | 0 | 89.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.41 wall paint | 1st Coat Wall Putty - | Sq.Ft | 446.3 | 1.5 | 669.45 | 0 | 669.45 | 2.5 | 439.3333 | 659 | 0 | 659 | 6.9667 | 10.45 |  | 98.439 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 92 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 106.6667 | 160 | 28.8 | 188.8 | 4.3033 | -22.35 |  | 96.1221 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.66 wall paint | Primer Water Base- Wall | Sq.Ft | 687.8 | 1.5 | 1031.7 | 0 | 1031.7 | 2.5 | 0 | 0 | 0 | 0 | 687.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.109 wall paint | Primer Water Base- Wall | Sq.Ft | 578.52 | 1.5 | 867.78 | 0 | 867.78 | 2.5 | 564 | 846 | 152.28 | 998.28 | 14.52 | -130.5 |  | 97.4901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 87 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 86.11 | 129.17 | 0 | 129.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 90 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.107 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 322 | 483 | 0 | 483 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.98 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 298.23 | 1.5 | 447.35 | 0 | 447.35 | 2.5 | 290 | 435 | 78.3 | 513.3 | 8.23 | -65.96 |  | 97.2404 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.28 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 539.31 | 1.5 | 808.97 | 0 | 808.97 | 2.5 | 0 | 0 | 0 | 0 | 539.31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 99 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 67.81 | 1.5 | 101.72 | 0 | 101.72 | 2.5 | 67.3333 | 101 | 0 | 101 | 0.4767 | 0.72 |  | 99.297 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 113 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 79.33 | 1.5 | 119 | 0 | 119 | 2.5 | 79.33 | 119 | 0 | 119 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.103 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 208.13 | 1.5 | 312.2 | 0 | 312.2 | 2.5 | 194 | 291 | 0 | 291 | 14.13 | 21.2 |  | 93.211 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.99 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 328.67 | 1.5 | 493.01 | 0 | 493.01 | 2.5 | 328.6667 | 493 | 0 | 493 | 0.0033 | 0 |  | 99.999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.46 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 403.34 | 1.5 | 605.01 | 0 | 605.01 | 2.5 | 0 | 0 | 0 | 0 | 403.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.57 wall paint | 1st Coat Wall Putty - | Sq.Ft | 245.67 | 1.5 | 368.51 | 0 | 368.51 | 2.5 | 245.67 | 368.51 | 0 | 368.51 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.114 wall paint | 1st Coat Wall Putty - | Sq.Ft | 550.16 | 1.5 | 825.24 | 0 | 825.24 | 2.5 | 0 | 0 | 0 | 0 | 550.16 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 71 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 123.78 | 1.5 | 185.67 | 0 | 185.67 | 2.5 | 123.78 | 185.67 | 0 | 185.67 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 90 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 29 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 99.02 | 1.5 | 148.53 | 0 | 148.53 | 2.5 | 0 | 0 | 0 | 0 | 99.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.53 wall paint | 1st Coat Wall Putty - | Sq.Ft | 443.8 | 1.5 | 665.7 | 0 | 665.7 | 2.5 | 440 | 660 | 118.8 | 778.8 | 3.8 | -113.1 |  | 99.1438 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.63 wall paint | Primer Water Base- Wall | Sq.Ft | 431.7 | 1.5 | 647.55 | 0 | 647.55 | 2.5 | 0 | 0 | 0 | 0 | 431.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.37 wall paint | Primer Water Base- Wall | Sq.Ft | 562.25 | 1.5 | 843.38 | 0 | 843.38 | 2.5 | 0 | 0 | 0 | 0 | 562.25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.71 wall paint | Primer Water Base- Wall | Sq.Ft | 545.99 | 1.5 | 818.99 | 0 | 818.99 | 2.5 | 545.99 | 818.99 | 0 | 818.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.28 wall paint | Primer Water Base- Wall | Sq.Ft | 539.31 | 1.5 | 808.97 | 0 | 808.97 | 2.5 | 0 | 0 | 0 | 0 | 539.31 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 59 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 120.66 | 180.99 | 0 | 180.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | 2nd floor Repaint of wall Shop 75 | 2nd coat Premium Emulsion on wall | Sq.Ft | 183.14 | 1.5 | 274.71 | 0 | 274.71 | 2.5 | 183 | 274.5 | 0 | 274.5 | 0.14 | 0.21 |  | 99.9236 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 48 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 80 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 139.93 | 1.5 | 209.9 | 0 | 209.9 | 2.5 | 121.3333 | 182 | 32.76 | 214.76 | 18.5967 | -4.87 |  | 86.71 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.41 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 446.3 | 1.5 | 669.45 | 0 | 669.45 | 2.5 | 0 | 0 | 0 | 0 | 446.3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 36 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 39 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 71.04 | 1.5 | 106.56 | 0 | 106.56 | 2.5 | 0 | 0 | 0 | 0 | 71.04 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.54 wall paint | 1st Coat Wall Putty - | Sq.Ft | 432.53 | 1.5 | 648.8 | 0 | 648.8 | 2.5 | 432.36 | 648.54 | 116.74 | 765.28 | 0.17 | -116.49 |  | 99.9607 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.71 wall paint | 1st Coat Wall Putty - | Sq.Ft | 545.99 | 1.5 | 818.99 | 0 | 818.99 | 2.5 | 545.99 | 818.99 | 0 | 818.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.47 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 436.7 | 1.5 | 655.05 | 0 | 655.05 | 2.5 | 0 | 0 | 0 | 0 | 436.7 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 34 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 181.69 | 1.5 | 272.54 | 0 | 272.54 | 2.5 | 0 | 0 | 0 | 0 | 181.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 21 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 175.13 | 1.5 | 262.7 | 0 | 262.7 | 2.5 | 0 | 0 | 0 | 0 | 175.13 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.72 wall paint | 1st Coat Wall Putty - | Sq.Ft | 577.69 | 1.5 | 866.54 | 0 | 866.54 | 2.5 | 0 | 0 | 0 | 0 | 577.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 35 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 220 | 1.5 | 330 | 0 | 330 | 2.5 | 0 | 0 | 0 | 0 | 220 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.104 wall paint | Primer Water Base- Wall | Sq.Ft | 285.3 | 1.5 | 427.95 | 0 | 427.95 | 2.5 | 283.3333 | 425 | 76.5 | 501.5 | 1.9667 | -73.55 |  | 99.3107 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 13 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 126.17 | 1.5 | 189.26 | 0 | 189.26 | 2.5 | 126 | 189 | 0 | 189 | 0.17 | 0.26 |  | 99.8653 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.32 wall paint | 1st Coat Wall Putty - | Sq.Ft | 531.8 | 1.5 | 797.7 | 0 | 797.7 | 2.5 | 0 | 0 | 0 | 0 | 531.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 06 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 180 | 1.5 | 270 | 0 | 270 | 2.5 | 0 | 0 | 0 | 0 | 180 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 90 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 22 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 250.16 | 1.5 | 375.24 | 0 | 375.24 | 2.5 | 172.6667 | 259 | 46.62 | 305.62 | 77.4933 | 69.62 |  | 69.0225 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.111 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 358.71 | 1.5 | 538.07 | 0 | 538.07 | 2.5 | 358.6667 | 538 | 0 | 538 | 0.0433 | 0.06 |  | 99.9879 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.25 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 772.06 | 1.5 | 1158.09 | 0 | 1158.09 | 2.5 | 0 | 0 | 0 | 0 | 772.06 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 02 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 76.6667 | 115 | 0 | 115 | 0.6193 | 0.93 |  | 99.1987 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 48 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 96.87 | 1.5 | 145.31 | 0 | 145.31 | 2.5 | 0 | 0 | 0 | 0 | 96.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.94 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 335.35 | 1.5 | 503.03 | 0 | 503.03 | 2.5 | 325.3333 | 488 | 87.84 | 575.84 | 10.0167 | -72.82 |  | 97.0131 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.55 wall paint | 1st Coat Wall Putty - | Sq.Ft | 425.03 | 1.5 | 637.55 | 0 | 637.55 | 2.5 | 420 | 630 | 113.4 | 743.4 | 5.03 | -105.86 |  | 98.8166 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.106 wall paint | 1st Coat Wall Putty - | Sq.Ft | 218.56 | 1.5 | 327.84 | 0 | 327.84 | 2.5 | 218.56 | 327.84 | 0 | 327.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.32 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 531.8 | 1.5 | 797.7 | 0 | 797.7 | 2.5 | 0 | 0 | 0 | 0 | 531.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 69 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 120.66 | 1.5 | 180.99 | 0 | 180.99 | 2.5 | 0 | 0 | 0 | 0 | 120.66 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 62 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 115.71 | 1.5 | 173.57 | 0 | 173.57 | 2.5 | 0 | 0 | 0 | 0 | 115.71 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.64 wall paint | 1st Coat Wall Putty - | Sq.Ft | 490.93 | 1.5 | 736.4 | 0 | 736.4 | 2.5 | 482 | 723 | 130.14 | 853.14 | 8.93 | -116.75 |  | 98.181 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 115 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 153.92 | 1.5 | 230.88 | 0 | 230.88 | 2.5 | 0 | 0 | 0 | 0 | 153.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 75 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 39.18 | 1.5 | 58.77 | 0 | 58.77 | 2.5 | 39.18 | 58.77 | 0 | 58.77 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 82 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 70.82 | 1.5 | 106.23 | 0 | 106.23 | 2.5 | 70.82 | 106.23 | 0 | 106.23 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 102 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 56.51 | 1.5 | 84.77 | 0 | 84.77 | 2.5 | 52.6667 | 79 | 14.22 | 93.22 | 3.8433 | -8.46 |  | 93.1989 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 10 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 102.473 | 1.5 | 153.71 | 0 | 153.71 | 2.5 | 102.473 | 153.71 | 0 | 153.71 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.65 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 437.12 | 1.5 | 655.68 | 0 | 655.68 | 2.5 | 0 | 0 | 0 | 0 | 437.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 01 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 77.286 | 1.5 | 115.93 | 0 | 115.93 | 2.5 | 77 | 115.5 | 20.8 | 136.3 | 0.286 | -20.37 |  | 99.6299 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.20 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 615.23 | 1.5 | 922.85 | 0 | 922.85 | 2.5 | 498 | 747 | 134.46 | 881.46 | 117.23 | 41.39 |  | 80.9453 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.109 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 578.52 | 1.5 | 867.78 | 0 | 867.78 | 2.5 | 564 | 846 | 152.28 | 998.28 | 14.52 | -130.5 |  | 97.4901 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 37 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 126.69 | 1.5 | 190.04 | 0 | 190.04 | 2.5 | 0 | 0 | 0 | 0 | 126.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 60 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 82.23 | 1.5 | 123.35 | 0 | 123.35 | 2.5 | 82 | 123 | 0 | 123 | 0.23 | 0.35 |  | 99.7203 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.40 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 554.75 | 1.5 | 832.13 | 0 | 832.13 | 2.5 | 0 | 0 | 0 | 0 | 554.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 1 | 01 Apr 2023 | AZAM KHAN | Shop 17 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 109.72 | 1.5 | 164.58 | 0 | 164.58 | 2.5 | 109.72 | 164.58 | 0 | 164.58 | 0 | 0 |  | 100 |  | ABHISHEK BANKAR | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 46 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 74.81 | 1.5 | 112.22 | 0 | 112.22 | 2.5 | 0 | 0 | 0 | 0 | 74.81 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.17 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 419.7 | 1.5 | 629.55 | 0 | 629.55 | 2.5 | 419.7 | 629.55 | 0 | 629.55 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 41 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 113.02 | 1.5 | 169.53 | 0 | 169.53 | 2.5 | 0 | 0 | 0 | 0 | 113.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.103 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 208.13 | 1.5 | 312.2 | 0 | 312.2 | 2.5 | 194 | 291 | 0 | 291 | 14.13 | 21.2 |  | 93.211 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 104 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 56.08 | 1.5 | 84.12 | 0 | 84.12 | 2.5 | 56 | 84 | 15.12 | 99.12 | 0.08 | -15 |  | 99.8573 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 28 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 178.58 | 1.5 | 267.87 | 0 | 267.87 | 2.5 | 0 | 0 | 0 | 0 | 178.58 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 57 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 87.94 | 1.5 | 131.91 | 0 | 131.91 | 2.5 | 87.3333 | 131 | 0 | 131 | 0.6067 | 0.91 |  | 99.3101 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 89 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 0 | 0 | 0 | 0 | 110.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 36 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 130 | 1.5 | 195 | 0 | 195 | 2.5 | 0 | 0 | 0 | 0 | 130 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.27 wall paint | 1st Coat Wall Putty - | Sq.Ft | 537.64 | 1.5 | 806.46 | 0 | 806.46 | 2.5 | 0 | 0 | 0 | 0 | 537.64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.33 wall paint | 1st Coat Wall Putty - | Sq.Ft | 410.43 | 1.5 | 615.65 | 0 | 615.65 | 2.5 | 0 | 0 | 0 | 0 | 410.43 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 86 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 166.84 | 1.5 | 250.26 | 0 | 250.26 | 2.5 | 0 | 0 | 0 | 0 | 166.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.59 wall paint | 1st Coat Wall Putty - | Sq.Ft | 222.31 | 1.5 | 333.47 | 0 | 333.47 | 2.5 | 222.31 | 333.47 | 0 | 333.47 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 07 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 250.707 | 1.5 | 376.06 | 0 | 376.06 | 2.5 | 248.6667 | 373 | 67.14 | 440.14 | 2.0403 | -64.08 |  | 99.1862 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.116 wall paint | Primer Water Base- Wall | Sq.Ft | 311.99 | 1.5 | 467.99 | 0 | 467.99 | 2.5 | 311.99 | 467.99 | 0 | 467.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.3 wall paint | Primer Water Base- Wall | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 04 ceiling paint - | 2nd Coat Ceiling Putty | Sq.Ft | 70.289 | 1.5 | 105.43 | 0 | 105.43 | 2.5 | 70 | 105 | 0 | 105 | 0.289 | 0.43 |  | 99.5888 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 07 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 250.707 | 1.5 | 376.06 | 0 | 376.06 | 2.5 | 248.6667 | 373 | 67.14 | 440.14 | 2.0403 | -64.08 |  | 99.1862 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.53 wall paint | Primer Water Base- Wall | Sq.Ft | 443.8 | 1.5 | 665.7 | 0 | 665.7 | 2.5 | 0 | 0 | 0 | 0 | 443.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 75 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 39.18 | 1.5 | 58.77 | 0 | 58.77 | 2.5 | 39.18 | 58.77 | 0 | 58.77 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 11 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 99.244 | 1.5 | 148.87 | 0 | 148.87 | 2.5 | 99.244 | 148.87 | 0 | 148.87 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.88 wall paint | 1st Coat Wall Putty - | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.38 wall paint | 1st Coat Wall Putty - | Sq.Ft | 387.07 | 1.5 | 580.61 | 0 | 580.61 | 2.5 | 0 | 0 | 0 | 0 | 387.07 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 96 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 104.62 | 1.5 | 156.93 | 0 | 156.93 | 2.5 | 103.3333 | 155 | 27.9 | 182.9 | 1.2867 | -25.97 |  | 98.7701 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 107 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 71.58 | 1.5 | 107.37 | 0 | 107.37 | 2.5 | 71.58 | 107.37 | 0 | 107.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.32 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 531.8 | 1.5 | 797.7 | 0 | 797.7 | 2.5 | 0 | 0 | 0 | 0 | 531.8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.82 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 354.53 | 1.5 | 531.8 | 0 | 531.8 | 2.5 | 354.53 | 531.8 | 0 | 531.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 18 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 116.251 | 1.5 | 174.38 | 0 | 174.38 | 2.5 | 0 | 0 | 0 | 0 | 116.251 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.71 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 545.99 | 1.5 | 818.99 | 0 | 818.99 | 2.5 | 545.99 | 818.99 | 0 | 818.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 99 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 67.81 | 1.5 | 101.72 | 0 | 101.72 | 2.5 | 67.3333 | 101 | 0 | 101 | 0.4767 | 0.72 |  | 99.297 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.8 wall paint | Primer Water Base- Wall | Sq.Ft | 469.24 | 1.5 | 703.86 | 0 | 703.86 | 2.5 | 0 | 0 | 0 | 0 | 469.24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.52 wall paint | 1st Coat Wall Putty - | Sq.Ft | 418.35 | 1.5 | 627.53 | 0 | 627.53 | 2.5 | 417.3333 | 626 | 112.68 | 738.68 | 1.0167 | -111.16 |  | 99.757 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.65 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 437.12 | 1.5 | 655.68 | 0 | 655.68 | 2.5 | 426 | 639 | 115.02 | 754.02 | 11.12 | -98.34 |  | 97.4561 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.31 wall paint | Primer Water Base- Wall | Sq.Ft | 291.97 | 1.5 | 437.96 | 0 | 437.96 | 2.5 | 291.3333 | 437 | 0 | 437 | 0.6367 | 0.96 |  | 99.7819 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.40 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 554.75 | 1.5 | 832.13 | 0 | 832.13 | 2.5 | 0 | 0 | 0 | 0 | 554.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 12 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 127.661 | 1.5 | 191.49 | 0 | 191.49 | 2.5 | 127.3333 | 191 | 0 | 191 | 0.3277 | 0.49 |  | 99.7433 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.52 wall paint | Primer Water Base- Wall | Sq.Ft | 418.35 | 1.5 | 627.53 | 0 | 627.53 | 2.5 | 0 | 0 | 0 | 0 | 418.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.67 wall paint | Primer Water Base- Wall | Sq.Ft | 255.26 | 1.5 | 382.89 | 0 | 382.89 | 2.5 | 190.6667 | 286 | 0 | 286 | 64.5933 | 96.89 |  | 74.6951 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 93 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 110.65 | 1.5 | 165.98 | 0 | 165.98 | 2.5 | 110.59 | 165.89 | 0 | 165.89 | 0.06 | 0.09 |  | 99.9458 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 65 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 110.33 | 1.5 | 165.5 | 0 | 165.5 | 2.5 | 105.3333 | 158 | 28.44 | 186.44 | 4.9967 | -20.95 |  | 95.4711 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 99 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 67.81 | 1.5 | 101.72 | 0 | 101.72 | 2.5 | 67.3333 | 101 | 0 | 101 | 0.4767 | 0.72 |  | 99.297 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.44 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 435.87 | 1.5 | 653.81 | 0 | 653.81 | 2.5 | 0 | 0 | 0 | 0 | 435.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.76 wall paint | 1st Coat Wall Putty - | Sq.Ft | 275.28 | 1.5 | 412.92 | 0 | 412.92 | 2.5 | 274.6667 | 412 | 0 | 412 | 0.6133 | 0.92 |  | 99.7772 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 117 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 67.27 | 1.5 | 100.91 | 0 | 100.91 | 2.5 | 67.27 | 100.91 | 0 | 100.91 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 84 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 90.74 | 1.5 | 136.11 | 0 | 136.11 | 2.5 | 90.6667 | 136 | 0 | 136 | 0.0733 | 0.11 |  | 99.9192 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.14 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 382.4 | 1.5 | 573.6 | 0 | 573.6 | 2.5 | 382.4 | 573.6 | 0 | 573.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.40 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 554.75 | 1.5 | 832.13 | 0 | 832.13 | 2.5 | 0 | 0 | 0 | 0 | 554.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.89 wall paint | 2nd Coat Wall Putty - | Sq.Ft | 485.51 | 1.5 | 728.27 | 0 | 728.27 | 2.5 | 329.3333 | 494 | 88.92 | 582.92 | 156.1767 | 145.35 |  | 67.8324 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 110 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 82.56 | 1.5 | 123.84 | 0 | 123.84 | 2.5 | 82.56 | 123.84 | 0 | 123.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.23 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 724.92 | 1.5 | 1087.38 | 0 | 1087.38 | 2.5 | 0 | 0 | 0 | 0 | 724.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.49 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 421.69 | 1.5 | 632.54 | 0 | 632.54 | 2.5 | 0 | 0 | 0 | 0 | 421.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 81 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 78.79 | 1.5 | 118.19 | 0 | 118.19 | 2.5 | 78.6667 | 118 | 0 | 118 | 0.1233 | 0.18 |  | 99.8435 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.24 wall paint | 1st Coat Wall Putty - | Sq.Ft | 792.5 | 1.5 | 1188.75 | 0 | 1188.75 | 2.5 | 0 | 0 | 0 | 0 | 792.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 71 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 123.78 | 1.5 | 185.67 | 0 | 185.67 | 2.5 | 123.78 | 185.67 | 0 | 185.67 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.70 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 573.51 | 1.5 | 860.27 | 0 | 860.27 | 2.5 | 0 | 0 | 0 | 0 | 573.51 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.8 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 469.24 | 1.5 | 703.86 | 0 | 703.86 | 2.5 | 0 | 0 | 0 | 0 | 469.24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 31 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 55.11 | 1.5 | 82.67 | 0 | 82.67 | 2.5 | 54.6667 | 82 | 0 | 82 | 0.4433 | 0.66 |  | 99.1956 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.76 wall paint | Primer Water Base- Wall | Sq.Ft | 275.28 | 1.5 | 412.92 | 0 | 412.92 | 2.5 | 274.6667 | 412 | 0 | 412 | 0.6133 | 0.92 |  | 99.7772 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 77 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 70.5 | 1.5 | 105.75 | 0 | 105.75 | 2.5 | 70.5 | 105.75 | 0 | 105.75 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 74 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 45.31 | 1.5 | 67.97 | 0 | 67.97 | 2.5 | 45.31 | 67.97 | 0 | 67.97 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 107 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 71.58 | 1.5 | 107.37 | 0 | 107.37 | 2.5 | 71.58 | 107.37 | 0 | 107.37 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 32 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 86.11 | 1.5 | 129.17 | 0 | 129.17 | 2.5 | 0 | 0 | 0 | 0 | 86.11 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 93 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 110.65 | 1.5 | 165.98 | 0 | 165.98 | 2.5 | 110.5 | 165.75 | 0 | 165.75 | 0.15 | 0.23 |  | 99.8644 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 26 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 250 | 1.5 | 375 | 0 | 375 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.4 wall paint | Primer Water Base- Wall | Sq.Ft | 214.809 | 1.5 | 322.21 | 0 | 322.21 | 2.5 | 214 | 321 | 0 | 321 | 0.809 | 1.21 |  | 99.6234 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 66 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 200.74 | 1.5 | 301.11 | 0 | 301.11 | 2.5 | 194.6667 | 292 | 52.56 | 344.56 | 6.0733 | -43.45 |  | 96.9745 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.10 wall paint | 1st Coat Wall Putty - | Sq.Ft | 423.77 | 1.5 | 635.66 | 0 | 635.66 | 2.5 | 423.77 | 635.66 | 0 | 635.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.19 wall paint | 1st Coat Wall Putty - | Sq.Ft | 608.97 | 1.5 | 913.46 | 0 | 913.46 | 2.5 | 0 | 0 | 0 | 0 | 608.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 100 ceiling paint | 2nd coat Premium Emulsion on Ceiling | Sq.Ft | 119.02 | 1.5 | 178.53 | 0 | 178.53 | 2.5 | 118.6667 | 178 | 0 | 178 | 0.3533 | 0.53 |  | 99.7032 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 42 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 101.28 | 1.5 | 151.92 | 0 | 151.92 | 2.5 | 100.6667 | 151 | 0 | 151 | 0.6133 | 0.92 |  | 99.3945 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 102 ceiling paint | Primer Water Base- Ceiling | Sq.Ft | 56.51 | 1.5 | 84.77 | 0 | 84.77 | 2.5 | 52.6667 | 79 | 14.22 | 93.22 | 3.8433 | -8.46 |  | 93.1989 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.18 wall paint | Primer Water Base- Wall | Sq.Ft | 503.86 | 1.5 | 755.79 | 0 | 755.79 | 2.5 | 0 | 0 | 0 | 0 | 503.86 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.90 wall paint | Primer Water Base- Wall | Sq.Ft | 258.18 | 1.5 | 387.27 | 0 | 387.27 | 2.5 | 0 | 0 | 0 | 0 | 258.18 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.20 wall paint | Primer Water Base- Wall | Sq.Ft | 615.23 | 1.5 | 922.85 | 0 | 922.85 | 2.5 | 0 | 0 | 0 | 0 | 615.23 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 25 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 270.02 | 1.5 | 405.03 | 0 | 405.03 | 2.5 | 0 | 0 | 0 | 0 | 270.02 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.104 wall paint | 1st coat Premium Emulsion on wall | Sq.Ft | 285.3 | 1.5 | 427.95 | 0 | 427.95 | 2.5 | 283.3333 | 425 | 76.5 | 501.5 | 1.9667 | -73.55 |  | 99.3107 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 72 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 133.36 | 1.5 | 200.04 | 0 | 200.04 | 2.5 | 0 | 0 | 0 | 0 | 133.36 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 94 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 63.35 | 1.5 | 95.03 | 0 | 95.03 | 2.5 | 59.3333 | 89 | 16.02 | 105.02 | 4.0167 | -10 |  | 93.6595 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.113 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 227.32 | 1.5 | 340.98 | 0 | 340.98 | 2.5 | 226.6667 | 340 | 0 | 340 | 0.6533 | 0.98 |  | 99.7126 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.49 wall paint | 1st Coat Wall Putty - | Sq.Ft | 421.69 | 1.5 | 632.54 | 0 | 632.54 | 2.5 | 421.3333 | 632 | 113.76 | 745.76 | 0.3567 | -113.23 |  | 99.9154 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 111 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 83.95 | 1.5 | 125.93 | 0 | 125.93 | 2.5 | 83.95 | 125.93 | 0 | 125.93 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.94 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 335.35 | 1.5 | 503.03 | 0 | 503.03 | 2.5 | 0 | 0 | 0 | 0 | 335.35 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.8 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 469.24 | 1.5 | 703.86 | 0 | 703.86 | 2.5 | 0 | 0 | 0 | 0 | 469.24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.108 wall paint | 2nd coat Premium Emulsion on wall | Sq.Ft | 568.09 | 1.5 | 852.14 | 0 | 852.14 | 2.5 | 0 | 0 | 0 | 0 | 568.09 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 65 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 110.33 | 1.5 | 165.5 | 0 | 165.5 | 2.5 | 105.3333 | 158 | 28.44 | 186.44 | 4.9967 | -20.95 |  | 95.4711 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | Shop No.15 wall paint | Primer Water Base- Wall | Sq.Ft | 325.59 | 1.5 | 488.39 | 0 | 488.39 | 2.5 | 325.3333 | 488 | 0 | 488 | 0.2567 | 0.39 |  | 99.9212 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.6 wall paint | 1st Coat Wall Putty - | Sq.Ft | 523.05 | 1.5 | 784.58 | 0 | 784.58 | 2.5 | 0 | 0 | 0 | 0 | 523.05 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.95 wall paint | 1st Coat Wall Putty - | Sq.Ft | 303.65 | 1.5 | 455.48 | 0 | 455.48 | 2.5 | 299.3333 | 449 | 80.82 | 529.82 | 4.3167 | -74.35 |  | 98.5784 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.46 wall paint | Primer Water Base- Wall | Sq.Ft | 403.34 | 1.5 | 605.01 | 0 | 605.01 | 2.5 | 0 | 0 | 0 | 0 | 403.34 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.81 wall paint | Primer Water Base- Wall | Sq.Ft | 228.99 | 1.5 | 343.49 | 0 | 343.49 | 2.5 | 228.99 | 343.49 | 0 | 343.49 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 2 | 01 Apr 2023 | AZAM KHAN | KEP-2nd Floor Dept labour for application of antirust paint | Department Labour- BC | No. | 6 | 700 | 4200 | 0 | 4200 | 2.5 | 6 | 4200 | 0 | 4200 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 10 Apr 2023 |  | B.C. RCC Substructure | Approved | abhishek bankar
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 74 ceiling paint | 2nd Coat Ceiling Putty | Sq.Ft | 45.31 | 1.5 | 67.97 | 0 | 67.97 | 2.5 | 45.31 | 67.97 | 0 | 67.97 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 89 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 110.97 | 1.5 | 166.46 | 0 | 166.46 | 2.5 | 0 | 0 | 0 | 0 | 110.97 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.91 wall paint | Primer Water Base- Wall | Sq.Ft | 322 | 1.5 | 483 | 0 | 483 | 2.5 | 0 | 0 | 0 | 0 | 322 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.77 wall paint | Primer Water Base- Wall | Sq.Ft | 214.8 | 1.5 | 322.2 | 0 | 322.2 | 2.5 | 214.8 | 322.2 | 0 | 322.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop No.101 wall paint | Primer Water Base- Wall | Sq.Ft | 446.71 | 1.5 | 670.07 | 0 | 670.07 | 2.5 | 446.6667 | 670 | 120.6 | 790.6 | 0.0433 | -120.54 |  | 99.9903 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 115 ceiling paint | 1st Coat Ceiling Putty | Sq.Ft | 153.92 | 1.5 | 230.88 | 0 | 230.88 | 2.5 | 0 | 0 | 0 | 0 | 153.92 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 262 | 0 | 01 Apr 2023 | AZAM KHAN | Shop 38 ceiling paint | 1st coat Premium Emulsion on Ceiling | Sq.Ft | 85.03 | 1.5 | 127.55 | 0 | 127.55 | 2.5 | 0 | 0 | 0 | 0 | 85.03 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | G.I.Cable tray 450 x 50mm (M) | Mtrs | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 25/6 Earthing Patti (M) | Mtrs | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 2.5 sqmm Cu wire (M) | Mtrs | 900 | 26.64 | 23976 | 4315.68 | 28291.68 | 0 | 0 | 0 | 0 | 0 | 900 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | 6sqmm Cu Wire (M) | Mtrs | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 1st Floor 1st Floor - 1 Shop HT Cable | 5C X 16sqmm 2XWY (M) | Mtrs | 75 | 1643 | 123225 | 22180.5 | 145405.5 | 0 | 0 | 0 | 0 | 0 | 75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 13 Amp International Socket (M) | No. | 0 | 152.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 3 Module Plate (M) | No. | 2 | 108.23 | 216.46 | 38.96 | 255.42 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Blank Plate (M) | No. | 0 | 22.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 20 & 25mm Flexible Pipe (M) | Mtrs | 0 | 8.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 25SQMM 2XWY (M) | Mtrs | 140 | 1723 | 241220 | 43419.6 | 284639.6 | 0 | 0 | 0 | 0 | 0 | 140 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 25/6 Earthing Patti (M) | Mtrs | 100 | 94 | 9400 | 1692 | 11092 | 0 | 87 | 8178 | 1472.04 | 9650.04 | 13 | 1441.96 |  | 87 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops HT Cable | 3C x 2.5 sqmm 2XWY Cable End Termination (M) | No. | 58 | 262 | 15196 | 2735.28 | 17931.28 | 0 | 50 | 13100 | 2358 | 15458 | 8 | 2473.28 |  | 86.2069 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 6 Module Box (M) | No. | 2 | 168.48 | 336.96 | 60.66 | 397.62 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | VTPN DB 6 Way (M) | No. | 0 | 15522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3 Module Box (M) | No. | 50 | 81 | 4050 | 729 | 4779 | 0 | 46 | 3726 | 670.68 | 4396.68 | 4 | 382.32 |  | 92 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 4 Module Plate (M) | No. | 2 | 114.29 | 228.58 | 41.14 | 269.72 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Casing Ptti 38/25 (M) | Mtrs | 800 | 43 | 34400 | 6192 | 40592 | 0 | 797.6 | 34296.8 | 6173.42 | 40470.22 | 2.4 | 121.78 |  | 99.7 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | G.I.Cable tray 300 x 50mm (M) | Mtrs | 40 | 761 | 30440 | 5479.2 | 35919.2 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | SUB I/C-25A DP RCCB 100mA (M) | No. | 0 | 1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 13 Amp International Socket (M) | No. | 50 | 178 | 8900 | 1602 | 10502 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - For 3rd Floor ODU - 63A FP RCBO,300mA-(Job)-(Jo - 1 | IP65 ENCLOSER Box-8 Module (M) | No. | 5 | 1759 | 8795 | 1583.1 | 10378.1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | I/C-25A FP MCB (M) | No. | 1 | 1120 | 1120 | 201.6 | 1321.6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | G.I.Cable tray 450 x 50mm (M) | Mtrs | 60 | 842 | 50520 | 9093.6 | 59613.6 | 0 | 44.8 | 37721.6 | 6789.88 | 44511.48 | 15.2 | 15102.12 |  | 74.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 60 Shops HT Cable | 3C x 6 sqmm 2XWY Cable End Termination (M) | No. | 68 | 352 | 23936 | 4308.48 | 28244.48 | 0 | 68 | 23936 | 4308.48 | 28244.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Holder | No. | 100 | 30 | 3000 | 540 | 3540 | 0 | 59 | 1770 | 318.6 | 2088.6 | 41 | 1451.4 |  | 59 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Fan Regulator (M) | No. | 10 | 398 | 3980 | 716.4 | 4696.4 | 0 | 1 | 398 | 71.64 | 469.64 | 9 | 4226.76 |  | 10 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 8SWG GI Earthing Wire (M) | Mtrs | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 25mm Dia PVC MMS Conduit | Mtrs | 0 | 19.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl 3rd Floor Main Panel-(No-Unit) | Main Panel (M) | No. | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | 6 Way ETPN DB (M) | No. | 0 | 2762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | 40A FP MCB (M) | No. | 0 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Amp Switch (M) | No. | 0 | 55.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3 Module Plate (M) | No. | 50 | 108 | 5400 | 972 | 6372 | 0 | 46 | 4968 | 894.24 | 5862.24 | 4 | 509.76 |  | 92 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Fan Hook (M) | No. | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3C 2.5sqmm Flex. Cable (M) | Mtrs | 200 | 105 | 21000 | 3780 | 24780 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops ACDB Panel | ACDB Panel (M) | No. | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - KIOSK DB | 40A DP RCCB Enclosure Box (M) | No. | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Amp Socket (M) | No. | 0 | 130.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | I/C-25A FP MCB (M) | No. | 0 | 958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | O/G 63A TP MCB (M) | No. | 0 | 1114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops HT Cable | 3C x 2.5 sqmm 2XWY Cable End Termination (M) | No. | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Ceiling Rose (M) | No. | 250 | 12 | 3000 | 540 | 3540 | 0 | 118 | 1416 | 254.88 | 1670.88 | 132 | 1869.12 |  | 47.2 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 1st Floor 1st Floor - 1 Shop HT Cable | 5C x 16 sqmm 2XWY Cable End Termination (M) | No. | 0 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | I/C 25A DP MCB(M) | No. | 0 | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg HT Cable for Society Fire Panel work | 3.5C x 95 sqmm A2XFY Cable End Termination (M) | No. | 6 | 1261 | 7566 | 1361.88 | 8927.88 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg Society Fire panel - 160A ATS Manual Pan | 160A ATS Manual Panel (M) | No. | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work KIOSK Shops | Floor Box - (4X16A socket+4X16A switch) - (M) | No. | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 1 Way (M) - | No. | 0 | 15.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | Earthing Bus Bar Box (M) | No. | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 60 Shops HT Cable | 3C X 6sqmm 2XWY (M) | Mtrs | 7500 | 372 | 2790000 | 502200 | 3292200 | 0 | 4270.9995 | 1588811.81 | 285986.12 | 1874797.93 | 3229.0005 | 1417402.07 |  | 56.9467 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Ceiling Rose (M) | No. | 50 | 11.56 | 578 | 104.04 | 682.04 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 1.5 sqmm Cu wire (M) | Mtrs | 0 | 15.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | 6 Way ETPN DB (M) | No. | 1 | 3231 | 3231 | 581.58 | 3812.58 | 0 | 1 | 3231 | 581.58 | 3812.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Ceiling Rose (M) | No. | 0 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 3 Way (M) | No. | 60 | 21 | 1260 | 226.8 | 1486.8 | 0 | 20 | 420 | 75.6 | 495.6 | 40 | 991.2 |  | 33.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Coupling (M) | No. | 30 | 4.56 | 136.8 | 24.62 | 161.42 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6/16 Amp Multi pin Socket (M) | No. | 0 | 181.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 4 Module Box (M) | No. | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10SQMM 2XWY (M) | Mtrs | 100 | 755 | 75500 | 13590 | 89090 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 4 sqmm Cu wire (M) | Mtrs | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 4 Module Plate (M) | No. | 0 | 97.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | RJ11 Telephone Socket (M) | No. | 0 | 85.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 1st Floor 1st Floor - 1 Shop HT Cable | 5C X 16sqmm 2XWY (M) | Mtrs | 0 | 1404.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | I/C 100A MCCB FP (M) | No. | 1 | 4419 | 4419 | 795.42 | 5214.42 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 8 Module Box (M) | No. | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (M) | No. | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 3 Module Box (M) | No. | 0 | 138.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 03 Jun 2024
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (M) | No. | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (M) | No. | 0 | 2002.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops HT Cable | 3CX2.5sqmm 2XWY (M) | Mtrs | 0 | 163.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | I/C 100A MCCB FP (M) | No. | 0 | 3777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C X 2.5sqmm 2XWY (M) | Mtrs | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | 8 Way SPN DB (M) | No. | 65 | 1299 | 84435 | 15198.3 | 99633.3 | 0 | 59 | 76641 | 13795.38 | 90436.38 | 6 | 9196.92 |  | 90.7692 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 8 Module Plate (M) | No. | 30 | 239 | 7170 | 1290.6 | 8460.6 | 0 | 2 | 478 | 86.04 | 564.04 | 28 | 7896.56 |  | 6.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2.5 sqmm Cu wire (M) | Mtrs | 0 | 25.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Junction Box 4 Way (M) | No. | 30 | 23.12 | 693.6 | 124.84 | 818.44 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | 8 way ETPN DB (M) | No. | 0 | 3313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10 sqmm 2XWY Cable End Termination (M) | No. | 8 | 401 | 3208 | 577.44 | 3785.44 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | G.I.Cable tray 300 x 50mm (M) | Mtrs | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Casing Ptti 38/25 (M) | Mtrs | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Casing Ptti 100/50 (M) | Mtrs | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Module Plate (M) | No. | 0 | 190.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Blank Plate (M) | No. | 2 | 26.84 | 53.68 | 9.66 | 63.34 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Holder | No. | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 4 Way (M) | No. | 0 | 19.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 25SQMM 2XWY (M) | Mtrs | 0 | 1472.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 20 Amp Switch (M) | No. | 0 | 157.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 sqmm Cu Wire (M) | Mtrs | 0 | 58.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | I/C 40A RCCB 100mA (M) | No. | 0 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | 8 Way SPN DB (M) | No. | 0 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops HT Cable | 4C x 6 sqmm 2XWY Cable End Termination (M) | No. | 0 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Amps Two Way Switch (M) | No. | 0 | 89.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2 Module Plate (M) | No. | 0 | 85.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | O/P 16A SP MCB (M) | No. | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | O/P 10 A SP MCB (M) | No. | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | O/G 16A SP MCB (M) | No. | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3 Module Plate (M) | No. | 0 | 92.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Plate (M) | No. | 0 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Fan Regulator (M) | No. | 0 | 340.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - For 3rd Floor ODU - 63A FP RCBO,300mA-(Job)-(Jo - 1 | 63A,4P,300mA,RCBO (M) | No. | 0 | 3411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2 Module Box (M) | No. | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2C x 2.5sqmm Flexi. Speaker Cable (M) | Mtrs | 0 | 65.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops HT Cable | 4C X 6 Sqmm 2XWY (M) | Mtrs | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Junction Box-2 Way (M) | No. | 20 | 18.25 | 365 | 65.7 | 430.7 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | RJ 45 Data Socket (M) | No. | 0 | 309.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | 6 Way ETPN DB (M) | No. | 0 | 2762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 6 Module Plate (M) | No. | 2 | 223.38 | 446.76 | 80.42 | 527.18 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 1.5 sqmm Cu wire (M) | Mtrs | 1800 | 16.12 | 29016 | 5222.88 | 34238.88 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 3 Way (M) | No. | 0 | 17.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg HT Cable for Society Fire Panel work | 3.5C x 95sqmm A2XFY XLPE (M) | Mtrs | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 25 sqmm 2XWY Cable End Termination (M) | No. | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3 Module Box (M) | No. | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - For 3rd Floor ODU - 63A FP RCBO,300mA-(Job)-(Jo - 1 | IP65 ENCLOSER Box-8 Module (M) | No. | 0 | 1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C x 2.5 sqmm 2XWY Cable End Termination (M) | No. | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 8 Module Plate (M) | No. | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | PVC 25mm Bend (M) | No. | 0 | 7.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | O/P 16A SP MCB (M) | No. | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP Point Wiring | 6sqmm Cu Wire (L) | Mtrs | 0 | 58.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 04 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10 sqmm 2XWY Cable End Termination (M) | No. | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - KIOSK DB | 40A DP RCCB (M) | No. | 0 | 1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Coupling (M) | No. | 50 | 5 | 250 | 45 | 295 | 0 | 20 | 100 | 18 | 118 | 30 | 177 |  | 40 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C X 2.5sqmm 2XWY (M) | Mtrs | 0 | 205.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | O/P 10 A SP MCB (M) | No. | 390 | 167 | 65130 | 11723.4 | 76853.4 | 0 | 59 | 9853 | 1773.54 | 11626.54 | 331 | 65226.86 |  | 15.1282 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Module Box (M) | No. | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | O/P 16A SP MCB (M) | No. | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops ACDB Panel | ACDB Panel (M) | No. | 1 | 210600 | 210600 | 37908 | 248508 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2.5 sqmm Cu wire (M) | Mtrs | 6500 | 30 | 195000 | 35100 | 230100 | 0 | 6497.0998 | 194912.99 | 35084.34 | 229997.33 | 2.9002 | 102.67 |  | 99.9554 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 8SWG GI Earthing Wire (M) | Mtrs | 60 | 47 | 2820 | 507.6 | 3327.6 | 0 | 60 | 2820 | 507.6 | 3327.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | O/G 63A TP MCB (M) | No. | 3 | 1304 | 3912 | 704.16 | 4616.16 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg HT Cable for Society Fire Panel work | 3.5C x 95 sqmm A2XFY Cable End Termination (M) | No. | 0 | 1078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (M) | No. | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 04 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | Sub I/C 40A DP RCCB 100mA (M) | No. | 0 | 1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - KIOSK DB | 40A DP RCCB Enclosure Box (M) | No. | 10 | 416 | 4160 | 748.8 | 4908.8 | 0 | 1 | 416 | 74.88 | 490.88 | 9 | 4417.92 |  | 10 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 3 Module Box (M) | No. | 2 | 80.73 | 161.46 | 29.06 | 190.52 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2 Module Plate (M) | No. | 10 | 100 | 1000 | 180 | 1180 | 0 | 10 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Amp Socket (M) | No. | 50 | 153 | 7650 | 1377 | 9027 | 0 | 50 | 7650 | 1377 | 9027 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 8 Module Plate (M) | No. | 2 | 238.96 | 477.92 | 86.02 | 563.94 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | I/C 25A DP MCB(M) | No. | 65 | 500 | 32500 | 5850 | 38350 | 0 | 59 | 29500 | 5310 | 34810 | 6 | 3540 |  | 90.7692 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - For 3rd Floor ODU - 63A FP RCBO,300mA-(Job)-(Jo - 1 | 63A,4P,300mA,RCBO (M) | No. | 5 | 3991 | 19955 | 3591.9 | 23546.9 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | Earthing Bus Bar Box (M) | No. | 3 | 995 | 2985 | 537.3 | 3522.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | 8 way ETPN DB (M) | No. | 1 | 3876 | 3876 | 697.68 | 4573.68 | 0 | 1 | 3876 | 697.68 | 4573.68 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | 40A FP MCB (M) | No. | 1 | 1603 | 1603 | 288.54 | 1891.54 | 0 | 1 | 1603 | 288.54 | 1891.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 4 Way (M) | No. | 50 | 23 | 1150 | 207 | 1357 | 0 | 20 | 460 | 82.8 | 542.8 | 30 | 814.2 |  | 40 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Fan Hook (M) | No. | 50 | 61 | 3050 | 549 | 3599 | 0 | 50 | 3050 | 549 | 3599 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 6 Amp Switch (M) | No. | 8 | 64.94 | 519.52 | 93.52 | 613.04 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | Sub I/C 40A DP RCCB 100mA (M) | No. | 3 | 2325 | 6975 | 1255.5 | 8230.5 | 0 | 3 | 6975 | 1255.5 | 8230.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (M) | No. | 10 | 297 | 2970 | 534.6 | 3504.6 | 0 | 2 | 594 | 106.92 | 700.92 | 8 | 2803.68 |  | 20 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 sqmm Cu Wire (M) | Mtrs | 2500 | 68 | 170000 | 30600 | 200600 | 0 | 1296 | 88128 | 15863.04 | 103991.04 | 1204 | 96608.96 |  | 51.84 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 4 Module Box (M) | No. | 10 | 108 | 1080 | 194.4 | 1274.4 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | O/G 40A TP MCB (M) | No. | 2 | 1304 | 2608 | 469.44 | 3077.44 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6/16 Amp Multi pin Socket (M) | No. | 80 | 212 | 16960 | 3052.8 | 20012.8 | 0 | 80 | 16960 | 3052.8 | 20012.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Amps Two Way Switch (M) | No. | 10 | 105 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | O/P 16A SP MCB (M) | No. | 54 | 167 | 9018 | 1623.24 | 10641.24 | 0 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Junction Box 3 Way (M) | No. | 30 | 20.99 | 629.7 | 113.34 | 743.04 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 8 Module Box (M) | No. | 30 | 198 | 5940 | 1069.2 | 7009.2 | 0 | 2 | 396 | 71.28 | 467.28 | 28 | 6541.92 |  | 6.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | RJ11 Telephone Socket (M) | No. | 10 | 100 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Module Box (M) | No. | 20 | 168 | 3360 | 604.8 | 3964.8 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 25mm Dia PVC MMS Conduit | Mtrs | 1800 | 22 | 39600 | 7128 | 46728 | 0 | 1264.9988 | 27829.97 | 5009.4 | 32839.37 | 535.0012 | 13888.63 |  | 70.2777 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | O/P 16A SP MCB (M) | No. | 12 | 167 | 2004 | 360.72 | 2364.72 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 25 sqmm 2XWY Cable End Termination (M) | No. | 10 | 641 | 6410 | 1153.8 | 7563.8 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Supply of Bend | No. | 25 | 8.52 | 213 | 38.34 | 251.34 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 20 & 25mm Flexible Pipe (M) | Mtrs | 250 | 10 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 1.5 sqmm Cu wire (M) | Mtrs | 8000 | 19 | 152000 | 27360 | 179360 | 0 | 7619.2 | 144764.8 | 26057.66 | 170822.46 | 380.8 | 8537.54 |  | 95.24 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 4 Module Box (M) | No. | 2 | 107.64 | 215.28 | 38.76 | 254.04 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | O/P 16A SP MCB (M) | No. | 18 | 167 | 3006 | 541.08 | 3547.08 | 0 | 18 | 3006 | 541.08 | 3547.08 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 8 Module Box (M) | No. | 2 | 193.73 | 387.46 | 69.74 | 457.2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | PVC Conduit (M) | Mtrs | 200 | 9.73 | 1946 | 350.28 | 2296.28 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | PVC 25mm Bend (M) | No. | 100 | 9 | 900 | 162 | 1062 | 0 | 10 | 90 | 16.2 | 106.2 | 90 | 955.8 |  | 10 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | I/C 40A RCCB 100mA (M) | No. | 3 | 2673 | 8019 | 1443.42 | 9462.42 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg Society Fire panel - 160A ATS Manual Pan | 160A ATS Manual Panel (M) | No. | 1 | 52650 | 52650 | 9477 | 62127 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 1 Way (M) - | No. | 100 | 18 | 1800 | 324 | 2124 | 0 | 60 | 1080 | 194.4 | 1274.4 | 40 | 849.6 |  | 60 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | 25mm Dia PVC MMS Conduit | Mtrs | 400 | 24.72 | 9888 | 1779.84 | 11667.84 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2 Module Box (M) | No. | 10 | 81 | 810 | 145.8 | 955.8 | 0 | 10 | 810 | 145.8 | 955.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | RJ 45 Data Socket (M) | No. | 10 | 362 | 3620 | 651.6 | 4271.6 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops HT Cable | 3CX2.5sqmm 2XWY (M) | Mtrs | 1600 | 192 | 307200 | 55296 | 362496 | 0 | 1451 | 278592 | 50146.56 | 328738.56 | 149 | 33757.44 |  | 90.6875 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Coupling (M) | No. | 0 | 3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | VTPN DB 6 Way (M) | No. | 1 | 18161 | 18161 | 3268.98 | 21429.98 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Casing Ptti 100/50 (M) | Mtrs | 100 | 461 | 46100 | 8298 | 54398 | 0 | 23.5 | 10833.5 | 1950.04 | 12783.54 | 76.5 | 41614.46 |  | 23.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 1 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Junction Box 1 Way (M) - | No. | 10 | 17.95 | 179.5 | 32.32 | 211.82 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C x 2.5 sqmm 2XWY Cable End Termination (M) | No. | 6 | 262 | 1572 | 282.96 | 1854.96 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Plate (M) | No. | 10 | 363 | 3630 | 653.4 | 4283.4 | 0 | 2 | 726 | 130.68 | 856.68 | 8 | 3426.72 |  | 20 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | 6 Way ETPN DB (M) | No. | 3 | 3231 | 9693 | 1744.74 | 11437.74 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 20 Amp Switch (M) | No. | 50 | 184 | 9200 | 1656 | 10856 | 0 | 50 | 9200 | 1656 | 10856 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg HT Cable for Society Fire Panel work | 3.5C x 95sqmm A2XFY XLPE (M) | Mtrs | 100 | 702 | 70200 | 12636 | 82836 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops HT Cable | 4C X 6 Sqmm 2XWY (M) | Mtrs | 230 | 461 | 106030 | 19085.4 | 125115.4 | 0 | 215.5 | 99345.5 | 17882.2 | 117227.7 | 14.5 | 7887.7 |  | 93.6957 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Amp Switch (M) | No. | 80 | 65 | 5200 | 936 | 6136 | 0 | 32 | 2080 | 374.4 | 2454.4 | 48 | 3681.6 |  | 40 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 6 Module Plate (M) | No. | 20 | 223 | 4460 | 802.8 | 5262.8 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2C x 2.5sqmm Flexi. Speaker Cable (M) | Mtrs | 1100 | 77 | 84700 | 15246 | 99946 | 0 | 594.9 | 45807.3 | 8245.32 | 54052.62 | 505.1 | 45893.38 |  | 54.0818 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 4 sqmm Cu wire (M) | Mtrs | 2500 | 46 | 115000 | 20700 | 135700 | 0 | 2500 | 115000 | 20700 | 135700 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 60 Shops HT Cable | 3C X 6sqmm 2XWY (M) | Mtrs | 0 | 317.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl 3rd Floor Main Panel-(No-Unit) | Main Panel (M) | No. | 1 | 292500 | 292500 | 52650 | 345150 | 0 | 1 | 292500 | 52650 | 345150 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 2 Way (M) | No. | 0 | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops HT Cable | 4C x 6 sqmm 2XWY Cable End Termination (M) | No. | 6 | 367 | 2202 | 396.36 | 2598.36 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 1st Floor 1st Floor - 1 Shop HT Cable | 5C x 16 sqmm 2XWY Cable End Termination (M) | No. | 2 | 599 | 1198 | 215.64 | 1413.64 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Junction Box 2 Way (M) | No. | 80 | 18 | 1440 | 259.2 | 1699.2 | 0 | 30 | 540 | 97.2 | 637.2 | 50 | 1062 |  | 37.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 60 Shops HT Cable | 3C x 6 sqmm 2XWY Cable End Termination (M) | No. | 0 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | O/G 16A SP MCB (M) | No. | 3 | 167 | 501 | 90.18 | 591.18 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C X 2.5sqmm 2XWY (M) | Mtrs | 80 | 240 | 19200 | 3456 | 22656 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10SQMM 2XWY (M) | Mtrs | 0 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - KIOSK DB | 40A DP RCCB (M) | No. | 10 | 2325 | 23250 | 4185 | 27435 | 0 | 1 | 2325 | 418.5 | 2743.5 | 9 | 24691.5 |  | 10 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | SUB I/C-25A DP RCCB 100mA (M) | No. | 3 | 2002 | 6006 | 1081.08 | 7087.08 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (M) | No. | 65 | 2343 | 152295 | 27413.1 | 179708.1 | 0 | 59 | 138237 | 24882.66 | 163119.66 | 6 | 16588.44 |  | 90.7692 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Blank Plate (M) | No. | 30 | 27 | 810 | 145.8 | 955.8 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work KIOSK Shops | Floor Box - (4X16A socket+4X16A switch) - (M) | No. | 10 | 6435 | 64350 | 11583 | 75933 | 0 | 10 | 64350 | 11583 | 75933 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 263 | 0 | 04 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 4 Module Plate (M) | No. | 10 | 114 | 1140 | 205.2 | 1345.2 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C X 2.5sqmm 2XWY (L) | Mtrs | 80 | 45 | 3600 | 648 | 4248 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | Removing of 3.5C x 35 Sq.mm Alu. Arm Cable | Mtrs | 70 | 100 | 7000 | 1260 | 8260 | 2.5 | 60 | 6000 | 1080 | 7080 | 10 | 1180 |  | 85.7143 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 60 Shops HT Cable | 3C x 6 sqmm 2XWY Cable End Termination (L) | No. | 68 | 60 | 4080 | 734.4 | 4814.4 | 2.5 | 68 | 4080 | 734.4 | 4814.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | 8 way ETPN DB (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Light Fixtures | LED Downlight surface & Concealed type | No. | 80 | 200 | 16000 | 2880 | 18880 | 2.5 | 46 | 9200 | 1656 | 10856 | 34 | 8024 |  | 57.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 100A,100mA 4P ELCB in metal boards enclosure (L) | No. | 3 | 500 | 1500 | 270 | 1770 | 2.5 | 3 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Fan Points Controlled by Switch | No. | 65 | 350 | 22750 | 4095 | 26845 | 2.5 | 64.9996 | 22749.86 | 4094.98 | 26844.84 | 0.0004 | 0.16 |  | 99.9994 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10 sqmm 2XWY Cable End Termination (L) | No. | 8 | 150 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | Removing of 2R x 6 + 1R x 4 Sq.mm Cu.Wire | Mtrs | 270 | 50 | 13500 | 2430 | 15930 | 2.5 | 270 | 13500 | 2430 | 15930 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | Removing of 3C x 6 Sq.mm Copper Arm Cable | Mtrs | 840 | 70 | 58800 | 10584 | 69384 | 2.5 | 793 | 55510 | 9991.8 | 65501.8 | 47 | 3882.2 |  | 94.4048 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 1st Floor 1st Floor - 1 Shop HT Cable | 5C X 16sqmm 2XWY (L) | Mtrs | 75 | 55 | 4125 | 742.5 | 4867.5 | 2.5 | 0 | 0 | 0 | 0 | 75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 40/6 Earthing Patti (L) | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 25/6 Earthing Patti (L) | Mtrs | 100 | 40 | 4000 | 720 | 4720 | 2.5 | 87 | 3480 | 626.4 | 4106.4 | 13 | 613.6 |  | 87 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Power Point BC | No. | 50 | 300 | 15000 | 2700 | 17700 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Primary Light Pt. (Controlled by Sw. Board) | No. | 100 | 300 | 30000 | 5400 | 35400 | 2.5 | 100 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 2C x 2.5sqmm Flexi. Speaker Cable (L) | Mtrs | 1100 | 20 | 22000 | 3960 | 25960 | 2.5 | 594.8998 | 11898 | 2141.64 | 14039.64 | 505.1002 | 11920.36 |  | 54.0818 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | Removing of 4C x 4 Sq.mm Copper Armored Cable | Mtrs | 100 | 80 | 8000 | 1440 | 9440 | 2.5 | 55 | 4400 | 792 | 5192 | 45 | 4248 |  | 55 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3C 2.5sqmm Flex. Cable (L) | Mtrs | 200 | 22 | 4400 | 792 | 5192 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 4 Core 16 sq.mm Termination Alu. Arm. cable (L) | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | Reinstall 150mm Perforated Cable Tray | Mtrs | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 05 Apr 2023
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - KIOSK DB | 40A DP RCCB (L) | No. | 10 | 150 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 16 Sq.mm Single Copper Flexible Termination Cable (L) | No. | 20 | 50 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | MCCB 200A FP,25kA with busbar (L) | No. | 2 | 2750 | 5500 | 990 | 6490 | 2.5 | 2 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Copper Armoured cable (L) | Mtrs | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | 200 A TP incomer Panel (L) | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops DB & MCB | 6 Way ETPN DB (L) | No. | 3 | 1500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Washing Area Electrical Work | 32 A 5 Pin Socket (L) | No. | 1 | 450 | 450 | 81 | 531 | 2.5 | 1 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 8 SWG GI Wire (L) | No. | 200 | 10 | 2000 | 360 | 2360 | 2.5 | 46 | 460 | 82.8 | 542.8 | 154 | 1817.2 |  | 23 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops HT Cable | 4C X 6 Sqmm 2XWY (L) | Mtrs | 230 | 45 | 10350 | 1863 | 12213 | 2.5 | 215.5 | 9697.5 | 1745.56 | 11443.06 | 14.5 | 769.94 |  | 93.6957 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 25/3 Earthing Patti (L) | Mtrs | 400 | 35 | 14000 | 2520 | 16520 | 2.5 | 158 | 5530 | 995.4 | 6525.4 | 242 | 9994.6 |  | 39.5 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 1st Floor 1st Floor - 1 Shop HT Cable | 5C x 16 sqmm 2XWY Cable End Termination (L) | No. | 2 | 100 | 200 | 36 | 236 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (ACDB) | 6 Way ETPN DB (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Secondary Light Points (Looping) | No. | 350 | 150 | 52500 | 9450 | 61950 | 2.5 | 116 | 17400 | 3132 | 20532 | 234 | 41418 |  | 33.1429 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 25SQMM 2XWY (L) | Mtrs | 140 | 80 | 11200 | 2016 | 13216 | 2.5 | 0 | 0 | 0 | 0 | 140 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 10 Sq.mm Single Copper Flexible Cable (L) | Mtrs | 60 | 40 | 2400 | 432 | 2832 | 2.5 | 52 | 2080 | 374.4 | 2454.4 | 8 | 377.6 |  | 86.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Fresh Air & Exhaust Fan HT Cable | 4C x 2.5 sqmm 2XWY Cable End Termination (L) | No. | 6 | 80 | 480 | 86.4 | 566.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 95 Sq.mm Single Copper Flexible Cable (L) | Mtrs | 8 | 60 | 480 | 86.4 | 566.4 | 2.5 | 8 | 480 | 86.4 | 566.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | Earthing Bus Bar Box (L) | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 10 Sq.mm Single Copper Flexible Termination Cable (L) | No. | 20 | 50 | 1000 | 180 | 1180 | 2.5 | 10 | 500 | 90 | 590 | 10 | 590 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3.5 Core 70 sq.mm Aluminium Armoured cable (L) | Mtrs | 60 | 100 | 6000 | 1080 | 7080 | 2.5 | 60 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | SITC PVC Pipe 25mm (L) | Mtrs | 150 | 25 | 3750 | 675 | 4425 | 2.5 | 150 | 3750 | 675 | 4425 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Power Point BC | No. | 100 | 450 | 45000 | 8100 | 53100 | 2.5 | 27 | 12150 | 2187 | 14337 | 73 | 38763 |  | 27 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for shops 1,2,3,4,5,10,11,12,13,25 | 4 Core 6 sq.mm Termination Copper Arm. cable (L) | No. | 45 | 80 | 3600 | 648 | 4248 | 2.5 | 45 | 3600 | 648 | 4248 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (Main DB) | VTPN DB 6 Way (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Termination Copper Arm. cable (L) | No. | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Power Point BC | No. | 25 | 250 | 6250 | 1125 | 7375 | 2.5 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 3.5 Core 35 sq.mm Aluminium Armoured cable (L) | Mtrs | 260 | 85 | 22100 | 3978 | 26078 | 2.5 | 255 | 21675 | 3901.5 | 25576.5 | 5 | 501.5 |  | 98.0769 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 25/6 Earthing Patti (L) | Mtrs | 200 | 40 | 8000 | 1440 | 9440 | 2.5 | 52 | 2080 | 374.4 | 2454.4 | 148 | 6985.6 |  | 26 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg HT Cable for Society Fire Panel work | 3.5C x 95sqmm A2XFY XLPE (L) | Mtrs | 100 | 140 | 14000 | 2520 | 16520 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - For 3rd Floor ODU - 63A FP RCBO,300mA-(Job)-(Jo - 1 | 63A,4P,300mA,RCBO (L) | No. | 5 | 350 | 1750 | 315 | 2065 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10SQMM 2XWY (L) | Mtrs | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Apr 2023
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg Society Fire panel - 160A ATS Manual Pan | 160A ATS Manual Panel (L) | No. | 1 | 4500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | 3 Phase Meter With MCB (L) | No. | 10 | 1250 | 12500 | 2250 | 14750 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | G.I.Cable tray 450 x 50mm (L) | Mtrs | 60 | 250 | 15000 | 2700 | 17700 | 2.5 | 44.8 | 11200 | 2016 | 13216 | 15.2 | 4484 |  | 74.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Installation Main Cable (L) | No. | 10 | 1200 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl 3rd Floor Main Panel-(No-Unit) | Main Panel (L) | No. | 1 | 14000 | 14000 | 2520 | 16520 | 2.5 | 1 | 14000 | 2520 | 16520 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | 3.5 Core 120 sq.mm Termination Alu. Arm. cable (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | Reinstall 150mm Perforated Cable Tray | Mtrs | 70 | 70 | 4900 | 882 | 5782 | 2.5 | 27 | 1890 | 340.2 | 2230.2 | 43 | 3551.8 |  | 38.5714 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | MCCB 250A FP,25kA with enclosure (L) | No. | 2 | 2750 | 5500 | 990 | 6490 | 2.5 | 2 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Installation Main Cable (L) | No. | 65 | 800 | 52000 | 9360 | 61360 | 2.5 | 0 | 0 | 0 | 0 | 65 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl A Common area Electrical Work | VTPN DB MCCB (L) | No. | 2 | 3000 | 6000 | 1080 | 7080 | 2.5 | 1 | 3000 | 540 | 3540 | 1 | 3540 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 70 Sq.mm Single Copper Flexible Termination Cable (L) | No. | 8 | 85 | 680 | 122.4 | 802.4 | 2.5 | 8 | 680 | 122.4 | 802.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | Starter Panel (L) | No. | 4 | 450 | 1800 | 324 | 2124 | 2.5 | 4 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 2 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Primary Light Pt. (Controlled by Sw. Board) | No. | 10 | 300 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops HT Cable | 3CX2.5sqmm 2XWY (L) | Mtrs | 1600 | 45 | 72000 | 12960 | 84960 | 2.5 | 1451 | 65295 | 11753.1 | 77048.1 | 149 | 7911.9 |  | 90.6875 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 3 Module Plate (L) | No. | 80 | 100 | 8000 | 1440 | 9440 | 2.5 | 24 | 2400 | 432 | 2832 | 56 | 6608 |  | 30 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3 Phase C.T. Meter (L) | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor Earthing patti | 8SWG GI Earthing Wire (L) | Mtrs | 60 | 10 | 600 | 108 | 708 | 2.5 | 60 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | AC Points Controlled by Switch | No. | 65 | 600 | 39000 | 7020 | 46020 | 2.5 | 59 | 35400 | 6372 | 41772 | 6 | 4248 |  | 90.7692 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 2 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | LED Downlight Fitting | No. | 12 | 400 | 4800 | 864 | 5664 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 25 sqmm 2XWY Cable End Termination (L) | No. | 10 | 100 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Maintenance of Bldg HT Cable for Society Fire Panel work | 3.5C x 95 sqmm A2XFY Cable End Termination (L) | No. | 6 | 180 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 63A,100mA 4P ELCB in metal boards enclosure.(L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - Guardian Ofiice (LRPDB) | 8 way ETPN DB (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 16 Sq.mm Single Copper Flexible Cable (L) | Mtrs | 50 | 40 | 2000 | 360 | 2360 | 2.5 | 50 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl HT Cable for ODU | 4C x 10SQMM 2XWY (L) | Mtrs | 100 | 75 | 7500 | 1350 | 8850 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | 150mm Peforated Cable Tray Removal | Mtrs | 70 | 35 | 2450 | 441 | 2891 | 0 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 35 Sq.mm Single Copper Flexible Termination Cable (L) | No. | 8 | 65 | 520 | 93.6 | 613.6 | 2.5 | 8 | 520 | 93.6 | 613.6 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Power Point BC | No. | 100 | 600 | 60000 | 10800 | 70800 | 2.5 | 27 | 16200 | 2916 | 19116 | 73 | 51684 |  | 27 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 4 Core 16 sq.mm Aluminium Armoured cable (L) | Mtrs | 130 | 70 | 9100 | 1638 | 10738 | 2.5 | 130 | 9100 | 1638 | 10738 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 35 Sq.mm Single Copper Flexible Cable (L) | Mtrs | 32 | 60 | 1920 | 345.6 | 2265.6 | 2.5 | 32 | 1920 | 345.6 | 2265.6 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Installation Main Cable (L) | No. | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Apr 2023
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Power Point BC | No. | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 08 Apr 2023
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | 3.5 Core 120 sq.mm Aluminium Armoured cable (L) | Mtrs | 60 | 120 | 7200 | 1296 | 8496 | 2.5 | 60 | 7200 | 1296 | 8496 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work KIOSK Shops | Floor Box - (4X16A socket+4X16A switch) - (L) | No. | 10 | 450 | 4500 | 810 | 5310 | 2.5 | 10 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Light Fixtures | Installation LED Tube | No. | 50 | 200 | 10000 | 1800 | 11800 | 2.5 | 50 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | G.I.Cable tray 300 x 50mm (L) | Mtrs | 40 | 150 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops HT Cable | 3C x 2.5 sqmm 2XWY Cable End Termination (L) | No. | 58 | 60 | 3480 | 626.4 | 4106.4 | 2.5 | 50 | 3000 | 540 | 3540 | 8 | 566.4 |  | 86.2069 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 32 Shops DB & MCB | 8 Way SPN DB (L) | No. | 65 | 1150 | 74750 | 13455 | 88205 | 2.5 | 59 | 67850 | 12213 | 80063 | 6 | 8142 |  | 90.7692 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 27 Shops ACDB Panel | ACDB Panel (L) | No. | 1 | 9000 | 9000 | 1620 | 10620 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 3C 2.5sqmm Flex. Cable (L) | Mtrs | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 08 Apr 2023
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (L) | No. | 65 | 200 | 13000 | 2340 | 15340 | 2.5 | 5 | 1000 | 180 | 1180 | 60 | 14160 |  | 7.6923 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3.5 Core 35 sq.mm Termination Alu. Arm. cable (L) | No. | 6 | 350 | 2100 | 378 | 2478 | 2.5 | 6 | 2100 | 378 | 2478 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 95 Sq.mm Single Copper Flexible Termination Cable (L) | No. | 8 | 100 | 800 | 144 | 944 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | 12 Module Box (L) | No. | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA CHOUGULE | 08 Apr 2023
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | Reinstall 300mm Perforated Cable Tray | Mtrs | 70 | 100 | 7000 | 1260 | 8260 | 2.5 | 31.2 | 3120 | 561.6 | 3681.6 | 38.8 | 4578.4 |  | 44.5714 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 2 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | LED Downlight Fitting | No. | 28 | 400 | 11200 | 2016 | 13216 | 2.5 | 0 | 0 | 0 | 0 | 28 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 3 Core 2.5 sq.mm Copper Flexible Cable (L) | Mtrs | 500 | 45 | 22500 | 4050 | 26550 | 2.5 | 281 | 12645 | 2276.1 | 14921.1 | 219 | 11628.9 |  | 56.2 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 2 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | LED Strip (Normal) (L) | Mtrs | 80 | 90 | 7200 | 1296 | 8496 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Primary Point Controlled by MCB (L) | No. | 200 | 800 | 160000 | 28800 | 188800 | 2.5 | 18 | 14400 | 2592 | 16992 | 182 | 171808 |  | 9 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for shops 1,2,3,4,5,10,11,12,13,25 | 4 Core 6 sq.mm Copper Armoured cable (L) | Mtrs | 1600 | 45 | 72000 | 12960 | 84960 | 2.5 | 1373.12 | 61790.4 | 11122.28 | 72912.68 | 226.88 | 12047.32 |  | 85.82 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd Floor - Cable Tray withour powder coatin | 300mm Perforated Cable Tray Removal | Mtrs | 70 | 50 | 3500 | 630 | 4130 | 0 | 70 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 1 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3.5 Core 70 sq.mm Termination Alu. Arm. cable (L) | No. | 2 | 400 | 800 | 144 | 944 | 2.5 | 2 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work Fexible Cable & Point wiring & Conduiting | Secondary Light Pt. (Controlled by Sw. Board) | No. | 200 | 150 | 30000 | 5400 | 35400 | 2.5 | 25 | 3750 | 675 | 4425 | 175 | 30975 |  | 12.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 3rd floor - 3 Shops HT Cable | 4C x 6 sqmm 2XWY Cable End Termination (L) | No. | 6 | 80 | 480 | 86.4 | 566.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 2 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Third Floor Toilet Block Electrical work | Secondary Light Pt. (Controlled by Sw. Board) | No. | 30 | 150 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 264 | 0 | 05 Apr 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work 2nd floor - 60 Shops HT Cable | 3C X 6sqmm 2XWY (L) | Mtrs | 7500 | 40 | 300000 | 54000 | 354000 | 2.5 | 4270.9995 | 170839.98 | 30751.2 | 201591.18 | 3229.0005 | 152408.82 |  | 56.9467 |  | ADITYA CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 265 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | B.O.C.W. Act Registration &Compliance. | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Cancelled | ADITYA.CHOUGULE | 20 Mar 2024
EAST POINT MARKET | 265 | 0 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | B.O.C.W. Act Registration &Compliance. | No. | 1 | 25200 | 25200 | 4536 | 29736 | 0 | 1 | 25200 | 4536 | 29736 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Approved | Swapnil Erande
EAST POINT MARKET | 265 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | Registration of Company (RC) | No. | 81 | 450 | 36450 | 6561 | 43011 | 0 | 81 | 36450 | 6561 | 43011 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 265 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | Registration of Company (RC) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Cancelled | ADITYA.CHOUGULE | 20 Mar 2024
EAST POINT MARKET | 265 | 0 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | Registration of Company (RC) | No. | 1 | 33950 | 33950 | 6111 | 40061 | 0 | 1 | 33950 | 6111 | 40061 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 265 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | B.O.C.W. Act Registration &Compliance. | No. | 81 | 400 | 32400 | 5832 | 38232 | 0 | 81 | 32400 | 5832 | 38232 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Approved | Swapnil Erande
EAST POINT MARKET | 265 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Consultancy Contract Labour Act Registration | B.O.C.W. Act Registration &Compliance. | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Cancelled | MONALI CHAUDHAR | 20 Mar 2024
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | DUSHANT GORE | 08 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 266 | 1 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 1 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 1 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 1 | 120000 | 120000 | 0 | 120000 | 0 | 1 | 120000 | 0 | 120000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Apr 2023 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 266 | 0 | 08 Apr 2023 | ARUP DEWAN ROY | Site Expenses- | Labour Lumpsum. | Month | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Apr 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S.Channel (L) | Kgs | 46.882 | 25 | 1172.05 | 210.96 | 1383.01 | 2.5 | 46.88 | 1172 | 210.96 | 1382.96 | 0.002 | 0.05 |  | 99.9957 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 85.5294 | 70 | 5987.06 | 1077.68 | 7064.74 | 2.5 | 73.9429 | 5176 | 931.68 | 6107.68 | 11.5865 | 957.06 |  | 86.4532 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 78.402 | 70 | 5488.14 | 987.86 | 6476 | 2.5 | 78.4 | 5488 | 987.84 | 6475.84 | 0.002 | 0.16 |  | 99.9974 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 23 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 130.75 | 3268.75 | 588.38 | 3857.13 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 173.4063 | 70 | 12138.44 | 2184.92 | 14323.36 | 2.5 | 160.6803 | 11247.62 | 2024.58 | 13272.2 | 12.726 | 1051.16 |  | 92.6612 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | M.S.Channel (L) | Kgs | 47.54 | 25 | 1188.5 | 213.94 | 1402.44 | 2.5 | 47.54 | 1188.5 | 213.94 | 1402.44 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | MS Plate (L) | Kgs | 72 | 21 | 1512 | 272.16 | 1784.16 | 2.5 | 72 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S.Channel (L) | Kgs | 48.22 | 25 | 1205.5 | 217 | 1422.5 | 2.5 | 48.2 | 1205 | 216.9 | 1421.9 | 0.02 | 0.6 |  | 99.9585 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | MS Plate (L) | Kgs | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 26 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | MS Channel. (L) | Kgs | 103.35 | 25 | 2583.75 | 465.08 | 3048.83 | 2.5 | 103.35 | 2583.75 | 465.08 | 3048.83 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 25 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 27 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Channel. (L) | Kgs | 101.982 | 25 | 2549.55 | 458.92 | 3008.47 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 6.902 | 203.61 |  | 93.2321 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Second Floor Rolling Shutter for shop - 1 No. | Mechanical Fastner (M+L) - No. | No. | 256 | 45 | 11520 | 2073.6 | 13593.6 | 2.5 | 256 | 11520 | 2073.6 | 13593.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 62.1077 | 70 | 4347.54 | 782.56 | 5130.1 | 2.5 | 62.1015 | 4347.11 | 782.48 | 5129.59 | 0.0062 | 0.51 |  | 99.99 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | MS Channel. (L) | Kgs | 59.859 | 25 | 1496.48 | 269.36 | 1765.84 | 2.5 | 55.8 | 1395 | 251.1 | 1646.1 | 4.059 | 119.74 |  | 93.2191 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | MS Channel. (L) | Kgs | 50.991 | 25 | 1274.78 | 229.46 | 1504.24 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 3.431 | 101.22 |  | 93.2714 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 0 | 0 | 0 | 0 | 36 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 162.85 | 70 | 11399.5 | 2051.92 | 13451.42 | 2.5 | 149.62 | 10473.4 | 1885.22 | 12358.62 | 13.23 | 1092.8 |  | 91.876 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 0 | 0 | 0 | 0 | 2.148 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 15.6 | 25 | 390 | 70.2 | 460.2 | 0 | 15.6 | 390 | 70.2 | 460.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 153.063 | 70 | 10714.41 | 1928.6 | 12643.01 | 2.5 | 138.0934 | 9666.54 | 1739.98 | 11406.52 | 14.9696 | 1236.49 |  | 90.22 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 7 Shop No 10 | MS Plate (L) | Kgs | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S.Channel (L) | Kgs | 48.22 | 25 | 1205.5 | 217 | 1422.5 | 2.5 | 48.2 | 1205 | 216.9 | 1421.9 | 0.02 | 0.6 |  | 99.9585 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S.Channel (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | M.S.Channel (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 48.24 | 1206 | 217.08 | 1423.08 | 48.2 | 1421.9 |  | 50.0207 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | M.S.Channel (L) | Kgs | 47.54 | 25 | 1188.5 | 213.94 | 1402.44 | 2.5 | 47.54 | 1188.5 | 213.94 | 1402.44 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Second Floor Rolling Shutter for shop - 1 No. | Mechanical Fastner (M+L) - No. | No. | 208 | 45 | 9360 | 1684.8 | 11044.8 | 2.5 | 96 | 4320 | 777.6 | 5097.6 | 112 | 5947.2 |  | 46.1538 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 67.4896 | 70 | 4724.27 | 850.36 | 5574.63 | 2.5 | 58.9497 | 4126.48 | 742.76 | 4869.24 | 8.5399 | 705.39 |  | 87.3463 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 56.188 | 70 | 3933.16 | 707.96 | 4641.12 | 2.5 | 55.2429 | 3867 | 696.06 | 4563.06 | 0.9451 | 78.06 |  | 98.318 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | M.S.Channel (L) | Kgs | 104.84 | 25 | 2621 | 471.78 | 3092.78 | 2.5 | 104.84 | 2621 | 471.78 | 3092.78 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 218.077 | 70 | 15265.39 | 2747.78 | 18013.17 | 2.5 | 148.783 | 10414.81 | 1874.66 | 12289.47 | 69.294 | 5723.7 |  | 68.225 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 28 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 80.504 | 70 | 5635.28 | 1014.36 | 6649.64 | 2.5 | 0 | 0 | 0 | 0 | 80.504 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | MS Channel. (L) | Kgs | 129.582 | 25 | 3239.55 | 583.12 | 3822.67 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 34.502 | 1017.81 |  | 73.3744 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 24.12 | 25 | 603 | 108.54 | 711.54 | 2.5 | 0 | 0 | 0 | 0 | 24.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 48.23 | 25 | 1205.75 | 217.04 | 1422.79 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 0.67 | 19.77 |  | 98.6108 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 67.087 | 70 | 4696.09 | 845.3 | 5541.39 | 2.5 | 0 | 0 | 0 | 0 | 67.087 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S.Channel (L) | Kgs | 48.22 | 25 | 1205.5 | 217 | 1422.5 | 2.5 | 48.2 | 1205 | 216.9 | 1421.9 | 0.02 | 0.6 |  | 99.9585 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | M.S.Channel (L) | Kgs | 50.991 | 25 | 1274.78 | 229.46 | 1504.24 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 3.431 | 101.22 |  | 93.2714 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 21.65 | 25 | 541.25 | 97.42 | 638.67 | 2.5 | 21.64 | 541 | 97.38 | 638.38 | 0.01 | 0.29 |  | 99.9538 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 177.808 | 70 | 12446.56 | 2240.38 | 14686.94 | 2.5 | 149.6714 | 10477 | 1885.86 | 12362.86 | 28.1366 | 2324.08 |  | 84.1759 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 130.75 | 3268.75 | 588.38 | 3857.13 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 108 Rolling Shutter - 82.856 Sq.Ft | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S.Channel (L) | Kgs | 54.55 | 25 | 1363.75 | 245.48 | 1609.23 | 2.5 | 54.52 | 1363 | 245.34 | 1608.34 | 0.03 | 0.89 |  | 99.945 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 2.28 | 25 | 57 | 10.26 | 67.26 | 2.5 | 2.28 | 57 | 10.26 | 67.26 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 86.4341 | 70 | 6050.39 | 1089.08 | 7139.47 | 2.5 | 86.4341 | 6050.39 | 1089.08 | 7139.47 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 67.683 | 70 | 4737.81 | 852.8 | 5590.61 | 2.5 | 0 | 0 | 0 | 0 | 67.683 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 85 Rolling Shutter - 86.123 Sq.Ft | Rolling Shutter (L) | Sq.Ft | 86.123 | 70 | 6028.61 | 1085.14 | 7113.75 | 2.5 | 86.123 | 6028.61 | 1085.14 | 7113.75 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 5 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 23 May 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | MS Channel. (L) | Kgs | 95.082 | 25 | 2377.05 | 427.86 | 2804.91 | 2.5 | 0 | 0 | 0 | 0 | 95.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 112 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 74.271 | 70 | 5198.97 | 935.82 | 6134.79 | 2.5 | 73.3523 | 5134.66 | 924.24 | 6058.9 | 0.9187 | 75.89 |  | 98.763 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 29 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 8 | 360 | 64.8 | 424.8 | 8 | 424.8 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 62.9688 | 70 | 4407.82 | 793.4 | 5201.22 | 2.5 | 62.9688 | 4407.82 | 793.4 | 5201.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 21 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 80.206 | 70 | 5614.42 | 1010.6 | 6625.02 | 2.5 | 0 | 0 | 0 | 0 | 80.206 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 72.6 | 70 | 5082 | 914.76 | 5996.76 | 2.5 | 69.72 | 4880.4 | 878.48 | 5758.88 | 2.88 | 237.88 |  | 96.0331 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | MS Plate (L) | Kgs | 54 | 21 | 1134 | 204.12 | 1338.12 | 2.5 | 54 | 1134 | 204.12 | 1338.12 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 55.809 | 25 | 1395.23 | 251.14 | 1646.37 | 2.5 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 77.1 | 70 | 5397 | 971.46 | 6368.46 | 2.5 | 67.32 | 4712.4 | 848.24 | 5560.64 | 9.78 | 807.82 |  | 87.3152 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | MS Channel. (L) | Kgs | 50.991 | 25 | 1274.78 | 229.46 | 1504.24 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 3.431 | 101.22 |  | 93.2714 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 27.95 | 25 | 698.75 | 125.78 | 824.53 | 2.5 | 27.95 | 698.75 | 125.78 | 824.53 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | MS Channel. (L) | Kgs | 68.241 | 25 | 1706.03 | 307.08 | 2013.11 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 20.681 | 610.09 |  | 69.6942 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 47.265 | 25 | 1181.63 | 212.7 | 1394.33 | 2.5 | 47.265 | 1181.63 | 212.7 | 1394.33 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 73.947 | 70 | 5176.29 | 931.74 | 6108.03 | 2.5 | 72.4571 | 5072 | 912.96 | 5984.96 | 1.4899 | 123.07 |  | 97.9852 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 78.14 | 70 | 5469.8 | 984.56 | 6454.36 | 2.5 | 78.14 | 5469.8 | 984.56 | 6454.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 32 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 134.549 | 70 | 9418.43 | 1695.32 | 11113.75 | 2.5 | 134.549 | 9418.43 | 1695.32 | 11113.75 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 24.12 | 25 | 603 | 108.54 | 711.54 | 2.5 | 0 | 0 | 0 | 0 | 24.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 39.98 | 25 | 999.5 | 179.92 | 1179.42 | 0 | 39.98 | 999.5 | 179.92 | 1179.42 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | M.S.Channel (L) | Kgs | 192.88 | 25 | 4822 | 867.96 | 5689.96 | 2.5 | 192.88 | 4822 | 867.96 | 5689.96 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | MS Channel. (L) | Kgs | 190.164 | 25 | 4754.1 | 855.74 | 5609.84 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 95.084 | 2804.98 |  | 49.9989 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | M.S.Channel (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 203.645 | 70 | 14255.15 | 2565.92 | 16821.07 | 2.5 | 0 | 0 | 0 | 0 | 203.645 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | M.S. Angle 50x50x5 (L)- BCo | Kgs | 30.19 | 25 | 754.75 | 135.86 | 890.61 | 2.5 | 30.19 | 754.75 | 135.86 | 890.61 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 20 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 79.013 | 70 | 5530.91 | 995.56 | 6526.47 | 2.5 | 0 | 0 | 0 | 0 | 79.013 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 116.937 | 70 | 8185.59 | 1473.4 | 9658.99 | 2.5 | 0 | 0 | 0 | 0 | 116.937 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 64.105 | 70 | 4487.35 | 807.72 | 5295.07 | 2.5 | 0 | 0 | 0 | 0 | 64.105 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | MS Channel. (L) | Kgs | 152.973 | 25 | 3824.33 | 688.38 | 4512.71 | 2.5 | 142.64 | 3566 | 641.88 | 4207.88 | 10.333 | 304.83 |  | 93.2452 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 59.417 | 70 | 4159.19 | 748.66 | 4907.85 | 2.5 | 59.417 | 4159.19 | 748.66 | 4907.85 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 77.522 | 70 | 5426.54 | 976.78 | 6403.32 | 2.5 | 0 | 0 | 0 | 0 | 77.522 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 144.452 | 70 | 10111.64 | 1820.1 | 11931.74 | 2.5 | 144.452 | 10111.64 | 1820.1 | 11931.74 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 64.701 | 70 | 4529.07 | 815.24 | 5344.31 | 2.5 | 0 | 0 | 0 | 0 | 64.701 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 62.108 | 70 | 4347.56 | 782.56 | 5130.12 | 2.5 | 61.7695 | 4323.87 | 778.3 | 5102.17 | 0.3385 | 27.96 |  | 99.455 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 77.5 | 70 | 5425 | 976.5 | 6401.5 | 2.5 | 77.5 | 5425 | 976.5 | 6401.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 53.371 | 70 | 3735.97 | 672.48 | 4408.45 | 2.5 | 0 | 0 | 0 | 0 | 53.371 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 146.497 | 70 | 10254.79 | 1845.86 | 12100.65 | 2.5 | 0 | 0 | 0 | 0 | 146.497 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | MS Plate (L) | Kgs | 54 | 25 | 1350 | 243 | 1593 | 2.5 | 36 | 900 | 162 | 1062 | 18 | 531 |  | 66.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 58.771 | 70 | 4113.97 | 740.52 | 4854.49 | 2.5 | 58.771 | 4113.97 | 740.52 | 4854.49 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 18 | 378 | 68.04 | 446.04 | 18 | 446.04 |  | 50 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 79.653 | 70 | 5575.71 | 1003.62 | 6579.33 | 2.5 | 64.147 | 4490.29 | 808.26 | 5298.55 | 15.506 | 1280.78 |  | 80.5331 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 149.403 | 70 | 10458.21 | 1882.48 | 12340.69 | 2.5 | 149.403 | 10458.21 | 1882.48 | 12340.69 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S.Channel (L) | Kgs | 93.724 | 25 | 2343.1 | 421.76 | 2764.86 | 2.5 | 93.72 | 2343 | 421.74 | 2764.74 | 0.004 | 0.12 |  | 99.9957 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 37 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 63.211 | 70 | 4424.77 | 796.46 | 5221.23 | 2.5 | 0 | 0 | 0 | 0 | 63.211 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 54.681 | 70 | 3827.67 | 688.98 | 4516.65 | 2.5 | 54.681 | 3827.67 | 688.98 | 4516.65 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 64 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 118.669 | 70 | 8306.83 | 1495.22 | 9802.05 | 2.5 | 0 | 0 | 0 | 0 | 118.669 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 7 | 25 | 175 | 31.5 | 206.5 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 172.33 | 70 | 12063.1 | 2171.36 | 14234.46 | 2.5 | 162.4458 | 11371.21 | 2046.82 | 13418.03 | 9.8842 | 816.43 |  | 94.2644 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | MS Plate (L) | Kgs | 72 | 21 | 1512 | 272.16 | 1784.16 | 2.5 | 72 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 24 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 55.809 | 25 | 1395.23 | 251.14 | 1646.37 | 2.5 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 61.2465 | 70 | 4287.26 | 771.7 | 5058.96 | 2.5 | 61.2465 | 4287.26 | 771.7 | 5058.96 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 80.184 | 70 | 5612.88 | 1010.32 | 6623.2 | 2.5 | 77.8143 | 5447 | 980.46 | 6427.46 | 2.3697 | 195.74 |  | 97.0447 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 111.618 | 25 | 2790.45 | 502.28 | 3292.73 | 2.5 | 111.6 | 2790 | 502.2 | 3292.2 | 0.018 | 0.53 |  | 99.9839 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S.Channel (L) | Kgs | 94.41 | 25 | 2360.25 | 424.84 | 2785.09 | 2.5 | 94.4 | 2360 | 424.8 | 2784.8 | 0.01 | 0.29 |  | 99.9894 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 198.278 | 70 | 13879.46 | 2498.3 | 16377.76 | 2.5 | 0 | 0 | 0 | 0 | 198.278 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 13.99 | 25 | 349.75 | 62.96 | 412.71 | 0 | 13.99 | 349.75 | 62.96 | 412.71 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | MS Channel. (L) | Kgs | 50.991 | 25 | 1274.78 | 229.46 | 1504.24 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 3.431 | 101.22 |  | 93.2714 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | M.S.Channel (L) | Kgs | 101.982 | 25 | 2549.55 | 458.92 | 3008.47 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 54.422 | 1605.45 |  | 46.6357 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | M.S. Angle 50x50x5 (L)- BCo | Kgs | 36.98 | 25 | 924.5 | 166.42 | 1090.92 | 2.5 | 36.98 | 924.5 | 166.42 | 1090.92 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | M.S. Angle 50x50x5 (L)- BCo | Kgs | 18.6 | 25 | 465 | 83.7 | 548.7 | 2.5 | 18.6 | 465 | 83.7 | 548.7 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 73.625 | 70 | 5153.75 | 927.68 | 6081.43 | 2.5 | 73.625 | 5153.75 | 927.68 | 6081.43 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 80.504 | 70 | 5635.28 | 1014.36 | 6649.64 | 2.5 | 0 | 0 | 0 | 0 | 80.504 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | MS Channel. (L) | Kgs | 215.073 | 25 | 5376.83 | 967.82 | 6344.65 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 119.993 | 3539.79 |  | 44.2082 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | M.S.Channel (L) | Kgs | 49.614 | 25 | 1240.35 | 223.26 | 1463.61 | 2.5 | 49.6 | 1240 | 223.2 | 1463.2 | 0.014 | 0.41 |  | 99.9718 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | MS Plate (L) | Kgs | 72 | 25 | 1800 | 324 | 2124 | 2.5 | 72 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 6.06 | 25 | 151.5 | 27.28 | 178.78 | 2.5 | 6.06 | 151.5 | 27.28 | 178.78 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S.Channel (L) | Kgs | 40.542 | 25 | 1013.55 | 182.44 | 1195.99 | 2.5 | 40.542 | 1013.55 | 182.44 | 1195.99 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 34.2 | 25 | 855 | 153.9 | 1008.9 | 0 | 34.2 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 111.618 | 25 | 2790.45 | 502.28 | 3292.73 | 2.5 | 55.8 | 1395 | 251.1 | 1646.1 | 55.818 | 1646.63 |  | 49.9919 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | MS Plate (L) | Kgs | 72 | 21 | 1512 | 272.16 | 1784.16 | 2.5 | 72 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S.Channel (L) | Kgs | 7.589 | 25 | 189.73 | 34.16 | 223.89 | 2.5 | 7.589 | 189.73 | 34.16 | 223.89 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | M.S.Channel (L) | Kgs | 152.973 | 25 | 3824.33 | 688.38 | 4512.71 | 2.5 | 0 | 0 | 0 | 0 | 152.973 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 152.943 | 70 | 10706.01 | 1927.08 | 12633.09 | 2.5 | 137.8 | 9646 | 1736.28 | 11382.28 | 15.143 | 1250.81 |  | 90.0989 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | MS Channel. (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S.Channel (L) | Kgs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 09 Jan 2024
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | MS Channel. (M) | Kgs | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | No category | Cancelled | abhishek bankar | 18 Oct 2023
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 31.02 | 25 | 775.5 | 139.6 | 915.1 | 2.5 | 31.02 | 775.5 | 139.6 | 915.1 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 70.7 | 70 | 4949 | 890.82 | 5839.82 | 2.5 | 70.7 | 4949 | 890.82 | 5839.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | MS Plate (L) | Kgs | 54 | 21 | 1134 | 204.12 | 1338.12 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 32 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | M.S.Channel (L) | Kgs | 55.8 | 25 | 1395 | 251.1 | 1646.1 | 2.5 | 55.8 | 1395 | 251.1 | 1646.1 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | M.S.Channel (L) | Kgs | 47.54 | 25 | 1188.5 | 213.94 | 1402.44 | 2.5 | 47.54 | 1188.5 | 213.94 | 1402.44 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 34 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 59.633 | 70 | 4174.31 | 751.38 | 4925.69 | 2.5 | 0 | 0 | 0 | 0 | 59.633 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | MS Plate (L) | Kgs | 54 | 25 | 1350 | 243 | 1593 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 24 | 504 | 90.72 | 594.72 | 6.32 | 156.6 |  | 79.1557 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 65 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 80.504 | 70 | 5635.28 | 1014.36 | 6649.64 | 2.5 | 0 | 0 | 0 | 0 | 80.504 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 63.509 | 70 | 4445.63 | 800.22 | 5245.85 | 2.5 | 0 | 0 | 0 | 0 | 63.509 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 72.462 | 70 | 5072.34 | 913.02 | 5985.36 | 2.5 | 71.7143 | 5020 | 903.6 | 5923.6 | 0.7477 | 61.76 |  | 98.9681 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 61 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 62.614 | 70 | 4382.98 | 788.94 | 5171.92 | 2.5 | 0 | 0 | 0 | 0 | 62.614 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 45.747 | 70 | 3202.29 | 576.42 | 3778.71 | 2.5 | 45.4368 | 3180.58 | 572.5 | 3753.08 | 0.3102 | 25.63 |  | 99.3219 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 79 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 81.995 | 70 | 5739.65 | 1033.14 | 6772.79 | 2.5 | 0 | 0 | 0 | 0 | 81.995 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 66.192 | 70 | 4633.44 | 834.02 | 5467.46 | 2.5 | 0 | 0 | 0 | 0 | 66.192 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | MS Channel. (L) | Kgs | 144.66 | 25 | 3616.5 | 650.98 | 4267.48 | 2.5 | 144.66 | 3616.5 | 650.98 | 4267.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 183.828 | 70 | 12867.96 | 2316.24 | 15184.2 | 2.5 | 169.8714 | 11891 | 2140.38 | 14031.38 | 13.9566 | 1152.82 |  | 92.4078 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | Anchor Fastner (M+L) | No. | 24 | 45 | 1080 | 194.4 | 1274.4 | 2.5 | 24 | 1080 | 194.4 | 1274.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 137.797 | 70 | 9645.79 | 1736.24 | 11382.03 | 2.5 | 115.5286 | 8087 | 1455.66 | 9542.66 | 22.2684 | 1839.37 |  | 83.8397 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 111 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 60.0625 | 70 | 4204.38 | 756.78 | 4961.16 | 2.5 | 60.0625 | 4204.38 | 756.78 | 4961.16 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 71.261 | 70 | 4988.27 | 897.88 | 5886.15 | 2.5 | 0 | 0 | 0 | 0 | 71.261 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 56.12 | 70 | 3928.4 | 707.12 | 4635.52 | 2.5 | 56.1143 | 3928 | 707.04 | 4635.04 | 0.0057 | 0.48 |  | 99.9898 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 16.8 | 25 | 420 | 75.6 | 495.6 | 0 | 16.8 | 420 | 75.6 | 495.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 73.947 | 70 | 5176.29 | 931.74 | 6108.03 | 2.5 | 56.7286 | 3971 | 714.78 | 4685.78 | 17.2184 | 1422.25 |  | 76.7152 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 81.668 | 70 | 5716.76 | 1029.02 | 6745.78 | 2.5 | 80.7714 | 5654 | 1017.72 | 6671.72 | 0.8966 | 74.06 |  | 98.9021 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 32 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 38.4 | 25 | 960 | 172.8 | 1132.8 | 0 | 38.4 | 960 | 172.8 | 1132.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 27.79 | 25 | 694.75 | 125.06 | 819.81 | 0 | 27.79 | 694.75 | 125.06 | 819.81 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 26.4 | 25 | 660 | 118.8 | 778.8 | 0 | 26.4 | 660 | 118.8 | 778.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 0 | 0 | 0 | 0 | 32 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 164.8 | 70 | 11536 | 2076.48 | 13612.48 | 2.5 | 151.406 | 10598.42 | 1907.72 | 12506.14 | 13.394 | 1106.34 |  | 91.8726 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 111 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 79.868 | 70 | 5590.76 | 1006.34 | 6597.1 | 2.5 | 79.868 | 5590.76 | 1006.34 | 6597.1 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 12 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 77.5 | 70 | 5425 | 976.5 | 6401.5 | 2.5 | 77.5 | 5425 | 976.5 | 6401.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 48.24 | 25 | 1206 | 217.08 | 1423.08 | 2.5 | 0 | 0 | 0 | 0 | 48.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | Anchor Fastner (M+L) | No. | 24 | 45 | 1080 | 194.4 | 1274.4 | 2.5 | 16 | 720 | 129.6 | 849.6 | 8 | 424.8 |  | 66.6667 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 25.03 | 25 | 625.75 | 112.64 | 738.39 | 2.5 | 25.03 | 625.75 | 112.64 | 738.39 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | MS Channel. (L) | Kgs | 95.082 | 25 | 2377.05 | 427.86 | 2804.91 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 0.002 | 0.05 |  | 99.9979 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 35 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 183.37 | 70 | 12835.9 | 2310.46 | 15146.36 | 2.5 | 0 | 0 | 0 | 0 | 183.37 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 77.823 | 70 | 5447.61 | 980.56 | 6428.17 | 2.5 | 77.5109 | 5425.76 | 976.64 | 6402.4 | 0.3121 | 25.77 |  | 99.599 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | MS Plate (L) | Kgs | 72 | 21 | 1512 | 272.16 | 1784.16 | 2.5 | 72 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 31.02 | 25 | 775.5 | 139.6 | 915.1 | 2.5 | 31.02 | 775.5 | 139.6 | 915.1 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 80 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 87.362 | 70 | 6115.34 | 1100.76 | 7216.1 | 2.5 | 0 | 0 | 0 | 0 | 87.362 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | MS Channel. (L) | Kgs | 96.98 | 25 | 2424.5 | 436.42 | 2860.92 | 2.5 | 96.98 | 2424.5 | 436.42 | 2860.92 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | M.S.Channel (L) | Kgs | 50.991 | 25 | 1274.78 | 229.46 | 1504.24 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 3.431 | 101.22 |  | 93.2714 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 22 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 101.972 | 70 | 7138.04 | 1284.84 | 8422.88 | 2.5 | 0 | 0 | 0 | 0 | 101.972 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 79.17 | 1979.25 | 356.26 | 2335.51 | 51.58 | 1521.62 |  | 60.5507 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 93.704 | 25 | 2342.6 | 421.66 | 2764.26 | 2.5 | 47.56 | 1189 | 214.02 | 1403.02 | 46.144 | 1361.24 |  | 50.7556 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | Rolling Shutter (L) | Sq.Ft | 58.801 | 70 | 4116.07 | 740.9 | 4856.97 | 2.5 | 58.8 | 4116 | 740.88 | 4856.88 | 0.001 | 0.09 |  | 99.9983 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 91.84 | 2296 | 413.28 | 2709.28 | 38.91 | 1147.85 |  | 70.2409 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 73.353 | 70 | 5134.71 | 924.24 | 6058.95 | 2.5 | 72.7571 | 5093 | 916.74 | 6009.74 | 0.5959 | 49.21 |  | 99.1876 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 67.167 | 70 | 4701.69 | 846.3 | 5547.99 | 2.5 | 66.67 | 4666.9 | 840.04 | 5506.94 | 0.497 | 41.05 |  | 99.2601 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 36 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | Anchor Fastner (M+L) | No. | 24 | 45 | 1080 | 194.4 | 1274.4 | 2.5 | 24 | 1080 | 194.4 | 1274.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 31.02 | 25 | 775.5 | 139.6 | 915.1 | 2.5 | 31.02 | 775.5 | 139.6 | 915.1 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 32.19 | 25 | 804.75 | 144.86 | 949.61 | 2.5 | 32.19 | 804.75 | 144.86 | 949.61 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | Anchor Fastner (M+L) | No. | 24 | 45 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | MS Channel. (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | MS Channel. (L) | Kgs | 108.882 | 25 | 2722.05 | 489.96 | 3212.01 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 13.802 | 407.15 |  | 87.3239 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 24.61 | 25 | 615.25 | 110.74 | 725.99 | 0 | 24.6 | 615 | 110.7 | 725.7 | 0.01 | 0.29 |  | 99.9594 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 140.556 | 25 | 3513.9 | 632.5 | 4146.4 | 2.5 | 140.55 | 3513.75 | 632.48 | 4146.23 | 0.006 | 0.17 |  | 99.9957 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | MS Channel. (L) | Kgs | 203.964 | 25 | 5099.1 | 917.84 | 6016.94 | 2.5 | 190.16 | 4754 | 855.72 | 5609.72 | 13.804 | 407.22 |  | 93.2321 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | MS Plate (L) | Kgs | 54 | 21 | 1134 | 204.12 | 1338.12 | 2.5 | 54 | 1134 | 204.12 | 1338.12 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 30.32 | 636.72 | 114.6 | 751.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 48.23 | 25 | 1205.75 | 217.04 | 1422.79 | 2.5 | 48.23 | 1205.75 | 217.04 | 1422.79 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 130.75 | 3268.75 | 588.38 | 3857.13 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Channel. (L) | Kgs | 101.982 | 25 | 2549.55 | 458.92 | 3008.47 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 6.902 | 203.61 |  | 93.2321 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | MS Channel. (L) | Kgs | 95.082 | 25 | 2377.05 | 427.86 | 2804.91 | 2.5 | 0 | 0 | 0 | 0 | 95.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | Anchor Fastner (M+L) | No. | 24 | 45 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 72.165 | 70 | 5051.55 | 909.28 | 5960.83 | 2.5 | 71.8714 | 5031 | 905.58 | 5936.58 | 0.2936 | 24.25 |  | 99.5932 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 183.37 | 70 | 12835.9 | 2310.46 | 15146.36 | 2.5 | 0 | 0 | 0 | 0 | 183.37 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | MS Channel. (L) | Kgs | 148.77 | 25 | 3719.25 | 669.46 | 4388.71 | 2.5 | 148.77 | 3719.25 | 669.46 | 4388.71 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | MS Plate (L) | Kgs | 72 | 21 | 1512 | 272.16 | 1784.16 | 2.5 | 36 | 756 | 136.08 | 892.08 | 36 | 892.08 |  | 50 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | MS Plate (L) | Kgs | 54 | 21 | 1134 | 204.12 | 1338.12 | 2.5 | 36 | 756 | 136.08 | 892.08 | 18 | 446.04 |  | 66.6667 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 64.798 | 70 | 4535.86 | 816.46 | 5352.32 | 2.5 | 64.798 | 4535.86 | 816.46 | 5352.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | MS Channel. (L) | Kgs | 95.082 | 25 | 2377.05 | 427.86 | 2804.91 | 2.5 | 0 | 0 | 0 | 0 | 95.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | MS Channel. (L) | Kgs | 95.082 | 25 | 2377.05 | 427.86 | 2804.91 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 0.002 | 0.05 |  | 99.9979 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 140.694 | 25 | 3517.35 | 633.12 | 4150.47 | 2.5 | 140.68 | 3517 | 633.06 | 4150.06 | 0.014 | 0.41 |  | 99.99 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | M.S.Channel (L) | Kgs | 109.1 | 25 | 2727.5 | 490.96 | 3218.46 | 2.5 | 109.1 | 2727.5 | 490.96 | 3218.46 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 8 | 360 | 64.8 | 424.8 | 8 | 424.8 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 68.876 | 70 | 4821.32 | 867.84 | 5689.16 | 2.5 | 0 | 0 | 0 | 0 | 68.876 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 114 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 91.834 | 70 | 6428.38 | 1157.1 | 7585.48 | 2.5 | 0 | 0 | 0 | 0 | 91.834 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 115 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 84.082 | 70 | 5885.74 | 1059.44 | 6945.18 | 2.5 | 0 | 0 | 0 | 0 | 84.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 146.497 | 70 | 10254.79 | 1845.86 | 12100.65 | 2.5 | 146.497 | 10254.79 | 1845.86 | 12100.65 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | MS Plate (L) | Kgs | 36 | 25 | 900 | 162 | 1062 | 2.5 | 18 | 450 | 81 | 531 | 18 | 531 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 24 | 504 | 90.72 | 594.72 | 6.32 | 156.6 |  | 79.1557 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | MS Channel. (L) | Kgs | 206.7 | 25 | 5167.5 | 930.16 | 6097.66 | 2.5 | 206.7 | 5167.5 | 930.16 | 6097.66 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | MS Channel. (L) | Kgs | 59.859 | 25 | 1496.48 | 269.36 | 1765.84 | 2.5 | 55.8 | 1395 | 251.1 | 1646.1 | 4.059 | 119.74 |  | 93.2191 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 12 | 252 | 45.36 | 297.36 | 18.32 | 453.96 |  | 39.5778 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | Anchor Fastner (M+L) | No. | 20 | 45 | 900 | 162 | 1062 | 2.5 | 20 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 77.2848 | 70 | 5409.94 | 973.78 | 6383.72 | 2.5 | 77.2848 | 5409.94 | 973.78 | 6383.72 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 91.469 | 70 | 6402.83 | 1152.5 | 7555.33 | 2.5 | 90.8714 | 6361 | 1144.98 | 7505.98 | 0.5976 | 49.35 |  | 99.3467 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | M.S.Channel (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 0 | 0 | 0 | 0 | 96.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 96.307 | 70 | 6741.49 | 1213.46 | 7954.95 | 2.5 | 0 | 0 | 0 | 0 | 96.307 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | MS Channel. (L) | Kgs | 95.082 | 25 | 2377.05 | 427.86 | 2804.91 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 0.002 | 0.05 |  | 99.9979 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 32 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 5 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 66.98 | 70 | 4688.6 | 843.94 | 5532.54 | 2.5 | 66.98 | 4688.6 | 843.94 | 5532.54 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 91.84 | 2296 | 413.28 | 2709.28 | 38.91 | 1147.85 |  | 70.2409 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 52.48 | 1312 | 236.16 | 1548.16 | 78.27 | 2308.97 |  | 40.1377 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 25.58 | 25 | 639.5 | 115.12 | 754.62 | 2.5 | 25.58 | 639.5 | 115.12 | 754.62 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 111.618 | 25 | 2790.45 | 502.28 | 3292.73 | 2.5 | 111.6 | 2790 | 502.2 | 3292.2 | 0.018 | 0.53 |  | 99.9839 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 39 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 58.738 | 70 | 4111.66 | 740.1 | 4851.76 | 2.5 | 0 | 0 | 0 | 0 | 58.738 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | MS Channel. (L) | Kgs | 101.982 | 25 | 2549.55 | 458.92 | 3008.47 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 6.902 | 203.61 |  | 93.2321 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 112 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 36 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 67.981 | 70 | 4758.67 | 856.56 | 5615.23 | 2.5 | 0 | 0 | 0 | 0 | 67.981 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 92.9 | 2322.5 | 418.06 | 2740.56 | 37.85 | 1116.57 |  | 71.0516 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 69.174 | 70 | 4842.18 | 871.6 | 5713.78 | 2.5 | 0 | 0 | 0 | 0 | 69.174 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 62.9688 | 70 | 4407.82 | 793.4 | 5201.22 | 2.5 | 62.9688 | 4407.82 | 793.4 | 5201.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 55.809 | 25 | 1395.23 | 251.14 | 1646.37 | 2.5 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 87 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 85.25 | 70 | 5967.5 | 1074.16 | 7041.66 | 2.5 | 85.25 | 5967.5 | 1074.16 | 7041.66 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | M.S.Channel (L) | Kgs | 101.982 | 25 | 2549.55 | 458.92 | 3008.47 | 2.5 | 95.08 | 2377 | 427.86 | 2804.86 | 6.902 | 203.61 |  | 93.2321 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 34.2 | 25 | 855 | 153.9 | 1008.9 | 0 | 34.2 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | M.S.Channel (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 7 Shop No 10 | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 192.92 | 25 | 4823 | 868.14 | 5691.14 | 2.5 | 190.16 | 4754 | 855.72 | 5609.72 | 2.76 | 81.42 |  | 98.5694 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 62.9688 | 70 | 4407.82 | 793.4 | 5201.22 | 2.5 | 62.9688 | 4407.82 | 793.4 | 5201.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 2.148 | 25 | 53.7 | 9.66 | 63.36 | 2.5 | 2.148 | 53.7 | 9.66 | 63.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | MS Channel. (L) | Kgs | 47.541 | 25 | 1188.53 | 213.94 | 1402.47 | 2.5 | 47.541 | 1188.53 | 213.94 | 1402.47 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 57.844 | 70 | 4049.08 | 728.84 | 4777.92 | 2.5 | 0 | 0 | 0 | 0 | 57.844 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 63.509 | 70 | 4445.63 | 800.22 | 5245.85 | 2.5 | 0 | 0 | 0 | 0 | 63.509 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 32 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 47.516 | 70 | 3326.12 | 598.7 | 3924.82 | 2.5 | 47.5143 | 3326 | 598.68 | 3924.68 | 0.0017 | 0.14 |  | 99.9964 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | Land Cost | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 67.087 | 70 | 4696.09 | 845.3 | 5541.39 | 2.5 | 0 | 0 | 0 | 0 | 67.087 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | MS Plate (L) | Kgs | 72 | 25 | 1800 | 324 | 2124 | 2.5 | 72 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | Rolling Shutter(L)-LC | Sq.Ft | 77.8229 | 70 | 5447.6 | 980.56 | 6428.16 | 2.5 | 67.7109 | 4739.76 | 853.16 | 5592.92 | 10.112 | 835.24 |  | 87.0064 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | MS Channel. (L) | Kgs | 135.918 | 25 | 3397.95 | 611.64 | 4009.59 | 2.5 | 111.6 | 2790 | 502.2 | 3292.2 | 24.318 | 717.39 |  | 82.1083 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 45.92 | 1148 | 206.64 | 1354.64 | 84.83 | 2502.49 |  | 35.1205 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | M.S.Channel (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 26.02 | 25 | 650.5 | 117.1 | 767.6 | 0 | 26.02 | 650.5 | 117.1 | 767.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 142.837 | 70 | 9998.59 | 1799.74 | 11798.33 | 2.5 | 142.837 | 9998.59 | 1799.74 | 11798.33 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 108 Rolling Shutter - 82.856 Sq.Ft | Rolling Shutter (L) | Sq.Ft | 82.856 | 70 | 5799.92 | 1043.98 | 6843.9 | 2.5 | 82.856 | 5799.92 | 1043.98 | 6843.9 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 69.77 | 70 | 4883.9 | 879.1 | 5763 | 2.5 | 0 | 0 | 0 | 0 | 69.77 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 55.809 | 25 | 1395.23 | 251.14 | 1646.37 | 2.5 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 55.809 | 25 | 1395.23 | 251.14 | 1646.37 | 2.5 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 63.807 | 70 | 4466.49 | 803.96 | 5270.45 | 2.5 | 0 | 0 | 0 | 0 | 63.807 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | MS Channel. (L) | Kgs | 96.44 | 25 | 2411 | 433.98 | 2844.98 | 2.5 | 96.44 | 2411 | 433.98 | 2844.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | Anchor Fastner (M+L) | No. | 32 | 45 | 1440 | 259.2 | 1699.2 | 2.5 | 32 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 179.111 | 70 | 12537.77 | 2256.8 | 14794.57 | 2.5 | 175.5127 | 12285.89 | 2211.46 | 14497.35 | 3.5983 | 297.22 |  | 97.991 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 31.02 | 25 | 775.5 | 139.6 | 915.1 | 2.5 | 31.02 | 775.5 | 139.6 | 915.1 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | MS Angle 50 x 50 x 6mm(L) | Kgs | 1.074 | 25 | 26.85 | 4.84 | 31.69 | 2.5 | 1.074 | 26.85 | 4.84 | 31.69 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | MS Plate (L) | Kgs | 54 | 21 | 1134 | 204.12 | 1338.12 | 2.5 | 36 | 756 | 136.08 | 892.08 | 18 | 446.04 |  | 66.6667 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter work | Fabrication Work (L) - Mkt | Kgs | 130.75 | 25 | 3268.75 | 588.38 | 3857.13 | 2.5 | 130.75 | 3268.75 | 588.38 | 3857.13 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 3.19 | 25 | 79.75 | 14.36 | 94.11 | 2.5 | 3.19 | 79.75 | 14.36 | 94.11 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 34.2 | 25 | 855 | 153.9 | 1008.9 | 0 | 34.2 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 33 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 66.192 | 70 | 4633.44 | 834.02 | 5467.46 | 2.5 | 0 | 0 | 0 | 0 | 66.192 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 0 | 0 | 0 | 0 | 36 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | MS Channel. (L) | Kgs | 245.364 | 25 | 6134.1 | 1104.14 | 7238.24 | 2.5 | 190.16 | 4754 | 855.72 | 5609.72 | 55.204 | 1628.52 |  | 77.5012 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 165.182 | 70 | 11562.74 | 2081.3 | 13644.04 | 2.5 | 0 | 0 | 0 | 0 | 165.182 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | M.S. Angle 75x75x6 (L)- Kgs - Kgs | Kgs | 24.12 | 25 | 603 | 108.54 | 711.54 | 2.5 | 0 | 0 | 0 | 0 | 24.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 36 | 756 | 136.08 | 892.08 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter work | MS Plate (L) | Kgs | 30.32 | 21 | 636.72 | 114.6 | 751.32 | 2.5 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | Anchor Fastner (M+L) | No. | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | Anchor Fastner (M+L) | No. | 8 | 45 | 360 | 64.8 | 424.8 | 2.5 | 8 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 18 | 378 | 68.04 | 446.04 | 18 | 446.04 |  | 50 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 58.142 | 70 | 4069.94 | 732.58 | 4802.52 | 2.5 | 0 | 0 | 0 | 0 | 58.142 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | MS Plate (L) | Kgs | 36 | 21 | 756 | 136.08 | 892.08 | 2.5 | 18 | 378 | 68.04 | 446.04 | 18 | 446.04 |  | 50 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | MS Plate (L) | Kgs | 18 | 21 | 378 | 68.04 | 446.04 | 2.5 | 18 | 378 | 68.04 | 446.04 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 3.19 | 25 | 79.75 | 14.36 | 94.11 | 2.5 | 3.19 | 79.75 | 14.36 | 94.11 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 267 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | MS Plate (L) | Kgs | 18 | 25 | 450 | 81 | 531 | 2.5 | 18 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | Rolling Shutter (L) | Sq.Ft | 55.756 | 70 | 3902.92 | 702.52 | 4605.44 | 2.5 | 0 | 0 | 0 | 0 | 55.756 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 267 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | M.S. Angle 50x50x5 (L)- BCo | Kgs | 15.74 | 25 | 393.5 | 70.84 | 464.34 | 2.5 | 0 | 0 | 0 | 0 | 15.74 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 0 | 0 | 0 | 0 | 96.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 183.37 | 280 | 51343.6 | 9241.84 | 60585.44 | 0 | 0 | 0 | 0 | 0 | 183.37 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 33 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 66.192 | 280 | 18533.76 | 3336.08 | 21869.84 | 0 | 0 | 0 | 0 | 0 | 66.192 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 62.108 | 280 | 17390.24 | 3130.24 | 20520.48 | 0 | 61.7709 | 17295.85 | 3113.26 | 20409.11 | 0.3371 | 111.37 |  | 99.4572 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 37 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 63.211 | 280 | 17699.08 | 3185.84 | 20884.92 | 0 | 0 | 0 | 0 | 0 | 63.211 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | M.S. Angle 50x50x5 (M)- BCo | Kgs | 18.6 | 65 | 1209 | 217.62 | 1426.62 | 0 | 18.6 | 1209 | 217.62 | 1426.62 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 77.2848 | 280 | 21639.74 | 3895.16 | 25534.9 | 0 | 0 | 0 | 0 | 0 | 77.2848 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 0 | 0 | 0 | 0 | 36 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 142.837 | 280 | 39994.36 | 7198.98 | 47193.34 | 0 | 142.837 | 39994.36 | 7198.98 | 47193.34 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 77.823 | 280 | 21790.44 | 3922.28 | 25712.72 | 0 | 77.5109 | 21703.05 | 3906.54 | 25609.59 | 0.3121 | 103.13 |  | 99.599 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 62.9688 | 280 | 17631.26 | 3173.62 | 20804.88 | 0 | 62.9679 | 17631.01 | 3173.58 | 20804.59 | 0.0009 | 0.29 |  | 99.9986 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | MS Channel. (M) | Kgs | 206.7 | 65 | 13435.5 | 2418.4 | 15853.9 | 0 | 206.7 | 13435.5 | 2418.4 | 15853.9 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 96.4308 | 6268 | 1128.24 | 7396.24 | 0.0092 | 0.7 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 111 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | MS Channel. (M) | Kgs | 68.241 | 65 | 4435.67 | 798.42 | 5234.09 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 20.7025 | 1587.88 |  | 69.6627 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 77.522 | 280 | 21706.16 | 3907.1 | 25613.26 | 0 | 0 | 0 | 0 | 0 | 77.522 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 13.99 | 65 | 909.35 | 163.68 | 1073.03 | 0 | 13.9846 | 909 | 163.62 | 1072.62 | 0.0054 | 0.41 |  | 99.9614 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 64.701 | 280 | 18116.28 | 3260.94 | 21377.22 | 0 | 0 | 0 | 0 | 0 | 64.701 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 77.5 | 280 | 21700 | 3906 | 25606 | 0 | 77.5 | 21700 | 3906 | 25606 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 63.211 | 280 | 17699.08 | 3185.84 | 20884.92 | 0 | 62.9679 | 17631.01 | 3173.58 | 20804.59 | 0.2431 | 80.33 |  | 99.6154 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 72.7639 | 280 | 20373.89 | 3667.3 | 24041.19 | 0 | 0 | 0 | 0 | 0 | 72.7639 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 47.516 | 280 | 13304.48 | 2394.8 | 15699.28 | 0 | 47.5143 | 13304 | 2394.72 | 15698.72 | 0.0017 | 0.56 |  | 99.9964 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | MS Channel. (M) | Kgs | 101.982 | 65 | 6628.83 | 1193.18 | 7822.01 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 6.9051 | 529.61 |  | 93.2291 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 58.771 | 280 | 16455.88 | 2962.06 | 19417.94 | 0 | 58.771 | 16455.88 | 2962.06 | 19417.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S.Channel (M) | Kgs | 94.41 | 65 | 6136.65 | 1104.6 | 7241.25 | 0 | 94.41 | 6136.65 | 1104.6 | 7241.25 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | M.S.Channel (M) | Kgs | 192.88 | 65 | 12537.2 | 2256.7 | 14793.9 | 0 | 192.8769 | 12537 | 2256.66 | 14793.66 | 0.0031 | 0.24 |  | 99.9984 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | MS Channel. (M) | Kgs | 95.082 | 65 | 6180.33 | 1112.46 | 7292.79 | 0 | 0 | 0 | 0 | 0 | 95.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | MS Channel. (M) | Kgs | 50.991 | 65 | 3314.42 | 596.6 | 3911.02 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 3.4525 | 264.81 |  | 93.2292 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 34.2 | 65 | 2223 | 400.14 | 2623.14 | 0 | 34.2 | 2223 | 400.14 | 2623.14 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 73.05 | 280 | 20454 | 3681.72 | 24135.72 | 0 | 69.7214 | 19521.99 | 3513.96 | 23035.95 | 3.3286 | 1099.77 |  | 95.4434 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 24.12 | 65 | 1567.8 | 282.2 | 1850 | 0 | 0 | 0 | 0 | 0 | 24.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | M.S. Angle 50x50x5 (M)- BCo | Kgs | 30.19 | 65 | 1962.35 | 353.22 | 2315.57 | 0 | 30.1846 | 1962 | 353.16 | 2315.16 | 0.0054 | 0.41 |  | 99.9821 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | M.S.Channel (M) | Kgs | 109.1 | 65 | 7091.5 | 1276.48 | 8367.98 | 0 | 109.0923 | 7091 | 1276.38 | 8367.38 | 0.0077 | 0.6 |  | 99.9929 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 61.2 | 280 | 17136 | 3084.48 | 20220.48 | 0 | 61.2 | 17136 | 3084.48 | 20220.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 21 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 80.206 | 280 | 22457.68 | 4042.38 | 26500.06 | 0 | 0 | 0 | 0 | 0 | 80.206 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 31.02 | 65 | 2016.3 | 362.94 | 2379.24 | 0 | 31.0154 | 2016 | 362.88 | 2378.88 | 0.0046 | 0.36 |  | 99.9852 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 31.02 | 65 | 2016.3 | 362.94 | 2379.24 | 0 | 31.0154 | 2016 | 362.88 | 2378.88 | 0.0046 | 0.36 |  | 99.9852 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 34 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 59.633 | 280 | 16697.24 | 3005.5 | 19702.74 | 0 | 0 | 0 | 0 | 0 | 59.633 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 55.809 | 65 | 3627.59 | 652.96 | 4280.55 | 0 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 203.645 | 280 | 57020.6 | 10263.7 | 67284.3 | 0 | 0 | 0 | 0 | 0 | 203.645 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 35 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 183.37 | 280 | 51343.6 | 9241.84 | 60585.44 | 0 | 0 | 0 | 0 | 0 | 183.37 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 66.192 | 280 | 18533.76 | 3336.08 | 21869.84 | 0 | 0 | 0 | 0 | 0 | 66.192 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 112 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 18 | 1440 | 259.2 | 1699.2 | 18 | 1699.2 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 15.74 | 65 | 1023.1 | 184.16 | 1207.26 | 0 | 15.7385 | 1023 | 184.14 | 1207.14 | 0.0015 | 0.12 |  | 99.9905 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 81.995 | 280 | 22958.6 | 4132.54 | 27091.14 | 0 | 0 | 0 | 0 | 0 | 81.995 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | M.S. Angle 50x50x5 (M)- BCo | Kgs | 36.98 | 65 | 2403.7 | 432.66 | 2836.36 | 0 | 36.98 | 2403.7 | 432.66 | 2836.36 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | MS Channel. (M) | Kgs | 135.918 | 65 | 8834.67 | 1590.24 | 10424.91 | 0 | 111.6154 | 7255 | 1305.9 | 8560.9 | 24.3026 | 1864.01 |  | 82.1197 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | MS Plate (M) | Kgs | 72 | 80 | 5760 | 1036.8 | 6796.8 | 0 | 72 | 5760 | 1036.8 | 6796.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | MS Channel. (M) | Kgs | 215.073 | 65 | 13979.75 | 2516.36 | 16496.11 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 119.9961 | 9203.71 |  | 44.2068 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 21.65 | 65 | 1407.25 | 253.3 | 1660.55 | 0 | 21.6462 | 1407 | 253.26 | 1660.26 | 0.0038 | 0.29 |  | 99.9824 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 63.509 | 280 | 17782.52 | 3200.86 | 20983.38 | 0 | 0 | 0 | 0 | 0 | 63.509 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 55.809 | 65 | 3627.59 | 652.96 | 4280.55 | 0 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 86.4341 | 280 | 24201.55 | 4356.28 | 28557.83 | 0 | 86.4321 | 24200.99 | 4356.18 | 28557.17 | 0.002 | 0.66 |  | 99.9977 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 64.105 | 280 | 17949.4 | 3230.9 | 21180.3 | 0 | 0 | 0 | 0 | 0 | 64.105 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | MS Plate (M) | Kgs | 54 | 80 | 4320 | 777.6 | 5097.6 | 0 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 96.4308 | 6268 | 1128.24 | 7396.24 | 0.0092 | 0.7 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 108 Rolling Shutter - 82.856 Sq.Ft | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | MS Plate (M) | Kgs | 72 | 80 | 5760 | 1036.8 | 6796.8 | 0 | 72 | 5760 | 1036.8 | 6796.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | MS Channel. (M) | Kgs | 95.082 | 65 | 6180.33 | 1112.46 | 7292.79 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 0.0051 | 0.39 |  | 99.9946 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 79.653 | 280 | 22302.84 | 4014.52 | 26317.36 | 0 | 64.147 | 17961.16 | 3233 | 21194.16 | 15.506 | 5123.2 |  | 80.5331 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | M.S.Channel (M) | Kgs | 101.982 | 65 | 6628.83 | 1193.18 | 7822.01 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 6.9051 | 529.61 |  | 93.2291 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | MS Plate (M) | Kgs | 72 | 84 | 6048 | 1088.64 | 7136.64 | 0 | 72 | 6048 | 1088.64 | 7136.64 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 72.46 | 280 | 20288.8 | 3651.98 | 23940.78 | 0 | 71.7214 | 20081.99 | 3614.76 | 23696.75 | 0.7386 | 244.03 |  | 98.9807 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 140.694 | 65 | 9145.11 | 1646.12 | 10791.23 | 0 | 140.6923 | 9145 | 1646.1 | 10791.1 | 0.0017 | 0.13 |  | 99.9988 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 162.85 | 280 | 45598 | 8207.64 | 53805.64 | 0 | 149.6179 | 41893.01 | 7540.74 | 49433.75 | 13.2321 | 4371.89 |  | 91.8747 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 6.06 | 65 | 393.9 | 70.9 | 464.8 | 0 | 6.06 | 393.9 | 70.9 | 464.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 57 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 179.111 | 280 | 50151.08 | 9027.2 | 59178.28 | 0 | 175.5127 | 49143.56 | 8845.84 | 57989.4 | 3.5983 | 1188.88 |  | 97.991 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 34.2 | 65 | 2223 | 400.14 | 2623.14 | 0 | 34.2 | 2223 | 400.14 | 2623.14 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | M.S.Channel (M) | Kgs | 101.982 | 65 | 6628.83 | 1193.18 | 7822.01 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 54.4435 | 4175.81 |  | 46.6146 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 81.668 | 280 | 22867.04 | 4116.06 | 26983.1 | 0 | 80.7786 | 22618.01 | 4071.24 | 26689.25 | 0.8894 | 293.85 |  | 98.911 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 72.165 | 280 | 20206.2 | 3637.12 | 23843.32 | 0 | 71.8679 | 20123.01 | 3622.14 | 23745.15 | 0.2971 | 98.17 |  | 99.5883 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | MS Channel. (M) | Kgs | 47.541 | 65 | 3090.17 | 556.24 | 3646.41 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 0.0025 | 0.2 |  | 99.9947 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 62.1077 | 280 | 17390.16 | 3130.22 | 20520.38 | 0 | 0 | 0 | 0 | 0 | 62.1077 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 59.417 | 280 | 16636.76 | 2994.62 | 19631.38 | 0 | 59.417 | 16636.76 | 2994.62 | 19631.38 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 55.756 | 280 | 15611.68 | 2810.1 | 18421.78 | 0 | 0 | 0 | 0 | 0 | 55.756 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | M.S.Channel (M) | Kgs | 49.614 | 65 | 3224.91 | 580.48 | 3805.39 | 0 | 49.614 | 3224.91 | 580.48 | 3805.39 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | MS Channel. (M) | Kgs | 245.364 | 65 | 15948.66 | 2870.76 | 18819.42 | 0 | 190.1692 | 12361 | 2224.98 | 14585.98 | 55.1948 | 4233.44 |  | 77.5049 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 165.182 | 280 | 46250.96 | 8325.18 | 54576.14 | 0 | 0 | 0 | 0 | 0 | 165.182 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 91.469 | 280 | 25611.32 | 4610.04 | 30221.36 | 0 | 90.875 | 25445 | 4580.1 | 30025.1 | 0.594 | 196.26 |  | 99.3506 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S.Channel (M) | Kgs | 93.724 | 65 | 6092.06 | 1096.58 | 7188.64 | 0 | 93.7231 | 6092 | 1096.56 | 7188.56 | 0.0009 | 0.08 |  | 99.999 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 67.167 | 280 | 18806.76 | 3385.22 | 22191.98 | 0 | 66.6706 | 18667.77 | 3360.2 | 22027.97 | 0.4964 | 164.01 |  | 99.2609 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | MS Channel. (M) | Kgs | 108.882 | 65 | 7077.33 | 1273.92 | 8351.25 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 13.8051 | 1058.85 |  | 87.321 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 48.2308 | 3135 | 564.3 | 3699.3 | 48.2092 | 3697.64 |  | 50.0112 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 153.063 | 280 | 42857.64 | 7714.38 | 50572.02 | 0 | 138.0934 | 38666.15 | 6959.9 | 45626.05 | 14.9696 | 4945.97 |  | 90.22 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 55.809 | 65 | 3627.59 | 652.96 | 4280.55 | 0 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | MS Channel. (M) | Kgs | 103.35 | 65 | 6717.75 | 1209.2 | 7926.95 | 0 | 103.35 | 6717.75 | 1209.2 | 7926.95 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 2.28 | 65 | 148.2 | 26.68 | 174.88 | 0 | 2.2769 | 148 | 26.64 | 174.64 | 0.0031 | 0.24 |  | 99.864 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 87 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 85.25 | 280 | 23870 | 4296.6 | 28166.6 | 0 | 85.25 | 23870 | 4296.6 | 28166.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 26.4 | 65 | 1716 | 308.88 | 2024.88 | 0 | 26.4 | 1716 | 308.88 | 2024.88 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | M.S.Channel (M) | Kgs | 47.54 | 65 | 3090.1 | 556.22 | 3646.32 | 0 | 47.54 | 3090.1 | 556.22 | 3646.32 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 26.02 | 65 | 1691.3 | 304.44 | 1995.74 | 0 | 26.0154 | 1691 | 304.38 | 1995.38 | 0.0046 | 0.36 |  | 99.9823 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | M.S.Channel (M) | Kgs | 50.991 | 65 | 3314.42 | 596.6 | 3911.02 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 3.4525 | 264.81 |  | 93.2292 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | M.S.Channel (M) | Kgs | 55.8 | 65 | 3627 | 652.86 | 4279.86 | 0 | 55.8 | 3627 | 652.86 | 4279.86 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | MS Channel. (M) | Kgs | 190.164 | 65 | 12360.66 | 2224.92 | 14585.58 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 95.0871 | 7293.18 |  | 49.9973 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 108 Rolling Shutter - 82.856 Sq.Ft | Rolling Shutter (M) | Sq.Ft | 82.856 | 280 | 23199.68 | 4175.94 | 27375.62 | 0 | 82.856 | 23199.68 | 4175.94 | 27375.62 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S.Channel (M) | Kgs | 48.22 | 65 | 3134.3 | 564.18 | 3698.48 | 0 | 48.2154 | 3134 | 564.12 | 3698.12 | 0.0046 | 0.36 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 85 Rolling Shutter - 86.123 Sq.Ft | Rolling Shutter (M) | Sq.Ft | 86.123 | 280 | 24114.44 | 4340.6 | 28455.04 | 0 | 86.1214 | 24113.99 | 4340.52 | 28454.51 | 0.0016 | 0.53 |  | 99.9981 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S.Channel (M) | Kgs | 48.22 | 65 | 3134.3 | 564.18 | 3698.48 | 0 | 48.2154 | 3134 | 564.12 | 3698.12 | 0.0046 | 0.36 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 0 | 0 | 0 | 0 | 36 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 5 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 86 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | MS Channel. (M) | Kgs | 95.082 | 65 | 6180.33 | 1112.46 | 7292.79 | 0 | 0 | 0 | 0 | 0 | 95.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 3.19 | 65 | 207.35 | 37.32 | 244.67 | 0 | 3.1846 | 207 | 37.26 | 244.26 | 0.0054 | 0.41 |  | 99.8307 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Second Floor Rolling Shutter for shop - 1 No. | Transportation | No. | 1 | 6000 | 6000 | 1080 | 7080 | 0 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | DEV. Ext Development | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 140.556 | 65 | 9136.14 | 1644.5 | 10780.64 | 0 | 140.5538 | 9136 | 1644.48 | 10780.48 | 0.0022 | 0.16 |  | 99.9984 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | MS Plate (M) | Kgs | 72 | 80 | 5760 | 1036.8 | 6796.8 | 0 | 72 | 5760 | 1036.8 | 6796.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 27 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 106 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 60.06 | 280 | 16816.8 | 3027.02 | 19843.82 | 0 | 60.06 | 16816.8 | 3027.02 | 19843.82 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 77.522 | 280 | 21706.16 | 3907.1 | 25613.26 | 0 | 0 | 0 | 0 | 0 | 77.522 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 7 Shop No 10 | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Channel. (M) | Kgs | 101.982 | 65 | 6628.83 | 1193.18 | 7822.01 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 6.9051 | 529.61 |  | 93.2291 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 114 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 91.834 | 280 | 25713.52 | 4628.44 | 30341.96 | 0 | 0 | 0 | 0 | 0 | 91.834 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 28 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 93.704 | 65 | 6090.76 | 1096.34 | 7187.1 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 46.1655 | 3540.9 |  | 50.7326 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Second Floor Rolling Shutter for shop - 1 No. | Transportation | No. | 1 | 6000 | 6000 | 1080 | 7080 | 0 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | DEV. Ext Development | Approved | abhishek bankar
EAST POINT MARKET | 268 | 5 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 23 May 2024
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | MS Plate (M) | Kgs | 54 | 84 | 4536 | 816.48 | 5352.48 | 0 | 36 | 3024 | 544.32 | 3568.32 | 18 | 1784.16 |  | 66.6667 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 16.8 | 65 | 1092 | 196.56 | 1288.56 | 0 | 16.8 | 1092 | 196.56 | 1288.56 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | MS Plate (M) | Kgs | 36 | 84 | 3024 | 544.32 | 3568.32 | 0 | 36 | 3024 | 544.32 | 3568.32 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 111.618 | 65 | 7255.17 | 1305.94 | 8561.11 | 0 | 111.6154 | 7255 | 1305.9 | 8560.9 | 0.0026 | 0.21 |  | 99.9977 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 77.2848 | 280 | 21639.74 | 3895.16 | 25534.9 | 0 | 77.2821 | 21638.99 | 3895.02 | 25534.01 | 0.0027 | 0.9 |  | 99.9965 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 116 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 24.61 | 65 | 1599.65 | 287.94 | 1887.59 | 0 | 24.61 | 1599.65 | 287.94 | 1887.59 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter work | Rolling Shutter(M) LC | Sq.Ft | 164.902 | 280 | 46172.56 | 8311.06 | 54483.62 | 0 | 0 | 0 | 0 | 0 | 164.902 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Land Cost | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 54.681 | 280 | 15310.68 | 2755.92 | 18066.6 | 0 | 54.681 | 15310.68 | 2755.92 | 18066.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 152.943 | 280 | 42824.04 | 7708.32 | 50532.36 | 0 | 138.65 | 38822 | 6987.96 | 45809.96 | 14.293 | 4722.4 |  | 90.6547 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 55.809 | 65 | 3627.59 | 652.96 | 4280.55 | 0 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 57.844 | 280 | 16196.32 | 2915.34 | 19111.66 | 0 | 0 | 0 | 0 | 0 | 57.844 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 198.278 | 280 | 55517.84 | 9993.22 | 65511.06 | 0 | 0 | 0 | 0 | 0 | 198.278 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | M.S.Channel (M) | Kgs | 47.54 | 65 | 3090.1 | 556.22 | 3646.32 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 0.0015 | 0.12 |  | 99.9968 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 172.33 | 280 | 48252.4 | 8685.44 | 56937.84 | 0 | 162.4452 | 45484.66 | 8187.24 | 53671.9 | 9.8848 | 3265.94 |  | 94.264 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | MS Channel. (M) | Kgs | 95.082 | 65 | 6180.33 | 1112.46 | 7292.79 | 0 | 0 | 0 | 0 | 0 | 95.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | MS Channel. (M) | Kgs | 50.991 | 65 | 3314.42 | 596.6 | 3911.02 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 3.4525 | 264.81 |  | 93.2292 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 26 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 17 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 45 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 63.807 | 280 | 17865.96 | 3215.88 | 21081.84 | 0 | 0 | 0 | 0 | 0 | 63.807 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | MS Plate (M) | Kgs | 36 | 84 | 3024 | 544.32 | 3568.32 | 0 | 18 | 1512 | 272.16 | 1784.16 | 18 | 1784.16 |  | 50 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 51 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 25.03 | 65 | 1626.95 | 292.86 | 1919.81 | 0 | 25.03 | 1626.95 | 292.86 | 1919.81 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 53.371 | 280 | 14943.88 | 2689.9 | 17633.78 | 0 | 0 | 0 | 0 | 0 | 53.371 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 24.12 | 65 | 1567.8 | 282.2 | 1850 | 0 | 0 | 0 | 0 | 0 | 24.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 144.452 | 280 | 40446.56 | 7280.38 | 47726.94 | 0 | 144.452 | 40446.56 | 7280.38 | 47726.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 75 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 96.4308 | 6268 | 1128.24 | 7396.24 | 0.0092 | 0.7 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 70 Rolling Shutter | MS Channel. (M) | Kgs | 59.859 | 65 | 3890.84 | 700.36 | 4591.2 | 0 | 55.8154 | 3628 | 653.04 | 4281.04 | 4.0436 | 310.15 |  | 93.2448 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | Rolling Shutter (M) | Sq.Ft | 58.801 | 280 | 16464.28 | 2963.58 | 19427.86 | 0 | 58.8 | 16464 | 2963.52 | 19427.52 | 0.001 | 0.34 |  | 99.9983 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 45.747 | 280 | 12809.16 | 2305.64 | 15114.8 | 0 | 45.4368 | 12722.3 | 2290.02 | 15012.32 | 0.3102 | 102.48 |  | 99.3219 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 44 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 116.937 | 280 | 32742.36 | 5893.62 | 38635.98 | 0 | 0 | 0 | 0 | 0 | 116.937 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 3.19 | 65 | 207.35 | 37.32 | 244.67 | 0 | 3.1846 | 207 | 37.26 | 244.26 | 0.0054 | 0.41 |  | 99.8307 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 48 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 69.77 | 280 | 19535.6 | 3516.4 | 23052 | 0 | 0 | 0 | 0 | 0 | 69.77 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | MS Plate (M) | Kgs | 54 | 80 | 4320 | 777.6 | 5097.6 | 0 | 54 | 4320 | 777.6 | 5097.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 52 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 67.087 | 280 | 18784.36 | 3381.18 | 22165.54 | 0 | 0 | 0 | 0 | 0 | 67.087 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 39 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 58.738 | 280 | 16446.64 | 2960.4 | 19407.04 | 0 | 0 | 0 | 0 | 0 | 58.738 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | MS Plate (M) | Kgs | 54 | 80 | 4320 | 777.6 | 5097.6 | 0 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | MS Plate (M) | Kgs | 36 | 84 | 3024 | 544.32 | 3568.32 | 0 | 36 | 3024 | 544.32 | 3568.32 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 56.12 | 280 | 15713.6 | 2828.44 | 18542.04 | 0 | 0 | 0 | 0 | 0 | 56.12 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | MS Plate (M) | Kgs | 72 | 80 | 5760 | 1036.8 | 6796.8 | 0 | 72 | 5760 | 1036.8 | 6796.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | MS Plate (M) | Kgs | 36 | 84 | 3024 | 544.32 | 3568.32 | 0 | 18 | 1512 | 272.16 | 1784.16 | 18 | 1784.16 |  | 50 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 73.353 | 280 | 20538.84 | 3697 | 24235.84 | 0 | 72.7607 | 20373 | 3667.14 | 24040.14 | 0.5923 | 195.7 |  | 99.1925 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 22 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 101.972 | 280 | 28552.16 | 5139.38 | 33691.54 | 0 | 0 | 0 | 0 | 0 | 101.972 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 91 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 32.19 | 65 | 2092.35 | 376.62 | 2468.97 | 0 | 32.1846 | 2092 | 376.56 | 2468.56 | 0.0054 | 0.41 |  | 99.9832 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 67.087 | 280 | 18784.36 | 3381.18 | 22165.54 | 0 | 0 | 0 | 0 | 0 | 67.087 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.1384 | 139 | 25.02 | 164.02 | 0.0096 | 0.74 |  | 99.5531 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 183.828 | 280 | 51471.84 | 9264.94 | 60736.78 | 0 | 169.8714 | 47563.99 | 8561.52 | 56125.51 | 13.9566 | 4611.27 |  | 92.4078 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 73.947 | 280 | 20705.16 | 3726.92 | 24432.08 | 0 | 72.4607 | 20289 | 3652.02 | 23941.02 | 1.4863 | 491.06 |  | 97.99 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 62.9688 | 280 | 17631.26 | 3173.62 | 20804.88 | 0 | 62.9679 | 17631.01 | 3173.58 | 20804.59 | 0.0009 | 0.29 |  | 99.9986 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 94 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 39.98 | 65 | 2598.7 | 467.76 | 3066.46 | 0 | 39.98 | 2598.7 | 467.76 | 3066.46 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 40 Rolling Shutter | MS Channel. (M) | Kgs | 95.082 | 65 | 6180.33 | 1112.46 | 7292.79 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 0.0051 | 0.39 |  | 99.9946 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 62 Rolling Shutter | MS Channel. (M) | Kgs | 152.973 | 65 | 9943.25 | 1789.78 | 11733.03 | 0 | 142.6154 | 9270 | 1668.6 | 10938.6 | 10.3576 | 794.42 |  | 93.2291 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | MS Channel. (M) | Kgs | 203.964 | 65 | 13257.66 | 2386.38 | 15644.04 | 0 | 190.1692 | 12361 | 2224.98 | 14585.98 | 13.7948 | 1058.06 |  | 93.2366 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 15.6 | 65 | 1014 | 182.52 | 1196.52 | 0 | 15.6 | 1014 | 182.52 | 1196.52 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 56.188 | 280 | 15732.64 | 2831.88 | 18564.52 | 0 | 55.2393 | 15467 | 2784.06 | 18251.06 | 0.9487 | 313.46 |  | 98.3116 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 165.48 | 280 | 46334.4 | 8340.2 | 54674.6 | 0 | 151.4071 | 42393.99 | 7630.92 | 50024.91 | 14.0729 | 4649.69 |  | 91.4957 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S.Channel (M) | Kgs | 46.882 | 65 | 3047.33 | 548.52 | 3595.85 | 0 | 46.8769 | 3047 | 548.46 | 3595.46 | 0.0051 | 0.39 |  | 99.9891 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 76 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 42 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 48.24 | 65 | 3135.6 | 564.4 | 3700 | 0 | 0 | 0 | 0 | 0 | 48.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 96.4308 | 6268 | 1128.24 | 7396.24 | 0.0092 | 0.7 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | MS Plate (M) | Kgs | 72 | 80 | 5760 | 1036.8 | 6796.8 | 0 | 72 | 5760 | 1036.8 | 6796.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 111 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 79.868 | 280 | 22363.04 | 4025.34 | 26388.38 | 0 | 79.868 | 22363.04 | 4025.34 | 26388.38 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 96.307 | 280 | 26965.96 | 4853.88 | 31819.84 | 0 | 0 | 0 | 0 | 0 | 96.307 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 80 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 87.362 | 280 | 24461.36 | 4403.04 | 28864.4 | 0 | 0 | 0 | 0 | 0 | 87.362 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 66 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 80.504 | 280 | 22541.12 | 4057.4 | 26598.52 | 0 | 0 | 0 | 0 | 0 | 80.504 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 90 Rolling Shutter work | MS Plate (M) | Kgs | 54 | 84 | 4536 | 816.48 | 5352.48 | 0 | 54 | 4536 | 816.48 | 5352.48 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 80.184 | 280 | 22451.52 | 4041.28 | 26492.8 | 0 | 77.8071 | 21785.99 | 3921.48 | 25707.47 | 2.3769 | 785.33 |  | 97.0357 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | M.S.Channel (M) | Kgs | 104.84 | 65 | 6814.6 | 1226.62 | 8041.22 | 0 | 104.84 | 6814.6 | 1226.62 | 8041.22 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 63.509 | 280 | 17782.52 | 3200.86 | 20983.38 | 0 | 0 | 0 | 0 | 0 | 63.509 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 68 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 69.174 | 280 | 19368.72 | 3486.36 | 22855.08 | 0 | 0 | 0 | 0 | 0 | 69.174 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 73 Rolling Shutter | M.S.Channel (M) | Kgs | 152.973 | 65 | 9943.25 | 1789.78 | 11733.03 | 0 | 0 | 0 | 0 | 0 | 152.973 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 137.797 | 280 | 38583.16 | 6944.96 | 45528.12 | 0 | 65.3357 | 18294 | 3292.92 | 21586.92 | 72.4613 | 23941.2 |  | 47.4145 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 55.809 | 65 | 3627.59 | 652.96 | 4280.55 | 0 | 0 | 0 | 0 | 0 | 55.809 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 73.947 | 280 | 20705.16 | 3726.92 | 24432.08 | 0 | 56.7214 | 15881.99 | 2858.76 | 18740.75 | 17.2256 | 5691.33 |  | 76.7055 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 64 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 118.669 | 280 | 33227.32 | 5980.92 | 39208.24 | 0 | 0 | 0 | 0 | 0 | 118.669 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 61 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 62.614 | 280 | 17531.92 | 3155.74 | 20687.66 | 0 | 0 | 0 | 0 | 0 | 62.614 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 32 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 58.142 | 280 | 16279.76 | 2930.36 | 19210.12 | 0 | 0 | 0 | 0 | 0 | 58.142 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 43 Rolling Shutter | MS Plate (M) | Kgs | 72 | 80 | 5760 | 1036.8 | 6796.8 | 0 | 36 | 2880 | 518.4 | 3398.4 | 36 | 3398.4 |  | 50 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 78.1 | 280 | 21868 | 3936.24 | 25804.24 | 0 | 78.1 | 21868 | 3936.24 | 25804.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 56 Rolling Shutter | MS Plate (M) | Kgs | 54 | 80 | 4320 | 777.6 | 5097.6 | 0 | 36 | 2880 | 518.4 | 3398.4 | 18 | 1699.2 |  | 66.6667 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 49 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 78.715 | 280 | 22040.2 | 3967.24 | 26007.44 | 0 | 0 | 0 | 0 | 0 | 78.715 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 5 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 66.98 | 280 | 18754.4 | 3375.8 | 22130.2 | 0 | 66.9786 | 18754.01 | 3375.72 | 22129.73 | 0.0014 | 0.47 |  | 99.9979 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 103 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 149.403 | 280 | 41832.84 | 7529.92 | 49362.76 | 0 | 149.403 | 41832.84 | 7529.92 | 49362.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 100 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 31.02 | 65 | 2016.3 | 362.94 | 2379.24 | 0 | 31.0154 | 2016 | 362.88 | 2378.88 | 0.0046 | 0.36 |  | 99.9852 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 12 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 77.5 | 280 | 21700 | 3906 | 25606 | 0 | 77.5 | 21700 | 3906 | 25606 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 47.706 | 280 | 13357.68 | 2404.38 | 15762.06 | 0 | 0 | 0 | 0 | 0 | 47.706 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 27.95 | 65 | 1816.75 | 327.02 | 2143.77 | 0 | 27.95 | 1816.75 | 327.02 | 2143.77 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 18 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 96 Rolling Shutter | M.S.Channel (M) | Kgs | 7.589 | 65 | 493.29 | 88.8 | 582.09 | 0 | 7.5846 | 493 | 88.74 | 581.74 | 0.0044 | 0.35 |  | 99.942 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 77 Rolling Shutter | M.S.Channel (M) | Kgs | 144.66 | 65 | 9402.9 | 1692.52 | 11095.42 | 0 | 144.66 | 9402.9 | 1692.52 | 11095.42 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 7 Shop No 10 | M.S.Channel (M) | Kgs | 47.54 | 65 | 3090.1 | 556.22 | 3646.32 | 0 | 47.54 | 3090.1 | 556.22 | 3646.32 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 59 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 1 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 70.7188 | 280 | 19801.26 | 3564.22 | 23365.48 | 0 | 70.7179 | 19801.01 | 3564.18 | 23365.19 | 0.0009 | 0.29 |  | 99.9987 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 62.316 | 280 | 17448.48 | 3140.72 | 20589.2 | 0 | 0 | 0 | 0 | 0 | 62.316 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 102 Rolling Shutter - 58.801 Sq.Ft | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 27.79 | 65 | 1806.35 | 325.14 | 2131.49 | 0 | 27.7846 | 1806 | 325.08 | 2131.08 | 0.0054 | 0.41 |  | 99.9806 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 47 Rolling Shutter | MS Channel. (M) | Kgs | 95.082 | 65 | 6180.33 | 1112.46 | 7292.79 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 0.0051 | 0.39 |  | 99.9946 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 63 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S.Channel (M) | Kgs | 40.542 | 65 | 2635.23 | 474.34 | 3109.57 | 0 | 40.5385 | 2635 | 474.3 | 3109.3 | 0.0035 | 0.27 |  | 99.9914 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 48.23 | 65 | 3134.95 | 564.3 | 3699.25 | 0 | 48.23 | 3134.95 | 564.3 | 3699.25 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 3 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 0.854 | 280 | 239.12 | 43.04 | 282.16 | 0 | 0.8536 | 239.01 | 43.02 | 282.03 | 0.0004 | 0.13 |  | 99.9532 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 220.939 | 280 | 61862.92 | 11135.32 | 72998.24 | 0 | 0 | 0 | 0 | 0 | 220.939 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 54 Rolling Shutter | MS Channel. (M) | Kgs | 129.582 | 65 | 8422.83 | 1516.1 | 9938.93 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 34.5051 | 2646.53 |  | 73.372 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 79 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 81.995 | 280 | 22958.6 | 4132.54 | 27091.14 | 0 | 0 | 0 | 0 | 0 | 81.995 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 146.497 | 280 | 41019.16 | 7383.44 | 48402.6 | 0 | 146.497 | 41019.16 | 7383.44 | 48402.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 177.808 | 280 | 49786.24 | 8961.52 | 58747.76 | 0 | 149.675 | 41909 | 7543.62 | 49452.62 | 28.133 | 9295.14 |  | 84.1779 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 64.5 | 280 | 18060 | 3250.8 | 21310.8 | 0 | 64.5 | 18060 | 3250.8 | 21310.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 85.5394 | 280 | 23951.03 | 4311.18 | 28262.21 | 0 | 73.9464 | 20704.99 | 3726.9 | 24431.89 | 11.593 | 3830.32 |  | 86.4472 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 24.12 | 65 | 1567.8 | 282.2 | 1850 | 0 | 0 | 0 | 0 | 0 | 24.12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 95 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 38.4 | 65 | 2496 | 449.28 | 2945.28 | 0 | 38.4 | 2496 | 449.28 | 2945.28 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 69 Rolling Shutter | MS Channel. (M) | Kgs | 59.859 | 65 | 3890.84 | 700.36 | 4591.2 | 0 | 55.8154 | 3628 | 653.04 | 4281.04 | 4.0436 | 310.15 |  | 93.2448 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 109 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 91.834 | 280 | 25713.52 | 4628.44 | 30341.96 | 0 | 0 | 0 | 0 | 0 | 91.834 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 65 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 80.504 | 280 | 22541.12 | 4057.4 | 26598.52 | 0 | 0 | 0 | 0 | 0 | 80.504 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 62.9688 | 280 | 17631.26 | 3173.62 | 20804.88 | 0 | 0 | 0 | 0 | 0 | 62.9688 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | M.S.Channel (M) | Kgs | 48.22 | 65 | 3134.3 | 564.18 | 3698.48 | 0 | 48.2154 | 3134 | 564.12 | 3698.12 | 0.0046 | 0.36 |  | 99.9905 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 50 Rolling Shutter | M.S. Angle 50x50x5 (M)- BCo | Kgs | 31.02 | 65 | 2016.3 | 362.94 | 2379.24 | 0 | 31.0154 | 2016 | 362.88 | 2378.88 | 0.0046 | 0.36 |  | 99.9852 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 9 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 72.752 | 280 | 20370.56 | 3666.7 | 24037.26 | 0 | 0 | 0 | 0 | 0 | 72.752 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 31 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 18 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 23 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 82 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 13 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 55 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 68.876 | 280 | 19285.28 | 3471.36 | 22756.64 | 0 | 0 | 0 | 0 | 0 | 68.876 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 80.504 | 280 | 22541.12 | 4057.4 | 26598.52 | 0 | 0 | 0 | 0 | 0 | 80.504 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 20 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 79.013 | 280 | 22123.64 | 3982.26 | 26105.9 | 0 | 0 | 0 | 0 | 0 | 79.013 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 93 Rolling Shutter work | M.S.Channel (M) | Kgs | 47.54 | 65 | 3090.1 | 556.22 | 3646.32 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 0.0015 | 0.12 |  | 99.9968 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 83 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | MS Plate (M) | Kgs | 18 | 84 | 1512 | 272.16 | 1784.16 | 0 | 18 | 1512 | 272.16 | 1784.16 | 0 | 0 |  | 100 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 97 Rolling Shutter | M.S. Angle 75x75x6 (M)- Kgs - Kgs | Kgs | 34.2 | 65 | 2223 | 400.14 | 2623.14 | 0 | 34.2 | 2223 | 400.14 | 2623.14 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 113 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 2 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 111.618 | 65 | 7255.17 | 1305.94 | 8561.11 | 0 | 111.6154 | 7255 | 1305.9 | 8560.9 | 0.0026 | 0.21 |  | 99.9977 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 74 Rolling Shutter | MS Plate (M) | Kgs | 54 | 80 | 4320 | 777.6 | 5097.6 | 0 | 36 | 2880 | 518.4 | 3398.4 | 18 | 1699.2 |  | 66.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 112 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 74.271 | 280 | 20795.88 | 3743.26 | 24539.14 | 0 | 73.3529 | 20538.81 | 3696.98 | 24235.79 | 0.9181 | 303.35 |  | 98.7639 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 41 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 47.265 | 65 | 3072.23 | 553 | 3625.23 | 0 | 47.2615 | 3072 | 552.96 | 3624.96 | 0.0035 | 0.27 |  | 99.9926 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 30 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 146.497 | 280 | 41019.16 | 7383.44 | 48402.6 | 0 | 0 | 0 | 0 | 0 | 146.497 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 110 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 67.4896 | 280 | 18897.09 | 3401.48 | 22298.57 | 0 | 59.75 | 16730 | 3011.4 | 19741.4 | 7.7396 | 2557.17 |  | 88.5322 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 101 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 67.683 | 280 | 18951.24 | 3411.22 | 22362.46 | 0 | 0 | 0 | 0 | 0 | 67.683 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 36 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 67.981 | 280 | 19034.68 | 3426.24 | 22460.92 | 0 | 0 | 0 | 0 | 0 | 67.981 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 53 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 71.261 | 280 | 19953.08 | 3591.56 | 23544.64 | 0 | 0 | 0 | 0 | 0 | 71.261 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 98 Rolling Shutter | MS Channel. (M) | Kgs | 101.982 | 65 | 6628.83 | 1193.18 | 7822.01 | 0 | 95.0769 | 6180 | 1112.4 | 7292.4 | 6.9051 | 529.61 |  | 93.2291 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 38 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 134.549 | 280 | 37673.72 | 6781.26 | 44454.98 | 0 | 134.549 | 37673.72 | 6781.26 | 44454.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 73.625 | 280 | 20615 | 3710.7 | 24325.7 | 0 | 73.625 | 20615 | 3710.7 | 24325.7 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 92 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 48.23 | 65 | 3134.95 | 564.3 | 3699.25 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 0.6915 | 53.05 |  | 98.5662 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 81 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 16 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 36 | 2880 | 518.4 | 3398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 56.055 | 280 | 15695.4 | 2825.18 | 18520.58 | 0 | 0 | 0 | 0 | 0 | 56.055 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 89 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 192.92 | 65 | 12539.8 | 2257.16 | 14796.96 | 0 | 190.1692 | 12361 | 2224.98 | 14585.98 | 2.7508 | 210.98 |  | 98.5741 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 30.32 | 2546.88 | 458.44 | 3005.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 46 Rolling Shutter | MS Plate (M) | Kgs | 36 | 80 | 2880 | 518.4 | 3398.4 | 0 | 18 | 1440 | 259.2 | 1699.2 | 18 | 1699.2 |  | 50 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 25 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 11 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 18 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 15 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 67 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 111.618 | 65 | 7255.17 | 1305.94 | 8561.11 | 0 | 55.8154 | 3628 | 653.04 | 4281.04 | 55.8026 | 4280.07 |  | 50.0057 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 60 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 29 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 115 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 84.082 | 280 | 23542.96 | 4237.74 | 27780.7 | 0 | 0 | 0 | 0 | 0 | 84.082 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 2 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 19 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 78.402 | 280 | 21952.56 | 3951.46 | 25904.02 | 0 | 78.4 | 21952 | 3951.36 | 25903.36 | 0.002 | 0.66 |  | 99.9974 |  | abhishek bankar | ABHISHEK BANKAR | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | ABHISHEK BANKAR
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 77.8229 | 280 | 21790.41 | 3922.28 | 25712.69 | 0 | 67.7109 | 18959.05 | 3412.62 | 22371.67 | 10.112 | 3341.02 |  | 87.0064 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 78 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Second Floor Rolling Shutter for shop - 1 No. | Transportation | No. | 1 | 6000 | 6000 | 1080 | 7080 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 | 0 | 0 | 0 | 130.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 218.077 | 280 | 61061.56 | 10991.08 | 72052.64 | 0 | 148.785 | 41659.8 | 7498.76 | 49158.56 | 69.292 | 22894.08 |  | 68.2259 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 107 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 58 Rolling Shutter | MS Channel. (M) | Kgs | 50.991 | 65 | 3314.42 | 596.6 | 3911.02 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 3.4525 | 264.81 |  | 93.2292 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 72 Rolling Shutter | M.S.Channel (M) | Kgs | 50.991 | 65 | 3314.42 | 596.6 | 3911.02 | 0 | 47.5385 | 3090 | 556.2 | 3646.2 | 3.4525 | 264.81 |  | 93.2292 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 117 Rolling Shutter | M.S.Channel (M) | Kgs | 96.44 | 65 | 6268.6 | 1128.34 | 7396.94 | 0 | 96.4154 | 6267 | 1128.06 | 7395.06 | 0.0246 | 1.88 |  | 99.9745 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 88 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 14 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | M.S.Channel (M) | Kgs | 54.55 | 65 | 3545.75 | 638.24 | 4183.99 | 0 | 54.5385 | 3545 | 638.1 | 4183.1 | 0.0115 | 0.89 |  | 99.9789 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 10 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 71 Rolling Shutter work | MS Plate (M) | Kgs | 30.32 | 84 | 2546.88 | 458.44 | 3005.32 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 84 Rolling Shutter work | Rolling Shutter (M) | Sq.Ft | 173.4063 | 280 | 48553.76 | 8739.68 | 57293.44 | 0 | 160.6786 | 44990.01 | 8098.2 | 53088.21 | 12.7277 | 4205.24 |  | 92.6602 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 105 Rolling Shutter | MS Angle 50 x 50 x 6mm(M) | Kgs | 2.148 | 65 | 139.62 | 25.14 | 164.76 | 0 | 2.148 | 139.62 | 25.14 | 164.76 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 0 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 99 Rolling Shutter work | Fabrication Work (M) - Mkt | Kgs | 130.75 | 65 | 8498.75 | 1529.78 | 10028.53 | 0 | 130.75 | 8498.75 | 1529.78 | 10028.53 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 1 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 104 Rolling Shutter | MS Plate (M) | Kgs | 18 | 80 | 1440 | 259.2 | 1699.2 | 0 | 18 | 1440 | 259.2 | 1699.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 268 | 4 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 4 Rolling Shutter work | MS Angle 50 x 50 x 6mm(M) | Kgs | 1.074 | 65 | 69.81 | 12.56 | 82.37 | 0 | 1.074 | 69.81 | 12.56 | 82.37 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 268 | 3 | 18 Apr 2023 | ANAND ROLLING SHUTTER & FABRICATOR | Shop No. 24 Rolling Shutter | Rolling Shutter (M) | Sq.Ft | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 25 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 269 | 0 | 01 Mar 2023 | METADOOR EXPERIENCE PRIVATE LIMITED | Marketing Expenses | Marketing Expenses | No. | 1 | 687720 | 687720 | 123789.6 | 811509.6 | 0 | 1 | 687720 | 123789.6 | 811509.6 | 0 | 0 |  | 100 |  | Swapnil Erande | Swapnil Erande | construction open | 19 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 270 | 0 | 20 Apr 2023 | DADAMIYA INFRASTRUCTURE LLP | Consultancy Parking lot handing over to Dhamma Seva | Liasoning Services- | No. | 1 | 250000 | 250000 | 45000 | 295000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Consultacy Architectural | Approved | Swapnil Erande
EAST POINT MARKET | 270 | 0 | 20 Apr 2023 | DADAMIYA INFRASTRUCTURE LLP | Consultancy BEST Plot joint | Plot Measurement | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Pressure Testing and Vaccuming (L) | Job | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | No category | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Drain Piping 25mm (L) | Mtrs | 40 | 30 | 1200 | 216 | 1416 | 2.5 | 14 | 420 | 75.6 | 495.6 | 26 | 920.4 |  | 35 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | No category | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Drain Piping 32mm (L) | Mtrs | 60 | 30 | 1800 | 324 | 2124 | 2.5 | 15 | 450 | 81 | 531 | 45 | 1593 |  | 25 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | No category | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Cassette A.C. Unit 4 Way (L) | No. | 5 | 2000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor Fouth floor Sample office Lowside AC works - 1 | Refrigerant Piping (L) | Mtrs | 100 | 350 | 35000 | 6300 | 41300 | 2.5 | 64.405 | 22541.75 | 4057.52 | 26599.27 | 35.595 | 14700.73 |  | 64.405 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Refnets (Joints for Indoor Units) (L) | No. | 6 | 405 | 2430 | 437.4 | 2867.4 | 2.5 | 6 | 2430 | 437.4 | 2867.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor Fouth floor Sample office Lowside AC works - 1 | MS Stand (L)- No. | No. | 1 | 975 | 975 | 175.5 | 1150.5 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | No category | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Cassette A.C. Unit 1 Way (L) | No. | 2 | 2000 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | 8 HP VRF ODU (L) | No. | 1 | 16000 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | No category | Approved | chetan jewalikar
EAST POINT MARKET | 271 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Control Cabling (L) | Mtrs | 160 | 35 | 5600 | 1008 | 6608 | 2.5 | 100 | 3500 | 630 | 4130 | 60 | 2478 |  | 62.5 |  | DUSHANT GORE | chetan jewalikar | construction open | 13 May 2023 |  | No category | Approved | chetan jewalikar
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Control Cabling (M) | Mtrs | 160 | 100 | 16000 | 2880 | 18880 | 0 | 100 | 10000 | 1800 | 11800 | 60 | 7080 |  | 62.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor Fouth floor Sample office Lowside AC works - 1 | 410 A Gas (M) | Kgs | 10 | 700 | 7000 | 1260 | 8260 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Cassette A.C. Unit 1 Way (M) | No. | 2 | 30988 | 61976 | 11155.68 | 73131.68 | 0 | 2 | 61976 | 17353.28 | 79329.28 | 0 | -6197.6 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Pressure Testing and Vaccuming (M) | Job | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor Fouth floor Sample office Lowside AC works - 1 | Refrigerant Piping (M) | Mtrs | 100 | 800 | 80000 | 14400 | 94400 | 0 | 64.405 | 51524 | 9274.32 | 60798.32 | 35.595 | 33601.68 |  | 91.2175 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Cable Tray (M) | Job | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Drain Piping 32mm (M) | Mtrs | 60 | 100 | 6000 | 1080 | 7080 | 0 | 15 | 1500 | 270 | 1770 | 45 | 5310 |  | 25 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Drain Piping 25mm (M) | Mtrs | 40 | 100 | 4000 | 720 | 4720 | 0 | 14 | 1400 | 252 | 1652 | 26 | 3068 |  | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Refnets (Joints for Indoor Units) (M) | No. | 6 | 5380 | 32280 | 5810.4 | 38090.4 | 0 | 6 | 32280 | 5810.4 | 38090.4 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | Cassette A.C. Unit 4 Way (M) | No. | 5 | 32250 | 161250 | 29025 | 190275 | 0 | 5 | 161250 | 45150 | 206400 | 0 | -16125 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor- Shop No-5 AC Work | 8 HP VRF ODU (M) | No. | 1 | 163700 | 163700 | 29466 | 193166 | 0 | 1 | 163700 | 45836 | 209536 | 0 | -16370 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 272 | 0 | 05 May 2023 | NEW INDIA REFRIGERATION | 4th Floor Fouth floor Sample office Lowside AC works - 1 | MS Stand (M) - No. | No. | 1 | 4800 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 May 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 273 | 2 | 13 May 2023 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Transport Charges- Med. | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | TRANSPORT CHARGES RS. 20000/- | 0 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 24 May 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 273 | 0 | 13 May 2023 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Eco Vinyal With Foam Sheet | Sq.Ft | 1200 | 105 | 126000 | 22680 | 148680 | 0 | 1200 | 126000 | 22680 | 148680 | 0 | 0 | ECO VINYAL + 5MM FOAM SHEET PRINTING, PASTING, INSTALLATION AT EAST POINT KURLA SITE BARICATTINGS @ 105/- + TAX PER SQ FT. TOTAL 1136 SQ FT. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 24 May 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 273 | 1 | 13 May 2023 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Black Back Flex | Sq.Ft | 5500 | 25 | 137500 | 24750 | 162250 | 0 | 5468.6 | 136715 | 24608.7 | 161323.7 | 31.4 | 926.3 | STAR BLACK BACK FLEX PRINT WITH PASTING AT EAST POINT KURLA SITE BRANDING @ 25/- PER SQ FT TOTAL SQ FT. AS 4442 SQ FT AREA | 99.4291 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 24 May 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 273 | 3 | 13 May 2023 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Eco Vinyal With Foam Sheet | Sq.Ft | 1200 | 15 | 18000 | 3240 | 21240 | 0 | 1200 | 18000 | 3240 | 21240 | 0 | 0 | ECO VINYAL WITH FOAM SHEET 5 MM (RATE INCRESED RS. 15/- PER SQ FT)X 1200 SQ FT. - RATE DIFF. | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 24 May 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 274 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500454 | KEP. 1st Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 1485 | 1485 | 267.3 | 1752.3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Meter Type- Three Phase, Meter Count -04, Load /meter- 80 KW. Meter Type- Three Phase, Meter Count -07, Load /meter- 10 KW. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 274 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500454 | KEP. 1st Fl Electricity Meter | Service connection charges | No. | 1 | 83550 | 83550 | 15039 | 98589 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Meter Type- Three Phase, Meter Count -04, Load /meter- 80 KW. Meter Type- Three Phase, Meter Count -07, Load /meter- 10 KW. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 274 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500454 | KEP. 1st Fl Electricity Meter | Security Deposit | No. | 1 | 39000 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Meter Type- Three Phase, Meter Count -04, Load /meter- 80 KW. Meter Type- Three Phase, Meter Count -07, Load /meter- 10 KW. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 275 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500456 | KEP-Gr Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 765 | 765 | 137.7 | 902.7 | 0 | 1 | 765 | 137.7 | 902.7 | 0 | 0 | Meter Type- Single Phase, Meter Count -09, Load /meter- 5 KW. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 275 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500456 | KEP-Gr Fl Electricity Meter | Security Deposit | No. | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 275 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500456 | KEP-Gr Fl Electricity Meter | Service connection charges | No. | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 275 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500456 | KEP-Gr Fl Electricity Meter | Applction, Regn & Processing charges | No. | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 275 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500456 | KEP-Gr Fl Electricity Meter | Security Deposit | No. | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 | Meter Type- Single Phase, Meter Count -09, Load /meter- 5 KW. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 275 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500456 | KEP-Gr Fl Electricity Meter | Service connection charges | No. | 1 | 21600 | 21600 | 3888 | 25488 | 0 | 1 | 21600 | 3888 | 25488 | 0 | 0 | Meter Type- Single Phase, Meter Count -09, Load /meter- 5 KW. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 276 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500046 | KEP.3rd Fl Electricity Meter | Security Deposit | No. | 1 | 39600 | 39600 | 0 | 39600 | 0 | 1 | 39600 | 0 | 39600 | 0 | 0 | Meter Type- Single Phase, Meter Count -22, Load /meter- 5 KW. Meter Type- Three Phase, Meter Count -24, Load /meter- 10 KW. Meter Type- Three Phase, Meter Count -01, Load /meter- 22 KW. Meter Type- Three Phase, Meter Count -01, Load /meter- 35 KW. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 276 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500046 | KEP.3rd Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 5380 | 5380 | 968.4 | 6348.4 | 0 | 1 | 5380 | 968.4 | 6348.4 | 0 | 0 | Meter Type- Single Phase, Meter Count -22, Load /meter- 5 KW. Meter Type- Three Phase, Meter Count -24, Load /meter- 10 KW. Meter Type- Three Phase, Meter Count -01, Load /meter- 22 KW. Meter Type- Three Phase, Meter Count -01, Load /meter- 35 KW. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 276 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500046 | KEP.3rd Fl Electricity Meter | Applction, Regn & Processing charges | No. | 0 | 5380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 15 Jun 2023
EAST POINT MARKET | 276 | 0 | 15 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153500046 | KEP.3rd Fl Electricity Meter | Service connection charges | No. | 1 | 156200 | 156200 | 28116 | 184316 | 0 | 1 | 156200 | 28116 | 184316 | 0 | 0 | Meter Type- Single Phase, Meter Count -22, Load /meter- 5 KW. Meter Type- Three Phase, Meter Count -24, Load /meter- 10 KW. Meter Type- Three Phase, Meter Count -01, Load /meter- 22 KW. Meter Type- Three Phase, Meter Count -01, Load /meter- 35 KW. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-1st Fl 1st Fl Meter PWD NOC-(No.) | Three Phase Meter Noc (PWD) | No. | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-Gr Fl Ground Fl- Meter PWD NOC | Single Phase Meter Noc (PWD) | No. | 9 | 2700 | 24300 | 0 | 24300 | 0 | 9 | 24300 | 0 | 24300 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 2 | 6000 | 12000 | 0 | 12000 | 0 | 2 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 24 | 4100 | 98400 | 0 | 98400 | 0 | 24 | 98400 | 0 | 98400 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-1st Fl 1st Fl Meter PWD NOC-(No.) | Three Phase Meter Noc (PWD) | No. | 4 | 7000 | 28000 | 0 | 28000 | 0 | 4 | 28000 | 0 | 28000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-Gr Fl Ground Fl- Meter PWD NOC | Single Phase Meter Noc (PWD) | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Single Phase Meter Noc (PWD) | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-1st Fl 1st Fl Meter PWD NOC-(No.) | Three Phase Meter Noc (PWD) | No. | 7 | 4100 | 28700 | 0 | 28700 | 0 | 7 | 28700 | 0 | 28700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Single Phase Meter Noc (PWD) | No. | 9 | 2700 | 24300 | 0 | 24300 | 0 | 9 | 24300 | 0 | 24300 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-1st Fl 1st Fl Meter PWD NOC-(No.) | Three Phase Meter Noc (PWD) | No. | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-Gr Fl Ground Fl- Meter PWD NOC | Meter Cabin Sanction | No. | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Meter Room approved from PWD at Ground Floor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Meter Cabin Sanction | No. | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Meter Room approved from PWD at Third Floor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Cancelled | DUSHANT.GORE | 20 Jul 2023
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Meter Cabin Sanction | No. | 1 | 29000 | 29000 | 0 | 29000 | 0 | 1 | 29000 | 0 | 29000 | 0 | 0 | Meter Room approved from PWD at Third Floor. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP-Gr Fl Ground Fl- Meter PWD NOC | Meter Cabin Sanction | No. | 1 | 29000 | 29000 | 0 | 29000 | 0 | 1 | 29000 | 0 | 29000 | 0 | 0 | Meter Room approved from PWD at Ground Floor. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 277 | 0 | 15 Jun 2023 | GARGI INFRATECH | KEP - 3rd Fl 3rd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 4 | 7000 | 28000 | 0 | 28000 | 0 | 4 | 28000 | 0 | 28000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 278 | 1 | 17 Jun 2023 | KHAN KAMAR ALAM | 4th Floor Sample Office Misc Work | Vertical Dhar (M+L) | R.Ft | 67.568 | 50 | 3378.4 | 0 | 3378.4 | 2.5 | 67.56 | 3378 | 0 | 3378 | 0.008 | 0.4 |  | 99.9882 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | No category | Approved | raviraj agarwal
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | False Ceiling Patta | R.Ft | 422 | 65 | 27430 | 0 | 27430 | 2.5 | 315 | 20475 | 0 | 20475 | 107 | 6955 |  | 74.6445 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 278 | 1 | 17 Jun 2023 | KHAN KAMAR ALAM | 4th Floor Sample Office Misc Work | A/C Grill Gala Cutting | No. | 7 | 600 | 4200 | 0 | 4200 | 2.5 | 7 | 4200 | 0 | 4200 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | 05 GYPSUM & PLASTER | Approved | raviraj agarwal
EAST POINT MARKET | 278 | 1 | 17 Jun 2023 | KHAN KAMAR ALAM | 4th Floor Sample Office Misc Work | Vertical Dhar with Sheet (M+L) | R.Ft | 62.689 | 70 | 4388.23 | 0 | 4388.23 | 2.5 | 62.6857 | 4388 | 0 | 4388 | 0.0033 | 0.23 |  | 99.9947 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | No category | Approved | raviraj agarwal
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-2nd Floor Gypsum misc Work | Gypsum Misc. work | No. | 26 | 2500 | 65000 | 0 | 65000 | 2.5 | 9 | 22500 | 0 | 22500 | 17 | 42500 | For Shop No. 9 to 26 & 66 to 73 | 34.6154 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-2nd Floor Gypsum misc Work | Lumpsum work- DCW | No. | 0 | 9500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | DEV. Compound Wall | Cancelled | ADITYA.CHOUGULE | 23 Jun 2023
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-2nd Floor Gypsum misc Work | Lumpsum work- DCW | No. | 0 | 65000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | DEV. Compound Wall | Cancelled | ADITYA.CHOUGULE | 03 Jul 2023
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-2nd Floor Gypsum misc Work | Lumpsum work- DCW | No. | 0 | 65000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | DEV. Compound Wall | Cancelled | ADITYA.CHOUGULE | 29 Jun 2023
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | 2nd Floor Shops buds filling | Lumpsum work- DCW | No. | 0 | 22000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | DEV. Compound Wall | Cancelled | ADITYA.CHOUGULE | 29 Jun 2023
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-2nd Floor Gypsum misc Work | Lumpsum work- DCW | No. | 0 | 83200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | False Ceiling work- Shop no. 9 to 26 and Shop No. 66 to 73. | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | DEV. Compound Wall | Cancelled | ADITYA.CHOUGULE | 23 Jun 2023
EAST POINT MARKET | 278 | 1 | 17 Jun 2023 | KHAN KAMAR ALAM | 2nd Floor Misc Works | Labour Lumpsum | No. | 1 | 9000 | 9000 | 0 | 9000 | 2.5 | 1 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | DEV. Ext Development | Approved | raviraj agarwal
EAST POINT MARKET | 278 | 1 | 17 Jun 2023 | KHAN KAMAR ALAM | 4th Floor Sample Office Misc Work | False Ceiling (m+l) - BRE | Sq.Ft | 253.87 | 75 | 19040.25 | 0 | 19040.25 | 2.5 | 253.8667 | 19040 | 0 | 19040 | 0.0033 | 0.25 |  | 99.9987 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | B.C. Rework/Extrawork | Approved | raviraj agarwal
EAST POINT MARKET | 278 | 1 | 17 Jun 2023 | KHAN KAMAR ALAM | 4th Floor Sample Office Misc Work | Gala Cutting | No. | 50 | 60 | 3000 | 0 | 3000 | 2.5 | 50 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open |  |  | B.C. Internal Finishing Itmes | Approved | raviraj agarwal
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-2nd Floor Gypsum misc Work | Lumpsum work- DCW | No. | 1 | 8500 | 8500 | 0 | 8500 | 2.5 | 1 | 8500 | 0 | 8500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | 2nd Floor Shops buds filling | Lumpsum work- DCW | No. | 1 | 18000 | 18000 | 0 | 18000 | 2.5 | 1 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Compound Wall | Approved | Swapnil Erande
EAST POINT MARKET | 278 | 0 | 17 Jun 2023 | KHAN KAMAR ALAM | KEP-3rd Fl Foodcourt Area False Ceiling Work | False Ceiling Patta | R.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 29 Jun 2023
EAST POINT MARKET | 279 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513198 | KEP.3rd Fl Electricity Meter | Service connection charges | No. | 1 | 3650 | 3650 | 657 | 4307 | 0 | 1 | 3650 | 657 | 4307 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 279 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513198 | KEP.3rd Fl Electricity Meter | Security Deposit | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 279 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513198 | KEP.3rd Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 135 | 135 | 24.3 | 159.3 | 0 | 1 | 135 | 24.3 | 159.3 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 280 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513197 | KEP.3rd Fl Electricity Meter | Security Deposit | No. | 1 | 8000 | 8000 | 0 | 8000 | 0 | 1 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 280 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513197 | KEP.3rd Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 135 | 135 | 24.3 | 159.3 | 0 | 1 | 135 | 24.3 | 159.3 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 280 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513197 | KEP.3rd Fl Electricity Meter | Service connection charges | No. | 1 | 14500 | 14500 | 2610 | 17110 | 0 | 1 | 14500 | 2610 | 17110 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 281 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513567 | KEP. 1st Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 1350 | 1350 | 243 | 1593 | 0 | 1 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 281 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513567 | KEP. 1st Fl Electricity Meter | Service connection charges | No. | 1 | 58200 | 58200 | 10476 | 68676 | 0 | 1 | 58200 | 10476 | 68676 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 281 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513567 | KEP. 1st Fl Electricity Meter | Security Deposit | No. | 1 | 24000 | 24000 | 0 | 24000 | 0 | 1 | 24000 | 0 | 24000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 282 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513565 | KEP. 1st Fl Electricity Meter | Service connection charges | No. | 1 | 32650 | 32650 | 5877 | 38527 | 0 | 1 | 32650 | 5877 | 38527 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 282 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513565 | KEP. 1st Fl Electricity Meter | Security Deposit | No. | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA.CHOUGULE | 23 Jun 2023
EAST POINT MARKET | 282 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513565 | KEP. 1st Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 405 | 405 | 72.9 | 477.9 | 0 | 1 | 405 | 72.9 | 477.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 282 | 0 | 23 Jun 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153513565 | KEP. 1st Fl Electricity Meter | Security Deposit | No. | 1 | 17000 | 17000 | 0 | 17000 | 0 | 1 | 17000 | 0 | 17000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 283 | 0 | 23 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (L) | Sq.Ft | 97.09 | 75 | 7281.75 | 1310.72 | 8592.47 | 2.5 | 97.09 | 7281.75 | 1310.72 | 8592.47 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 283 | 1 | 23 Jun 2023 | SAHARA ENGINEERING | 3rd Fl Fire Fighting pipe covering by ACP with Toughened gla | ACP Work (M+L) | Sq.Ft | 30.14 | 250 | 7535 | 1356.3 | 8891.3 | 2.5 | 30.14 | 7535 | 1356.3 | 8891.3 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jun 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 283 | 1 | 23 Jun 2023 | SAHARA ENGINEERING | KEP-3rd Floor Railway side scaffolding rework for FC logo | Labour Lumpsum | No. | 1 | 15000 | 15000 | 2700 | 17700 | 2.5 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jun 2023 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 283 | 1 | 23 Jun 2023 | SAHARA ENGINEERING | 3rd Fl Fire Fighting pipe covering by ACP with Toughened gla | ACP Work (M+L) | Sq.Ft | 230.34 | 250 | 57585 | 10365.3 | 67950.3 | 2.5 | 230.34 | 57585 | 10365.3 | 67950.3 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jun 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 283 | 0 | 23 Jun 2023 | SAHARA ENGINEERING | 2nd floor Shop 10 Glass Door with fix glass | Fix Glass+Glass Door- Mkt | Sq.Ft | 65.404 | 195 | 12753.78 | 2295.68 | 15049.46 | 2.5 | 65.404 | 12753.78 | 2295.68 | 15049.46 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 284 | 0 | 23 Jun 2023 | SAHARA ENGINEERING | 2nd floor Shop 10 Glass Door with fix glass | Fix Glass+Glass Door (M) | Sq.Ft | 65.404 | 455 | 29758.82 | 5356.58 | 35115.4 | 0 | 65.404 | 29758.82 | 5356.58 | 35115.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 284 | 0 | 23 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (M) | Sq.Ft | 97.09 | 175 | 16990.75 | 3058.34 | 20049.09 | 0 | 97.09 | 16990.75 | 3058.34 | 20049.09 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 72 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 113 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 61 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 1 | 24 Jun 2023 | SAHARA ENGINEERING | 3rd Floor Scaffolding Work | Labour Lumpsum | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 103 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 63 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 73 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 60 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 95 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 66 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 109 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 31 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 81 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 110 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 20 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 86 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 76 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 104 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 36 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 112 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 97 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 87 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 45 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 115 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 52 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 55 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 13 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 58 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 90 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 43 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 53 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 105 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 38 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 39 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 48 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 96 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 16 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 93 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 101 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 83 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 79 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 28 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 15 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 41 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | KEP-Scaffolding Work for Signage & Plumbing | Labour Lumpsum | No. | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jun 2023 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 47 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 21 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 44 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 84 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 56 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 88 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 35 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 54 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 09 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 64 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 111 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 46 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 17 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 59 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 117 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 62 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 22 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 25 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 51 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 30 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 27 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 91 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 78 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 26 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 106 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 50 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 89 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 57 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 42 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 92 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 12 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 34 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 94 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 49 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 107 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 70 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 19 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 67 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 80 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 14 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 98 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 11 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 40 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 108 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 116 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 65 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 114 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 33 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 10 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 100 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 68 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 23 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 102 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 37 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 85 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 04 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 29 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 77 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 32 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 71 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 99 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 74 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 24 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 75 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 18 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 69 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 285 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | ACP for Shop 82 Sinage | ACP Work- (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 24 Jun 2023
EAST POINT MARKET | 286 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 4th Floor Shop No 5 Glass Work | Labour Lumpsum | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 286 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 4th Floor Shop 5 ACP work | ACP Work (M+L) | Sq.Ft | 54.25 | 250 | 13562.5 | 2441.26 | 16003.76 | 0 | 54.25 | 13562.5 | 2441.26 | 16003.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 286 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 4th Floor Shop No 5 Glass Work | Labour Lumpsum | No. | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | DEV. Ext Development | Cancelled | ADITYA.CHOUGULE | 29 Jun 2023
EAST POINT MARKET | 287 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 3rd Fl Dual window ACP work with Aluminium | ACP with Aluminium (L) | Sq.Ft | 20.58 | 75 | 1543.5 | 277.84 | 1821.34 | 2.5 | 20.58 | 1543.5 | 277.84 | 1821.34 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 287 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 3rd Fl Fire Fighting pipe covering by ACP with Toughened gla | ACP with toughened glass (L) | Sq.Ft | 126.42 | 135 | 17066.7 | 3072 | 20138.7 | 2.5 | 126.42 | 17066.7 | 3072 | 20138.7 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 288 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 3rd Fl Dual window ACP work with Aluminium | ACP with Aluminium (M) | Sq.Ft | 20.58 | 175 | 3601.5 | 648.28 | 4249.78 | 0 | 20.58 | 3601.5 | 648.28 | 4249.78 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 288 | 0 | 24 Jun 2023 | SAHARA ENGINEERING | 3rd Fl Fire Fighting pipe covering by ACP with Toughened gla | ACP with toughened glass (M) | Sq.Ft | 126.42 | 315 | 39822.3 | 7168.02 | 46990.32 | 0 | 126.42 | 39822.3 | 7168.02 | 46990.32 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jun 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.8986 | 26958 | 0 | 26958 | 0.1014 | 3042 |  | 89.86 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.4833 | 14499 | 0 | 14499 | 0.5167 | 15501 |  | 48.33 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.7223 | 21669 | 0 | 21669 | 0.2777 | 8331 |  | 72.23 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.7413 | 22239 | 0 | 22239 | 0.2587 | 7761 |  | 74.13 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.2754 | 8262 | 0 | 8262 | 0.7246 | 21738 |  | 27.54 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.2486 | 7458 | 0 | 7458 | 0.7514 | 22542 |  | 24.86 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.4035 | 12105 | 0 | 12105 | 0.5965 | 17895 |  | 40.35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.8733 | 26199 | 0 | 26199 | 0.1267 | 3801 |  | 87.33 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.7089 | 21267 | 0 | 21267 | 0.2911 | 8733 |  | 70.89 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.9437 | 28311 | 0 | 28311 | 0.0563 | 1689 |  | 94.37 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.7872 | 23616 | 0 | 23616 | 0.2128 | 6384 |  | 78.72 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 1 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.9318 | 27954 | 0 | 27954 | 0.0682 | 2046 |  | 93.18 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.4789 | 14367 | 0 | 14367 | 0.5211 | 15633 |  | 47.89 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 289 | 0 | 01 Jul 2023 | VIJAY KUMAR (STAFF) | Leasing and Sales Team Expenses | Marketing Operating Expenses | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0.6753 | 20259 | 0 | 20259 | 0.3247 | 9741 |  | 67.53 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande
EAST POINT MARKET | 290 | 0 | 15 Jul 2023 | KHAN KAMAR ALAM | 3rd Floor Shop 14, Meter room & Dishwasher room Gypsum | Labour Lumpsum BCE- | No. | 1 | 12000 | 12000 | 0 | 12000 | 2.5 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jul 2023 |  | B.C. Elevation Features | Approved | Swapnil Erande
EAST POINT MARKET | 290 | 0 | 15 Jul 2023 | KHAN KAMAR ALAM | 3rd Floor Shop 14, Meter room & Dishwasher room Gypsum | Labour Lumpsum BCE- | No. | 0 | 14000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jul 2023 |  | B.C. Elevation Features | Cancelled | ADITYA.CHOUGULE | 20 Jul 2023
EAST POINT MARKET | 291 | 0 | 15 Jul 2023 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | Material Shifting | Sq.Ft | 1636.25 | 3 | 4908.75 | 0 | 4908.75 | 0 | 1636.25 | 4908.75 | 0 | 4908.75 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 291 | 0 | 15 Jul 2023 | SURESH KUMAR MURALIDHAR | KEP-2nd Fl Single coat plaster Shop 23 | Single Coat Plaster (L) | Sq.Ft | 221.66 | 20 | 4433.2 | 0 | 4433.2 | 2.5 | 0 | 0 | 0 | 0 | 221.66 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 291 | 0 | 15 Jul 2023 | SURESH KUMAR MURALIDHAR | 2nd Floor Misc Works | PCC Work | Sq.Ft | 1636.25 | 10 | 16362.5 | 0 | 16362.5 | 2.5 | 1636.25 | 16362.5 | 0 | 16362.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 02 RCC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 292 | 0 | 15 Jul 2023 | AZAM KHAN | 4th Floor Sample shop no 5 Painting Work (L) | 1st Coat Putty (L) | Sq.Ft | 1690.586 | 1.5 | 2535.88 | 0 | 2535.88 | 2.5 | 1690 | 2535 | 0 | 2535 | 0.586 | 0.88 |  | 99.9653 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 06 Sep 2023 |  | 10 PAINTING WORK | Approved | raviraj agarwal
EAST POINT MARKET | 292 | 0 | 15 Jul 2023 | AZAM KHAN | 4th Floor Sample shop no 5 Painting Work (L) | 2nd Coat Putty (L) | Sq.Ft | 1690.586 | 1.5 | 2535.88 | 0 | 2535.88 | 2.5 | 1690 | 2535 | 0 | 2535 | 0.586 | 0.88 |  | 99.9653 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 06 Sep 2023 |  | 10 PAINTING WORK | Approved | raviraj agarwal
EAST POINT MARKET | 292 | 0 | 15 Jul 2023 | AZAM KHAN | 4th Floor Sample shop no 5 Painting Work (L) | 1st Coat Premium Emulsion Paint (L) | Sq.Ft | 1690.586 | 1.5 | 2535.88 | 0 | 2535.88 | 2.5 | 1690 | 2535 | 0 | 2535 | 0.586 | 0.88 |  | 99.9653 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 06 Sep 2023 |  | 10 PAINTING WORK | Approved | raviraj agarwal
EAST POINT MARKET | 292 | 0 | 15 Jul 2023 | AZAM KHAN | 4th Floor Sample shop no 5 Painting Work (L) | Primer -BC | Sq.Ft | 1690.58 | 1.5 | 2535.87 | 0 | 2535.87 | 2.5 | 1690 | 2535 | 0 | 2535 | 0.58 | 0.87 |  | 99.9657 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 06 Sep 2023 |  | B.C. Internal Finishing Itmes | Approved | raviraj agarwal
EAST POINT MARKET | 292 | 0 | 15 Jul 2023 | AZAM KHAN | 4th Floor Sample shop no 5 Painting Work (L) | 2nd Coat Premium Emulsion Paint (L) | Sq.Ft | 1690.586 | 1.5 | 2535.88 | 0 | 2535.88 | 2.5 | 1690 | 2535 | 0 | 2535 | 0.586 | 0.88 |  | 99.9653 |  | ADITYA.CHOUGULE | raviraj agarwal | construction open | 06 Sep 2023 |  | 10 PAINTING WORK | Approved | raviraj agarwal
EAST POINT MARKET | 293 | 0 | 19 Jul 2023 | CHETAN ELECTRICAL | KEP-2nd Fl Electric Meter Liasoning Charges | Three Phase Meter Sanction | No. | 24 | 7000 | 168000 | 0 | 168000 | 0 | 1 | 7000 | 0 | 7000 | 23 | 161000 |  | 4.1667 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 293 | 0 | 19 Jul 2023 | CHETAN ELECTRICAL | KEP-4th Fl Electric Meter Liasoning Charges | Electrical Meter Liasoning Charges | No. | 1 | 23000 | 23000 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 293 | 0 | 19 Jul 2023 | CHETAN ELECTRICAL | KEP-2nd Fl Electric Meter Liasoning Charges | Single Phase Meter Sanction | No. | 93 | 3000 | 279000 | 0 | 279000 | 0 | 52 | 156000 | 0 | 156000 | 41 | 123000 |  | 55.914 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 293 | 0 | 19 Jul 2023 | CHETAN ELECTRICAL | KEP-2nd Fl Electric Meter Liasoning Charges | Three Phase Meter Sanction | No. | 1 | 23000 | 23000 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 293 | 0 | 19 Jul 2023 | CHETAN ELECTRICAL | KEP-4th Fl Electric Meter Liasoning Charges | Three Phase Meter Sanction | No. | 1 | 23000 | 23000 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 293 | 0 | 19 Jul 2023 | CHETAN ELECTRICAL | KEP-4th Fl Electric Meter Liasoning Charges | Three Phase Meter Sanction | No. | 26 | 7000 | 182000 | 0 | 182000 | 0 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-2nd Fl Meter PWD NOC | Meter Cabin Sanction | No. | 1 | 30000 | 30000 | 0 | 30000 | 0 | 1 | 30000 | 0 | 30000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-4th Fl Meter PWD NOC | Meter Cabin Sanction | No. | 1 | 30000 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-2nd Fl Meter PWD NOC | Single Phase Meter Noc (PWD) | No. | 93 | 2800 | 260400 | 0 | 260400 | 0 | 52 | 145600 | 0 | 145600 | 41 | 114800 |  | 55.914 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-4th Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 1 | 8000 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-2nd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 24 | 4200 | 100800 | 0 | 100800 | 0 | 1 | 4200 | 0 | 4200 | 23 | 96600 |  | 4.1667 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-4th Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 26 | 4200 | 109200 | 0 | 109200 | 0 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 294 | 0 | 19 Jul 2023 | GARGI INFRATECH | KEP-2nd Fl Meter PWD NOC | Three Phase Meter Noc (PWD) | No. | 1 | 8000 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 295 | 0 | 20 Jul 2023 | ZAPLON TECH SOLUTIONS PRIVATE LIMITED | Media Digital Campaining (2nd & 4th Floor) | Digital Mktg. | No. | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jul 2023 |  | MKT. Media | Approved | Swapnil Erande
EAST POINT MARKET | 295 | 1 | 20 Jul 2023 | ZAPLON TECH SOLUTIONS PRIVATE LIMITED | Media Digital Campaining (2nd & 4th Floor) | Digital Mktg. | No. | 1 | 1386000 | 1386000 | 249480 | 1635480 | 0 | 0.1443 | 199999.8 | 36000 | 235999.8 | 0.8557 | 1399480.2 |  | 14.43 |  | abhishek bankar | abhishek bankar | construction open | 21 Jul 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 296 | 0 | 22 Jul 2023 | ANTS DESIGN | 4th Floor show office fitout | Lumpsum work (M+L) | Lumsum | 1 | 2275000 | 2275000 | 409500 | 2684500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 06 Jun 2024 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 296 | 0 | 22 Jul 2023 | ANTS DESIGN | 4th Floor show office fitout | Lumpsum work (M+L) | Lumsum | 0 | 2275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 06 Jun 2024 |  | No category | Cancelled | abhishek bankar | 06 Jun 2024
EAST POINT MARKET | 296 | 0 | 22 Jul 2023 | ANTS DESIGN | 4th Floor show office fitout | Lumpsum work (M+L) | Lumsum | 0 | 2850000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 06 Jun 2024 |  | No category | Cancelled | abhishek bankar | 06 Jun 2024
EAST POINT MARKET | 297 | 0 | 27 Jul 2023 | REDKING TECHNOLOGIES | EDP & IT Expenses-(No.) - 1 No. | Software liasoning charges | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 03 Aug 2023
EAST POINT MARKET | 297 | 0 | 27 Jul 2023 | REDKING TECHNOLOGIES | EDP & IT Expenses-(No.) - 1 No. | Software Installation charges | No. | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 03 Aug 2023
EAST POINT MARKET | 298 | 0 | 09 Aug 2023 | PREFAB INFRAPROJECTS PVT LTD | KEP - Gr Fl Shop Aerocon Panel-75mm | Aerocon Partition (M+L) BC | Sq.Ft | 808.88 | 130 | 105154.4 | 18927.8 | 124082.2 | 0 | 808.88 | 105154.4 | 18927.8 | 124082.2 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 18 Aug 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 298 | 0 | 09 Aug 2023 | PREFAB INFRAPROJECTS PVT LTD | KEP - Gr Fl Shop.No.9+10,16,17,18,19,20,21,25 Aerocon Panel- | Aerocon Partition (M+L) BC | Sq.Ft | 814.5 | 130 | 105885 | 19059.3 | 124944.3 | 0 | 395.2815 | 51386.6 | 9249.58 | 60636.18 | 419.2185 | 64308.13 |  | 48.5306 |  | DUSHANT.GORE | Swapnil Erande | construction open | 18 Aug 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | GF Escalator behind shop rolling - 1 No. | SS Pipe Fixing (M+L) | No. | 2 | 8000 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | 3rd Floor Mall Management Glass Door film work | Film Fixing on Glass (m+l) - BRE | Sq.Ft | 128 | 80 | 10240 | 1843.2 | 12083.2 | 2.5 | 0 | 0 | 0 | 0 | 128 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | 3rd Floor Misc work | Scaffolding (M+L) | Lumsum | 1 | 55000 | 55000 | 9900 | 64900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | 3rd Floor Al. Window work | Window repairing (M+L) | No. | 12 | 3500 | 42000 | 7560 | 49560 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | 3rd Floor Shifting work | Labour Lumpsum - BC | No. | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 09 Aug 2023
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | GF Misc MS Work | Toughen Glass 12mm M+L- BC | Sq.Ft | 288.99 | 650 | 187843.5 | 33811.84 | 221655.34 | 2.5 | 0 | 0 | 0 | 0 | 288.99 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | GF Escalator behind shop rolling - 1 No. | SS Pipe Fixing (M+L) | No. | 0 | 8000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 09 Aug 2023
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | 3rd Floor Al. Window work | Aluminium Window (m+l) - SOS | No. | 12 | 9000 | 108000 | 19440 | 127440 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 299 | 0 | 09 Aug 2023 | SAHARA ENGINEERING | GF Toilet window louvers fixing | Aluminium Louver (m+l) | No. | 7 | 1500 | 10500 | 1890 | 12390 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 09 CARPENTRY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 300 | 0 | 11 Aug 2023 | AMPLE IMPRESSIONS | Media BRANDING | Booklet / Notepad / Diary / Pocket Print | No. | 500 | 60 | 30000 | 3600 | 33600 | 0 | 500 | 30000 | 1500 | 31500 | 0 | 2100 | FRACTIONAL OWNERS - - THE BIG LEAP - EAST POINT MARKET PROJECT BRANDING WITH SALES PROMOTION - BOOKLET PRINT QTY 500 (270 RENDEVOUZ PAPER WITH AQUAS QUOATING 3 GATE FOLD F/B MULTICOLOUR PRINT | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Aug 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 301 | 0 | 26 Aug 2023 | MAHESH RANGRAO GHORPADE | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 4 | 25000 | 100000 | 0 | 100000 | 0 | 3.2219 | 80547.5 | 0 | 80547.5 | 0.7781 | 19452.5 |  | 80.5475 |  | abhishek bankar | abhishek bankar | construction open | 01 Sep 2023 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 302 | 0 | 28 Aug 2023 | GOURI CONSTRUCTION | 4th Floor Internal Waterproofing Shops | Screeding W/P-BCo | Sq.Ft | 8961.78 | 25 | 224044.5 | 40328.02 | 264372.52 | 10 | 8360.9999 | 209025 | 37624.5 | 246649.5 | 600.7801 | 17723.02 |  | 93.2962 |  | abhishek bankar | abhishek bankar | construction open | 01 Sep 2023 |  | B.C. Building Common Items | Approved | abhishek bankar
EAST POINT MARKET | 302 | 0 | 28 Aug 2023 | GOURI CONSTRUCTION | 4th Floor Internal Waterproofing Shops | Chemical W/ P (M+L)- SO | Sq.Ft | 8961.78 | 22 | 197159.16 | 35488.64 | 232647.8 | 10 | 8360.9999 | 183942 | 33109.56 | 217051.56 | 600.7801 | 15596.24 |  | 93.2962 |  | abhishek bankar | abhishek bankar | construction open | 01 Sep 2023 |  | S OH Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 303 | 0 | 02 Sep 2023 | DREAMTREE EXPERIENCE | Media BRANDING | SIGNAGES / SIGN BOARD / DROPDOWN / LED BOARDS | No. | 0 | 616800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EAST POINT KURLA FOOD COURT - COMMERCIAL SPACES + SHOPS BRANDING SIGNAGES BOARD | 0 |  | TEJAS RAVERKAR |  | Construction | 02 Sep 2023 |  | MKT. Media | Cancelled | TEJAS RAVERKAR | 02 Sep 2023
EAST POINT MARKET | 304 | 0 | 02 Sep 2023 | DREAMTREE EXPERIENCE | Media BRANDING | SIGNAGES / SIGN BOARD / DROPDOWN / LED BOARDS | No. | 1 | 616800 | 616800 | 111024 | 727824 | 0 | 1 | 616800 | 111024 | 727824 | 0 | 0 | EAST POINT KURLA FOOD COURT - COMMERCIAL SPACES + SHOPS BRANDING SIGNAGES BOARD | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 07 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 0 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software liasoning charges | No. | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 40 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 40 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0.5143 | 13500.38 | 2430.07 | 15930.45 | 0.4857 | 15044.56 |  | 51.43 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 2 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 3750 | 3750 | 675 | 4425 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 45.71 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 0 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software liasoning charges | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 04 Sep 2023
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0.5143 | 13500.38 | 2430.07 | 15930.45 | 0.4857 | 15044.56 |  | 51.43 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0.4857 | 12749.63 | 2294.93 | 15044.56 | 0.5143 | 15930.45 |  | 48.57 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 0 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Installation charges | No. | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 2 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0.3714 | 9749.25 | 1754.86 | 11504.11 | 0.6286 | 19470.89 |  | 37.14 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0.5143 | 13500.38 | 2430.07 | 15930.45 | 0.4857 | 15044.56 |  | 51.43 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Software Service Charges | Month | 1 | 26250 | 26250 | 4725 | 30975 | 0 | 0.2857 | 7499.63 | 1349.93 | 8849.56 | 0.7143 | 22125.45 |  | 28.57 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 305 | 1 | 04 Sep 2023 | PATHFINDER ENTERPRISE SOLUTIONS P LTD | EDP & IT Expenses-(No.) - 1 No. | Management service charges | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open |  |  | No category | Approved | DUSHANT.GORE | 31 Jul 2024
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl A Common area Electrical Work | Outgoing-32A,TP,MCBs-1No (M) | No. | 2 | 841 | 1682 | 302.76 | 1984.76 | 0 | 1 | 841 | 151.38 | 992.38 | 1 | 992.38 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 8 SWG GI Wire (M) | No. | 200 | 26 | 5200 | 936 | 6136 | 0 | 46 | 1196 | 215.28 | 1411.28 | 154 | 4724.72 |  | 23 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Washing Area Electrical Work | 32 A 5 Pin Socket (M) | No. | 1 | 9324 | 9324 | 1678.32 | 11002.32 | 0 | 1 | 9324 | 1678.32 | 11002.32 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | I/C 40A FP MCB (M) | No. | 1 | 1523 | 1523 | 274.14 | 1797.14 | 0 | 1 | 1523 | 274.14 | 1797.14 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 63A,100mA 4P ELCB in metal boards enclosure.(M) | No. | 2 | 2778 | 5556 | 1000.08 | 6556.08 | 0 | 2 | 5556 | 1000.08 | 6556.08 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3.5 Core 70 sq.mm Termination Alu. Arm. cable (M) | No. | 2 | 1027 | 2054 | 369.72 | 2423.72 | 0 | 2 | 2054 | 369.72 | 2423.72 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3 Phase C.T. Meter (M) | No. | 0 | 18135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 3 Module Plate (M) | No. | 80 | 117 | 9360 | 1684.8 | 11044.8 | 0 | 24 | 2808 | 505.44 | 3313.44 | 56 | 7731.36 |  | 30 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | 200 A TP incomer Panel (M) | No. | 1 | 134550 | 134550 | 24219 | 158769 | 0 | 1 | 134550 | 24219 | 158769 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 16 Sq.mm Single Copper Flexible Cable (M) | Mtrs | 50 | 174 | 8700 | 1566 | 10266 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for shops 1,2,3,4,5,10,11,12,13,25 | 4 Core 6 sq.mm Copper Armoured cable (M) | Mtrs | 1600 | 341 | 545600 | 98208 | 643808 | 0 | 1373 | 468193 | 84274.74 | 552467.74 | 227 | 91340.26 |  | 85.8125 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 4 Core 16 sq.mm Termination Alu. Arm. cable (M) | No. | 4 | 415 | 1660 | 298.8 | 1958.8 | 0 | 4 | 1660 | 298.8 | 1958.8 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl A Common area Electrical Work | Incomer-125A MCCB (M) | No. | 2 | 3527 | 7054 | 1269.72 | 8323.72 | 0 | 1 | 3527 | 634.86 | 4161.86 | 1 | 4161.86 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | 8 way ETPN DB (M) | No. | 1 | 3682 | 3682 | 662.76 | 4344.76 | 0 | 1 | 3682 | 662.76 | 4344.76 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 35 Sq.mm Single Copper Flexible Termination Cable (M) | No. | 8 | 48 | 384 | 69.12 | 453.12 | 0 | 8 | 384 | 69.12 | 453.12 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for shops 1,2,3,4,5,10,11,12,13,25 | 4 Core 6 sq.mm Copper Armoured cable (M) | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 35 Sq.mm Single Copper Flexible Cable (M) | Mtrs | 32 | 378 | 12096 | 2177.28 | 14273.28 | 0 | 32 | 12096 | 2177.28 | 14273.28 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for shops 1,2,3,4,5,10,11,12,13,25 | 4 Core 6 sq.mm Termination Copper Arm. cable (M) | No. | 45 | 305 | 13725 | 2470.5 | 16195.5 | 0 | 45 | 13725 | 2470.5 | 16195.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 16 Sq.mm Single Copper Flexible Termination Cable (M) | No. | 20 | 22 | 440 | 79.2 | 519.2 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 6/16 Amp.Multi Pin Socket (M) | No. | 80 | 229 | 18320 | 3297.6 | 21617.6 | 0 | 24 | 5496 | 989.28 | 6485.28 | 56 | 15132.32 |  | 30 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 25/3 Earthing Patti (M) | Mtrs | 400 | 76 | 30400 | 5472 | 35872 | 0 | 158 | 12008 | 2161.44 | 14169.44 | 242 | 21702.56 |  | 39.5 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Copper Armoured cable (M) | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Termination Copper Arm. cable (M) | No. | 0 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 10 Sq.mm Single Copper Flexible Termination Cable (M) | No. | 20 | 18 | 360 | 64.8 | 424.8 | 0 | 10 | 180 | 32.4 | 212.4 | 10 | 212.4 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | MCCB 250A FP,25kA with enclosure (M) | No. | 2 | 28080 | 56160 | 10108.8 | 66268.8 | 0 | 2 | 56160 | 10108.8 | 66268.8 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Copper Armoured cable (M) | Mtrs | 0 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 11 Sep 2023
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 10 Sq.mm Single Copper Flexible Cable (M) | Mtrs | 60 | 108 | 6480 | 1166.4 | 7646.4 | 0 | 52 | 5616 | 1010.88 | 6626.88 | 8 | 1019.52 |  | 86.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | 3.5 Core 120 sq.mm Aluminium Armoured cable (M) | Mtrs | 60 | 672 | 40320 | 7257.6 | 47577.6 | 0 | 60 | 40320 | 7257.6 | 47577.6 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 20 Amp Switch (M) | No. | 80 | 199 | 15920 | 2865.6 | 18785.6 | 0 | 24 | 4776 | 859.68 | 5635.68 | 56 | 13149.92 |  | 30 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3 Phase C.T. Meter (M) | No. | 1 | 8190 | 8190 | 1474.2 | 9664.2 | 0 | 1 | 8190 | 1474.2 | 9664.2 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl Meter room Electrical Work | 3.5 Core 120 sq.mm Termination Alu. Arm. cable (M) | No. | 2 | 1465 | 2930 | 527.4 | 3457.4 | 0 | 2 | 2930 | 527.4 | 3457.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | Starter Panel (M) | No. | 4 | 2075 | 8300 | 1494 | 9794 | 0 | 4 | 8300 | 1494 | 9794 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 100A,100mA 4P ELCB in metal boards enclosure (M) | No. | 3 | 5157 | 15471 | 2784.78 | 18255.78 | 0 | 3 | 15471 | 2784.78 | 18255.78 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3.5 Core 35 sq.mm Termination Alu. Arm. cable (M) | No. | 6 | 542 | 3252 | 585.36 | 3837.36 | 0 | 6 | 3252 | 585.36 | 3837.36 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl A Common area Electrical Work | VTPN DB MCCB (M) | No. | 2 | 8709 | 17418 | 3135.24 | 20553.24 | 0 | 1 | 8709 | 1567.62 | 10276.62 | 1 | 10276.62 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 3.5 Core 35 sq.mm Aluminium Armoured cable (M) | Mtrs | 260 | 242 | 62920 | 11325.6 | 74245.6 | 0 | 255 | 61710 | 11107.8 | 72817.8 | 5 | 1427.8 |  | 98.0769 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 3 Module Box (M) | No. | 80 | 81 | 6480 | 1166.4 | 7646.4 | 0 | 24 | 1944 | 349.92 | 2293.92 | 56 | 5352.48 |  | 30 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 95 Sq.mm Single Copper Flexible Termination Cable (M) | No. | 8 | 101 | 808 | 145.44 | 953.44 | 0 | 8 | 808 | 145.44 | 953.44 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | 3 Phase Meter With MCB (M) | No. | 10 | 8483 | 84830 | 15269.4 | 100099.4 | 0 | 7 | 59381 | 10688.58 | 70069.58 | 3 | 30029.82 |  | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 70 Sq.mm Single Copper Flexible Termination Cable (M) | No. | 8 | 64 | 512 | 92.16 | 604.16 | 0 | 8 | 512 | 92.16 | 604.16 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Food court Area-Fly catcher Machine | 3 Core 2.5 sq.mm Copper Flexible Cable (M) | Mtrs | 500 | 184 | 92000 | 16560 | 108560 | 0 | 281 | 51704 | 9306.72 | 61010.72 | 219 | 47549.28 |  | 56.2 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | MCCB 200A FP,25kA with busbar (M) | No. | 2 | 40950 | 81900 | 14742 | 96642 | 0 | 2 | 81900 | 14742 | 96642 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | SUB I/C-40A,100mA,DP RCCB (M) | No. | 3 | 2209 | 6627 | 1192.86 | 7819.86 | 0 | 3 | 6627 | 1192.86 | 7819.86 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl common Area Electrical Work | O/G 16A SP MCB (M) | No. | 18 | 158 | 2844 | 511.92 | 3355.92 | 0 | 18 | 2844 | 511.92 | 3355.92 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | Electrical Work for pizza hut shop | 3.5 Core 70 sq.mm Aluminium Armoured cable (M) | Mtrs | 60 | 438 | 26280 | 4730.4 | 31010.4 | 0 | 60 | 26280 | 4730.4 | 31010.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 25/6 Earthing Patti (M) | Mtrs | 200 | 94 | 18800 | 3384 | 22184 | 0 | 52 | 4888 | 879.84 | 5767.84 | 148 | 16416.16 |  | 26 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP - 3rd Fl AC Outdoor area electrical Work | 4 Core 16 sq.mm Aluminium Armoured cable (M) | Mtrs | 130 | 170 | 22100 | 3978 | 26078 | 0 | 130 | 22100 | 3978 | 26078 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl A Common area Electrical Work | Outgoing-32A,SP,MCBs-15No (M) | No. | 30 | 163 | 4890 | 880.2 | 5770.2 | 0 | 15 | 2445 | 440.1 | 2885.1 | 15 | 2885.1 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 306 | 0 | 09 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | KEP-Gr Fl Meter room Electrical Work | 95 Sq.mm Single Copper Flexible Cable (M) | Mtrs | 8 | 1031 | 8248 | 1484.64 | 9732.64 | 0 | 8 | 8248 | 1484.64 | 9732.64 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 307 | 0 | 11 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Termination Copper Arm. cable (M) | No. | 10 | 367 | 3670 | 660.6 | 4330.6 | 0 | 6 | 2202 | 396.36 | 2598.36 | 4 | 1732.24 |  | 60 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 307 | 0 | 11 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Copper Armoured cable (M) | Mtrs | 400 | 341 | 136400 | 24552 | 160952 | 0 | 214 | 72974 | 13135.32 | 86109.32 | 186 | 74842.68 |  | 53.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 308 | 0 | 11 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Copper Armoured cable (L) | Mtrs | 400 | 45 | 18000 | 3240 | 21240 | 2.5 | 214 | 9630 | 1733.4 | 11363.4 | 186 | 9876.6 |  | 53.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 308 | 0 | 11 Sep 2023 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 2nd fl Al/Copper Armoured/Flexible Cable for Shop-85,86,108 | 4 Core 6 sq.mm Termination Copper Arm. cable (L) | No. | 10 | 80 | 800 | 144 | 944 | 2.5 | 6 | 480 | 86.4 | 566.4 | 4 | 377.6 |  | 60 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 309 | 0 | 16 Sep 2023 | HARI OM VENTURES | Media FLEX PRINTING & MOUNTING | PRINTING | No. | 1 | 42800 | 42800 | 7704 | 50504 | 0 | 1 | 42800 | 7704 | 50504 | 0 | 0 | including Light with Fitting Charges & Gas & Installation Charges | 100 |  | abhishek bankar | abhishek bankar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 310 | 0 | 16 Sep 2023 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | Certificate with Glass & Frame | No. | 25 | 200 | 5000 | 900 | 5900 | 0 | 25 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 18 Sep 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 310 | 0 | 16 Sep 2023 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | Brochure Printing | No. | 2000 | 32 | 64000 | 11520 | 75520 | 0 | 500 | 16000 | 2880 | 18880 | 1500 | 56640 |  | 25 |  | abhishek bankar | abhishek bankar | construction open | 18 Sep 2023 |  | 19.MEDIA | Approved | abhishek bankar
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 29091 | 29091 | 0 | 29091 | 0 | 1 | 29091 | 0 | 29091 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 7000 | 7000 | 0 | 7000 | 0 | 1 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 19900 | 19900 | 0 | 19900 | 0 | 1 | 19900 | 0 | 19900 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 9400 | 9400 | 0 | 9400 | 0 | 1 | 9400 | 0 | 9400 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 12000 | 12000 | 0 | 12000 | 0 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 12050 | 12050 | 0 | 12050 | 0 | 1 | 12050 | 0 | 12050 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 311 | 0 | 16 Sep 2023 | VIJAY KUMAR (STAFF) | Office Hold Item Purchase From IKEA STORE Msc .Expenses | Misc Work - AIE | No. | 1 | 32000 | 32000 | 0 | 32000 | 0 | 1 | 32000 | 0 | 32000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Sep 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 312 | 0 | 18 Sep 2023 | PREETI SIDDHARTH PAWAR | Marketing Infra Marketing Expenses/Misc | Food Expenses | No. | 1 | 18000 | 18000 | 0 | 18000 | 0 | 1 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 18 Sep 2023 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 313 | 0 | 18 Sep 2023 | ANAND ROLLING SHUTTER & FABRICATOR | 4th floor Sales Lounge work | Board Fixing - Mkt | Sq.Ft | 990 | 22 | 21780 | 3920.4 | 25700.4 | 2.5 | 987.2273 | 21719 | 3909.42 | 25628.42 | 2.7727 | 71.98 |  | 99.7199 |  | abhishek bankar | abhishek bankar | construction open | 23 Sep 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 315 | 0 | 18 Sep 2023 | AZAM KHAN | 4th floor Sales Lounge work | Painting Work | Sq.Ft | 1335 | 3 | 4005 | 0 | 4005 | 2.5 | 1335 | 4005 | 0 | 4005 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 23 Sep 2023 |  | DEV. Ext Development | Approved | abhishek bankar
EAST POINT MARKET | 316 | 0 | 20 Sep 2023 | Triangular Media Creation Pvt. Ltd | Outdoor Advertising | Light Pole | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 26 Sep 2023 |  | No category | Cancelled | abhishek bankar | 26 Sep 2023
EAST POINT MARKET | 316 | 0 | 20 Sep 2023 | Triangular Media Creation Pvt. Ltd | Outdoor Advertising | Bus Shelter | No. | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 26 Sep 2023 |  | No category | Cancelled | abhishek bankar | 26 Sep 2023
EAST POINT MARKET | 316 | 0 | 20 Sep 2023 | Triangular Media Creation Pvt. Ltd | Outdoor Advertising | Outdoor Advertising | No. | 1 | 1255000 | 1255000 | 225900 | 1480900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 26 Sep 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 316 | 0 | 20 Sep 2023 | Triangular Media Creation Pvt. Ltd | Outdoor Advertising | Auto Rishshaw Back Branding | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 26 Sep 2023 |  | No category | Cancelled | abhishek bankar | 26 Sep 2023
EAST POINT MARKET | 316 | 0 | 20 Sep 2023 | Triangular Media Creation Pvt. Ltd | Outdoor Advertising | Tricycle | No. | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open | 26 Sep 2023 |  | No category | Cancelled | abhishek bankar | 26 Sep 2023
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0.95 | 14250 | 2565 | 16815 | 0.05 | 885 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 95 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0.95 | 14250 | 2565 | 16815 | 0.05 | 885 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 95 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0.95 | 14250 | 2565 | 16815 | 0.05 | 885 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 95 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1.Rodent services- Basement with duct,Ground Floor station side,Fatima side,Top Terrace area. 2.Cockroach & Ants services- All Food Court area, service coridoor, passage, office pantry,Toilets. 3. Mosquitos Spray- Top Terrace, Basement area and Toilets. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande
EAST POINT MARKET | 317 | 0 | 20 Sep 2023 | HICARE SERVICES PRIVATE LIMITED | Maintenance of Bldg Pest Control | Pest Control | Month | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Sep 2023 |  | B.C. RCC Substructure | Foreclose | MONALI CHAUDHAR | 10 Jan 2024
EAST POINT MARKET | 318 | 0 | 26 Sep 2023 | ARYAN PRINT AND SIGN | 2nd floor Media Flex Printing | Labour Charges. | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 04 Oct 2023 |  | 04 ELECTRICAL WORK | Approved | abhishek bankar
EAST POINT MARKET | 318 | 0 | 26 Sep 2023 | ARYAN PRINT AND SIGN | 2nd floor Media Flex Printing | Eco Vinyal With Foam Sheet | Sq.Ft | 15 | 90 | 1350 | 243 | 1593 | 0 | 15 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 04 Oct 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 318 | 0 | 26 Sep 2023 | ARYAN PRINT AND SIGN | 2nd floor Media Flex Printing | Printed Black Back Flex | Sq.Ft | 1120 | 16 | 17920 | 3225.6 | 21145.6 | 0 | 1120 | 17920 | 3225.6 | 21145.6 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 04 Oct 2023 |  | S OH Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 318 | 0 | 26 Sep 2023 | ARYAN PRINT AND SIGN | 2nd floor Media Flex Printing | Eco Vinyal with Lamination | Sq.Ft | 153 | 60 | 9180 | 1652.4 | 10832.4 | 0 | 153 | 9180 | 1652.4 | 10832.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 04 Oct 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 318 | 0 | 26 Sep 2023 | ARYAN PRINT AND SIGN | 2nd floor Media Flex Printing | Transport Charges | No. | 1 | 9000 | 9000 | 1620 | 10620 | 0 | 1 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 04 Oct 2023 |  | S OH Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 318 | 0 | 26 Sep 2023 | ARYAN PRINT AND SIGN | 2nd floor Media Flex Printing | Eco Vinyal with Lamination | Sq.Ft | 6 | 75 | 450 | 81 | 531 | 0 | 6 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 04 Oct 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Labour Lumpsum - BC | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Repair Work DEn | No. | 8 | 1100 | 8800 | 0 | 8800 | 2.5 | 8 | 8800 | 0 | 8800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | DEV. Entrance Gate | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Gypsum Partition. (M+L) | Sq.Ft | 140 | 140 | 19600 | 0 | 19600 | 2.5 | 140 | 19600 | 0 | 19600 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Gypsum Work (M+L) (No) | No. | 9 | 1000 | 9000 | 0 | 9000 | 2.5 | 9 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Labour Lumpsum - BC | No. | 1 | 21000 | 21000 | 0 | 21000 | 2.5 | 1 | 21000 | 0 | 21000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Gypsum Partition (M+L) | R.Ft | 35 | 90 | 3150 | 0 | 3150 | 2.5 | 35 | 3150 | 0 | 3150 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Gala Cutting | No. | 70 | 60 | 4200 | 0 | 4200 | 2.5 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Misc Work - AIE | No. | 8 | 1800 | 14400 | 0 | 14400 | 2.5 | 8 | 14400 | 0 | 14400 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Framing Work (M+L) | No. | 16 | 200 | 3200 | 0 | 3200 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 319 | 0 | 27 Sep 2023 | KHAN KAMAR ALAM | 3rd Floor Misc Gypsum & False ceiling work | Misc Work - AIE | No. | 8 | 1100 | 8800 | 0 | 8800 | 2.5 | 8 | 8800 | 0 | 8800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Oct 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 320 | 0 | 27 Sep 2023 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | AUTO / BUS / TRAIN / POLE KIOSK /BUS SHELTER / OTHER VECHICL | No. | 1000 | 110 | 110000 | 19800 | 129800 | 0 | 1000 | 110000 | 19800 | 129800 | 0 | 0 | EAST POINT MALL KURLA BRANDING THROUGH AUTO RICKSHWA QTY 1000 @ 110/- EACH FOR THE PERIOD MONTH OF SEPT. 2023 NEAR BY KURLA, DADAR, AREA | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 29 Sep 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 320 | 1 | 27 Sep 2023 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | AUTO / BUS / TRAIN / POLE KIOSK /BUS SHELTER / OTHER VECHICL | No. | 2 | 111000 | 222000 | 39960 | 261960 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | MASCOT BRANDING @ EAST POINT KURLA MARKET QTY. 2 X 3700/- EACH FOR 1 MONTHS | 0 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 29 Sep 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 1 | 142.5 | 142.5 | 25.66 | 168.16 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 1 | 142.5 | 142.5 | 25.66 | 168.16 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 8 | 95 | 760 | 136.8 | 896.8 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Canvas Connection (L) | No. | 12 | 700 | 8400 | 1512 | 9912 | 2.5 | 4 | 2800 | 504 | 3304 | 8 | 6608 |  | 33.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Removing of Twin Speed Fan 13000/20000 CFM | No. | 2 | 5775 | 11550 | 2079 | 13629 | 0 | 2 | 11550 | 2079 | 13629 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 8 | 95 | 760 | 136.8 | 896.8 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Removing of Single Speed FA fan -13000 CFM | No. | 2 | 5775 | 11550 | 2079 | 13629 | 0 | 2 | 11550 | 2079 | 13629 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 18 | 95 | 1710 | 307.8 | 2017.8 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 1 | 142.5 | 142.5 | 25.66 | 168.16 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Removing 24 Guage Ducting (L) | Sq.m. | 100 | 167 | 16700 | 3006 | 19706 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Twin Speed Tube Axial EX Fan 13000 CFM (L) | No. | 3 | 8160 | 24480 | 4406.4 | 28886.4 | 2.5 | 2 | 16320 | 2937.6 | 19257.6 | 1 | 9628.8 |  | 66.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Fabrication with Paint (L) | Kgs | 500 | 22 | 11000 | 1980 | 12980 | 2.5 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (L) | No. | 1 | 237.5 | 237.5 | 42.76 | 280.26 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Bird Mesh (L) | No. | 12 | 700 | 8400 | 1512 | 9912 | 2.5 | 3 | 2100 | 378 | 2478 | 9 | 7434 |  | 25 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 321 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Single Speed Tube Axial FA fan -13000 CFM (L) | No. | 2 | 8160 | 16320 | 2937.6 | 19257.6 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Nov 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Canvas Connection (M) | No. | 12 | 2500 | 30000 | 5400 | 35400 | 0 | 4 | 10000 | 1800 | 11800 | 8 | 23600 |  | 33.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 1 | 2722 | 2722 | 489.96 | 3211.96 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Bird Mesh (M) | No. | 12 | 1875 | 22500 | 4050 | 26550 | 0 | 3 | 5625 | 1012.5 | 6637.5 | 9 | 19912.5 |  | 25 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 1 | 2521 | 2521 | 453.78 | 2974.78 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 8 | 788.5 | 6308 | 1135.44 | 7443.44 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 1 | 1130 | 1130 | 203.4 | 1333.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 1 | 1192.25 | 1192.25 | 214.6 | 1406.85 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 18 | 714.4 | 12859.2 | 2314.66 | 15173.86 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Fabrication with Paint (M) | Kgs | 500 | 76 | 38000 | 6840 | 44840 | 0 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 322 | 0 | 02 Oct 2023 | NEPTUNE ENGINEERS PRIVATE LIMITED | Food Court- 3rd floor Fresh Air & Exhaust system FC 01-11 - | Exhaust Air Grill (M) | No. | 8 | 902.5 | 7220 | 1299.6 | 8519.6 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 323 | 0 | 03 Oct 2023 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | LEAFLET PRINTING | No. | 10000 | 1.15 | 11500 | 2070 | 13570 | 0 | 10000 | 11500 | 2070 | 13570 | 0 | 0 | EAST POINT MARKET- PROJECT SALES PROMOTION WITH LEAD GENERATION QTY. 10000 @ 1.15/- PER LEAFLET + TAX (SIZE AS A-4, 90 GSM ) | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 05 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 324 | 0 | 04 Oct 2023 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | FLEX PRINTING & MOUNTING | Sq.Ft | 512 | 150 | 76800 | 13824 | 90624 | 0 | 512 | 76800 | 13824 | 90624 | 0 | 0 |  | 100 |  | swapnil jadhav | sunita shirolkar | construction open | 05 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 324 | 0 | 04 Oct 2023 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | AGENCY FEE | No. | 1 | 7680 | 7680 | 1382.4 | 9062.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | swapnil jadhav | sunita shirolkar | construction open | 05 Oct 2023 |  | No category | Approved | sunita shirolkar
EAST POINT MARKET | 325 | 0 | 04 Oct 2023 | GOOD OLD DELIGHT | Media BRANDING | Radio / Television Spot | No. | 1 | 624000 | 624000 | 112320 | 736320 | 0 | 1 | 624000 | 112320 | 736320 | 0 | 0 | EAST POINT MARKET PROJECT SALES PROMOTION, BRANDING , LEAD GENERATION ETC. AIR FREQUENCY RADIO CAMPAIGN THROUGH FEVER 104 FM & BIG 92.7 FM TOTAL 4800 SPOT (20 SEC. EACH SPOT) FOR 12 FREQENTLY DAYS. | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 04 Oct 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 325 | 1 | 04 Oct 2023 | GOOD OLD DELIGHT | Media BRANDING | EXECUTION / MONETORING / MANAGEMENT CHARGES - FEES | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 9000 | 59000 | 0 | 0 | EAST POINT MARKET RADIO CAMPAIGN - SUPERVISON / MONITORING CHARGES RS. 50000/- + TAX | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 04 Oct 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 326 | 0 | 05 Oct 2023 | SHIVAM INTERIOR HUB | KEP-2nd Floor Sample shop aerocon panel removing | Aerocon Partition wall removing- Mkt | Sq.Ft | 681.144 | 25 | 17028.6 | 0 | 17028.6 | 0 | 681.144 | 17028.6 | 3065.14 | 20093.74 | 0 | -3065.14 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 09 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 327 | 0 | 06 Oct 2023 | SHIVAM INTERIOR HUB | KEP-3rd Floor Old Aerocon Panel Removing and shifting | Aerocon Panel Installation | Sq.Ft | 336 | 50 | 16800 | 3024 | 19824 | 2.5 | 336 | 16800 | 3024 | 19824 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Oct 2023 |  | 12 MASONARY WORK | Approved | Swapnil Erande
EAST POINT MARKET | 327 | 0 | 06 Oct 2023 | SHIVAM INTERIOR HUB | KEP-3rd Floor Old Aerocon Panel Removing and shifting | Panel Removing work | Sq.Ft | 210 | 25 | 5250 | 945 | 6195 | 0 | 210 | 5250 | 945 | 6195 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 328 | 0 | 07 Oct 2023 | SATISH RAMCHANDRA JAGTAP | LPG Gas for Gas Bank | Gas Batla | No. | 20 | 1640 | 32800 | 0 | 32800 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 328 | 0 | 07 Oct 2023 | SATISH RAMCHANDRA JAGTAP | LPG Gas for Gas Bank | Gas Batla Deposite | No. | 20 | 2400 | 48000 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 328 | 0 | 07 Oct 2023 | SATISH RAMCHANDRA JAGTAP | LPG Gas for Gas Bank | Registration Charges | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 329 | 0 | 10 Oct 2023 | WHATSTHIS STUDIOS PRIVATE LIMITED | Consultancy Lighting Design Services | Professional Fees. | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Charges for Professional Lighting Design Services. | 0 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 13 Oct 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Mirror Paneling in Ply & finish with mirror | SITC of Partition | Sq.Ft | 80 | 752 | 60160 | 10828.8 | 70988.8 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Housekeeping Storage | SITC of Storage 16" Depth | Sq.Ft | 88 | 1269 | 111672 | 20100.96 | 131772.96 | 2.5 | 81 | 102789 | 18502.02 | 121291.02 | 7 | 10481.94 |  | 92.0455 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Housekeeping Office | SITC of Table 30" Depth | Sq.Ft | 13.75 | 1598 | 21972.5 | 3955.06 | 25927.56 | 2.5 | 12.3905 | 19800.02 | 3564 | 23364.02 | 1.3595 | 2563.54 |  | 90.1127 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Office | Glass Frosted (M+L) | Sq.Ft | 50 | 173.9 | 8695 | 1565.1 | 10260.1 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor DB Storage | SITC of DB Storage 14" Depth | Sq.Ft | 36 | 1269 | 45684 | 8223.12 | 53907.12 | 2.5 | 27.5 | 34897.5 | 6281.56 | 41179.06 | 8.5 | 12728.06 |  | 76.3889 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Housekeeping Office | SITC of Storage 16" Depth | Sq.Ft | 68.89 | 1269 | 87421.41 | 15735.86 | 103157.27 | 2.5 | 0 | 0 | 0 | 0 | 68.89 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Food Court Storage | SITC of Overhead storage 30" Depth | Sq.Ft | 114.8 | 1692 | 194241.6 | 34963.48 | 229205.08 | 2.5 | 0 | 0 | 0 | 0 | 114.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Fire Duct Paneling | Fire Duct Panelling (M+L) | Sq.Ft | 105.6 | 799 | 84374.4 | 15187.4 | 99561.8 | 2.5 | 103 | 82297 | 14813.46 | 97110.46 | 2.6 | 2451.34 |  | 97.5379 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Security Cabin (Locker+mirror+Door+Partition) | SITC of Locker storage 12" Depth | Sq.Ft | 49 | 1692 | 82908 | 14923.44 | 97831.44 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Mirror Paneling in Ply & finish with mirror | SITC of Partition | Sq.Ft | 70 | 752 | 52640 | 9475.2 | 62115.2 | 2.5 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Janitor Room (Open Racks) | SITC of Open Rack 17" Depth | Sq.Ft | 28 | 1269 | 35532 | 6395.76 | 41927.76 | 2.5 | 0 | 0 | 0 | 0 | 28 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Mirror Paneling in Ply & finish with mirror | SITC of Room Doors | Sq.Ft | 1 | 11938 | 11938 | 2148.84 | 14086.84 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Control Room | SITC of Table 30" Depth | Sq.Ft | 25.2 | 1560.4 | 39322.08 | 7077.98 | 46400.06 | 2.5 | 0 | 0 | 0 | 0 | 25.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor DB Storage | SITC of DB Storage 24" Depth | Sq.Ft | 12 | 1739 | 20868 | 3756.24 | 24624.24 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Food Court Storage | SITC of Storage 3" Depth | Sq.Ft | 90 | 2256 | 203040 | 36547.2 | 239587.2 | 2.5 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Mirror Paneling in Ply & finish with mirror | Mirror Panelling (M+L) | Sq.Ft | 40 | 611 | 24440 | 4399.2 | 28839.2 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Mirror Paneling in Ply & finish with mirror | SITC of Room Doors | Sq.Ft | 2 | 11938 | 23876 | 4297.68 | 28173.68 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 330 | 0 | 10 Oct 2023 | ANAND FURNITURE AND INTERIOR | KEP-3rd Floor Mirror Paneling in Ply & finish with mirror | Mirror Panelling (M+L) | Sq.Ft | 20 | 611 | 12220 | 2199.6 | 14419.6 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 331 | 1 | 12 Oct 2023 | DREAMTREE EXPERIENCE | Media BRANDING | SIGNAGES / SIGN BOARD / DROPDOWN / LED BOARDS | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 | EAST POINT MARKET KURLA - 3RD FLOOR FOOD COURT INTERNAL BRANDING WITH SIGNAGES WORK WITH ACP SHEETS. | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 13 Oct 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 331 | 0 | 12 Oct 2023 | DREAMTREE EXPERIENCE | Media BRANDING | SIGNAGES / SIGN BOARD / DROPDOWN / LED BOARDS | No. | 1 | 403950 | 403950 | 72711 | 476661 | 0 | 1 | 403950 | 72711 | 476661 | 0 | 0 | EAST POINT MARKET KURLA - 3RD FLOOR FOOD COURT INTERNAL BRANDING WITH SIGNAGES WORK WITH ACP SHEETS. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 13 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 332 | 0 | 14 Oct 2023 | PRAJAPATI INTERIOR | KEP-2nd Floor Dept labour for Cleaning & material shifting | Departmental Labour- BC | No. | 28 | 800 | 22400 | 0 | 22400 | 0 | 28 | 22400 | 0 | 22400 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 21 Oct 2023 |  | B.C. Rework/Extrawork | Approved | abhishek bankar
EAST POINT MARKET | 333 | 0 | 14 Oct 2023 | PRAJAPATI INTERIOR | KEP-4th Floor Dept labour for Carpentry & Cleaning work | Department Labour- BC | No. | 23 | 800 | 18400 | 0 | 18400 | 2.5 | 7 | 5600 | 0 | 5600 | 16 | 12800 |  | 30.4348 |  | abhishek bankar | abhishek bankar | construction open | 21 Oct 2023 |  | B.C. RCC Substructure | Approved | abhishek bankar
EAST POINT MARKET | 333 | 0 | 14 Oct 2023 | PRAJAPATI INTERIOR | KEP-4th Floor Dept labour for Carpentry & Cleaning work | Carpenter- BC | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 21 Oct 2023 |  | B.C. RCC Superstructure | Approved | abhishek bankar
EAST POINT MARKET | 334 | 0 | 14 Oct 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | KEP-2nd Floor Dept Labour for Tile repairing work | Departmental Labour- BC | No. | 24 | 2200 | 52800 | 9504 | 62304 | 2.5 | 24 | 52800 | 0 | 52800 | 0 | 9504 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 21 Oct 2023 |  | B.C. Rework/Extrawork | Approved | abhishek bankar
EAST POINT MARKET | 334 | 1 | 14 Oct 2023 | ARVIND KUMAR SINGH KALAPNATH SINGH | Departmental Labour & Mason for Repair Work | Labour Lumpsum | No. | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 | 5 x 2200= 11000 (2200 Rs/- Per Jodi) | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Oct 2023 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 335 | 0 | 16 Oct 2023 | ANUBHAV GOEL | Media Digital Campaining (2nd & 4th Floor) | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 18 Oct 2023 |  | MKT. Media | Cancelled | abhishek bankar | 19 Oct 2023
EAST POINT MARKET | 335 | 0 | 16 Oct 2023 | ANUBHAV GOEL | Media Digital Campaining (2nd & 4th Floor) | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 50 | 800 | 40000 | 0 | 40000 | 0 | 50 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 18 Oct 2023 |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 336 | 0 | 16 Oct 2023 | POWAI BENGALI WELFARE ASSOCIATION | Media Digital Campaining (2nd & 4th Floor) | OUTDOOR DISPLAY BRANDING | No. | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 16 Oct 2023 |  | MKT. Media | Cancelled | abhishek bankar | 16 Oct 2023
EAST POINT MARKET | 336 | 0 | 16 Oct 2023 | POWAI BENGALI WELFARE ASSOCIATION | Media Digital Campaining (2nd & 4th Floor) | OUTDOOR DISPLAY BRANDING | No. | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 16 Oct 2023 |  | MKT. Media | Cancelled | abhishek bankar | 16 Oct 2023
EAST POINT MARKET | 337 | 0 | 16 Oct 2023 | POWAI BENGALI WELFARE ASSOCIATION | Media Digital Campaining (2nd & 4th Floor) | OUTDOOR DISPLAY BRANDING | No. | 1 | 125000 | 125000 | 22500 | 147500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 16 Oct 2023 |  | MKT. Media | Approved | abhishek bankar | 17 Oct 2023
EAST POINT MARKET | 338 | 0 | 16 Oct 2023 | DREAMTREE EXPERIENCE | Media BRANDING | Event Expenses | No. | 1 | 234500 | 234500 | 42210 | 276710 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 16 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 339 | 0 | 16 Oct 2023 | DREAMTREE EXPERIENCE | Media BRANDING | Event Expenses | No. | 1 | 189000 | 189000 | 34020 | 223020 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1) CUTOUT OF CRICKETERS 2) WORLD CUP 3) TRANSPORT + GTS | 0 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 18 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 340 | 0 | 16 Oct 2023 | TAJ SERVICES | Media BRANDING | STAND (WWODEN / METALIC / M S STAND ETC/ ACRYLIC ETC.) | No. | 1 | 10500 | 10500 | 0 | 10500 | 0 | 1 | 10500 | 0 | 10500 | 0 | 0 |  | 100 |  | SWAPNIL JADHAV | TEJAS RAVERKAR | construction open | 16 Oct 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 17 Oct 2023
EAST POINT MARKET | 341 | 0 | 16 Oct 2023 | DREAMTREE EXPERIENCE | Media BRANDING | Event Expenses | No. | 1 | 103900 | 103900 | 18702 | 122602 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 18 Oct 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 25 Oct 2023
EAST POINT MARKET | 342 | 0 | 17 Oct 2023 | DREAMTREE EXPERIENCE | Media BRANDING | Event Expenses | No. | 1 | 603000 | 603000 | 108540 | 711540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1)P3 LED SCREEN 8x12 FT QTY 1 NOS @ 17000/- RS PER DAY FOR 34 DAYS FROM 17TH OCT 23 TO 19TH NOV 23 2) RAISER & FULL STEUP 25000/-RS FOR 34 DAYS FROM 17TH OCT 23 TO 19TH NOV 23 | 0 |  | SWAPNIL JADHAV | TEJAS RAVERKAR | construction open | 17 Oct 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR
EAST POINT MARKET | 343 | 0 | 17 Oct 2023 | VED ENGINEERS AND CONTRACTORS | Ved Engineers and cont. Fire Blanket | Fire Blanket 2 x 1meter | No. | 10 | 600 | 6000 | 1080 | 7080 | 0 | 10 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 344 | 0 | 26 Oct 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153575159 | KEP.3rd Fl Electricity Meter | Service connection charges | No. | 1 | 14500 | 14500 | 2610 | 17110 | 0 | 1 | 14500 | 2610 | 17110 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 27 Oct 2023
EAST POINT MARKET | 344 | 0 | 26 Oct 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153575159 | KEP.3rd Fl Electricity Meter | Security Deposit | No. | 1 | 12000 | 12000 | 0 | 12000 | 0 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 27 Oct 2023
EAST POINT MARKET | 344 | 0 | 26 Oct 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153575159 | KEP.3rd Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 135 | 135 | 24.3 | 159.3 | 0 | 1 | 135 | 24.3 | 159.3 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 27 Oct 2023
EAST POINT MARKET | 345 | 0 | 26 Oct 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153574747 | KEP.3rd Fl Electricity Meter | Service connection charges | No. | 1 | 14500 | 14500 | 2610 | 17110 | 0 | 1 | 14500 | 2610 | 17110 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 27 Oct 2023
EAST POINT MARKET | 345 | 0 | 26 Oct 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153574747 | KEP.3rd Fl Electricity Meter | Applction, Regn & Processing charges | No. | 1 | 135 | 135 | 24.3 | 159.3 | 0 | 1 | 135 | 24.3 | 159.3 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 27 Oct 2023
EAST POINT MARKET | 345 | 0 | 26 Oct 2023 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 153574747 | KEP.3rd Fl Electricity Meter | Security Deposit | No. | 1 | 12000 | 12000 | 0 | 12000 | 0 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | 04 ELECTRICAL WORK | Approved | DUSHANT.GORE | 27 Oct 2023
EAST POINT MARKET | 346 | 0 | 10 Nov 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Meter room No.5 Ms work | M.S. Work (L)- BC | Sq.Ft | 288 | 30 | 8640 | 1555.2 | 10195.2 | 2.5 | 288 | 8640 | 1555.2 | 10195.2 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 28 Nov 2023 |  | B.C. Internal Finishing Itmes | Approved | abhishek bankar
EAST POINT MARKET | 346 | 0 | 10 Nov 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Meter room No.5 Ms work | M.S. Angle (M+L) - UTI | Kgs | 32.85 | 90 | 2956.5 | 532.18 | 3488.68 | 2.5 | 32.85 | 2956.5 | 532.18 | 3488.68 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 28 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | abhishek bankar
EAST POINT MARKET | 346 | 1 | 10 Nov 2023 | ANAND ROLLING SHUTTER & FABRICATOR | 3rd Floor MS Stand making for Exhaust Fan | Labour Lumpsum | No. | 1 | 9500 | 9500 | 1710 | 11210 | 0 | 1 | 9500 | 1710 | 11210 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Nov 2023 |  | DEV. Ext Development | Approved | Swapnil Erande
EAST POINT MARKET | 346 | 0 | 10 Nov 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Meter room No.5 Ms work | M.S. Work (L) - BC | Kgs | 492.903 | 25 | 12322.58 | 2218.06 | 14540.64 | 2.5 | 492.903 | 12322.58 | 2218.06 | 14540.64 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 28 Nov 2023 |  | B.C. Internal Finishing Itmes | Approved | abhishek bankar
EAST POINT MARKET | 346 | 0 | 10 Nov 2023 | ANAND ROLLING SHUTTER & FABRICATOR | KEP-Gr Floor Meter room No.5 Ms work | M.S. Plate (M+L)-Mkt | Kgs | 36 | 105 | 3780 | 680.4 | 4460.4 | 2.5 | 36 | 3780 | 680.4 | 4460.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 28 Nov 2023 |  | MKT. Marketing Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 347 | 0 | 22 Nov 2023 | TAMANNA ENTERPRISES | KEP-3rd FL Gypsum Plaster On Wall (M) | Gypsum on Wall (M) | Sq.Ft | 6888.32 | 8.5 | 58550.72 | 0 | 58550.72 | 0 | 4033.5294 | 34285 | 0 | 34285 | 2854.7906 | 24265.72 |  | 58.5561 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 05 GYPSUM & PLASTER | Approved | DUSHANT.GORE
EAST POINT MARKET | 347 | 0 | 22 Nov 2023 | TAMANNA ENTERPRISES | KEP-1st FL Gypsum Plaster On Wall (M) | Gypsum on Wall (M) | Sq.Ft | 6323.01 | 8.5 | 53745.59 | 0 | 53745.59 | 0 | 0 | 0 | 0 | 0 | 6323.01 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 05 GYPSUM & PLASTER | Approved | DUSHANT.GORE
EAST POINT MARKET | 348 | 0 | 16 Dec 2023 | VIJAY KUMAR (STAFF) | Admin / IT Indirect expenses | Installation Charges | No. | 1 | 8000 | 8000 | 0 | 8000 | 0 | 1 | 8000 | 0 | 8000 | 0 | 0 | Tara Kahanes office DELL Laptop need to replace Battery & Windows 10 Installation | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 349 | 2 | 16 Dec 2023 | CROWN OUTDOOR MEDIA | Media BRANDING | Hoarding display charges | No. | 3 | 80000 | 240000 | 43200 | 283200 | 0 | 3 | 239997.33 | 43199.72 | 283197.05 | 0 | 2.95 | KURLA MIDDLE FOB 8X3 | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 16 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 349 | 0 | 16 Dec 2023 | CROWN OUTDOOR MEDIA | Media BRANDING | Hoarding display charges | No. | 3 | 200000 | 600000 | 108000 | 708000 | 0 | 3 | 599993.33 | 107999.28 | 707992.61 | 0 | 7.39 | 4X3 -40 DISPLAY KURLA FOB LIT 2,00,000/-RS PER MONTH + TAX | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 16 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 349 | 5 | 16 Dec 2023 | CROWN OUTDOOR MEDIA | Media BRANDING | Hoarding display charges | No. | 3 | 66666.5 | 199999.5 | 35999.92 | 235999.42 | 0 | 1 | 66666.43 | 11999.96 | 78666.39 | 2 | 157333.03 | KURLA MIDDLE FOB 8 X 3 QTY 10 NOS | 33.3333 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 16 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 349 | 1 | 16 Dec 2023 | CROWN OUTDOOR MEDIA | Media BRANDING | Hoarding display charges | No. | 3 | 20000 | 60000 | 10800 | 70800 | 0 | 3 | 59999.33 | 10799.92 | 70799.25 | 0 | 0.75 | 15X6B -1 NOS KURLA FO LIT | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 16 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 349 | 4 | 16 Dec 2023 | CROWN OUTDOOR MEDIA | Media BRANDING | Hoarding display charges | No. | 3 | 16666.68 | 50000.03 | 9000 | 59000.03 | 0 | 1 | 16666.67 | 3000 | 19666.67 | 2 | 39333.35 | 15 x 6 - QTY 1 NOS KURLA FO LIT | 33.3333 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 16 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 349 | 3 | 16 Dec 2023 | CROWN OUTDOOR MEDIA | Media BRANDING | Hoarding display charges | No. | 3 | 166666.68 | 500000.03 | 90000 | 590000.03 | 0 | 1 | 166666.51 | 29999.88 | 196666.39 | 2 | 393333.64 | 4 X 3 - QTY 40 DISPLAY KURLA FOB LIT 166666.675 /-RS PER MONTH. | 33.3333 |  | Swapnil Jadhav | SWAPNIL JADHAV | construction open | 16 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 351 | 2 | 18 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Print on Vinyal Sticker | Sq.Ft | 605 | 55 | 33275 | 5989.5 | 39264.5 | 0 | 605 | 33275 | 5989.5 | 39264.5 | 0 | 0 | PRINT ON VINY | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 18 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 351 | 1 | 18 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Eco Vinyal With Foam Sheet | Sq.Ft | 1248 | 90 | 112320 | 20217.6 | 132537.6 | 0 | 1248 | 112320 | 20217.6 | 132537.6 | 0 | 0 | PRINT ON 5MM SUNBOARD | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 18 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 351 | 0 | 18 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Star Flex | Sq.Ft | 3975 | 19 | 75525 | 13594.5 | 89119.5 | 0 | 3969.5789 | 75422 | 13575.96 | 88997.96 | 5.4211 | 121.54 | FLEX | 99.8636 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 18 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 351 | 3 | 18 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Transport Charges- Med. | No. | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 | TRANSPORT CHARGES | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 18 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 352 | 0 | 19 Dec 2023 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | LEAFLET PRINTING | No. | 10000 | 0.78 | 7800 | 1404 | 9204 | 0 | 10000 | 7800 | 1404 | 9204 | 0 | 0 | LEAFLET PRINTING A-4 90GSM | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 19 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 352 | 1 | 19 Dec 2023 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | Event Expenses | No. | 1 | 45000 | 45000 | 8100 | 53100 | 0 | 1 | 45000 | 8100 | 53100 | 0 | 0 | BMC CHARGES FOR PERMISSION | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 19 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 352 | 1 | 19 Dec 2023 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | AUTO / BUS / TRAIN / POLE KIOSK /BUS SHELTER / OTHER VECHICL | No. | 3 | 45000 | 135000 | 24300 | 159300 | 0 | 3 | 135000 | 24300 | 159300 | 0 | 0 | TRICYCLE BRANDING FOR EPM | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 19 Dec 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 353 | 0 | 20 Dec 2023 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | Media BRANDING | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 2 | 50000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | FACEBOOK CAMPAING BOOST | 0 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 20 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 354 | 0 | 26 Dec 2023 | ARYAN PRINT AND SIGN | Flex Printing & Pasting | Transportation | No. | 1 | 9000 | 9000 | 1620 | 10620 | 0 | 1 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 30 Dec 2023 |  | DEV. Ext Development | Approved | abhishek bankar
EAST POINT MARKET | 354 | 0 | 26 Dec 2023 | ARYAN PRINT AND SIGN | Flex Printing & Pasting | Printed Black Back Flex | Sq.Ft | 1028 | 16 | 16448 | 2960.64 | 19408.64 | 0 | 1028 | 16448 | 2960.64 | 19408.64 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 30 Dec 2023 |  | S OH Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 354 | 0 | 26 Dec 2023 | ARYAN PRINT AND SIGN | Flex Printing & Pasting | Gray Black Vinyl | Sq.Ft | 3 | 60 | 180 | 32.4 | 212.4 | 0 | 3 | 180 | 32.4 | 212.4 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 30 Dec 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 354 | 0 | 26 Dec 2023 | ARYAN PRINT AND SIGN | Flex Printing & Pasting | Labour Charges. | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 30 Dec 2023 |  | 04 ELECTRICAL WORK | Approved | abhishek bankar
EAST POINT MARKET | 354 | 0 | 26 Dec 2023 | ARYAN PRINT AND SIGN | Flex Printing & Pasting | Printed Eco-Vinyl + Matt | Sq.Ft | 6 | 60 | 360 | 64.8 | 424.8 | 0 | 6 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open | 30 Dec 2023 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 355 | 0 | 26 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Transport Charges- Med. | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | TRANSPORT | 0 |  | SWAPNIL JADHAV |  | construction open | 26 Dec 2023 |  | MKT. Media | Un-Approved
EAST POINT MARKET | 355 | 0 | 26 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Flex Printing & Pasting | Sq.Ft | 3000 | 19 | 57000 | 10260 | 67260 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | FLEX PRINTING + PASTING | 0 |  | SWAPNIL JADHAV |  | construction open | 26 Dec 2023 |  | MKT. Media | Un-Approved
EAST POINT MARKET | 355 | 0 | 26 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Print on Vinyal Sticker | Sq.Ft | 1200 | 55 | 66000 | 11880 | 77880 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | VENYL | 0 |  | SWAPNIL JADHAV |  | construction open | 26 Dec 2023 |  | MKT. Media | Un-Approved
EAST POINT MARKET | 355 | 0 | 26 Dec 2023 | N.V GRAPHICS & ADVERTISING PVT LTD | Media FLEX PRINTING & MOUNTING | Eco Vinyal With Foam Sheet | Sq.Ft | 1000 | 90 | 90000 | 16200 | 106200 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | VINYAL + FOAM SHEET | 0 |  | SWAPNIL JADHAV |  | construction open | 26 Dec 2023 |  | MKT. Media | Un-Approved
EAST POINT MARKET | 356 | 0 | 09 Jan 2024 | AJINKYA RAMESH TEKALE | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.8654 | 4327 | 0 | 4327 | 0.1346 | 673 |  | 86.54 |  | abhishek bankar | abhishek bankar | construction open | 29 Jan 2024 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 356 | 0 | 09 Jan 2024 | AJINKYA RAMESH TEKALE | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.811 | 4055 | 0 | 4055 | 0.189 | 945 |  | 81.1 |  | abhishek bankar | abhishek bankar | construction open | 29 Jan 2024 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 356 | 0 | 09 Jan 2024 | AJINKYA RAMESH TEKALE | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.9924 | 4962 | 0 | 4962 | 0.0076 | 38 |  | 99.24 |  | abhishek bankar | abhishek bankar | construction open | 29 Jan 2024 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 356 | 0 | 09 Jan 2024 | AJINKYA RAMESH TEKALE | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.8644 | 4322 | 0 | 4322 | 0.1356 | 678 |  | 86.44 |  | abhishek bankar | abhishek bankar | construction open | 29 Jan 2024 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 356 | 0 | 09 Jan 2024 | AJINKYA RAMESH TEKALE | Site Expenses PETTY CASH | Miscellaneous Expenses | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.9832 | 4916 | 0 | 4916 | 0.0168 | 84 |  | 98.32 |  | abhishek bankar | abhishek bankar | construction open | 29 Jan 2024 |  | 14 MISC WORK | Approved | abhishek bankar
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | P3 Outdoor LED Screen | Sq.Ft | 0 | 653832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jan 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jan 2024
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | P3 Outdoor LED Screen | Sq.Ft | 90.81 | 7000 | 635670 | 114420.6 | 750090.6 | 0 | 90.81 | 635670 | 114420.6 | 750090.6 | 0 | 0 | Size- 11.54 ft x 7.87ft = 90.81 sqft. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jan 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | Installation Charges | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jan 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | Fabrication Work | Sq.Ft | 1 | 28000 | 28000 | 5040 | 33040 | 0 | 1 | 28000 | 5040 | 33040 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jan 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | Fabrication Work | Sq.Ft | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jan 2024 |  | B.C. Rework/Extrawork | Cancelled | ADITYA.CHOUGULE | 20 Jan 2024
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | Controller | No. | 1 | 18000 | 18000 | 3240 | 21240 | 0 | 1 | 18000 | 3240 | 21240 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jan 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 357 | 0 | 20 Jan 2024 | VISHWANJALI TECHNOLOGY PVT LTD | Outdoor LED Screen | Transportation Charges-SO | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jan 2024 |  | S OH Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 358 | 0 | 24 Jan 2024 | SHREEJI INTERNATIONAL | Media BRANDING | T SHIRT / BAGS / PENS / DRESS - BRANDING | No. | 36 | 525 | 18900 | 945 | 19845 | 0 | 36 | 18900 | 945 | 19845 | 0 | 0 | T-SHIRT FOR REPUBLIC DAY EVENT ON 3RD FLOOR FOOD COURT BRANDING | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 01 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 359 | 0 | 25 Jan 2024 | SAHARA ENGINEERING | Rework Extrawork Glass Removing & ACP Work for Haldiram | Labour Lumpsum - Mkt | No. | 1 | 15000 | 15000 | 2700 | 17700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Feb 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of 5 pin Indu.Plug & Socket | Outgoing-32A,TP,MCBs-1No (M) | No. | 3 | 885.32 | 2655.96 | 478.08 | 3134.04 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Make-Legrand | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5 Core 120 sq.mm Aluminium Armoured cable (M) | Mtrs | 150 | 637.66 | 95649 | 17216.82 | 112865.82 | 0 | 120 | 76519.2 | 13773.46 | 90292.66 | 30 | 22573.16 | Make-Polycab / KEI | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Distribution Boards & MCB's | I/C 25A DP MCB(M) | No. | 5 | 565.34 | 2826.7 | 508.8 | 3335.5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Make-Legrand | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Distribution Boards & MCB's | O/P 16A SP MCB (M) | No. | 30 | 234 | 7020 | 1263.6 | 8283.6 | 0 | 3 | 702 | 126.36 | 828.36 | 27 | 7455.24 | Make-Legrand | 10 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Casing Ptti 38/25 (M) | Mtrs | 100 | 35.69 | 3569 | 642.42 | 4211.42 | 0 | 16 | 571.04 | 102.78 | 673.82 | 84 | 3537.6 |  | 16 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of cable tray without powde | 300 mm without powder coated.(M) | Mtrs | 20 | 754.98 | 15099.6 | 2717.92 | 17817.52 | 0 | 20 | 15099.6 | 2717.92 | 17817.52 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 63A FP MCB (M) | No. | 1 | 1651 | 1651 | 297.18 | 1948.18 | 0 | 1 | 1651 | 297.18 | 1948.18 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 3 Module Plate (M) | No. | 25 | 117 | 2925 | 526.5 | 3451.5 | 0 | 4 | 468 | 84.24 | 552.24 | 21 | 2899.26 |  | 16 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 50 sqmm Copper Lead (M) | No. | 12 | 541.77 | 6501.24 | 1170.22 | 7671.46 | 0 | 9 | 4875.93 | 877.66 | 5753.59 | 3 | 1917.87 |  | 75 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Holder | No. | 5 | 29.25 | 146.25 | 26.32 | 172.57 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 40A FP MCB Enclosure (M) | No. | 20 | 427 | 8540 | 1537.2 | 10077.2 | 0 | 20 | 8540 | 1537.2 | 10077.2 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Point Wiring FRLS Wires | 2.5 sqmm Cu wire (M) | Mtrs | 1500 | 28.92 | 43380 | 7808.4 | 51188.4 | 0 | 450 | 13014 | 2342.52 | 15356.52 | 1050 | 35831.88 | Make-Polycab / KEI | 30 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | SITC 63A FP MCB with incloser (M) | No. | 1 | 427 | 427 | 76.86 | 503.86 | 0 | 1 | 427 | 76.86 | 503.86 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Fan Hook (M) | No. | 5 | 58.5 | 292.5 | 52.66 | 345.16 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 4 Sq.mm Lead Cable Termination (M) | No. | 100 | 24.63 | 2463 | 443.34 | 2906.34 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Make-Dowells/ Cosmos | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 20 Amp Switch (M) | No. | 25 | 194 | 4850 | 873 | 5723 | 0 | 22 | 4268 | 768.24 | 5036.24 | 3 | 686.76 |  | 88 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Supply of Bend | No. | 20 | 8.19 | 163.8 | 29.48 | 193.28 | 0 | 20 | 163.8 | 29.48 | 193.28 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5C x 185 Sq.mm Aluminium Armoured Cable (M) | Mtrs | 214 | 947.62 | 202790.68 | 36502.32 | 239293 | 0 | 210 | 199000.2 | 35820.04 | 234820.24 | 4 | 4472.76 | Make-Polycab / KEI | 98.1308 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 2 Module Plate (M) | No. | 1 | 108 | 108 | 19.44 | 127.44 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work LED Panel Light -15W | LED panel Light-15W (Round)-3000K (M) | No. | 30 | 1093.95 | 32818.5 | 5907.34 | 38725.84 | 0 | 30 | 32818.5 | 5907.34 | 38725.84 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 2 Module Box (M) | No. | 1 | 78 | 78 | 14.04 | 92.04 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 125A FP MCB (M) | No. | 1 | 5803 | 5803 | 1044.54 | 6847.54 | 0 | 1 | 5803 | 1044.54 | 6847.54 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | 25mm Dia PVC MMS Conduit | Mtrs | 1000 | 23.4 | 23400 | 4212 | 27612 | 0 | 461.5 | 10799.1 | 1943.84 | 12742.94 | 538.5 | 14869.06 |  | 46.15 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Lf-Led Recessed downlight | Lf-Led Recessed downlight 12W-3000K (M) | No. | 30 | 1093.95 | 32818.5 | 5907.34 | 38725.84 | 0 | 30 | 32818.5 | 5907.34 | 38725.84 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5C x 95 Sq.mm Alu Armoured Cable Termination (M) | No. | 2 | 1470.64 | 2941.28 | 529.44 | 3470.72 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Make-Dowells/ Cosmos. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | 20 & 25mm Flexible Pipe (M) | Mtrs | 50 | 9.36 | 468 | 84.24 | 552.24 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box 3 Way (M) | No. | 15 | 20.18 | 302.7 | 54.48 | 357.18 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 50 Sq.mm Lead Cable Termination (M) | No. | 2 | 296.65 | 593.3 | 106.8 | 700.1 | 0 | 2 | 593.3 | 106.8 | 700.1 | 0 | 0 | Make-Dowells/ Cosmos | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | Blank Plate (M) | No. | 200 | 28 | 5600 | 1008 | 6608 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 6 Module Plate (M) | No. | 10 | 241 | 2410 | 433.8 | 2843.8 | 0 | 7 | 1687 | 303.66 | 1990.66 | 3 | 853.14 |  | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3C x 6 Sq.mm Copper Armoured Cable (M) | Mtrs | 530 | 264.5 | 140185 | 25233.3 | 165418.3 | 0 | 450 | 119025 | 21424.5 | 140449.5 | 80 | 24968.8 | Make-Polycab / KEI | 84.9057 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5 Core 35 sq.mm Termination Alu. Arm. cable (M) | No. | 6 | 718.05 | 4308.3 | 775.5 | 5083.8 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Make-Polycab / KEI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box 4 Way (M) | No. | 30 | 22.23 | 666.9 | 120.04 | 786.94 | 0 | 30 | 666.9 | 120.04 | 786.94 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 6 Sq.mm Lead Cable (M) | Mtrs | 800 | 63.41 | 50728 | 9131.04 | 59859.04 | 0 | 254 | 16106.14 | 2899.1 | 19005.24 | 546 | 40853.8 |  | 31.75 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Rubber Mats | Rubber Mats (M) | Sq.m. | 50 | 1474 | 73700 | 13266 | 86966 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 125A FP MCB Enclosure (M) | No. | 1 | 2430 | 2430 | 437.4 | 2867.4 | 0 | 1 | 2430 | 437.4 | 2867.4 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3C x 6 sqmm 2XWY Cable End Termination (M) | No. | 23 | 444.51 | 10223.73 | 1840.28 | 12064.01 | 0 | 8 | 3556.08 | 640.1 | 4196.18 | 15 | 7867.83 | Make-Polycab / KEI | 34.7826 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 4 Sq.mm Lead Cable (M) | Mtrs | 500 | 42.54 | 21270 | 3828.6 | 25098.6 | 0 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 3 Module Box (M) | No. | 25 | 78 | 1950 | 351 | 2301 | 0 | 4 | 312 | 56.16 | 368.16 | 21 | 1932.84 |  | 16 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4 Core 6 sq.mm Copper Armoured cable (M) | Mtrs | 700 | 341.13 | 238791 | 42982.38 | 281773.38 | 0 | 402 | 137134.26 | 24684.16 | 161818.42 | 298 | 119954.96 | Make-Polycab / KEI | 57.4286 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 10 sqmm Copper Lead (M) | No. | 0 | 110.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Ceiling Rose (M) | No. | 0 | 12.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box 4 Way (M) | No. | 0 | 24.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | 25mm Dia PVC MMS Conduit | Mtrs | 0 | 25.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 6 Sq.mm Lead Cable Termination (M) | No. | 50 | 24.63 | 1231.5 | 221.68 | 1453.18 | 0 | 50 | 1231.5 | 221.68 | 1453.18 | 0 | 0 | Make-Dowells/ Cosmos | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | 20 & 25mm Flexible Pipe (M) | Mtrs | 0 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of cable tray without powde | 450 mm without powder coated.(M) | Mtrs | 80 | 836.28 | 66902.4 | 12042.44 | 78944.84 | 0 | 80 | 66902.4 | 12042.44 | 78944.84 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5 Core 70 sq.mm Aluminium Armoured cable (M) | Mtrs | 100 | 415.58 | 41558 | 7480.44 | 49038.44 | 0 | 90 | 37402.2 | 6732.4 | 44134.6 | 10 | 4903.84 | Make-Polycab / KEI | 90 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 12 Module Plate (M) | No. | 1 | 392 | 392 | 70.56 | 462.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box 3 Way (M) | No. | 0 | 22.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of cable tray without powde | 45 x 25 mm PVC Trunking (M) | Mtrs | 150 | 140.4 | 21060 | 3790.8 | 24850.8 | 0 | 40 | 5616 | 1010.88 | 6626.88 | 110 | 18223.92 |  | 26.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5 Core 70 sq.mm Termination Alu. Arm. cable (M) | No. | 2 | 1263.6 | 2527.2 | 454.9 | 2982.1 | 0 | 2 | 2527.2 | 454.9 | 2982.1 | 0 | 0 | Make-Polycab / KEI | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4C x 16 Sq.mm Copper Armoured Cable (M) | Mtrs | 155 | 818.18 | 126817.9 | 22827.22 | 149645.12 | 0 | 73 | 59727.14 | 10750.88 | 70478.02 | 82 | 79167.1 | Make-Polycab / KEI | 47.0968 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 70 sqmm Copper Lead (M) | No. | 20 | 751.02 | 15020.4 | 2703.68 | 17724.08 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Point Wiring FRLS Wires | 1.5 sqmm Cu wire (M) | Mtrs | 2000 | 17.8 | 35600 | 6408 | 42008 | 0 | 1062 | 18903.6 | 3402.64 | 22306.24 | 938 | 19701.76 | Make-Polycab / KEI | 53.1 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 8 Module Plate (M) | No. | 2 | 258 | 516 | 92.88 | 608.88 | 0 | 2 | 516 | 92.88 | 608.88 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5C x 95 Sq.mm Aluminium Armoured Cable (M) | Mtrs | 11 | 519.48 | 5714.28 | 1028.58 | 6742.86 | 0 | 11 | 5714.28 | 1028.58 | 6742.86 | 0 | 0 | Make-Polycab / KEI | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | End Termination 4C x 6sqmm (M) | No. | 15 | 444.51 | 6667.65 | 1200.18 | 7867.83 | 0 | 10 | 4445.1 | 800.12 | 5245.22 | 5 | 2622.61 | Make-Polycab / KEI | 66.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Ceiling Rose (M) | No. | 5 | 11.12 | 55.6 | 10 | 65.6 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Supply % Installation of earthing | G.I.Earthing Strip 50 x 6 mm (M) | Mtrs | 150 | 269.1 | 40365 | 7265.7 | 47630.7 | 0 | 100 | 26910 | 4843.8 | 31753.8 | 50 | 15876.9 |  | 66.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Holder | No. | 0 | 32.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 10 sqmm Copper Lead (M) | No. | 12 | 108.35 | 1300.2 | 234.04 | 1534.24 | 0 | 12 | 1300.2 | 234.04 | 1534.24 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Fan Hook (M) | No. | 0 | 64.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Distribution Boards & MCB's | 8 Way SPN DB (M) | No. | 5 | 1353.46 | 6767.3 | 1218.12 | 7985.42 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Make-Legrand | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 8 Module Box (M) | No. | 2 | 190 | 380 | 68.4 | 448.4 | 0 | 2 | 380 | 68.4 | 448.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 6 Amp Socket (M) | No. | 25 | 162 | 4050 | 729 | 4779 | 0 | 18 | 2916 | 524.88 | 3440.88 | 7 | 1338.12 |  | 72 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I Of MCCB | 160 Amp DPX MCCB 25 KA (M) | No. | 1 | 25564.5 | 25564.5 | 4601.62 | 30166.12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Make-DB Electrical | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 6/16 Amp Multi pin Socket (M) | No. | 15 | 224 | 3360 | 604.8 | 3964.8 | 0 | 4 | 896 | 161.28 | 1057.28 | 11 | 2907.52 |  | 26.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 40A FP MCB (M) | No. | 20 | 1651 | 33020 | 5943.6 | 38963.6 | 0 | 20 | 33020 | 5943.6 | 38963.6 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 12 Module Box (M) | No. | 1 | 285 | 285 | 51.3 | 336.3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 6 Module Box (M) | No. | 10 | 162 | 1620 | 291.6 | 1911.6 | 0 | 2 | 324 | 58.32 | 382.32 | 8 | 1529.28 |  | 20 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I Of MCCB | 250 Amp DPX MCCB 25 KA (M) | No. | 2 | 27787.5 | 55575 | 10003.5 | 65578.5 | 0 | 2 | 55575 | 10003.5 | 65578.5 | 0 | 0 | Make-DB Electrical | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box 2 Way (M) | No. | 15 | 17.55 | 263.25 | 47.38 | 310.63 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Coupling (M) | No. | 0 | 4.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box 2 Way (M) | No. | 0 | 19.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 4 Core 16 sq.mm Termination Alu. Arm. cable (M) | No. | 6 | 635.4 | 3812.4 | 686.24 | 4498.64 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Make-Polycab / KEI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 70 sqmm Copper Lead (M) | No. | 0 | 766.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Casing Ptti 38/25 (M) | Mtrs | 0 | 42.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5 Core 120 sq.mm Termination Alu. Arm. cable (M) | No. | 8 | 1685.19 | 13481.52 | 2426.68 | 15908.2 | 0 | 2 | 3370.38 | 606.66 | 3977.04 | 6 | 11931.16 | Make-Polycab / KEI | 25 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | 6 Amp Switch (M) | No. | 15 | 68 | 1020 | 183.6 | 1203.6 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4C x 10 Sq.mm Copper Armoured Cable (M) | Mtrs | 180 | 558.44 | 100519.2 | 18093.46 | 118612.66 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | Make-Polycab / KEI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5C x 185 Sqmm Alu Armoured Cable Termination (M) | No. | 4 | 2012.03 | 8048.12 | 1448.66 | 9496.78 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Make-Polycab / KEI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 40A DP MCB (M) | No. | 22 | 868 | 19096 | 3437.28 | 22533.28 | 0 | 22 | 19096 | 3437.28 | 22533.28 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Power Socket Outlet | Fan Regulator (M) | No. | 1 | 420 | 420 | 75.6 | 495.6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 6 Sq.mm Lead Cable (M) | Mtrs | 0 | 64.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 40A DP MCB Enclosure (M) | No. | 22 | 427 | 9394 | 1690.92 | 11084.92 | 0 | 22 | 9394 | 1690.92 | 11084.92 | 0 | 0 | Make-Legrand | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Supply of Bend | No. | 0 | 9.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 50 sqmm Copper Lead (M) | No. | 0 | 552.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 10 Sq.mm Lead Cable Termination (M) | No. | 2 | 39.99 | 79.98 | 14.4 | 94.38 | 0 | 2 | 79.98 | 14.4 | 94.38 | 0 | 0 | Make-Dowells/ Cosmos | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box-1 Way (M) | No. | 10 | 17.26 | 172.6 | 31.06 | 203.66 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of 5 pin Indu.Plug & Socket | 5 Pin Industrial Plug (M) | No. | 0 | 3780.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 70 Sq.mm Lead Cable Termination (M) | No. | 4 | 392.46 | 1569.84 | 282.58 | 1852.42 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Make-Dowells/ Cosmos | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Junction Box-1 Way (M) | No. | 0 | 18.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of 5 pin Indu.Plug & Socket | 5 Pin Industrial Plug (M) | No. | 3 | 3099.46 | 9298.38 | 1673.7 | 10972.08 | 0 | 3 | 9298.38 | 1673.7 | 10972.08 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Abv Ceiling Conduits ,Accessories | Coupling (M) | No. | 20 | 4.39 | 87.8 | 15.8 | 103.6 | 0 | 20 | 87.8 | 15.8 | 103.6 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 4 Sq.mm Lead Cable (M) | Mtrs | 0 | 43.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Receesed Light | Receesed Light 3000K-1200mm (M) | No. | 17 | 3296.77 | 56045.09 | 10088.12 | 66133.21 | 0 | 17 | 56045.09 | 10088.12 | 66133.21 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 361 | 0 | 01 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work LED Canopy Light 50W | LED Canopy Light 50 W (M) | No. | 30 | 3729.38 | 111881.4 | 20138.66 | 132020.06 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 362 | 5 | 01 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 1 | 275000 | 275000 | 49500 | 324500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | EAST POINT - VALENTINES WEEK FEB 2024 | 0 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open |  |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 362 | 3 | 01 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open |  |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 01 Feb 2024
EAST POINT MARKET | 362 | 4 | 01 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open |  |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 01 Feb 2024
EAST POINT MARKET | 362 | 0 | 01 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 1 | 120000 | 120000 | 21600 | 141600 | 0 | 1 | 120000 | 21600 | 141600 | 0 | 0 | EAST POINT - EVENT EXPENSES FOR THE MONTH OF JAN 2024 | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open |  |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 362 | 1 | 01 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open |  |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 01 Feb 2024
EAST POINT MARKET | 362 | 2 | 01 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 1 | 275000 | 275000 | 49500 | 324500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | EAST POINT - MARCH 2024 EVENT EXPENSES | 0 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open |  |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 363 | 1 | 03 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | Booklet / Notepad / Diary / Pocket Print | No. | 5000 | 7 | 35000 | 4200 | 39200 | 0 | 5000 | 35000 | 4200 | 39200 | 0 | 0 | BOOKLET COUPONS COVER 170GSM , INNER 130 GSM SIZE 105mm x 49.5 MM QTY 5,000 @ 7/-RS PER NOS . | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 05 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 363 | 2 | 03 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media FLEX PRINTING & MOUNTING | Transport Charges- Med. | No. | 1 | 900 | 900 | 0 | 900 | 0 | 1 | 900 | 0 | 900 | 0 | 0 | TRANSPORT CHARGES FROM PUNE TO KURLA | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 05 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 363 | 0 | 03 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | LEAFLET PRINTING | No. | 20000 | 0.65 | 13000 | 650 | 13650 | 0 | 20000 | 13000 | 650 | 13650 | 0 | 0 | 100GSM F/B SIZE A-5 LEAFLET QTY 20,000 @0.65/-RS PER NOS | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 05 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Installation of NeonLight,Tree Light & LED Strip | Mtrs | 7000 | 20 | 140000 | 25200 | 165200 | 2.5 | 7000 | 140000 | 25200 | 165200 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Receesed Light | Receesed Light 3000K-1200mm (L) | No. | 17 | 300 | 5100 | 918 | 6018 | 2.5 | 17 | 5100 | 918 | 6018 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 10 sqmm Copper Lead (L) | No. | 12 | 25 | 300 | 54 | 354 | 2.5 | 12 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Primary Light Points (Controlled by MCB) | No. | 40 | 800 | 32000 | 5760 | 37760 | 2.5 | 10 | 8000 | 1440 | 9440 | 30 | 28320 |  | 25 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Power POINTS 16 A Socket & Switch.(L) | No. | 50 | 600 | 30000 | 5400 | 35400 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5 Core 120 sq.mm Aluminium Armoured cable (L) | Mtrs | 150 | 120 | 18000 | 3240 | 21240 | 2.5 | 120 | 14400 | 2592 | 16992 | 30 | 4248 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Fan Fixing. | No. | 2 | 275 | 550 | 99 | 649 | 2.5 | 2 | 550 | 99 | 649 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I Of MCCB | 160 Amp DPX MCCB 25 KA (L) | No. | 1 | 4500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3C x 6 Sq.mm Copper Armoured Cable (L) | Mtrs | 530 | 35 | 18550 | 3339 | 21889 | 2.5 | 450 | 15750 | 2835 | 18585 | 80 | 3304 |  | 84.9057 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 50 Sq.mm Lead Cable Termination (L) | No. | 2 | 45 | 90 | 16.2 | 106.2 | 2.5 | 2 | 90 | 16.2 | 106.2 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of cable tray without powde | 45 x 25 mm PVC Trunking (L) | Mtrs | 150 | 50 | 7500 | 1350 | 8850 | 2.5 | 40 | 2000 | 360 | 2360 | 110 | 6490 |  | 26.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4C x 16 Sq.mm Copper Armoured Cable (L) | Mtrs | 155 | 70 | 10850 | 1953 | 12803 | 2.5 | 73 | 5110 | 919.8 | 6029.8 | 82 | 6773.2 |  | 47.0968 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4C x 10 Sq.mm Copper Armoured Cable (L) | Mtrs | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 06 Feb 2024
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I Of MCCB | 250 Amp DPX MCCB 25 KA (L) | No. | 2 | 4500 | 9000 | 1620 | 10620 | 2.5 | 2 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5C x 95 Sq.mm Aluminium Armoured Cable (L) | Mtrs | 11 | 100 | 1100 | 198 | 1298 | 2.5 | 11 | 1100 | 198 | 1298 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 4 Core 16 sq.mm Termination Alu. Arm. cable (L) | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 4 Sq.mm Lead Cable (L) | Mtrs | 500 | 15 | 7500 | 1350 | 8850 | 2.5 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Installation of 100Watt Light Fixture | No. | 12 | 475 | 5700 | 1026 | 6726 | 2.5 | 10 | 4750 | 855 | 5605 | 2 | 1121 |  | 83.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 120 Sq.mm Lead Cable (L) | Mtrs | 60 | 90 | 5400 | 972 | 6372 | 2.5 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 4 Sq.mm Lead Cable Termination (L) | No. | 100 | 10 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work LED Canopy Light 50W | LED Canopy Light 50 W (L) | No. | 30 | 475 | 14250 | 2565 | 16815 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of cable tray without powde | 450 mm without powder coated.(L) | Mtrs | 80 | 250 | 20000 | 3600 | 23600 | 2.5 | 80 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Aluminium Armoured Cable | 3.5 Core 120 sq.mm Aluminium Armoured cable (L) | Mtrs | 250 | 120 | 30000 | 5400 | 35400 | 2.5 | 0 | 0 | 0 | 0 | 250 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5 Core 35 sq.mm Termination Alu. Arm. cable (L) | No. | 6 | 350 | 2100 | 378 | 2478 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3C x 6 sqmm 2XWY Cable End Termination (L) | No. | 23 | 80 | 1840 | 331.2 | 2171.2 | 2.5 | 8 | 640 | 115.2 | 755.2 | 15 | 1416 |  | 34.7826 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of 5 pin Indu.Plug & Socket | 5 Pin Industrial Plug (L) | No. | 3 | 500 | 1500 | 270 | 1770 | 2.5 | 3 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Fan Points Controlled by Switch | No. | 3 | 350 | 1050 | 189 | 1239 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | SITC 63A FP MCB with incloser (L) | No. | 1 | 450 | 450 | 81 | 531 | 2.5 | 1 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4C x 16 Sq.mm Copper Armoured Cable (L) | Mtrs | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 06 Feb 2024
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4 Core 6 sq.mm Copper Armoured cable (L) | Mtrs | 700 | 45 | 31500 | 5670 | 37170 | 2.5 | 402 | 18090 | 3256.2 | 21346.2 | 298 | 15823.8 |  | 57.4286 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Lf-Led Recessed downlight | Lf-Led Recessed downlight 12W-3000K (L) | No. | 30 | 275 | 8250 | 1485 | 9735 | 2.5 | 30 | 8250 | 1485 | 9735 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Primary Light Pt. (Controlled by Sw. Board) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 125A FP MCB Enclosure (L) | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Removing of cable | Removing of 3.5C x 35 Sq.mm Alu. Arm Cable | Mtrs | 100 | 50 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 6 Sq.mm Lead Cable Termination (L) | No. | 50 | 20 | 1000 | 180 | 1180 | 2.5 | 50 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 120 Sq.mm Lead Cable Termination (L) | No. | 4 | 90 | 360 | 64.8 | 424.8 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Supply % Installation of earthing | GI Earthing Patti 50 x 6mm (L) | Mtrs | 150 | 60 | 9000 | 1620 | 10620 | 2.5 | 100 | 6000 | 1080 | 7080 | 50 | 3540 |  | 66.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of cable tray without powde | 300 mm without powder coated.(L) | Mtrs | 20 | 150 | 3000 | 540 | 3540 | 2.5 | 20 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Inst,test & Comm. Power Points | No. | 50 | 450 | 22500 | 4050 | 26550 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Fan Points Controlled by Switch | No. | 10 | 350 | 3500 | 630 | 4130 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Installation of Decorative Light Fixture | No. | 12 | 275 | 3300 | 594 | 3894 | 2.5 | 10 | 2750 | 495 | 3245 | 2 | 649 |  | 83.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 6 Sq.mm Lead Cable (L) | Mtrs | 800 | 20 | 16000 | 2880 | 18880 | 2.5 | 254 | 5080 | 914.4 | 5994.4 | 546 | 12885.6 |  | 31.75 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Secondary Pt. above Primary Pt. Looped (L) | No. | 150 | 150 | 22500 | 4050 | 26550 | 2.5 | 61 | 9150 | 1647 | 10797 | 89 | 15753 |  | 40.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 50 sqmm Copper Lead (L) | No. | 12 | 60 | 720 | 129.6 | 849.6 | 2.5 | 9 | 540 | 97.2 | 637.2 | 3 | 212.4 |  | 75 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 40A FP MCB Enclosure (L) | No. | 20 | 450 | 9000 | 1620 | 10620 | 2.5 | 20 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5 Core 120 sq.mm Termination Alu. Arm. cable (L) | No. | 8 | 475 | 3800 | 684 | 4484 | 2.5 | 2 | 950 | 171 | 1121 | 6 | 3363 |  | 25 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Removing & Reinstln. 5HP Starer p | Removing & Reinstallation of 5HP Starter Panel | No. | 4 | 500 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | AC Points Controlled by Switch | No. | 2 | 600 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Installation of Decorative Light Fixture (Ballon) | No. | 10 | 475 | 4750 | 855 | 5605 | 2.5 | 1 | 475 | 85.5 | 560.5 | 9 | 5044.5 |  | 10 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Power POINTS 6 A Socket Switch.(L) | No. | 50 | 300 | 15000 | 2700 | 17700 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4C x 10 Sq.mm Copper Armoured Cable (L) | Mtrs | 180 | 50 | 9000 | 1620 | 10620 | 2.5 | 0 | 0 | 0 | 0 | 180 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 4 Core 6 sq.mm Copper Armoured cable (L) | Mtrs | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open |  |  | No category | Cancelled | DUSHANT.GORE | 06 Feb 2024
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Rubber Mats | Rubber Mats (L) | Sq.m. | 50 | 75 | 3750 | 675 | 4425 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable | 1C x 70 sqmm Copper Lead (L) | No. | 20 | 70 | 1400 | 252 | 1652 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Removing of cable | Removing of 4C x 16 sq.mm Alu Arm Cable | Mtrs | 100 | 30 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 70 Sq.mm Lead Cable Termination (L) | No. | 4 | 60 | 240 | 43.2 | 283.2 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Secondary Light Pt. (Controlled by Sw. Board) | No. | 5 | 150 | 750 | 135 | 885 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Aluminium Armoured Cable | 3.5 Core 70 sq.mm Aluminium Armoured cable (L) | Mtrs | 120 | 85 | 10200 | 1836 | 12036 | 2.5 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of flexible cable end termi | 10 Sq.mm Lead Cable Termination (L) | No. | 2 | 20 | 40 | 7.2 | 47.2 | 2.5 | 2 | 40 | 7.2 | 47.2 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Removing of NeonLight,Tree Light & LED Strip | Mtrs | 7000 | 20 | 140000 | 25200 | 165200 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work LED Panel Light -15W | LED panel Light-15W (Round)-3000K (L) | No. | 30 | 275 | 8250 | 1485 | 9735 | 2.5 | 30 | 8250 | 1485 | 9735 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Distribution Boards & MCB's | 8 Way SPN DB (L) | No. | 5 | 1150 | 5750 | 1035 | 6785 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5 Core 70 sq.mm Aluminium Armoured cable (L) | Mtrs | 100 | 85 | 8500 | 1530 | 10030 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & I of MCB & Enclosure | 40A DP MCB Enclosure (L) | No. | 22 | 450 | 9900 | 1782 | 11682 | 2.5 | 22 | 9900 | 1782 | 11682 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5 Core 70 sq.mm Termination Alu. Arm. cable (L) | No. | 2 | 375 | 750 | 135 | 885 | 2.5 | 2 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | 3.5C x 185 Sqmm Alu Armoured Cable Termination (L) | No. | 4 | 525 | 2100 | 378 | 2478 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Removing Shifting & Reinstln. ma | Removing,Shifting & Reinstallation of Main AC Panel | No. | 1 | 9000 | 9000 | 1620 | 10620 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | End Termination 4C x 6sqmm (L) | No. | 15 | 80 | 1200 | 216 | 1416 | 2.5 | 10 | 800 | 144 | 944 | 5 | 472 |  | 66.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Light Fixture Installation only | Halogen Light fitting- BC | No. | 6 | 450 | 2700 | 486 | 3186 | 2.5 | 6 | 2700 | 486 | 3186 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Termination of abv cable with hea | End Termination 3.5C x 95sqmm Al Arm (L) | No. | 2 | 425 | 850 | 153 | 1003 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | AC Points Controlled by Switch | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work S & L of Aluminium/Copper armoure | 3.5C x 185 Sq.mm Aluminium Armoured Cable (L) | Mtrs | 214 | 145 | 31030 | 5585.4 | 36615.4 | 2.5 | 210 | 30450 | 5481 | 35931 | 4 | 684.4 |  | 98.1308 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Removing of cable | Removing of 3.5C x 120 Sq.mm Alu Arm Cable | Mtrs | 240 | 90 | 21600 | 3888 | 25488 | 0 | 0 | 0 | 0 | 0 | 240 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 364 | 0 | 06 Feb 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Work Primary Point Controll by MCB | Power POINTS 5 A Socket & Switch.(L) | No. | 10 | 250 | 2500 | 450 | 2950 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 365 | 0 | 06 Feb 2024 | RAFIULLAH EHSANULLAH | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 365 | 0 | 06 Feb 2024 | RAFIULLAH EHSANULLAH | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.144 | 1440 | 0 | 1440 | 0.856 | 8560 |  | 14.4 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 365 | 0 | 06 Feb 2024 | RAFIULLAH EHSANULLAH | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 365 | 0 | 06 Feb 2024 | RAFIULLAH EHSANULLAH | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.403 | 4030 | 0 | 4030 | 0.597 | 5970 |  | 40.3 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 365 | 0 | 06 Feb 2024 | RAFIULLAH EHSANULLAH | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.0264 | 264 | 0 | 264 | 0.9736 | 9736 |  | 2.64 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 365 | 0 | 06 Feb 2024 | RAFIULLAH EHSANULLAH | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.944 | 9440 | 0 | 9440 | 0.056 | 560 |  | 94.4 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | S OH Expenses | Approved | Swapnil Erande
EAST POINT MARKET | 366 | 0 | 16 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | Coupon Cover | No. | 3000 | 1 | 3000 | 360 | 3360 | 0 | 3000 | 3000 | 360 | 3360 | 0 | 0 | 1) VALENTINE MONTH COUPON COVER QTY 3,000NOS @1/-RS PER NOS | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 16 Feb 2024 |  | No category | Approved | sunita shirolkar
EAST POINT MARKET | 366 | 3 | 16 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | Transport Charges- Med. | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 | 4) TRANSPORT CHARGES FROM PUNE TO KURLA. | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 16 Feb 2024 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 366 | 2 | 16 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | LEAFLET PRINTING | No. | 3000 | 1.4 | 4200 | 504 | 4704 | 0 | 3000 | 4200 | 504 | 4704 | 0 | 0 | 3) VALENTINE MONTH LEAFLET QTY 3,000 NOS @ 1.40/-RS PER NOS. | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 16 Feb 2024 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 366 | 1 | 16 Feb 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | COUPON | No. | 21000 | 0.4 | 8400 | 1008 | 9408 | 0 | 21000 | 8400 | 1008 | 9408 | 0 | 0 | 2) VALENTINE MONTH COUPON 7X100 QTY 21,000/- NOS @ 0.40/-RS PER NOS. | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 16 Feb 2024 |  | No category | Approved | sunita shirolkar
EAST POINT MARKET | 367 | 0 | 16 Feb 2024 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | Event Expenses | No. | 1 | 21900 | 21900 | 3942 | 25842 | 0 | 1 | 21900 | 3942 | 25842 | 0 | 0 | FEB 2024 EVENT EXPENSES | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 17 Feb 2024 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 367 | 0 | 16 Feb 2024 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | Event Expenses | No. | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open | 17 Feb 2024 |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 28 Feb 2024
EAST POINT MARKET | 368 | 1 | 28 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 | MARCH & APRIL EVENT 2024 | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 28 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 368 | 0 | 28 Feb 2024 | PARTY AND TRAVEL GROUP | Media BRANDING | Event Expenses | No. | 1 | 300000 | 300000 | 54000 | 354000 | 0 | 1 | 300000 | 54000 | 354000 | 0 | 0 | 1ST MARCH TO 31ST MARCH 2024 FOOD COURT BRANDING CHARGES. | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 28 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 369 | 0 | 28 Feb 2024 | HANKS ADVERTISING SERVICES LLP | Media BRANDING | Event Expenses | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0.65 | 65000 | 11700 | 76700 | 0.35 | 41300 | EAST POINT MARKET 3RD FLOOR FOOD COURT BRANDING FOR THE MONTH OF MARCH 2024 | 65 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 28 Feb 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 370 | 0 | 01 Mar 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | LEAFLET PRINTING | No. | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open | 01 Mar 2024 |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 01 Mar 2024
EAST POINT MARKET | 371 | 2 | 01 Mar 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | COUPON | No. | 3000 | 8.15 | 24450 | 2934 | 27384 | 0 | 3000 | 24450 | 2934 | 27384 | 0 | 0 | COUPON BOOK MULTICOLOR -19 PAGES + COVER FURLA COMPLEX MALL QTY 3,000 @ 8.15/- RS | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 01 Mar 2024 |  | No category | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 371 | 0 | 01 Mar 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | LEAFLET PRINTING | No. | 10000 | 0.8 | 8000 | 400 | 8400 | 0 | 10000 | 8000 | 400 | 8400 | 0 | 0 | A5 LEAFLET BOTHSIDE MULTICOLOR KURLA COMPLEX MALL QTY 10,000 NOS @ 0.80/-RS | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 01 Mar 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 371 | 1 | 01 Mar 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | COUPON | No. | 10000 | 6.3 | 63000 | 7560 | 70560 | 0 | 10000 | 63000 | 7560 | 70560 | 0 | 0 | 2)COUPON BOOK MULTICOLOR - 19 PAGES + COVER KURLA COMPLEX MALL QTY 10,000NOS @6.30/-RS | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 01 Mar 2024 |  | No category | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 372 | 0 | 06 Mar 2024 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media BRANDING | LEAFLET PRINTING | No. | 10000 | 0.8 | 8000 | 400 | 8400 | 0 | 10000 | 8000 | 400 | 8400 | 0 | 0 | A5 LEAFLETS 90 GSM BACK TO BACK PRINTING QTY 10,000 @ 0.8/-RS | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 11 Mar 2024 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 373 | 0 | 19 Mar 2024 | ADANI ELECTRICITY MUMBAI LTD | Guest House & Food court units electricity expenses | Electricity Bills | No. | 12 | 9000 | 108000 | 19440 | 127440 | 0 | 7.6541 | 68887.07 | 0 | 68887.07 | 4.3459 | 58552.93 | Electricity Charges for Food Court Non-leased Shops. Per Shop 600 Rs/- lumpsum (15 Shops x 600 = 9000/-) | 63.7842 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Mar 2024 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 374 | 0 | 19 Mar 2024 | ADANI ELECTRICITY MUMBAI LTD A/C NO. 101485662 | Guest House & Food court units electricity expenses | Electricity Bills | No. | 12 | 8500 | 102000 | 18360 | 120360 | 0 | 2.9348 | 24945.77 | 0 | 24945.77 | 9.0652 | 95414.23 | Electricity Charges for Kurla Guest House (Monthly Consumption 850 units) = 850x10= 8500/- Guest House :- 1) 1 Hall- 1 Split AC, 2 Fan, 2 Bulb. 2) 2 Bedroom- 1 Window AC, 1 Fan, 1 Bulb. 3) 1 Kitchen- Fridge, Washing Machine. 4)1 Washroom- Bulb,Geyser. | 34.4475 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Mar 2024 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
EAST POINT MARKET | 375 | 0 | 05 Apr 2024 | DREAMTREE EXPERIENCE | Media FLEX PRINTING & MOUNTING | Flex Printing & Pasting | Sq.Ft | 736 | 150 | 110400 | 19872 | 130272 | 0 | 544 | 81600 | 14688 | 96288 | 192 | 33984 | EAST POINT - OUTER BOX FLEX CHANGE COSTING @150 RS PER SQFT - 736SQFT | 73.913 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 09 May 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 375 | 0 | 05 Apr 2024 | DREAMTREE EXPERIENCE | Media BRANDING | Repair & Maintenance Work | Job | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | FOOD COURT LOGO REPAIRING @25,000/-RS | 0 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 09 May 2024 |  | 14 MISC WORK | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Labour lumpsum | No. | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Labour lumpsum | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Breaker | Day | 5 | 1800 | 9000 | 0 | 9000 | 0 | 5 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Labour lumpsum | No. | 1 | 1800 | 1800 | 0 | 1800 | 0 | 1 | 1800 | 0 | 1800 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Labour lumpsum | No. | 1 | 700 | 700 | 0 | 700 | 2.5 | 1 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Debris Shifting work. | No. | 5 | 700 | 3500 | 0 | 3500 | 0 | 5 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | 14 MISC WORK | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 1 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Ground Floor SRM Machine Lifting | Crane Charges - | No. | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Apr 2024 |  | MKT. Marketing Infrastructure | Cancelled | MONALI CHAUDHAR | 26 Jul 2024
EAST POINT MARKET | 376 | 1 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Ground Floor SRM Machine Lifting | Crane Charges - | No. | 2 | 5200 | 10400 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 376 | 0 | 10 Apr 2024 | RAFIULLAH EHSANULLAH | Hume pipe laying for Adani cable | Transportaion | No. | 1 | 3300 | 3300 | 0 | 3300 | 0 | 1 | 3300 | 0 | 3300 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 377 | 0 | 12 Apr 2024 | KHAN KAMAR ALAM | Third floor Toilet False Ceiling work | False Ceiling Work (M+L)- BC | Sq.Ft | 766.607 | 90 | 68994.63 | 0 | 68994.63 | 2.5 | 0 | 0 | 0 | 0 | 766.607 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande
EAST POINT MARKET | 377 | 0 | 12 Apr 2024 | KHAN KAMAR ALAM | Third floor Toilet False Ceiling work | Gypsum False Ceiling Patta (M+L) | R.Ft | 223.04 | 70 | 15612.8 | 0 | 15612.8 | 2.5 | 0 | 0 | 0 | 0 | 223.04 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande
EAST POINT MARKET | 377 | 0 | 12 Apr 2024 | KHAN KAMAR ALAM | Third floor Toilet False Ceiling work | Gala Cutting | No. | 60 | 60 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande
EAST POINT MARKET | 378 | 0 | 28 May 2024 | N.V GRAPHICS & ADVERTISING PVT LTD | Media BRANDING | Event Expenses | No. | 1 | 66528 | 66528 | 11975.04 | 78503.04 | 0 | 0.7739 | 51488.19 | 9267.86 | 60756.05 | 0.2261 | 17746.99 | T20 WORLD CUP - BRANDING | 77.39 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 11 Jun 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 379 | 0 | 28 May 2024 | V CREATION | ACP for Shop 03 Sinage 2nd floor | ACP Work- (L) | Sq.Ft | 315.806 | 80 | 25264.48 | 0 | 25264.48 | 2.5 | 297.125 | 23770 | 4278.6 | 28048.6 | 18.681 | -2784.12 |  | 94.0847 |  | abhishek bankar | abhishek bankar | construction open | 03 Jun 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 380 | 0 | 28 May 2024 | V CREATION | ACP for Shop 03 Sinage 2nd floor | ACP Work- (M) | Sq.Ft | 315.806 | 170 | 53687.02 | 0 | 53687.02 | 0 | 297.1294 | 50512 | 9092.16 | 59604.16 | 18.6766 | -5917.14 |  | 94.0861 |  | abhishek bankar | abhishek bankar | construction open | 03 Jun 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | abhishek bankar
EAST POINT MARKET | 381 | 0 | 29 May 2024 | GUARDIANS REAL ESTATE ADVISORY PRIVATE LIMITED | Marketing Creative agency Fees | AGENCY FEE | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | abhishek bankar | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 381 | 1 | 29 May 2024 | GUARDIANS REAL ESTATE ADVISORY PRIVATE LIMITED | Marketing Digital Campaigning | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | abhishek bankar |  | construction open |  |  | MKT. Media | Cancelled | abhishek bankar | 31 May 2024
EAST POINT MARKET | 381 | 1 | 29 May 2024 | GUARDIANS REAL ESTATE ADVISORY PRIVATE LIMITED | Marketing Digital Campaigning | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 1034000 | 1034000 | 186120 | 1220120 | 0 | 1 | 1034000 | 186120 | 1220120 | 0 | 0 |  | 100 |  | abhishek bankar | abhishek bankar | construction open |  |  | MKT. Media | Approved | abhishek bankar
EAST POINT MARKET | 382 | 0 | 30 May 2024 | AJINKYA RAMESH TEKALE | Site Expenses | Site Expences | No. | 3 | 5000 | 15000 | 0 | 15000 | 0 | 2.835 | 14175 | 0 | 14175 | 0.165 | 825 |  | 94.5 |  | abhishek bankar | abhishek bankar | construction open | 31 May 2024 |  | SOC. M. Maintenace Overheads | Approved | abhishek bankar
EAST POINT MARKET | 383 | 1 | 04 Jun 2024 | RUPALI DEEPAK LOKHANDE | Media BRANDING | Event Expenses | No. | 1 | 159600 | 159600 | 0 | 159600 | 0 | 1 | 159600 | 0 | 159600 | 0 | 0 |  | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 04 Jun 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV
EAST POINT MARKET | 385 | 0 | 08 Jun 2024 | JAY ENTERPRISES | 3rd floor Shop no. R-2 Aerocon Panel Removing & Shifting | Aerocon Partition wall refixing- Mkt | Sq.Ft | 527.796 | 40 | 21111.84 | 0 | 21111.84 | 0 | 527.796 | 21111.84 | 0 | 21111.84 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 14 Jun 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
EAST POINT MARKET | 386 | 0 | 11 Jun 2024 | SKY TOUCH EVENTS | Telecalling | TELECALLING | No. | 432 | 1100 | 475200 | 85536 | 560736 | 0 | 0 | 0 | 0 | 0 | 432 | 0 |  | 0 |  | abhishek bankar |  | construction open |  |  | MKT. Media | Un-Approved
EAST POINT MARKET | 387 | 0 | 26 Jun 2024 | N.V GRAPHICS & ADVERTISING PVT LTD | Media BRANDING | Event Expenses | No. | 1 | 40170 | 40170 | 7230.6 | 47400.6 | 0 | 1 | 40170 | 7230.62 | 47400.62 | 0 | -0.02 | MARCH & APRIL 2024 PRINTING EXPENSES | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 27 Jun 2024 |  | MKT. Media | Approved | sunita shirolkar
EAST POINT MARKET | 388 | 0 | 03 Jul 2024 | ANAND ROLLING SHUTTER & FABRICATOR | 4th floor Temporary MS Staircase making | MS Work | Lumsum | 1 | 18000 | 18000 | 3240 | 21240 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 03 Jul 2024 |  | No category | Approved | abhishek bankar
EAST POINT MARKET | 389 | 0 | 03 Jul 2024 | AMIRUL ISLAM | 4th floor access closing | Labour Lumpsum | No. | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 03 Jul 2024 |  | Land Cost | Approved | abhishek bankar
EAST POINT MARKET | 389 | 0 | 03 Jul 2024 | AMIRUL ISLAM | 4th floor access closing | Material Shifting Work - SOS | No. | 1 | 14000 | 14000 | 0 | 14000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | abhishek bankar | abhishek bankar | construction open | 03 Jul 2024 |  | S OH Infrastructure | Approved | abhishek bankar
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | 3'' Elbow seamless sch 40 (M+L) | No. | 6 | 522.5 | 3135 | 564.3 | 3699.3 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Bracket M.S Fabricated 35 x 35 x3mm (M+L) | No. | 4 | 332.5 | 1330 | 239.4 | 1569.4 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Labour lumpsum | No. | 1 | 4750 | 4750 | 855 | 5605 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Labour lumpsum | No. | 1 | 14250 | 14250 | 2565 | 16815 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | 3"x2" Reducer (M+L) | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Pressure Gauge (M+L) | set | 1 | 1757.5 | 1757.5 | 316.36 | 2073.86 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Labour lumpsum | No. | 1 | 14250 | 14250 | 2565 | 16815 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Labour lumpsum | No. | 1 | 4750 | 4750 | 855 | 5605 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | 3'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 1 | 427.5 | 427.5 | 76.96 | 504.46 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | 3'' Dia M.S ERW Pipe (M+L) | R.Ft | 20 | 570 | 11400 | 2052 | 13452 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | 1/2" Ball Valve (M+L) | No. | 1 | 522.5 | 522.5 | 94.06 | 616.56 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | Labour lumpsum | No. | 1 | 7600 | 7600 | 1368 | 8968 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
EAST POINT MARKET | 390 | 0 | 13 Jul 2024 | VED ENGINEERS AND CONTRACTORS | 3rd Floor Food Court Gas line Connection at Ground Floor | 2'' Flange SA.-150 with Studs & Gasket (M+L) | No. | 2 | 332.5 | 665 | 119.7 | 784.7 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable (M) | Mtrs | 140 | 1110 | 155400 | 27972 | 183372 | 0 | 140 | 155400 | 27972 | 183372 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 sqmm 2XWY Cable End Termination (M) | No. | 1 | 234 | 234 | 42.12 | 276.12 | 0 | 1 | 234 | 42.12 | 276.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 12 Way VTPN DB (M) | No. | 1 | 11812 | 11812 | 2126.16 | 13938.16 | 0 | 1 | 11812 | 2126.16 | 13938.16 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 70sqmm A2XFY XLPE (M) | Mtrs | 90 | 546 | 49140 | 8845.2 | 57985.2 | 0 | 90 | 49140 | 8845.2 | 57985.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 Sq.mm Copper Armoured Cable (M) | Mtrs | 85 | 346 | 29410 | 5293.8 | 34703.8 | 0 | 85 | 29410 | 5293.8 | 34703.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable (M) | Mtrs | 65 | 1110 | 72150 | 12987 | 85137 | 0 | 65 | 72150 | 12987 | 85137 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 20 A SP MCB (M) | No. | 36 | 176 | 6336 | 1140.48 | 7476.48 | 0 | 36 | 6336 | 1140.48 | 7476.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 95 sqmm A2XFY Cable End Termination (M) | No. | 2 | 1404 | 2808 | 505.44 | 3313.44 | 0 | 2 | 2808 | 505.44 | 3313.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Earthing Work (M) | No. | 2 | 16965 | 33930 | 6107.4 | 40037.4 | 0 | 2 | 33930 | 6107.4 | 40037.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | End Termination 3.5C x 70sqmm (M) | No. | 2 | 702 | 1404 | 252.72 | 1656.72 | 0 | 2 | 1404 | 252.72 | 1656.72 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 sqmm 2XWY Cable End Termination (M) | No. | 2 | 234 | 468 | 84.24 | 552.24 | 0 | 2 | 468 | 84.24 | 552.24 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of End termi 16/25/35sqmm cable | No. | 3 | 351 | 1053 | 189.54 | 1242.54 | 0 | 3 | 1053 | 189.54 | 1242.54 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 95sqmm A2XFY XLPE (M) | Mtrs | 7 | 681 | 4767 | 858.06 | 5625.06 | 0 | 7 | 4767 | 858.06 | 5625.06 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of End term 50sqmm cable | No. | 4 | 585 | 2340 | 421.2 | 2761.2 | 0 | 4 | 2340 | 421.2 | 2761.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable End Termination (M) | No. | 2 | 702 | 1404 | 252.72 | 1656.72 | 0 | 1 | 702 | 126.36 | 828.36 | 1 | 828.36 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 185 sqmm A2XFY Cable End Termination (M) | No. | 4 | 2165 | 8660 | 1558.8 | 10218.8 | 0 | 4 | 8660 | 1558.8 | 10218.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable End Termination (M) | No. | 2 | 702 | 1404 | 252.72 | 1656.72 | 0 | 1 | 702 | 126.36 | 828.36 | 1 | 828.36 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 63A 4P MCB (M) | No. | 1 | 1779 | 1779 | 320.22 | 2099.22 | 0 | 1 | 1779 | 320.22 | 2099.22 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | End terminatiom 3c x 16sqmm cable (M) | No. | 2 | 351 | 702 | 126.36 | 828.36 | 0 | 2 | 702 | 126.36 | 828.36 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | GI Strip 25 x 6mm (M) | Mtrs | 140 | 195 | 27300 | 4914 | 32214 | 0 | 140 | 27300 | 4914 | 32214 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 25 sqmm 2XWY Cable End Termination (M) | No. | 1 | 410 | 410 | 73.8 | 483.8 | 0 | 1 | 410 | 73.8 | 483.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 2.5 sqmm 2XWY Cable End Termination (M) | No. | 28 | 88 | 2464 | 443.52 | 2907.52 | 0 | 28 | 2464 | 443.52 | 2907.52 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 391 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | CU Strip 25 x 3 sqmm (M) | Mtrs | 85 | 995 | 84575 | 15223.5 | 99798.5 | 0 | 70 | 69650 | 12537 | 82187 | 15 | 17611.5 |  | 82.3529 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | GI Strip 25 x 6mm (L) | Mtrs | 140 | 65 | 9100 | 1638 | 10738 | 2.5 | 140 | 9100 | 1638 | 10738 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | End terminatiom 3c x 16sqmm cable (L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable (L) | Mtrs | 65 | 70 | 4550 | 819 | 5369 | 2.5 | 65 | 4550 | 819 | 5369 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 Sq.mm Copper Armoured Cable (L) | Mtrs | 85 | 35 | 2975 | 535.5 | 3510.5 | 2.5 | 85 | 2975 | 535.5 | 3510.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing of 3.5 C x 95sqmm Cable | Mtrs | 205 | 120 | 24600 | 4428 | 29028 | 0 | 205 | 24600 | 4428 | 29028 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 12 Way VTPN DB (L) | No. | 1 | 2200 | 2200 | 396 | 2596 | 2.5 | 1 | 2200 | 396 | 2596 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | CU Strip 25 x 3 sqmm (L) | Mtrs | 85 | 65 | 5525 | 994.5 | 6519.5 | 2.5 | 70 | 4550 | 819 | 5369 | 15 | 1150.5 |  | 82.3529 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 25 sqmm 2XWY Cable End Termination (L) | No. | 1 | 150 | 150 | 27 | 177 | 2.5 | 1 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 95sqmm A2XFY XLPE (L) | Mtrs | 7 | 100 | 700 | 126 | 826 | 2.5 | 7 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 185 sqmm A2XFY Cable End Termination (L) | No. | 4 | 400 | 1600 | 288 | 1888 | 2.5 | 4 | 1600 | 288 | 1888 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of 63A FP MCB | No. | 4 | 600 | 2400 | 432 | 2832 | 0 | 4 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 2.5 sqmm 2XWY Cable End Termination (L) | No. | 28 | 50 | 1400 | 252 | 1652 | 2.5 | 28 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | GI Strip 25 x 6mm (L) | Mtrs | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 sqmm 2XWY Cable End Termination (L) | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Earthing Work (L) | No. | 2 | 6500 | 13000 | 2340 | 15340 | 2.5 | 2 | 13000 | 2340 | 15340 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | End Termination 3.5C x 70sqmm (L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of End termi 16/25/35sqmm cable | No. | 3 | 150 | 450 | 81 | 531 | 0 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable (L) | Mtrs | 140 | 70 | 9800 | 1764 | 11564 | 2.5 | 140 | 9800 | 1764 | 11564 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of End term 50sqmm cable | No. | 4 | 150 | 600 | 108 | 708 | 0 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable End Termination (L) | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing of 3.5 C x 95sqmm Cable | Mtrs | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of DOL Starter | No. | 4 | 1200 | 4800 | 864 | 5664 | 0 | 4 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of 16/25/35 sqmm cable | Mtrs | 239 | 180 | 43020 | 7743.6 | 50763.6 | 0 | 239 | 43020 | 7743.6 | 50763.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing & Reinstallation of 50sqmm Cable | Mtrs | 13 | 180 | 2340 | 421.2 | 2761.2 | 0 | 13 | 2340 | 421.2 | 2761.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | End Termination 3.5C x 70sqmm (L) | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable End Termination (L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 1 | 150 | 27 | 177 | 1 | 177 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing 3.5Cx70sqmm Alum. Armd Cable | Mtrs | 95 | 120 | 11400 | 2052 | 13452 | 0 | 95 | 11400 | 2052 | 13452 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable (L) | Mtrs | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 sqmm 2XWY Cable End Termination (L) | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 sqmm 2XWY Cable End Termination (L) | No. | 2 | 80 | 160 | 28.8 | 188.8 | 2.5 | 2 | 160 | 28.8 | 188.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable (L) | Mtrs | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 95 sqmm A2XFY Cable End Termination (L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable End Termination (L) | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | Removing 3.5Cx70sqmm Alum. Armd Cable | Mtrs | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 70sqmm A2XFY XLPE (L) | Mtrs | 0 | 120 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 04 ELECTRICAL WORK | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 sqmm 2XWY Cable End Termination (L) | No. | 1 | 80 | 80 | 14.4 | 94.4 | 2.5 | 1 | 80 | 14.4 | 94.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3c x 16sqmm cable (L) | Mtrs | 30 | 80 | 2400 | 432 | 2832 | 2.5 | 30 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 4C x 16 Sq.mm. YWY Cable End Termination (L) | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 1 | 150 | 27 | 177 | 1 | 177 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | No category | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3.5C x 70sqmm A2XFY XLPE (L) | Mtrs | 90 | 60 | 5400 | 972 | 6372 | 2.5 | 90 | 5400 | 972 | 6372 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open |  |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande
EAST POINT MARKET | 392 | 0 | 18 Jul 2024 | A.D. ASSOCIATES ELECTRICALS PVT LTD | 3rd Floor Electrical Cable Work | 3C x 6 Sq.mm Copper Armoured Cable (L) | Mtrs | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | No category | Cancelled | ADITYA.CHOUGULE | 20 Jul 2024
EAST POINT MARKET | 393 | 0 | 18 Jul 2024 | NEPTUNE ENGINEERS PRIVATE LIMITED | KEP-3rd Floor FC02 AC installation purpose 16HP System pump | 16 HP System Pump Shut down & Start | No. | 1 | 50000 | 50000 | 9000 | 59000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Jul 2024 |  | No category | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 3 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 09 Jul 2020
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 3 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 09 Jul 2020
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 3 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 09 Jul 2020
GANGA ARCADIA | 634 | 3 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 09 Jul 2020
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 3 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 09 Jul 2020
GANGA ARCADIA | 634 | 3 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 09 Jul 2020
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 5 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 4 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 634 | 7 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 02 Apr 2024
GANGA ARCADIA | 634 | 6 | 02 Jan 2016 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Garden Maintanance - MWB | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Feb 2016 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Feb 2019 |  | S OH Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 727 | 2 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker - Mkt | Trips | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 02 Feb 2019 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Feb 2019 |  | S OH Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Feb 2019 |  | S OH Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 727 | 2 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker - Mkt | Trips | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 02 Feb 2019 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 727 | 2 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker - Mkt | Trips | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 02 Feb 2019 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 727 | 2 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker - Mkt | Trips | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | tausif | construction open | 02 Feb 2019 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Feb 2019 |  | S OH Infrastructure | Cancelled | skmishra | 29 Jan 2022
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Feb 2019 |  | S OH Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 02 Feb 2019 |  | S OH Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 727 | 2 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker - Mkt | Trips | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 02 Feb 2019 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 727 | 3 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker Supply.-SO | Month | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 02 Feb 2019 |  | S OH Infrastructure | Approved | chetan.jewalikar
GANGA ARCADIA | 727 | 2 | 31 Jan 2019 | SNEHA GARDEN DEVELOPERS | PMC Road Divider Plantation | Water Tanker - Mkt | Trips | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 02 Feb 2019 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 733 | 1 | 04 Feb 2020 | SHRUSTI FLORALS | PMC Road Divider Plantation | Supervision Charges | Month | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | construction open | 05 Feb 2020 |  | DEV. Landscape/Equipment | Cancelled | tausif | 10 Oct 2020
GANGA ARCADIA | 733 | 1 | 04 Feb 2020 | SHRUSTI FLORALS | PMC Road Divider Plantation | Professional Charges | Month | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | construction open | 05 Feb 2020 |  | Consultancy Proffessional | Cancelled | tausif | 10 Oct 2020
GANGA ARCADIA | 738 | 0 | 16 Dec 2020 | GREENSOL TECH | STP-160 KLD | Sewage Treatment Plant (L) | No. | 1 | 412500 | 412500 | 74250 | 486750 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1.STP 160 KLD (MBBR TECHNOLOGY) (L) | 0 |  | tausif |  | Construction | 16 Dec 2020 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
GANGA ARCADIA | 739 | 0 | 16 Dec 2020 | GREENSOL TECH | STP-160 KLD | Sewage Treatment Plant (M) | No. | 1 | 962500 | 962500 | 173250 | 1135750 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1. STP 160 KLD (MBBR TECHNOLOGY). (M) | 0 |  | tausif |  | Construction | 16 Dec 2020 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved
GANGA ARCADIA | 740 | 0 | 09 Jan 2021 | A K INTERIOR CONTRACTOR | B-Parking Lobby Gypsum False Ceiling Repairing Work. | False Ceiling Repairing- DER | Sq.Ft | 220 | 65 | 14300 | 2574 | 16874 | 0 | 220 | 14300 | 0 | 14300 | 0 | 2574 |  | 100 |  | tausif | tausif | construction open | 21 Jan 2021 |  | DEV. Extrawork/Rework | Approved | tausif
GANGA ARCADIA | 741 | 0 | 16 Feb 2021 | SS ENTERPRISES | A RCC Substructure JCB Work For Excavation | JCB Charges BC | Hrs | 109.83 | 800 | 87864 | 15815.52 | 103679.52 | 0 | 109.83 | 87864 | 15815.52 | 103679.52 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 17 Feb 2021 |  | B.C. RCC Substructure | Approved | tausif
GANGA ARCADIA | 741 | 0 | 16 Feb 2021 | SS ENTERPRISES | A RCC Substructure JCB Work For Excavation | JCB Charges BC | Hrs | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 17 Feb 2021 |  | B.C. RCC Substructure | Cancelled | tausif | 17 Feb 2021
GANGA ARCADIA | 742 | 0 | 17 Feb 2021 | AMAN ASSOCIATES | A RCC Substructure JCB Work For Excavation | JCB Charges BC | Hrs | 62.83 | 800 | 50264 | 9047.52 | 59311.52 | 0 | 62.83 | 50264 | 9047.52 | 59311.52 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. RCC Substructure | Approved | tausif
GANGA ARCADIA | 743 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Dismentalling and Installation of split Unit (L) | No. | 1 | 1968 | 1968 | 354.24 | 2322.24 | 0 | 1 | 1968 | 354.24 | 2322.24 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 743 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Wet Servicing (L) | No. | 1 | 172.2 | 172.2 | 31 | 203.2 | 0 | 1 | 172.2 | 31 | 203.2 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 743 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Gas Charging (L) | No. | 1 | 213.2 | 213.2 | 38.38 | 251.58 | 0 | 1 | 213.2 | 38.38 | 251.58 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 743 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Copper Pipe with Insulation (L) | Mtrs | 7.5 | 121.36 | 910.2 | 163.84 | 1074.04 | 0 | 7.5 | 910.2 | 163.84 | 1074.04 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 743 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | SITC of Drain Pipe (L) | Mtrs | 7.5 | 22.96 | 172.2 | 31 | 203.2 | 0 | 7.5 | 172.2 | 31 | 203.2 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jawalikar
GANGA ARCADIA | 743 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | SITC of Communication Cable (L) | Mtrs | 9.5 | 27.06 | 257.07 | 46.28 | 303.35 | 0 | 9.5 | 257.07 | 46.28 | 303.35 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jawalikar
GANGA ARCADIA | 744 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Copper Pipe with Insulation (M) | Mtrs | 7.5 | 485.44 | 3640.8 | 655.34 | 4296.14 | 0 | 7.5 | 3640.8 | 655.34 | 4296.14 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 744 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | SITC of Drain Pipe (M) | Mtrs | 7.5 | 91.84 | 688.8 | 123.98 | 812.78 | 0 | 7.5 | 688.8 | 123.98 | 812.78 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jawalikar
GANGA ARCADIA | 744 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Wet Servicing (M) | No. | 1 | 688.8 | 688.8 | 123.98 | 812.78 | 0 | 1 | 688.8 | 123.98 | 812.78 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 744 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | Gas Charging (M) | No. | 1 | 852.8 | 852.8 | 153.5 | 1006.3 | 0 | 1 | 852.8 | 153.5 | 1006.3 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | chetan.jawalikar
GANGA ARCADIA | 744 | 0 | 24 Feb 2021 | NEPTUNE ENGINEERS | Sales Office AC Re-Installation Work-(No.) | SITC of Communication Cable (M) | Mtrs | 9.5 | 108.24 | 1028.28 | 185.1 | 1213.38 | 0 | 9.5 | 1028.28 | 185.1 | 1213.38 | 0 | 0 |  | 100 |  | shubham giri | chetan.jawalikar | Construction | 25 Feb 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jawalikar
GANGA ARCADIA | 745 | 0 | 04 Mar 2021 | AMFEW AND CO | Sales Office -AC Repairing Work | A.C. Repair & maintenance.-SO | No. | 1 | 82325 | 82325 | 14818.5 | 97143.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | shubham giri | tausif | Construction | 08 Mar 2021 |  | S OH Repair & Maintenance | Approved | tausif
GANGA ARCADIA | 746 | 0 | 04 Mar 2021 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Media Brochure Printing | Booklet / Notepad / Diary / Pocket Print | No. | 1000 | 40 | 40000 | 4800 | 44800 | 0 | 1000 | 40000 | 4800 | 44800 | 0 | 0 | GANGA ARCADIA A BUILDING BROCHURE PRINT QTY 1000 ( 24 + 4 PAGES COVER 250 GSM, INNER PAGES 170 GSM WITH CENTRE PINNING READY SIZE AS A - 4 | 100 |  | Tejas Raverkar | chetan.jawalikar | construction open | 12 May 2021 |  | MKT. Media | Approved | chetan.jawalikar
GANGA ARCADIA | 747 | 0 | 04 Mar 2021 | PRAKASH CONTRACTOR | A-Bldg GI sheet fixing work | Departmental work- SO | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 11 Mar 2021 |  | S OH Infrastructure | Cancelled | tausif | 12 Mar 2021
GANGA ARCADIA | 747 | 0 | 04 Mar 2021 | PRAKASH CONTRACTOR | A-Bldg GI sheet fixing work | Departmental Labour- BC | No. | 10 | 450 | 4500 | 0 | 4500 | 0 | 10 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 11 Mar 2021 |  | B.C. Rework/Extrawork | Approved | tausif
GANGA ARCADIA | 747 | 0 | 04 Mar 2021 | PRAKASH CONTRACTOR | A-Bldg GI sheet fixing work | G.I. Sheet Fixing - BC | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | construction open | 11 Mar 2021 |  | B.C. Internal Finishing Itmes | Cancelled | tausif | 11 Mar 2021
GANGA ARCADIA | 748 | 0 | 12 Mar 2021 | S. V. ENTERPRISES | Rain water harvesting chamber repair work | Chamber Repairing Work-SO | No. | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | tausif
GANGA ARCADIA | 749 | 0 | 18 Mar 2021 | R.T.S. STEEL SERVICES | Site Boundary GI Sheet Barrication | Fabrication work (L) | Kgs | 1948.18 | 21.2 | 41301.42 | 7434.26 | 48735.68 | 2.5 | 0 | 0 | 0 | 0 | 1948.18 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | Admin. Direct Expenses | Approved | tausif
GANGA ARCADIA | 749 | 0 | 18 Mar 2021 | R.T.S. STEEL SERVICES | Site Boundary GI Sheet Barrication | GI Sheet Fixing | Sq.Ft | 2600 | 5 | 13000 | 2340 | 15340 | 2.5 | 0 | 0 | 0 | 0 | 2600 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Entrance Gate | Approved | tausif
GANGA ARCADIA | 750 | 0 | 18 Mar 2021 | R.T.S. STEEL SERVICES | Site Boundary GI Sheet Barrication | Fabrication work (M) | Kgs | 1948.18 | 53 | 103253.54 | 18585.64 | 121839.18 | 0 | 0 | 0 | 0 | 0 | 1948.18 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | Admin. Direct Expenses | Approved | tausif
GANGA ARCADIA | 750 | 0 | 18 Mar 2021 | R.T.S. STEEL SERVICES | Site Boundary GI Sheet Barrication | Self Tapping Screw - SOSB | No. | 594 | 2.5 | 1485 | 267.3 | 1752.3 | 0 | 0 | 0 | 0 | 0 | 594 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | tausif
GANGA ARCADIA | 751 | 0 | 03 Apr 2021 | PRAKASH CONTRACTOR | B-Bldg Wall demolition & material shifting work | Material Shifting | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 15 Apr 2021 |  | S OH Infrastructure | Cancelled | tausif | 15 Apr 2021
GANGA ARCADIA | 751 | 0 | 03 Apr 2021 | PRAKASH CONTRACTOR | B-Bldg Wall demolition & material shifting work | Demolition work- BCE - | Sq.Ft | 256.5 | 5 | 1282.5 | 0 | 1282.5 | 0 | 256.5 | 1282.5 | 0 | 1282.5 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 15 Apr 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jawalikar
GANGA ARCADIA | 752 | 1 | 07 Apr 2021 | SAFIYA BHAIJAN SHAH | B-Bldg Shop-17 Gypsum partition work | Gypsum Board Partition (M+L) Rate Diff | Sq.Ft | 72 | 45 | 3240 | 0 | 3240 | 2.5 | 72 | 3240 | 0 | 3240 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 16 Apr 2021 |  | 05 GYPSUM & PLASTER | Approved | tausif
GANGA ARCADIA | 752 | 0 | 07 Apr 2021 | SAFIYA BHAIJAN SHAH | B-Bldg Shop-17 Gypsum partition work | Gypsum Board Partition (M+L)-BC | Sq.Ft | 72 | 65 | 4680 | 0 | 4680 | 2.5 | 72 | 4680 | 0 | 4680 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | B.C. BBM, Plaster, POP | Approved | chetan.jawalikar
GANGA ARCADIA | 753 | 0 | 08 Apr 2021 | PUNDLIK P MAHAJAN | B-bldg rabbit shifting work | Rabbit Shifting - BRE | Trips | 5 | 700 | 3500 | 0 | 3500 | 0 | 5 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jawalikar
GANGA ARCADIA | 754 | 0 | 01 May 2021 | SAFIYA BHAIJAN SHAH | B-Bldg Gypsum touch-up work | Touchup Work Mkt | No. | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 11 May 2021 |  | MKT. Marketing Infrastructure | Approved | tausif
GANGA ARCADIA | 755 | 0 | 21 May 2021 | SAFIYA BHAIJAN SHAH | Basement wall- Gypsum plaster work | Tikki Dhada (L) | Sq.Ft | 736.54 | 9.5 | 6997.13 | 0 | 6997.13 | 2.5 | 736.54 | 6997.13 | 0 | 6997.13 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 07 Jun 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jawalikar
GANGA ARCADIA | 755 | 0 | 21 May 2021 | SAFIYA BHAIJAN SHAH | Basement wall- Gypsum plaster work | Gypsum Ceiling (L) | Sq.Ft | 383.54 | 4 | 1534.16 | 0 | 1534.16 | 2.5 | 383.54 | 1534.16 | 0 | 1534.16 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 07 Jun 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jawalikar
GANGA ARCADIA | 756 | 0 | 21 May 2021 | SAFIYA BHAIJAN SHAH | Basement wall- Gypsum plaster work | Gypsum Ceiling (M) | Sq.Ft | 383.54 | 3.5 | 1342.39 | 0 | 1342.39 | 0 | 0 | 0 | 0 | 0 | 383.54 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 07 Jun 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jawalikar
GANGA ARCADIA | 756 | 0 | 21 May 2021 | SAFIYA BHAIJAN SHAH | Basement wall- Gypsum plaster work | Tikki Dhada (M) | Sq.Ft | 736.54 | 9 | 6628.86 | 0 | 6628.86 | 0 | 666.6667 | 6000 | 1080 | 7080 | 69.8733 | -451.14 |  | 90.5133 |  | tausif | chetan.jawalikar | construction open | 07 Jun 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jawalikar
GANGA ARCADIA | 757 | 0 | 21 Jun 2021 | SHINDE PLUMBING CONTRACTOR | B Parking Area Pressure Grouting Work | Pressure Grouting | No. | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 21 Jun 2021 |  | B.C. Rework/Extrawork | Cancelled | tausif | 21 Jun 2021
GANGA ARCADIA | 757 | 0 | 21 Jun 2021 | SHINDE PLUMBING CONTRACTOR | B Parking Area Pressure Grouting Work | Pressure Grouting | No. | 61 | 160 | 9760 | 1756.8 | 11516.8 | 10 | 61 | 9760 | 1756.8 | 11516.8 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 21 Jun 2021 |  | B.C. Rework/Extrawork | Approved | tausif | 21 Jun 2021
GANGA ARCADIA | 758 | 0 | 22 Jun 2021 | SHINDE PLUMBING CONTRACTOR | B Solar Line Repairing Work | Departmental Labour- BC | Day | 4 | 450 | 1800 | 324 | 2124 | 0 | 4 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 03 Jul 2021 |  | B.C. BBM, Plaster, POP | Approved | tausif
GANGA ARCADIA | 758 | 0 | 22 Jun 2021 | SHINDE PLUMBING CONTRACTOR | B Solar Line Repairing Work | Departmental Labour- BC | Day | 2 | 600 | 1200 | 216 | 1416 | 0 | 2 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 03 Jul 2021 |  | B.C. BBM, Plaster, POP | Approved | tausif
GANGA ARCADIA | 758 | 0 | 22 Jun 2021 | SHINDE PLUMBING CONTRACTOR | B Solar Line Repairing Work | Departmental Labour- BC | Day | 2 | 450 | 900 | 162 | 1062 | 0 | 2 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 03 Jul 2021 |  | B.C. BBM, Plaster, POP | Approved | tausif
GANGA ARCADIA | 758 | 0 | 22 Jun 2021 | SHINDE PLUMBING CONTRACTOR | B Solar Line Repairing Work | Departmental Labour- BC | Day | 3 | 600 | 1800 | 324 | 2124 | 0 | 3 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 03 Jul 2021 |  | B.C. BBM, Plaster, POP | Approved | tausif
GANGA ARCADIA | 759 | 0 | 01 Jul 2021 | PATILS FABRICATORS | B MS Beam Fabrication Work | Fastner (L) - SOSB | No. | 36 | 60 | 2160 | 0 | 2160 | 2.5 | 0 | 0 | 0 | 0 | 36 | 0 |  | 0 |  | tausif | tausif | construction open | 08 Jul 2021 |  | S OH Infrastructure | Approved | tausif
GANGA ARCADIA | 759 | 0 | 01 Jul 2021 | PATILS FABRICATORS | B MS Beam Fabrication Work | Fabrication work (L) | Kgs | 43.2 | 28.8 | 1244.16 | 223.94 | 1468.1 | 2.5 | 0 | 0 | 0 | 0 | 43.2 | 0 |  | 0 |  | tausif | tausif | construction open | 08 Jul 2021 |  | Admin. Direct Expenses | Approved | tausif
GANGA ARCADIA | 759 | 0 | 01 Jul 2021 | PATILS FABRICATORS | B MS Beam Fabrication Work | Fabrication work (L) | Kgs | 406.9 | 21.6 | 8789.04 | 1582.02 | 10371.06 | 2.5 | 0 | 0 | 0 | 0 | 406.9 | 0 |  | 0 |  | tausif | tausif | construction open | 08 Jul 2021 |  | Admin. Direct Expenses | Approved | tausif
GANGA ARCADIA | 760 | 0 | 01 Jul 2021 | PATILS FABRICATORS | B MS Beam Fabrication Work | Fabrication work (M) | Kgs | 43.2 | 72 | 3110.4 | 559.88 | 3670.28 | 0 | 0 | 0 | 0 | 0 | 43.2 | 0 |  | 0 |  | tausif | tausif | construction open | 08 Jul 2021 |  | Admin. Direct Expenses | Approved | tausif
GANGA ARCADIA | 760 | 0 | 01 Jul 2021 | PATILS FABRICATORS | B MS Beam Fabrication Work | Fabrication work (M) | Kgs | 406.9 | 54 | 21972.6 | 3955.06 | 25927.66 | 0 | 0 | 0 | 0 | 0 | 406.9 | 0 |  | 0 |  | tausif | tausif | construction open | 08 Jul 2021 |  | Admin. Direct Expenses | Approved | tausif
GANGA ARCADIA | 761 | 0 | 09 Sep 2021 | SHINDE PLUMBING CONTRACTOR | Plumbing Maintenance Work | plumbing maint: work | No. | 1 | 30000 | 30000 | 5400 | 35400 | 2.5 | 1 | 30000 | 0 | 30000 | 0 | 5400 | B Bldg Plumbing maintenance work. Rainwater line changes, Grouting. Flat Linkage. External box elevation box conduit pipe fixing for drain water. External wall crack filling. | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | SOC. M. Civil Work Maintenace | Approved | skmishra
GANGA ARCADIA | 762 | 0 | 16 Oct 2021 | HI TEK INDUSTRIES | Club House FD Door Shutter work | Folding Door Shutter (M) | Sq.Ft | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Size-4.5 ftx 7ft, 2 Shutter Door, Centre Panel Standard Design, Standard Accessories with Grout Door Frame. | 0 |  | Avinash Padmanabha |  | construction open | 19 Nov 2021 |  | B.C. Internal Finishing Itmes | Cancelled | Avinash Padmanabha | 19 Nov 2021
GANGA ARCADIA | 762 | 0 | 16 Oct 2021 | HI TEK INDUSTRIES | Club House FD Door Shutter work | Folding Door Shutter (M) | Sq.Ft | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Size-6.5 ftx 7ft, 3 Shutter Door, Centre Panel Standard Design, Standard Accessories with Grout Door Frame. | 0 |  | Avinash Padmanabha |  | construction open | 19 Nov 2021 |  | B.C. Internal Finishing Itmes | Cancelled | Avinash Padmanabha | 19 Nov 2021
GANGA ARCADIA | 762 | 0 | 16 Oct 2021 | HI TEK INDUSTRIES | Club House FD Door Shutter work | Folding Door Shutter (M+L) | Sq.Ft | 31.5 | 325 | 10237.5 | 1842.76 | 12080.26 | 0 | 31.5 | 10237.5 | 1842.76 | 12080.26 | 0 | 0 | Size-4.5 ftx 7ft, 2 Shutter Door, Centre Panel Standard Design, Standard Accessories with Grout Door Frame. | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar
GANGA ARCADIA | 762 | 0 | 16 Oct 2021 | HI TEK INDUSTRIES | Club House FD Door Shutter work | Transport Charges-DCH | No. | 1 | 1800 | 1800 | 324 | 2124 | 0 | 1 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | DEV. Club House | Approved | chetan.jewalikar
GANGA ARCADIA | 762 | 0 | 16 Oct 2021 | HI TEK INDUSTRIES | Club House FD Door Shutter work | Folding Door Shutter (M+L) | Sq.Ft | 45.5 | 325 | 14787.5 | 2661.76 | 17449.26 | 0 | 45.5 | 14787.5 | 2661.76 | 17449.26 | 0 | 0 | Size-6.5 ftx 7ft, 3 Shutter Door, Centre Panel Standard Design, Standard Accessories with Grout Door Frame. | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 19 Nov 2021 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar
GANGA ARCADIA | 763 | 0 | 16 Oct 2021 | HI TEK INDUSTRIES | Club House FD Door Shutter work | Installation Charges | No. | 0 | 900 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 19 Nov 2021 |  | B.C. Building Common Items | Cancelled | Avinash Padmanabha | 19 Nov 2021
GANGA ARCADIA | 764 | 0 | 02 Jun 2022 | YUGESH KUMAR | Club House Internal Painting Work | One coat Satin Matt Paint (L) | Sq.Ft | 1657 | 3 | 4971 | 0 | 4971 | 2.5 | 0 | 0 | 0 | 0 | 1657 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jun 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande
GANGA ARCADIA | 764 | 0 | 02 Jun 2022 | YUGESH KUMAR | Club House Internal Painting Work | Cleaning Work - Bco | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jun 2022 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 04 Jun 2022
GANGA ARCADIA | 764 | 0 | 02 Jun 2022 | YUGESH KUMAR | Club House Internal Painting Work | 1st Coat Satin Matt Paint (L) | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jun 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 04 Jun 2022
GANGA ARCADIA | 764 | 0 | 02 Jun 2022 | YUGESH KUMAR | Club House Internal Painting Work | Wall Touch up | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jun 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 04 Jun 2022
GANGA ARCADIA | 765 | 0 | 05 Jul 2022 | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | Legal Consultancy Legal Consultancy for CGWB | Legal Consultancy.- | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 22 Jul 2022 |  | Consultancy Legal | Approved | Swapnil Erande
GANGA ARCADIA | 766 | 0 | 04 Aug 2022 | AJAY KUMAR GUPTA | B Building Flat Maintenance | Helper-SOS | Day | 10 | 500 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 23 Aug 2022 |  | S OH Infrastructure | Approved | Swapnil Erande
GANGA ARCADIA | 766 | 0 | 04 Aug 2022 | AJAY KUMAR GUPTA | B Building Flat Maintenance | Mason - SOS | Day | 10 | 800 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 23 Aug 2022 |  | S OH Site Staff | Approved | Swapnil Erande
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% After SEAC recommendation | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% After SEAC Recommendation. | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | DUSHANT GORE | 21 Feb 2023
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% Submission of EIA report | Environmental Clearance- SEAC & SEIAA | No. | 1 | 375000 | 375000 | 67500 | 442500 | 0 | 1 | 375000 | 67500 | 442500 | 0 | 0 | 25 % Submission of EIA Report | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% on obtaining Environmental Clearance | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | ADITYA CHOUGULE | 16 Sep 2022
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC- 25% Advance along with W.O. | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | ADITYA CHOUGULE | 16 Sep 2022
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% Submission of EIA report | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | ADITYA CHOUGULE | 16 Sep 2022
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% After SEAC recommendation | Environmental Clearance- SEAC & SEIAA | No. | 1 | 375000 | 375000 | 67500 | 442500 | 0 | 1 | 375000 | 67500 | 442500 | 0 | 0 | 25 % After SEAC Recommendation. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% Submission of EIA report | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% Submission of EIA Report. | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | DUSHANT GORE | 21 Feb 2023
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% on obtaining Environmental Clearance | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% on obtaining Environmental Clearance. | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | DUSHANT GORE | 21 Feb 2023
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC- 25% Advance along with W.O. | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% as Advance along with WorkOrder. | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | DUSHANT GORE | 21 Feb 2023
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% on obtaining Environmental Clearance | Environmental Clearance- SEAC & SEIAA | No. | 1 | 375000 | 375000 | 67500 | 442500 | 0 | 1 | 375000 | 67500 | 442500 | 0 | 0 | 25 % on obtaining Environmenatal Clearance. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC- 25% Advance along with W.O. | Environmental Clearance- SEAC & SEIAA | No. | 1 | 375000 | 375000 | 67500 | 442500 | 0 | 1 | 375000 | 67500 | 442500 | 0 | 0 | 25 % Advance along with Work order. | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande
GANGA ARCADIA | 767 | 0 | 16 Sep 2022 | MAHABAL ENVIRO ENGINEERS PRIVATE LIMITED | EC - 25% After SEAC recommendation | Environmental Clearance- SEAC & SEIAA | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% As Advance along with Purcha | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Sep 2022 |  | 03 CONSULTANCY | Cancelled | ADITYA CHOUGULE | 16 Sep 2022
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2016 to Jan 2017) | Water Tanker supply | Trips | 365 | 550 | 200750 | 0 | 200750 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2012 to Dec 2012) | Water Tanker supply | Trips | 365 | 700 | 255500 | 0 | 255500 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2015 to Dec 2015) | Water Tanker supply | Trips | 365 | 550 | 200750 | 0 | 200750 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2011 to Dec 2011) | Water Tanker supply | Trips | 365 | 700 | 255500 | 0 | 255500 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2016 to Jan 2017) | Water Tanker supply | Trips | 365 | 700 | 255500 | 0 | 255500 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2011 to Dec 2011) | Water Tanker supply | Trips | 365 | 550 | 200750 | 0 | 200750 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2013 to Dec 2013) | Water Tanker supply | Trips | 365 | 700 | 255500 | 0 | 255500 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2014 to Dec 2014) | Water Tanker supply | Trips | 365 | 700 | 255500 | 0 | 255500 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2012 to Dec 2012) | Water Tanker supply | Trips | 365 | 550 | 200750 | 0 | 200750 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2015 to Dec 2015) | Water Tanker supply | Trips | 365 | 700 | 255500 | 0 | 255500 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2014 to Dec 2014) | Water Tanker supply | Trips | 365 | 550 | 200750 | 0 | 200750 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 768 | 0 | 06 Oct 2022 | VIJAY WATER SUPPLIERS | Water Tanker Supply (Jan 2013 to Dec 2013) | Water Tanker supply | Trips | 365 | 550 | 200750 | 0 | 200750 | 0 | 0 | 0 | 0 | 0 | 365 | 0 |  | 0 |  | Dushant Gore |  | construction open |  |  | S OH Infrastructure | Un-Approved
GANGA ARCADIA | 769 | 0 | 10 Aug 2023 | URJAL CONSULTANT PRIVATE LIMITED | Professional Consultancy for EC Expansion | Environmental Clearance Expansion | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0.5 | 50000 | 9000 | 59000 | 0.5 | 59000 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 18 Aug 2023 |  | Consultacy Environmental | Approved | Swapnil Erande