## Project_Work_Order6385871916518
Project Work Order
From 01 Jan 2000 To 31 Jul 2024
Page 1 of 1
Total Records: 183 Records 1 To 183
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 2 | 0 | 08 Feb 2020 | KAKADE RASHMI RAVINDRA | ECBC compliance report | ECBC Compliance | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | consultancy | 22 Feb 2020 |  | 03 CONSULTANCY | Approved | chetan | 1900-01-01
GANGA ALTUS | 3 | 0 | 08 Feb 2020 | KAKADE RASHMI RAVINDRA | Traffic Analysis Report | Detailed Traffic & Transportation study | No. | 1 | 65000 | 65000 | 0 | 65000 | 0 | 1 | 65000 | 0 | 65000 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | consultancy | 22 Feb 2020 |  | Consultacy Architectural | Approved | chetan | 1900-01-01
GANGA ALTUS | 4 | 0 | 08 Feb 2020 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | No. | 1 | 425000 | 425000 | 76500 | 501500 | 0 | 1 | 425000 | 76500 | 501500 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | consultancy | 22 Feb 2020 |  | 03 CONSULTANCY | Approved | edp | 07 Aug 2020
GANGA ALTUS | 4 | 1 | 08 Feb 2020 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | No. | 1 | 595000 | 595000 | 107100 | 702100 | 0 | 1 | 595000 | 107100 | 702100 | 0 | 0 | (Amendment) | 100 |  | tausif | chetan.jewalikar | consultancy | 22 Feb 2020 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 11 | 0 | 22 Feb 2020 | GOLDEN POOLS | Environmental Clearance Consultancy | Professional Fees. | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | GANDHI | chetan | consultancy | 26 Feb 2020 |  | 03 CONSULTANCY | Approved | GANDHI | 22 Feb 2020
GANGA ALTUS | 25 | 0 | 19 Mar 2020 | SSAP ADVISORS LLP | Professional Consultancy (RERA) (D Bldg) - 1 Job | Professional Fees. | No. | 1 | 7500 | 7500 | 1350 | 8850 | 0 | 1 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | SHUBHAM GIRI | chetan | Construction | 11 Jul 2020 |  | 03 CONSULTANCY | Approved | chetan | 1900-01-01
GANGA ALTUS | 26 | 0 | 19 Mar 2020 | SSAP ADVISORS LLP | Professional Consultancy (RERA) (E Bldg) - 1 Job | Professional Fees. | No. | 1 | 7500 | 7500 | 1350 | 8850 | 0 | 1 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | SHUBHAM GIRI | chetan | Construction | 11 Jul 2020 |  | 03 CONSULTANCY | Approved | chetan | 1900-01-01
GANGA ALTUS | 33 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | D (Comm) MEP Consultancy | MEP Consultancy | Sq.Ft | 4907 | 4 | 19628 | 3533.04 | 23161.04 | 0 | 4170.65 | 16682.6 | 3002.86 | 19685.46 | 736.35 | 3475.58 |  | 84.9939 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ALTUS | 33 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | D MEP Consultancy | MEP Consultancy | Sq.Ft | 204565 | 4 | 818260 | 147286.8 | 965546.8 | 0 | 204565 | 818260 | 147286.8 | 965546.8 | 0 | 0 |  | 100 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ALTUS | 33 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | E MEP Consultancy | MEP Consultancy | Sq.Ft | 204565 | 4 | 818260 | 147286.8 | 965546.8 | 0 | 184096.25 | 736385 | 132549.3 | 868934.3 | 20468.75 | 96612.5 |  | 89.994 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ALTUS | 33 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | F (Comm) MEP Consultancy | MEP Consultancy | Sq.Ft | 44742 | 4 | 178968 | 32214.24 | 211182.24 | 0 | 29060.05 | 116240.2 | 20923.24 | 137163.44 | 15681.95 | 74018.8 |  | 64.9503 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ALTUS | 33 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | E (Comm) MEP Consultancy | MEP Consultancy | Sq.Ft | 6460 | 4 | 25840 | 4651.2 | 30491.2 | 0 | 5491 | 21964 | 3953.52 | 25917.52 | 969 | 4573.68 |  | 85 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ALTUS | 33 | 1 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | MEP Consultancy Difference Area for D, E & F | MEP Consultancy (Qty Diff.) | Sq.Ft | 10450 | 4 | 41800 | 7524 | 49324 | 0 | 0 | 0 | 0 | 0 | 10450 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 26 Jun 2020 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 84 | 0 | 18 Sep 2020 | SPACE TECK | Virtual Walkthrough Consultancy | Virtual Walkthrough | No. | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | consultancy | 21 Sep 2020 |  | Consultacy Architectural | Cancelled | skmishra | 21 Sep 2020
GANGA ALTUS | 84 | 0 | 18 Sep 2020 | SPACE TECK | Virtual Walkthrough Consultancy | Virtual Walkthrough | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | tausif.shaikh | chetan.jawalikar | consultancy | 21 Sep 2020 |  | Consultacy Architectural | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 106 | 0 | 28 Sep 2020 | GLOBAL GEOTECHNICS | Highrise Clearance | H.R.C. Consultancy | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | consultancy | 03 Oct 2020 |  | 03 CONSULTANCY | Approved | tausif.shaikh | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Consultancy Charges - Transformer room (Not to refer) | Consultancy Charges | No. | 0 | 1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Cancelled | DUSHANT GORE | 30 Jan 2023
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Consultancy Charges - Compound Wall details | Consultancy Charges | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Consultancy Charges - Transformer room Roof Slab | RCC Consultancy | Sq.Ft | 1079 | 5.25 | 5664.75 | 1019.66 | 6684.41 | 0 | 0 | 0 | 0 | 0 | 1079 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Club House - RCC Consultancy | RCC Consultancy | Sq.Ft | 16344 | 5.25 | 85806 | 15445.08 | 101251.08 | 0 | 16344 | 85806 | 15445.12 | 101251.12 | 0 | -0.04 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Podium - RCC Consultancy | RCC Consultancy | Sq.Ft | 2362 | 6 | 14172 | 2550.96 | 16722.96 | 0 | 0 | 0 | 0 | 0 | 2362 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-D RCC Consultancy | RCC Consultancy | Sq.Ft | 226154 | 6 | 1356924 | 244246.32 | 1601170.32 | 0 | 226153.7999 | 1356922.8 | 244246.14 | 1601168.94 | 0.2001 | 1.38 |  | 99.9999 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Tejas Raverkar | 01 Nov 2020
GANGA ALTUS | 114 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-D&E Parking RCC Consultancy | RCC Consultancy | Sq.Ft | 222076 | 6 | 1332456 | 239842.08 | 1572298.08 | 0 | 222075.4 | 1332452.4 | 239841.42 | 1572293.82 | 0.6 | 4.26 |  | 99.9997 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Tejas Raverkar | 01 Nov 2020
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-E RCC Consultancy (Area Diff.) | RCC Consultancy Area Diff. | Sq.Ft | 12872 | 6 | 77232 | 13901.76 | 91133.76 | 0 | 12872 | 77232 | 13901.78 | 91133.78 | 0 | -0.02 |  | 100 |  | DUSHANT GORE | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-E RCC Consultancy (Area Diff.) | RCC Consultancy Area Diff. | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Cancelled | DUSHANT GORE | 30 Jan 2023
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Podium - RCC Consultancy | RCC Consultancy | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | consultancy | 31 Oct 2020 |  | Consultacy RCC | Cancelled | DUSHANT GORE | 30 Jan 2023
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-D RCC Consultancy (Area Diff.) | RCC Consultancy Area Diff. | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Cancelled | DUSHANT GORE | 30 Jan 2023
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg - F RCC Consultancy | RCC Consultancy | Sq.Ft | 41849 | 6 | 251094 | 45196.92 | 296290.92 | 0 | 34735.5833 | 208413.5 | 37514.46 | 245927.96 | 7113.4167 | 50362.96 |  | 83.0022 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-D RCC Consultancy (Area Diff.) | RCC Consultancy Area Diff. | Sq.Ft | 12872 | 6 | 77232 | 13901.76 | 91133.76 | 0 | 12872 | 77232 | 13901.78 | 91133.78 | 0 | -0.02 |  | 100 |  | DUSHANT GORE | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Bldg-E RCC Consultancy | RCC Consultancy | Sq.Ft | 226154 | 6 | 1356924 | 244246.32 | 1601170.32 | 0 | 226153.6 | 1356921.6 | 244245.9 | 1601167.5 | 0.4 | 2.82 |  | 99.9998 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Tejas Raverkar | 01 Nov 2020
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Consultancy Charges - Well covering details | Consultancy Charges | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Consultancy Charges - Entrance Gate | Consultancy Charges | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | RCC Consultancy - UGWT F | RCC Consultancy | Ltrs | 42076 | 0.15 | 6311.4 | 1136.06 | 7447.46 | 0 | 42076 | 6311.4 | 1136.06 | 7447.46 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | RCC Consultancy - OHWT D & E | RCC Consultancy | Ltrs | 329800 | 0.15 | 49470 | 8904.6 | 58374.6 | 0 | 329800 | 49470 | 8904.6 | 58374.6 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | RCC Consultancy - OHWT F | RCC Consultancy | Ltrs | 45465 | 0.15 | 6819.75 | 1227.56 | 8047.31 | 0 | 45465 | 6819.75 | 1227.56 | 8047.31 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 114 | 1 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | RCC Consultancy - UGWT D & E | RCC Consultancy | Ltrs | 608206 | 0.15 | 91230.9 | 16421.56 | 107652.46 | 0 | 608206 | 91230.9 | 16421.56 | 107652.46 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 121 | 0 | 03 Dec 2020 | AMIT KUMAR PODDAR | Professional Consultancy (Commercial F-Bldg) | Professional Fees. | No. | 1 | 13000 | 13000 | 0 | 13000 | 0 | 1 | 13000 | 0 | 13000 | 0 | 0 |  | 100 |  | tausif | tausif | consultancy | 08 Dec 2020 |  | 03 CONSULTANCY | Approved | tausif | 1900-01-01
GANGA ALTUS | 134 | 0 | 12 Jan 2021 | SUPRABHA VISHWA ENVIRO CONSULTANTS | Professional Consultancy Environmental Consultancy | Consultancy Charges | No. | 1 | 847457.63 | 847457.63 | 152542.38 | 1000000.01 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | sunita shirolkar | consultancy | 20 Jan 2021 |  | Consultacy Architectural | Approved | sunita shirolkar | 1900-01-01
GANGA ALTUS | 139 | 0 | 16 Feb 2021 | VISION MANAGEMENT SERVICES | Contract Labour act Registration & Compliance | Consultancy Charges | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | tausif | tausif | consultancy | 16 Feb 2021 |  | Consultacy Architectural | Approved | tausif | 1900-01-01
GANGA ALTUS | 139 | 0 | 16 Feb 2021 | VISION MANAGEMENT SERVICES | Contract Labour act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 1 | 18500 | 18500 | 0 | 18500 | 0 | 1 | 18500 | 0 | 18500 | 0 | 0 |  | 100 |  | tausif | tausif | consultancy | 16 Feb 2021 |  | Consultancy Labour act Regist. | Approved | tausif | 1900-01-01
GANGA ALTUS | 139 | 0 | 16 Feb 2021 | VISION MANAGEMENT SERVICES | Contract Labour act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 16 Feb 2021 |  | Consultancy Labour act Regist. | Cancelled | tausif | 16 Feb 2021
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 4 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 145 | 3 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 66666 | 66666 | 0 | 66666 | 0 | 1 | 66666 | 0 | 66666 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 17315 | 17315 | 0 | 17315 | 0 | 1 | 17315 | 0 | 17315 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 2 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 1 | 25865 | 25865 | 0 | 25865 | 0 | 1 | 25865 | 0 | 25865 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 145 | 0 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 12 | 51000 | 612000 | 0 | 612000 | 0 | 2.1912 | 111749.54 | 0 | 111749.54 | 9.8088 | 500250.46 |  | 18.26 |  | tausif | tausif | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | tausif | 1900-01-01
GANGA ALTUS | 145 | 1 | 23 Feb 2021 | BHASKAR VITTAL SONPARATE | Legal Consultancy | Legal Consultancy | Month | 11.6128 | 51000 | 592252.8 | 0 | 592252.8 | 0 | 1.7677 | 90154.7 | 0 | 90154.7 | 9.8451 | 502098.1 |  | 15.222 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Foreclose | Dushant Gore | 18 Jul 2022
GANGA ALTUS | 146 | 1 | 23 Feb 2021 | MADHAVI ANJAN GHOSH | G CUBE- Professional Consultancy | Professional Fees | Month | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Cancelled | skmishra | 29 Jan 2022
GANGA ALTUS | 146 | 4 | 23 Feb 2021 | MADHAVI ANJAN GHOSH | G CUBE- Professional Consultancy | Professional Fees | Month | 12 | 50000 | 600000 | 0 | 600000 | 0 | 6.9997 | 349986 | 0 | 349986 | 5.0003 | 250014 |  | 58.3308 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 146 | 2 | 23 Feb 2021 | MADHAVI ANJAN GHOSH | G CUBE- Professional Consultancy | Professional Fees | Month | 12 | 50000 | 600000 | 0 | 600000 | 0 | 12 | 600000 | 0 | 600000 | 0 | 0 |  | 100 |  | dushant gore | skmishra | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | ADITYA CHOUGULE | 05 Jan 2023
GANGA ALTUS | 146 | 3 | 23 Feb 2021 | MADHAVI ANJAN GHOSH | G CUBE- Professional Consultancy | Professional Fees | Month | 12 | 50000 | 600000 | 0 | 600000 | 0 | 10.0008 | 500040 | 0 | 500040 | 1.9992 | 99960 |  | 83.34 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 146 | 0 | 23 Feb 2021 | MADHAVI ANJAN GHOSH | G CUBE- Professional Consultancy | Professional Fees | Month | 12 | 60000 | 720000 | 0 | 720000 | 0 | 10 | 599998.04 | 0 | 599998.04 | 2 | 120001.96 |  | 83.3333 |  | tausif | tausif | construction open | 24 Feb 2021 |  | 03 CONSULTANCY | Approved | tausif | 23 Feb 2021
GANGA ALTUS | 168 | 0 | 26 Mar 2021 | SKETCH MARK | Architectural & Liasoning Consultancy | Consultancy Charges | No. | 1 | 350000 | 350000 | 0 | 350000 | 0 | 0.4286 | 149999.5 | 0 | 149999.5 | 0.5714 | 200000.5 |  | 42.86 |  | tausif | tausif | consultancy | 12 Jul 2021 |  | Consultacy Architectural | Approved | tausif | 1900-01-01
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Navgraha Treatment Large | set | 0 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 17 Apr 2021 |  | Consultancy Vastu | Cancelled | tausif | 17 Apr 2021
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Navratna Set (L) | No. | 1 | 22100 | 22100 | 663 | 22763 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | Consultancy Vastu | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Loose Pyramid (L) | No. | 945 | 91.8 | 86751 | 15615.18 | 102366.18 | 0 | 0 | 0 | 0 | 0 | 945 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Loose Pyramid (L) | No. | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Cancelled | tausif | 17 Apr 2021
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Navgraha Treatment Large | set | 1 | 9860 | 9860 | 1774.8 | 11634.8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | Consultancy Vastu | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Large Yantras (L) | No. | 21 | 561 | 11781 | 2120.58 | 13901.58 | 0 | 0 | 0 | 0 | 0 | 21 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 184 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Large Yantras (L) | No. | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Cancelled | tausif | 17 Apr 2021
GANGA ALTUS | 185 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Loose Pyramid (M) | No. | 945 | 137.7 | 130126.5 | 23422.78 | 153549.28 | 0 | 0 | 0 | 0 | 0 | 945 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 185 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Large Yantras (M) | No. | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Cancelled | tausif | 17 Apr 2021
GANGA ALTUS | 185 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Navgrah Treatment Large (M) | set | 1 | 14790 | 14790 | 2662.2 | 17452.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 185 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Large Yantras (M) | No. | 21 | 841.5 | 17671.5 | 3180.88 | 20852.38 | 0 | 0 | 0 | 0 | 0 | 21 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 185 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Navratna Set (M) | No. | 1 | 33150 | 33150 | 994.5 | 34144.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 17 Apr 2021 |  | Consultancy Vastu | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 185 | 0 | 17 Apr 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Loose Pyramid (M) | No. | 0 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 17 Apr 2021 |  | 03 CONSULTANCY | Cancelled | tausif | 17 Apr 2021
GANGA ALTUS | 226 | 1 | 22 Jun 2021 | PERITUS REALITY SOLUTIONS LLP | D- Project Services Consultancy | Consultancy Charges | Sq.Ft | 18089.35 | 0.95 | 17184.88 | 3093.28 | 20278.16 | 0 | 18089.35 | 17184.88 | 3093.28 | 20278.16 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | consultancy | 03 Jul 2021 |  | Consultacy Architectural | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 226 | 1 | 22 Jun 2021 | PERITUS REALITY SOLUTIONS LLP | E- Project Services Consultancy | Consultancy Charges | Sq.Ft | 19625.28 | 0.95 | 18644.02 | 3355.92 | 21999.94 | 0 | 19625.0644 | 18643.81 | 3355.88 | 21999.69 | 0.2156 | 0.24 |  | 99.9989 |  | chetan.jewalikar | chetan.jewalikar | consultancy | 03 Jul 2021 |  | Consultacy Architectural | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 226 | 0 | 22 Jun 2021 | PERITUS REALITY SOLUTIONS LLP | D/E/F Commercial- Project Services Consultancy | Consultancy Charges | Sq.Ft | 56109.58 | 0.95 | 53304.1 | 9594.74 | 62898.84 | 0 | 0 | 0 | 0 | 0 | 56109.58 | 0 | Note 1) Quantity Survey & BOQ Preparation 2) Listing of Specification 3) Listing of Material & Labour Rates 4) Rate Analysis of Every Item 5) Costing of all Construction items | 0 |  | tausif | tausif | consultancy | 03 Jul 2021 |  | Consultacy Architectural | Approved | tausif | 1900-01-01
GANGA ALTUS | 226 | 0 | 22 Jun 2021 | PERITUS REALITY SOLUTIONS LLP | E- Project Services Consultancy | Consultancy Charges | Sq.Ft | 199893.99 | 0.95 | 189899.29 | 34181.88 | 224081.17 | 0 | 199893.99 | 189899.29 | 34181.88 | 224081.17 | 0 | 0 | Note 1) Quantity Survey & BOQ Preparation 2) Listing of Specification 3) Listing of Material & Labour Rates 4) Rate Analysis of Every Item 5) Costing of all Construction items | 100 |  | tausif | tausif | consultancy | 03 Jul 2021 |  | Consultacy Architectural | Approved | tausif | 1900-01-01
GANGA ALTUS | 226 | 0 | 22 Jun 2021 | PERITUS REALITY SOLUTIONS LLP | D- Project Services Consultancy | Consultancy Charges | Sq.Ft | 199893.29 | 0.95 | 189898.63 | 34181.76 | 224080.39 | 0 | 199893.2502 | 189898.59 | 34181.74 | 224080.33 | 0.0398 | 0.06 | Note 1) Quantity Survey & BOQ Preparation 2) Listing of Specification 3) Listing of Material & Labour Rates 4) Rate Analysis of Every Item 5) Costing of all Construction items | 100 |  | tausif | tausif | consultancy | 03 Jul 2021 |  | Consultacy Architectural | Approved | tausif | 1900-01-01
GANGA ALTUS | 282 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Vastu Consultancy | No. | 1 | 33898.3 | 33898.3 | 6101.7 | 40000 | 0 | 1 | 33898.3 | 6101.7 | 40000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | consultancy | 28 Oct 2021 |  | Admin. Indirect Expenses | Approved | skmishra | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Photo Frame | No. | 1 | 2069.1 | 2069.1 | 372.44 | 2441.54 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | MKT. Marketing Infrastructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Yantra Large | No. | 40 | 1575 | 63000 | 11340 | 74340 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Yantra XL | No. | 2 | 6750 | 13500 | 2430 | 15930 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Navratna Treatment | set | 1 | 40500 | 40500 | 7290 | 47790 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | Consultancy Vastu | Un-Approved |  | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Special Pyramid | No. | 59 | 990 | 58410 | 10513.8 | 68923.8 | 0 | 0 | 0 | 0 | 0 | 59 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | Consultancy Vastu | Un-Approved |  | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Copper Strips | No. | 197 | 481.5 | 94855.5 | 17074 | 111929.5 | 0 | 0 | 0 | 0 | 0 | 197 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | Consultancy Vastu | Un-Approved |  | 1900-01-01
GANGA ALTUS | 287 | 0 | 23 Nov 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy | Medium Swastik (Pyramids) | No. | 377 | 243 | 91611 | 16489.98 | 108100.98 | 0 | 0 | 0 | 0 | 0 | 377 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ALTUS | 396 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | Registration Charges | No. | 1 | 300 | 300 | 54 | 354 | 0 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 396 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 1 | 14750 | 14750 | 2655 | 17405 | 0 | 1 | 14750 | 2655 | 17405 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | Consultancy Labour act Regist. | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 396 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | Registration Charges | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 396 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | Registration of Company (RC) | No. | 1 | 34250 | 34250 | 6165 | 40415 | 0 | 1 | 34250 | 6165 | 40415 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 438 | 0 | 03 Jun 2022 | AYAZ RAFIK SHAIKH | Professional fees for liaisoning | Liasoning Consultancy (Architectural) | Sq.Ft | 724404.067 | 3 | 2173212.2 | 0 | 2173212.2 | 0 | 488861.6667 | 1466585 | 0 | 1466585 | 235542.4003 | 706627.2 |  | 67.4847 |  | Dushant Gore | chetan.jewalikar | consultancy | 25 Jun 2022 |  | Consultacy Architectural | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 466 | 0 | 05 Jul 2022 | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | Legal Consultancy for CGWB | Legal Consultancy.- | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 22 Jul 2022 |  | Consultancy Legal | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 530 | 0 | 30 Aug 2022 | YOGESH R INGALE & ASSOCIATES | Professional Fees For Annual Return & GST Audit Services | Professional Fees (Yrs) | Yearly | 1 | 12000 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 530 | 0 | 30 Aug 2022 | YOGESH R INGALE & ASSOCIATES | Professional Fees For Monthly Retainership Services | Professional Fees | Month | 12 | 1500 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ALTUS | 634 | 0 | 04 Mar 2023 | PRITESH SURESH BANSAL | Professional Fees | Internal Audit Fees -AIE- | Month | 12 | 30000 | 360000 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ALTUS | 651 | 0 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 1 | 34000 | 34000 | 6120 | 40120 | 0 | 1 | 34000 | 6120 | 40120 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 651 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | Registration of Company (RC) | No. | 375 | 350 | 131250 | 23625 | 154875 | 0 | 375 | 131250 | 23625 | 154875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 651 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Cancelled | MONALI CHAUDHAR | 16 Mar 2024
GANGA ALTUS | 651 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 375 | 350 | 131250 | 23625 | 154875 | 0 | 375 | 131250 | 23625 | 154875 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 651 | 0 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour act Registration & Compliance | Registration of Company (RC) | No. | 1 | 72250 | 72250 | 13005 | 85255 | 0 | 1 | 72250 | 13005 | 85255 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 766 | 1 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 766 | 0 | 06 Sep 2023 | TARUSH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 1 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 767 | 0 | 06 Sep 2023 | KRITESH ATUL GOEL | Professional Fees | Professional Fees | Month | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Sep 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 1 | 150000 | 0 | 150000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Cancelled | ADITYA.CHOUGULE | 06 Jul 2024
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 1 | 150000 | 0 | 150000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1046 | 0 | 06 Jul 2024 | ANITADEVI SURESHKUMAR BANSAL | Professional Fees | Professional Fees | Month | 1 | 150000 | 150000 | 0 | 150000 | 0 | 1 | 150000 | 0 | 150000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01