## Project_Work_Order6385872176972
Project Work Order
From 01 Jan 2000 To 31 Jul 2024
Page 1 of 1
Total Records: 1595 Records 1 To 1595
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 51 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | DG Plinth work | Brickwork 9"- UDG | Sq.Ft | 40 | 15 | 600 | 0 | 600 | 2.5 | 40 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | GANDHI | tausif | construction open | 15 Dec 2020 |  | UTI. D.G.Set | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 51 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | DG Plinth work | Tar Plaster-Dld | Sq.Ft | 40 | 12 | 480 | 0 | 480 | 2.5 | 40 | 480 | 0 | 480 | 0 | 0 |  | 100 |  | GANDHI | tausif | construction open | 15 Dec 2020 |  | DEV. Landscape/Equipment | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 51 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | DG Plinth work | PCC - UDG | Sq.Ft | 36 | 5 | 180 | 0 | 180 | 2.5 | 36 | 180 | 0 | 180 | 0 | 0 |  | 100 |  | GANDHI | tausif | construction open | 15 Dec 2020 |  | UTI. D.G.Set | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 118 | 0 | 27 Nov 2020 | HARISH CHANDRA JADHAV ELECTRICALS | Earthing Work | Earthing work(m+l)- BC | No. | 5 | 4000 | 20000 | 3600 | 23600 | 0 | 5 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | tausif | tausif | Construction | 22 Dec 2020 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ALTUS | 118 | 0 | 27 Nov 2020 | HARISH CHANDRA JADHAV ELECTRICALS | Earthing Work | Excavation work- BC. | No. | 5 | 500 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | tausif | tausif | Construction | 22 Dec 2020 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ALTUS | 118 | 0 | 27 Nov 2020 | HARISH CHANDRA JADHAV ELECTRICALS | Earthing Work | Excavation work- BC. | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | Construction | 22 Dec 2020 |  | B.C. RCC Substructure | Cancelled | tausif | 22 Dec 2020
GANGA ALTUS | 118 | 0 | 27 Nov 2020 | HARISH CHANDRA JADHAV ELECTRICALS | Earthing Work | Earthing work(m+l)- BC | No. | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | Construction | 22 Dec 2020 |  | B.C. Building Common Items | Cancelled | tausif | 22 Dec 2020
GANGA ALTUS | 122 | 3 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Perma Waterproofing (L) | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Cancelled | Avinash Padmanabha | 25 Nov 2021
GANGA ALTUS | 122 | 2 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT mambrane waterproofing at Base | Perma Waterproofing (L) | Sq.Ft | 395.11 | 10 | 3951.1 | 711.2 | 4662.3 | 10 | 395.11 | 3951.1 | 711.2 | 4662.3 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 122 | 3 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Perma Waterproofing (L) | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 13 Jan 2022
GANGA ALTUS | 122 | 2 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi External W/P | Perma Waterproofing (L) | Sq.Ft | 831.45 | 12 | 9977.4 | 1795.94 | 11773.34 | 10 | 831.45 | 9977.4 | 1795.94 | 11773.34 | 0 | 0 | Honeycomb and tie rod repairing treatment by using perma polycrete plus SBR Bond,Apply NEOPROOF RC-202 plus 50 GSM Coating. | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 122 | 3 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Perma Waterproofing (L) | Sq.Ft | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Honeycomb and tie rod repairing treatment by using perma polycrete plus SBR Bond,Apply NEOPROOF RC-202 plus 50 GSM Coating. | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 13 Jan 2022
GANGA ALTUS | 123 | 3 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Perma Waterproofing (M) | Sq.Ft | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 13 Jan 2022
GANGA ALTUS | 123 | 2 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT mambrane waterproofing at Base | Perma Waterproofing (M) | Sq.Ft | 395.11 | 27 | 10667.97 | 1920.24 | 12588.21 | 0 | 395.11 | 10667.97 | 1920.24 | 12588.21 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 123 | 2 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi External W/P | Perma Waterproofing (M) | Sq.Ft | 831.45 | 30 | 24943.5 | 4489.84 | 29433.34 | 0 | 831.45 | 24943.5 | 4489.84 | 29433.34 | 0 | 0 | Also including all other required material | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 123 | 3 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Perma Waterproofing (M) | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 13 Jan 2022
GANGA ALTUS | 123 | 3 | 08 Dec 2020 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Perma Waterproofing (M) | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2020 |  | 06 WATERPROOFING WORK | Cancelled | Avinash Padmanabha | 25 Nov 2021
GANGA ALTUS | 127 | 0 | 16 Dec 2020 | GREENSOL TECH | STP-265 KLD | Sewage Treatment Plant (L) | No. | 1 | 585000 | 585000 | 105300 | 690300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | STP-265KLD (MBBR TECHNOLOGY) (L) | 0 |  | tausif | Swapnil Erande | Construction | 16 Dec 2020 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 128 | 0 | 16 Dec 2020 | GREENSOL TECH | STP-265 KLD | Sewage Treatment Plant (M) | No. | 1 | 1365000 | 1365000 | 245700 | 1610700 | 0 | 1 | 1365000 | 245700 | 1610700 | 0 | 0 | STP-265KLD (MBBR TECHNOLOGY) (M) | 100 |  | tausif | Swapnil Erande | Construction | 16 Dec 2020 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 2 | 08 Apr 2021 | SS ENTERPRISES | Transformer Room Loose material excavation work | Excavation by Bucket | Cu.Mtrs | 60.75 | 60 | 3645 | 656.1 | 4301.1 | 0 | 60.75 | 3645 | 0 | 3645 | 0 | 656.1 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Apr 2021 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 2 | 08 Apr 2021 | SS ENTERPRISES | Transformer Room Loose material excavation work | Spreading & Levelling Work | Cu.Mtrs | 60.75 | 20 | 1215 | 218.7 | 1433.7 | 0 | 60.75 | 1215 | 0 | 1215 | 0 | 218.7 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 0 | 08 Apr 2021 | SS ENTERPRISES | Bldg D,E & Podium UGWT Excavation work | Spreading & Levelling Work | Cu.Mtrs | 1908.08 | 15 | 28621.2 | 5151.82 | 33773.02 | 0 | 1908.0667 | 28621 | 5151.78 | 33772.78 | 0.0133 | 0.24 |  | 99.9993 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 175 | 4 | 08 Apr 2021 | SS ENTERPRISES | Bldg D,E & Podium UGWT Excavation work | Excavation by Needle (Rate Diff.) | Cu.Mtrs | 1908.08 | 100 | 190808 | 34345.44 | 225153.44 | 0 | 1908.08 | 190808 | 34345.44 | 225153.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Apr 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 3 | 08 Apr 2021 | SS ENTERPRISES | LG Floor- Excavation Work for Service line | Excavation Manually | Cu.Mtrs | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 10 Dec 2022
GANGA ALTUS | 175 | 0 | 08 Apr 2021 | SS ENTERPRISES | Bldg D,E & Podium UGWT Excavation work | Breaking By Needle -BC | Cu.Mtrs | 1908.08 | 210 | 400696.8 | 72125.42 | 472822.22 | 0 | 1908.0715 | 400695.02 | 72125.1 | 472820.12 | 0.0085 | 2.11 |  | 99.9996 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 175 | 1 | 08 Apr 2021 | SS ENTERPRISES | F-Building STP & ETP Excavation Work | Spreading & Levelling | Cu.Ft | 823.72 | 20 | 16474.4 | 2965.4 | 19439.8 | 0 | 823.7 | 16474 | 1710 | 18184 | 0.02 | 1255.8 |  | 99.9976 |  | Dushant Gore | Swapnil Erande | construction open | 16 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 1 | 08 Apr 2021 | SS ENTERPRISES | F-Building STP & ETP Excavation Work | Excavation By Needle | Cu.Mtrs | 74.88 | 250 | 18720 | 3369.6 | 22089.6 | 0 | 74.88 | 18720 | 0 | 18720 | 0 | 3369.6 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 16 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 4 | 08 Apr 2021 | SS ENTERPRISES | Bldg D,E & Podium UGWT Excavation work | Excavation by Needle (Rate Diff.) | Cu.Mtrs | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Apr 2021 |  | No category | Cancelled | ADITYA CHOUGULE | 01 Mar 2023
GANGA ALTUS | 175 | 3 | 08 Apr 2021 | SS ENTERPRISES | LG Floor- Excavation Work for Service line | Backfilling - UDR | Cu.Ft | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Apr 2021 |  | UTI. Drainage | Cancelled | ADITYA CHOUGULE | 10 Dec 2022
GANGA ALTUS | 175 | 1 | 08 Apr 2021 | SS ENTERPRISES | F-Building STP & ETP Excavation Work | Excavation by Bucket | Cu.Mtrs | 823.72 | 60 | 49423.2 | 8896.18 | 58319.38 | 0 | 823.6 | 49416 | 7431.48 | 56847.48 | 0.12 | 1471.9 |  | 99.9854 |  | Dushant Gore | Swapnil Erande | construction open | 16 Apr 2021 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 4 | 08 Apr 2021 | SS ENTERPRISES | Bldg D,E & Podium UGWT Excavation work | Spreading & Levelling Work (Rate Diff.) | Cu.Mtrs | 1908.08 | 5 | 9540.4 | 1717.28 | 11257.68 | 0 | 0 | 0 | 0 | 0 | 1908.08 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Apr 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 175 | 1 | 08 Apr 2021 | SS ENTERPRISES | F-Building STP & ETP Excavation Work | Spreading & Levelling | Cu.Ft | 74.88 | 15 | 1123.2 | 202.18 | 1325.38 | 0 | 74.88 | 1123.2 | 0 | 1123.2 | 0 | 202.18 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 16 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 215 | 0 | 18 Jun 2021 | PRAKASH CONTRACTOR | DG 125 KVA Foundation Work | PCC Work | Sq.Ft | 180 | 4 | 720 | 0 | 720 | 2.5 | 180 | 720 | 0 | 720 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Jun 2021 |  | 02 RCC WORK | Approved | tausif | 1900-01-01
GANGA ALTUS | 215 | 0 | 18 Jun 2021 | PRAKASH CONTRACTOR | DG 125 KVA Foundation Work | Murum filling Dld | Cu.Ft | 172 | 3.5 | 602 | 0 | 602 | 0 | 172 | 602 | 0 | 602 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Jun 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ALTUS | 215 | 0 | 18 Jun 2021 | PRAKASH CONTRACTOR | DG 125 KVA Foundation Work | Brickwork 9" BC | Sq.Ft | 69 | 15 | 1035 | 0 | 1035 | 2.5 | 69 | 1035 | 0 | 1035 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Jun 2021 |  | B.C. BBM, Plaster, POP | Approved | tausif | 1900-01-01
GANGA ALTUS | 224 | 0 | 22 Jun 2021 | VNE INFRA PROJECTS P LTD | D&E Bldg -UGWT RCC Work (L) | Concreting Work | Cu.Mtrs | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 22 Jun 2021 |  | B.C. RCC Substructure | Cancelled | tausif | 22 Jun 2021
GANGA ALTUS | 225 | 0 | 22 Jun 2021 | VNE INFRA PROJECTS P LTD | D&E Bldg -UGWT RCC Work (L) | Reinforcement- Ded | Kgs | 45132.83 | 7.5 | 338496.23 | 60929.32 | 399425.55 | 2.5 | 41747.4668 | 313106 | 56359.08 | 369465.08 | 3385.3632 | 29960.46 |  | 92.4991 |  | tausif | tausif | construction open | 03 Jul 2021 |  | DEV. Ext Development | Approved | tausif | 1900-01-01
GANGA ALTUS | 225 | 0 | 22 Jun 2021 | VNE INFRA PROJECTS P LTD | D&E Bldg -UGWT RCC Work (L) | Shuttering Work-Dev | Sq.m. | 2277.4 | 450 | 1024830 | 184469.4 | 1209299.4 | 2.5 | 2106.2333 | 947804.99 | 170604.9 | 1118409.89 | 171.1667 | 90889.52 |  | 92.4841 |  | tausif | tausif | construction open | 03 Jul 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ALTUS | 225 | 0 | 22 Jun 2021 | VNE INFRA PROJECTS P LTD | D&E Bldg -UGWT RCC Work (L) | Concreting Work | Cu.Mtrs | 596.03 | 300 | 178809 | 32185.62 | 210994.62 | 2.5 | 551.63 | 165489 | 29788.02 | 195277.02 | 44.4 | 15717.6 |  | 92.5507 |  | tausif | tausif | construction open | 03 Jul 2021 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ALTUS | 225 | 4 | 22 Jun 2021 | VNE INFRA PROJECTS P LTD | D&E Bldg -UGWT RCC Work (L) | Schedule & Quality - BC | No. | 0 | 251000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 03 Jul 2021 |  | B.C. Internal Finishing Itmes | Cancelled | Dushant Gore | 16 Aug 2022
GANGA ALTUS | 252 | 1 | 31 Aug 2021 | RITU ENTERPRISES | D&E Bldg -UGWT RCC Work (L) | Schedule & Quality - BC | No. | 1 | 251000 | 251000 | 45180 | 296180 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Sep 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 262 | 1 | 08 Sep 2021 | S S ENTERISES (PROP. SOBRAN SINGH) | Excavation & Backfilling for stormwater line work | Excavation work-SO | Cu.Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Sep 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 21 Feb 2022
GANGA ALTUS | 262 | 1 | 08 Sep 2021 | S S ENTERISES (PROP. SOBRAN SINGH) | Excavation & Backfilling for stormwater line work | Excavation work-SO | Cu.Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Sep 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 21 Feb 2022
GANGA ALTUS | 299 | 1 | 09 Dec 2021 | SS ENTERPRISES | Excavation & Backfilling for stormwater line work | Excavation work-SO | Cu.Mtrs | 48.96 | 100 | 4896 | 881.28 | 5777.28 | 0 | 0 | 0 | 0 | 0 | 48.96 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ALTUS | 299 | 1 | 09 Dec 2021 | SS ENTERPRISES | Excavation & Backfilling for stormwater line work | Excavation work-SO | Cu.Mtrs | 163.2 | 100 | 16320 | 2937.6 | 19257.6 | 0 | 0 | 0 | 0 | 0 | 163.2 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ALTUS | 299 | 0 | 09 Dec 2021 | SS ENTERPRISES | LG Floor Drainage line Excavation work (L) | Excavation Work | Cu.Mtrs | 139.45 | 100 | 13945 | 2510.1 | 16455.1 | 0 | 139.45 | 13945 | 2510.1 | 16455.1 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 299 | 1 | 09 Dec 2021 | SS ENTERPRISES | Excavation & Backfilling for stormwater line work | Backfilling | Cu.Mtrs | 169 | 60 | 10140 | 1825.2 | 11965.2 | 0 | 0 | 0 | 0 | 0 | 169 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 4" HDPE Pipe Laying-USL | R.Ft | 120.19 | 6 | 721.14 | 0 | 721.14 | 2.5 | 0 | 0 | 0 | 0 | 120.19 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 11 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 1 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | Storm water line laying work infront of shops (L) | 12" RCC Hume Pipe laying & fixing -UDR | R.Ft | 89.74 | 22 | 1974.28 | 0 | 1974.28 | 2.5 | 0 | 0 | 0 | 0 | 89.74 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 11 Dec 2021 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 4" HDPE Pipe Laying-USL | R.Ft | 127.8 | 15 | 1917 | 0 | 1917 | 2.5 | 0 | 0 | 0 | 0 | 127.8 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 11 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 1 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | Storm water line laying work infront of shops (L) | 8" RCC Hume Pipe laying & fixing -UDR | R.Ft | 321.83 | 18 | 5792.94 | 0 | 5792.94 | 2.5 | 0 | 0 | 0 | 0 | 321.83 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 11 Dec 2021 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 4" HDPE Pipe Laying-USL | R.Ft | 0 | 4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | UTI. Strom Line | Cancelled | skmishra | 14 Jan 2022
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 4" HDPE Pipe Laying-USL | R.Ft | 22.78 | 4 | 91.12 | 0 | 91.12 | 2.5 | 0 | 0 | 0 | 0 | 22.78 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 11 Dec 2021 |  | UTI. Strom Line | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 1 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | Storm water line laying work infront of shops (L) | Chamber 18" x 36" (3ft Ht) - UTI | No. | 12 | 1500 | 18000 | 0 | 18000 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 11 Dec 2021 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | Chamber (12" x 12") (2ft 4" Ht) | No. | 23 | 100 | 2300 | 0 | 2300 | 2.5 | 0 | 0 | 0 | 0 | 23 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 11 Dec 2021 |  | SOC. M. Maintenace of Utilitie | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | Chamber (12" x 12") (2ft 4" Ht) | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | SOC. M. Maintenace of Utilitie | Cancelled | skmishra | 14 Jan 2022
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | Round Chamber 1ft 12" dia (3ft 9" Ht) | No. | 12 | 2500 | 30000 | 0 | 30000 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 11 Dec 2021 |  | SOC. M. Maintenace of Utilitie | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 10" RCC Hume Pipe Laying | R.Ft | 160.62 | 19 | 3051.78 | 0 | 3051.78 | 2.5 | 0 | 0 | 0 | 0 | 160.62 | 0 | STP Excess size 250mm | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 11 Dec 2021 |  | DEV. Podium | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 6" RCC Hume Pipe Laying | R.Ft | 547.97 | 15 | 8219.55 | 0 | 8219.55 | 2.5 | 0 | 0 | 0 | 0 | 547.97 | 0 | size 150mm | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 4" HDPE Pipe Laying-USL | R.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | UTI. Strom Line | Cancelled | skmishra | 14 Jan 2022
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | Chamber (18" x 36") (2ft 4" Ht) | No. | 12 | 1000 | 12000 | 0 | 12000 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | SOC. M. Maintenace of Utilitie | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 4" HDPE Pipe Laying-USL | R.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | UTI. Strom Line | Cancelled | skmishra | 14 Jan 2022
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | Round Chamber 1ft 12" dia (3ft 9" Ht) | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 11 Dec 2021 |  | SOC. M. Maintenace of Utilitie | Cancelled | skmishra | 14 Jan 2022
GANGA ALTUS | 321 | 0 | 11 Dec 2021 | SHINDE PLUMBING CONTRACTOR | LG Floor Drainage line pipe laying From Bldg to Nala | 6" RCC Hume Pipe Laying | R.Ft | 0 | 547 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 11 Dec 2021 |  | S OH Infrastructure | Cancelled | Aniket Mohite | 11 Dec 2021
GANGA ALTUS | 344 | 1 | 15 Jan 2022 | RITU ENTERPRISES | F - Bldg STP RCC Work ( L) | RCC Work STP | Ltrs | 82992 | 4 | 331968 | 59754.24 | 391722.24 | 2.5 | 82991.75 | 331967 | 59754.06 | 391721.06 | 0.25 | 1.18 |  | 99.9997 |  | Dushant Gore | Swapnil Erande | construction open | 15 Jan 2022 |  | UTI. S.T.P | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 344 | 0 | 15 Jan 2022 | RITU ENTERPRISES | F-Bldg UGWT - RCC Work | RCC work - UWT | Ltrs | 45000 | 3.5 | 157500 | 28350 | 185850 | 2.5 | 45000 | 157500 | 28350 | 185850 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 15 Jan 2022 |  | UTI. U.G.W.T | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 344 | 0 | 15 Jan 2022 | RITU ENTERPRISES | F-Bldg UGWT - RCC Work | RCC work - UWT | Ltrs | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 15 Jan 2022 |  | UTI. U.G.W.T | Cancelled | skmishra | 15 Jan 2022
GANGA ALTUS | 346 | 0 | 15 Jan 2022 | AQUARIUS WATERPROOFING | UGWT RCC Pardi External W/P | Brickbat W/P-cc | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | VAIBHAV BIRADAR |  | construction open | 15 Jan 2022 |  | B.C. Customer Changes | Cancelled | skmishra | 15 Jan 2022
GANGA ALTUS | 346 | 0 | 15 Jan 2022 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Cement Ghotai inside W/P-UWT- | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | VAIBHAV BIRADAR |  | construction open | 15 Jan 2022 |  | UTI. U.G.W.T | Cancelled | skmishra | 15 Jan 2022
GANGA ALTUS | 346 | 0 | 15 Jan 2022 | AQUARIUS WATERPROOFING | UGWT RCC Pardi Internal-Chemical W/P | Chemical W/P-UWT- | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | VAIBHAV BIRADAR |  | construction open | 15 Jan 2022 |  | UTI. U.G.W.T | Cancelled | skmishra | 15 Jan 2022
GANGA ALTUS | 347 | 0 | 15 Jan 2022 | SHINDE PLUMBING CONTRACTOR | UGWT RCC Pardi External W/P | Brickbat W/P-cc | Sq.Ft | 190.42 | 18 | 3427.56 | 0 | 3427.56 | 2.5 | 0 | 0 | 0 | 0 | 190.42 | 0 |  | 0 |  | VAIBHAV BIRADAR | Swapnil Erande | construction open | 06 Jan 2023 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 347 | 0 | 15 Jan 2022 | SHINDE PLUMBING CONTRACTOR | UGWT RCC Pardi Internal-Chemical W/P | Cement Ghotai inside W/P-UWT- | Sq.Ft | 806.89 | 15 | 12103.35 | 0 | 12103.35 | 2.5 | 806.89 | 12103.35 | 1742.88 | 13846.23 | 0 | -1742.88 |  | 100 |  | VAIBHAV BIRADAR | Swapnil Erande | construction open | 06 Jan 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 347 | 0 | 15 Jan 2022 | SHINDE PLUMBING CONTRACTOR | UGWT RCC Pardi Internal-Chemical W/P | Chemical W/P-UWT- | Sq.Ft | 806.89 | 22 | 17751.58 | 0 | 17751.58 | 2.5 | 806.89 | 17751.58 | 3195.28 | 20946.86 | 0 | -3195.28 |  | 100 |  | VAIBHAV BIRADAR | Swapnil Erande | construction open | 06 Jan 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 379 | 0 | 18 Feb 2022 | GREENSOL TECH | STP-45 KLD | Sewage Treatment Plant (M) | No. | 1 | 616000 | 616000 | 110880 | 726880 | 0 | 1 | 616000 | 110880 | 726880 | 0 | 0 | STP-45KLD MBBR TECHNOLOGY | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 380 | 0 | 18 Feb 2022 | GREENSOL TECH | STP-45 KLD | Sewage Treatment Plant (L) | No. | 1 | 154000 | 154000 | 27720 | 181720 | 0 | 0.75 | 115500 | 20790 | 136290 | 0.25 | 45430 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 381 | 0 | 18 Feb 2022 | GREENSOL TECH | STP ETP-15 KLD | Effluenr Treatment Plant (M) | No. | 1 | 848000 | 848000 | 152640 | 1000640 | 0 | 1 | 848000 | 152640 | 1000640 | 0 | 0 | EFFLUENT TREATMENT PLANT 15KLD MBBR TECHNOLOGY | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 382 | 0 | 18 Feb 2022 | GREENSOL TECH | STP ETP-15 KLD | Effluenr Treatment Plant (L) | No. | 1 | 212000 | 212000 | 38160 | 250160 | 0 | 0.75 | 159000 | 28620 | 187620 | 0.25 | 62540 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Feb 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 384 | 0 | 21 Feb 2022 | P. L. VISHWAKARAMA | Earthing Work | Earthing work(m+l)- BC | No. | 0 | 4000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 24 Feb 2022
GANGA ALTUS | 384 | 0 | 21 Feb 2022 | P. L. VISHWAKARAMA | Sparten Lift DG Earthing work | Earthing work(m+l)- BC | No. | 0 | 4000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 24 Feb 2022
GANGA ALTUS | 390 | 0 | 24 Feb 2022 | P.L. VISHWAKARMA ELECTRICALS (FIRM) | Sparten Lift DG Earthing work | Pit Excavation - BC | No. | 4 | 500 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 390 | 0 | 24 Feb 2022 | P.L. VISHWAKARMA ELECTRICALS (FIRM) | Earthing Work | Earthing work(m+l)- BC | No. | 4 | 4000 | 16000 | 2880 | 18880 | 2.5 | 4 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 390 | 0 | 24 Feb 2022 | P.L. VISHWAKARMA ELECTRICALS (FIRM) | Sparten Lift DG Earthing work | Earthing work(m+l)- BC | No. | 4 | 4000 | 16000 | 2880 | 18880 | 2.5 | 4 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 390 | 0 | 24 Feb 2022 | P.L. VISHWAKARMA ELECTRICALS (FIRM) | Earthing Work | Pit Excavation - BC | No. | 4 | 500 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 394 | 0 | 12 Mar 2022 | PRATHAM ELECTRICALS | Fire Fighting line in front of shops only | Wrapping Coating sheet 4mm Thick (with all accessories) (M) | Mtrs | 180 | 290 | 52200 | 0 | 52200 | 0 | 0 | 0 | 0 | 0 | 180 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 394 | 0 | 12 Mar 2022 | PRATHAM ELECTRICALS | Fire Fighting line in front of shops only | GI Pipe C Class 150 NB-(M) | Mtrs | 150 | 2345 | 351750 | 0 | 351750 | 0 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 395 | 0 | 12 Mar 2022 | PRATHAM ELECTRICALS | Fire Fighting line in front of shops only | GI Pipe C Class 150 NB-(L) - | Mtrs | 150 | 540 | 81000 | 0 | 81000 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 395 | 0 | 12 Mar 2022 | PRATHAM ELECTRICALS | Fire Fighting line in front of shops only | Wrapping Coating sheet 4mm Thick (with all accessories) (L) | Mtrs | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 12 Mar 2022
GANGA ALTUS | 395 | 0 | 12 Mar 2022 | PRATHAM ELECTRICALS | Fire Fighting line in front of shops only | Wrapping Coating sheet 4mm Thick (with all accessories) (L) | Mtrs | 180 | 170 | 30600 | 0 | 30600 | 2.5 | 0 | 0 | 0 | 0 | 180 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 408 | 0 | 07 Apr 2022 | AQUARIUS WATERPROOFING | UGWT- D&E External waterrproofing work | Membrane Vertical Waterproofing (L) | Sq.Ft | 8490.85 | 15 | 127362.75 | 22925.3 | 150288.05 | 10 | 8490.6667 | 127360 | 22924.8 | 150284.8 | 0.1833 | 3.25 |  | 99.9978 |  | Dushant Gore | Swapnil Erande | construction open | 20 Apr 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 408 | 0 | 07 Apr 2022 | AQUARIUS WATERPROOFING | UGWT- D&E External waterrproofing work | Membrane Horizontal Waterproofing (L) | Sq.Ft | 5916.15 | 13 | 76909.95 | 13843.8 | 90753.75 | 10 | 5916.15 | 76909.95 | 13843.8 | 90753.75 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 20 Apr 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 409 | 0 | 07 Apr 2022 | AQUARIUS WATERPROOFING | UGWT- D&E External waterrproofing work | Membrane Horizontal Waterproofing (M) | Sq.Ft | 5916.15 | 34 | 201149.1 | 36206.84 | 237355.94 | 0 | 5916.15 | 201149.1 | 36206.84 | 237355.94 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 26 Apr 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 409 | 0 | 07 Apr 2022 | AQUARIUS WATERPROOFING | UGWT- D&E External waterrproofing work | Membrane Vertical Waterproofing (M) | Sq.Ft | 8490.85 | 40 | 339634 | 61134.12 | 400768.12 | 0 | 8490.675 | 339627 | 61132.86 | 400759.86 | 0.175 | 8.26 |  | 99.9979 |  | Dushant Gore | Swapnil Erande | construction open | 26 Apr 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 420 | 0 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | Chamber 36" x 36" (3ft Ht) - UTI | No. | 0 | 1000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 27 Apr 2022 |  | UTI. Electricity Infrastructur | Cancelled | Dushant Gore | 27 Apr 2022
GANGA ALTUS | 420 | 1 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | 12" RCC Hume Pipe laying & fixing -UTR - | R.Ft | 373.1 | 19 | 7088.9 | 0 | 7088.9 | 2.5 | 0 | 0 | 0 | 0 | 373.1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 27 Apr 2022 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 420 | 0 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | 12" RCC Hume Pipe laying & fixing -UTR - | R.Ft | 629.76 | 19 | 11965.44 | 0 | 11965.44 | 2.5 | 553 | 10507 | 769.5 | 11276.5 | 76.76 | 688.94 |  | 87.8112 |  | Dushant Gore | Swapnil Erande | construction open | 27 Apr 2022 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 420 | 1 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | Chamber 60" x 48" (3.5ft Ht) | No. | 4 | 1500 | 6000 | 0 | 6000 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 27 Apr 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 420 | 0 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | Chamber 60" x 48" (3.5ft Ht) | No. | 2 | 1500 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 27 Apr 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 420 | 0 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | Chamber 36" x 36" (3ft Ht) - UTI | No. | 9 | 1500 | 13500 | 0 | 13500 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 27 Apr 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 420 | 0 | 27 Apr 2022 | SHINDE PLUMBING CONTRACTOR | Basement level Electrical pipe laying & chamber work (L) | Chamber 36" x 36" (3ft Ht) - UTI | No. | 0 | 1000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 27 Apr 2022 |  | UTI. Electricity Infrastructur | Cancelled | skmishra | 29 Apr 2022
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | LT Earthing Set (m+l) | No. | 0 | 5000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Excavation & Filling. | Mtrs | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Excavation & Filling. | Mtrs | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 3Cx95 sqmm Cable Laying | Mtrs | 0 | 110 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Stepthrough Jointing Kit (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | DTC Meter Fixing | No. | 0 | 2200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | 04 ELECTRICAL WORK | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Gland Plate Hole Making (L) | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Full round pipe | No. | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Outdoor Jointing Kit (M+L) | No. | 0 | 6300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 300sqmm x 3.5C Cable Laying (L) | Mtrs | 0 | 90 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | End Termination 300sqmm X 3.5 core cable (M+L) | No. | 0 | 1700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Half round pipe | No. | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Indoor Jointing Kit (M+L) | No. | 0 | 6300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Cable Laying 22/300 | Mtrs | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 50x5 GI Earthing Strip (M+L) | Mtrs | 0 | 235 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Touchproof Jointing Kit (L) | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Stepthrough Jointing Kit (L) - No. | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Cable Laying (L) | Mtrs | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Excavation by breaker. | Mtrs | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | RMU Installation | No. | 0 | 8000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 35x5 GI Earthing Strip (M+L) | Mtrs | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Touchproof Jointing Kit (L) | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 4 Way Feeder Pillar | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | Transformer Installation | No. | 0 | 6300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | HT Earthing Set (m+l) | No. | 0 | 5000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 430 | 1 | 20 May 2022 | LAXMI ELECTRICALS | Electrical Work Electrical Labour work for Transformer Room | 6 way Feeder Piller (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 25 May 2022 |  | No category | Cancelled | DUSHANT GORE | 30 Mar 2023
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Elect Meters UTI | No. | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Residential Common Ammenity LT SPL CT Meter. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Transformer Charging -UTI | No. | 3 | 75000 | 225000 | 40500 | 265500 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Elect Meters Installation (L)-UTI | No. | 500 | 1747.2 | 873600 | 157248 | 1030848 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 1 phase Residential, Commercial & 3 phase Residential, Commercial & Building wise common. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Highrise Perm UTI | No. | 2 | 75000 | 150000 | 27000 | 177000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Elect Meters Installation (L)-UTI | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Residential Common Ammenity LT SPL CT Mete | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Elect Meters UTI | No. | 500 | 2620.8 | 1310400 | 235872 | 1546272 | 0 | 500 | 1310400 | 235872 | 1546272 | 0 | 0 | 1 phase Residential, Commercial & 3 phase Residential, Commercial & Building wise common. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 507 | 0 | 02 Aug 2022 | ARYA CONSULTANCY | Electricity Infrastructure | Highrise Perm UTI | No. | 1 | 45000 | 45000 | 8100 | 53100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Oct 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Brass Ball Valve 50mm (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Rotameter | No. | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (L) | No. | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Start/Stop push button station (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Erection of emergency start / stop push button station weather proof type for Booster pump. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of foot valves with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts. The installation as per the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Orifice Plate (L) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 80mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm.Cable. (L) | Mtrs | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (L) | Mtrs | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I,of size and pressure rating as indicated below, with required flanges, nuts, bolts.The installation must be carried out as per the standard procedure of EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Non Return Valve 100mm (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I,of size and pressure rating as indicated below, with required flanges, nuts, bolts.The installation must be carried out as per the standard procedure of EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (L) | No. | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of electrical motor driven main pump of approved makes confirming to I.S. 12469-1988 of horizontal centrifugal single stage single outlet type and capable to deliver 171Cum/Hr at 145 mwc. The pump shall be coupled to TEFC motor of suitable HP with preferred speed of 2900 RPM | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Start/Stop push button station (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Erection of emergency start / stop push button station weather proof type for Booster pump. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Air Release Valve 25mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (L) | Mtrs | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. The strip shall run on floor / ceiling / walls ,from the equipment to the nearest earth pit with neccessory accessories as require | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (L) | Mtrs | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (L). | set | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Single headed (Type A) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet , gunmetal blank caps, chain and hand wheels etc complete. The installation must be carried out as per the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm (L) - set | set | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Hydraulically operated sprinkler alarm valve with accesories; 2 nos of pressure guages,2 nos isolation valves.The installation must be carried out as per the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Earthing Strip 50 x 6 mm (L) | Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC GI earthing strips of size 50mm x 6mm of approved makes confirming to I.S. 3043:1987. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (L) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 32mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | Orifice Plate (L) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(L) | No. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC portable fire extinguisers CO2 type fire extinguishers 4.5 KG.Fitted with gun metal union, high pressure CO2 gas cartridge & wall mounting bracket etc.complete. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 200 x 50mm (L) | Mtrs | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm.Cable. (L) | Mtrs | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (L) | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (L) | No. | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | Double Hydrant Valve (L) | set | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | 3C x 1.5sqmm (L) | Mtrs | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Pressure Switch (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (L) | set | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (L) | Mtrs | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. The strip shall run on floor / ceiling / walls ,from the equipment to the nearest earth pit with neccessory accessories as require | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (L) | No. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Sluice Valve 200mm (L) | No. | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs.Complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe | Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 65mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | 4 way 63mm,Fire service inlet | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | UTI Fire fight. (underground) | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass, with unions etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Orifice Plate (L) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (L) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design,installation,testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | Orifice Plate (L) | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Strainer "Y" (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | Double Hydrant Valve (L) | set | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Diesel Engine Driven Pump | No. | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Control Panel (L) | No. | 0 | 32737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (L) | No. | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 18 Aug 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Electrical Motor Driven Pump (L) | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of electrical motor driven booster pump of approved makes confirming to I.S. 12469:1988 capable to deliver 54 Cum/ Hr at 45 MWC The pump shall be coupled to TEFC motor of suitable HP with speed of 2900 RPM. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Electrical Motor Driven Pump (L) | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of electrical motor driven booster pump of approved makes confirming to I.S. 12469:1988 capable to deliver 54 Cum/ Hr at 45 MWC The pump shall be coupled to TEFC motor of suitable HP with speed of 2900 RPM. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass, with unions etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe | Mtrs | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 200mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (L) | No. | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 300 x 50mm (L) | Mtrs | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe | Mtrs | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 200mm of GI Heavey grade pipes and fittings including painting with fire red colour confirming to I.S 5:1978 | 0 |  | Sanket Patil |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Strainer "Y" (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Air Release Valve 25mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 80mm (L) | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (L). | set | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC Single headed (Type A) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet , gunmetal blank caps, chain and hand wheels etc.complete.The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass, with unions etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (L) | No. | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | 4 way 63mm,Fire service inlet | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | UTI Fire fight. (underground) | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm (L) | No. | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of Hydraulically operated sprinkler alarm valve with accesories; 2 nos of pressure guages,2 nos isolation valves.The installation must be carried out as per the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 18 Aug 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (L) | No. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 150mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (L). | Mtrs | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation of Exhaust pipe for Diesel engine of M.S.medium grade with mineral wool insulation and aluminum sheet for protection.The installation must be as per the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (L) | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (L) | No. | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Air Release Valve 25mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(L) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 516 | 0 | 16 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (L) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore |  | construction open | 18 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand HD Fire/Jacumin | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm.(M) | set | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Hydraulically operated sprinkler alarm valve 15mm with all accesories; 2 nos of pressure guages,2 nos isolation valves, 1 no of angle valve, 1 no of strainer, 1 no of non return valve, 1 no of alarm control valve, 1 no of alarm test valve etc | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | No. | 0 | 4890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in 100 mm size with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (M) | No. | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (M) | No. | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (M). | set | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-KARTAR/PARSHWA | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Brand Kartar /HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | 4 Way 63mm,Fire Service inlet (M) | No. | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand Kartar/Parshwa | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | 4 Way 63mm,Fire Service inlet (M) | No. | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand Kartar/Parshwa | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 300 x 50mm (M) | Mtrs | 0 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of perforated G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports , anchor fasteners etc. complete.Brand | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (M) | No. | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar.Supply of electrical motor driven main pump of approved makes confirming to I.S. 12469-1988 of horizontal centrifugal single stage single outlet type and capable to deliver 171Cum/Hr at 145 mwc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (M) | No. | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar.Supply of electrical motor driven main pump of approved makes confirming to I.S. 12469-1988 of horizontal centrifugal single stage single outlet type and capable to deliver 171Cum/Hr at 145 mwc | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (M). | Mtrs | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Exhaust pipe for Diesel engine of M.S.medium grade with mineral wool insulation and aluminum sheet for protection.Brand Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (M) | No. | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (M) | No. | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (M) | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying of Air Vessel with required standard connections & required it supports,anchor fastners & nut bolts etc.(Dia 300 x 1200mm Height). | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (M) | set | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of landing Hydrants a) Double headed (Type B) hydrant valve made of stainless steel with 63mm dia outlets & 80mm/100 mm dia flanged inlet,gunmetal blank caps,chain and hand wheels b) 2 L of 15 mtr long,63mm dia RRL hose. Brand-KARTAR/PARSHWA | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 0 | 7850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand AARAKO / KARTAR | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand Polycab | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 0 | 7850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand AARAKO / KARTAR | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Pressure Switch (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of pressure switches of approved makes of suitable range for pumpsets.Brand Danfoss | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | 4 Way Fire Service inlet (M) | set | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand ESSEL.Supplying of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Control Panel (M) | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps.Brand HCL Components | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (M) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Early Suppression Fast Response Upright sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. Brand- Newage/HD Fire | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | 4 Way Fire Service inlet (M) | set | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand ESSEL.Supplying of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (M) | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand Kartar/Parshwa | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (M) | No. | 0 | 14747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (M) | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand Kartar/Parshwa | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Brand Kartar /HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002 Brand- Newage/HD Fire | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | No. | 0 | 4890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of portable fire extinguisers CO2 type fire extinguishers 4.5 KG. capacity with intial filling in brand new cylinder with powder coated finish ,fitted with gun metal union, high pressure CO2 gas cartridge & wall mounting bracket etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (M) | No. | 0 | 5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (M) | No. | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Electrical Motor Driven Pump (M) | No. | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar.Supply of electrical motor driven booster pump of approved makes confirming to I.S. 12469:1988 capable to deliver 54 Cum/ Hr at 45 MWC The pump shall be coupled to TEFC motor of suitable HP with speed of 2900 RPM. | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Earthing Strip 50 x 6 mm (M) | Mtrs | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply GI earthing strips of size 50mm x 6mm of approved makes confirming to I.S. 3043:1987. | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (M). | set | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-KARTAR/PARSHWA | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 0 | 2547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Rotameter (M) | No. | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SupplyingRotameter of approved make of flow range 2.5 to 40000 lph of approved make etc complete. Brand- STANDARD | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (M) | No. | 0 | 5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand Polycab | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (M) | No. | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar. Supply of electrical motor driven jockey pump of horizontal centrifugal end suction back pull out type with gland packing and capable to deliver 10.8Cum/Hr at 145mwc. | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (M) | set | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of landing Hydrants a) Double headed (Type B) hydrant valve made of stainless steel with 63mm dia outlets & 80mm/100 mm dia flanged inlet,gunmetal blank caps,chain and hand wheels b) 2 L of 15 mtr long ,63mm dia RRL hose. Brand-KARTAR/PARSHWA | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | Orifice Plate (M) | No. | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (M) | No. | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar. Supply of electrical motor driven jockey pump of horizontal centrifugal end suction back pull out type with gland packing and capable to deliver 10.8Cum/Hr at 145mwc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 0 | 1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand Polycab | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (M) | Mtrs | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of perforated G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports , anchor fasteners etc. complete.Brand | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 300 x 50mm (M) | Mtrs | 0 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of perforated G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports , anchor fasteners etc. complete.Brand | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (M) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Early Suppression Fast Response Upright sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. Brand- Newage/HD Fire | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (M) | No. | 0 | 14747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (M) | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 80mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(M) | No. | 0 | 1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(M) | No. | 0 | 1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Electrical Motor Driven Pump (M) | No. | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar.Supply of electrical motor driven booster pump of approved makes confirming to I.S. 12469:1988 capable to deliver 54 Cum/ Hr at 45 MWC The pump shall be coupled to TEFC motor of suitable HP with speed of 2900 RPM. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand Polycab | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of portable fire extinguisers CO2 type fire extinguishers 4.5 KG. capacity with intial filling in brand new cylinder with powder coated finish ,fitted with gun metal union, high pressure CO2 gas cartridge & wall mounting bracket etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (M) | Mtrs | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of perforated G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports , anchor fasteners etc. complete.Brand | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 200 x 50mm (M) | Mtrs | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of perforated G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports , anchor fasteners etc. complete.Brand | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand Polycab | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 200 x 50mm (M) | Mtrs | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of perforated G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports , anchor fasteners etc. complete.Brand | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (M) | No. | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (M) | No. | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 80 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (M) | No. | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of foot valves with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts.Brand Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 0 | 2547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 200mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 0 | 7850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand AARAKO / KARTAR | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | Orifice Plate (M) | No. | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 0 | 1730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 0 | 1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Diesel Engine Driven Pump (M) | No. | 0 | 678085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | supply diesel engine driven stand-by pump of approved makes confirming to I.S. 12469:1988 of horizontal centrifugal single stage single outlet type pump and capable to deliver 171 Cum/Hr at 145 mwc.Brand KSB | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. Brand- Newage/HD Fire | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (M). | Mtrs | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Exhaust pipe for Diesel engine of M.S.medium grade with mineral wool insulation and aluminum sheet for protection.Brand Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Sluice Valve 200mm (M) | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Sluice Valve. Brand KARTAR | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in 150 mm size with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (M) | No. | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | G.I.Earthing Strip 50 x 6 mm (M) | Mtrs | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply GI earthing strips of size 50mm x 6mm of approved makes confirming to I.S. 3043:1987. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 0 | 2547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Pressure Guage 100mm | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Pressure Guage 100mm | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (M) | No. | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 0 | 7890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 0 | 7890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 0 | 7890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 0 | 1730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors,unions and pressure testing for water tightness. Brand-Matrix | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (M) | No. | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand HD Fire/Jacumin | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand HD Fire/Jacumin | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand HD Fire/Jacumin | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (M) | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying of Air Vessel with required standard connections & required it supports,anchor fastners & nut bolts etc.(Dia 300 x 1200mm Height). | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(M) | No. | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (M) | No. | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 80mm (M) | No. | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (M) | No. | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply C.I. "Basket" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges, nuts, bolts, gaskets etc. complete.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (M) | No. | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply C.I. "Basket" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges, nuts, bolts, gaskets etc. complete.Brand Kartar | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Brand Kartar /HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 200mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 65mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand Polycab | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand Polycab | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand Polycab | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 0 | 1777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Matrix | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Electrical Motor Driven Pump (M) | No. | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brand Kirloskar.Supply of electrical motor driven booster pump of approved makes confirming to I.S. 12469:1988 capable to deliver 54 Cum/ Hr at 45 MWC The pump shall be coupled to TEFC motor of suitable HP with speed of 2900 RPM. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | Orifice Plate (M) | No. | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. Brand- Newage/HD Fire | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 65mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Rotameter (M) | No. | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SupplyingRotameter of approved make of flow range 2.5 to 40000 lph of approved make etc complete. Brand- STANDARD | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002 Brand- Newage/HD Fire | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 18 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Control Panel (M) | No. | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps.Brand HCL Components | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(M) | No. | 0 | 1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Brand Kartar /HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Pressure Switch (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of pressure switches of approved makes of suitable range for pumpsets.Brand Danfoss | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (M). | set | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-KARTAR/PARSHWA | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (M). | set | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-KARTAR/PARSHWA | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(M) | No. | 0 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand HD Fire/Jacumin | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (M) | No. | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of stainless steel single stage single hole restriction 80 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (M) | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Diesel Engine Driven Pump (M) | No. | 0 | 730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | supply diesel engine driven stand-by pump of approved makes confirming to I.S. 12469:1988 of horizontal centrifugal single stage single outlet type pump and capable to deliver 171 Cum/Hr at 145 mwc.Brand KSB | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Diesel Engine Driven Pump (M) | No. | 0 | 730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | supply diesel engine driven stand-by pump of approved makes confirming to I.S. 12469:1988 of horizontal centrifugal single stage single outlet type pump and capable to deliver 171 Cum/Hr at 145 mwc.Brand KSB | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 24 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (M) | No. | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of foot valves with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Sluice Valve 200mm (M) | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Sluice Valve. Brand KARTAR | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (M) | No. | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplying and installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand Polycab | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (M) | No. | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(M) | No. | 0 | 1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of C.I. 80mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-NVR/KARTAR/NORMAX | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Brand Kartar /HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (M) | Mtrs | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 18 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Pumproom Fire Equipment - 1 No. | Non Return Valve 80mm (M) | No. | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand Kartar | 0 |  | Sanket Patil |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Brand Kartar /HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | No category | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | E-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 517 | 0 | 18 Aug 2022 | VANGUARD ENGINEERS | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ALTUS | 538 | 2 | 16 Sep 2022 | AJAY KUMAR GUPTA | F Bldg.-OHWT-Core Cutting Work | Horizontal Core Cut 2'' | No. | 4 | 265 | 1060 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | Cement Ghotai Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 07 Dec 2022 |  | S OH Infrastructure | Cancelled | DUSHANT GORE | 07 Feb 2023
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP External Waterproofing Work | Membrane Horizontal Waterproofing (L) | Sq.Ft | 773 | 13 | 10049 | 1808.82 | 11857.82 | 10 | 593.26 | 7712.38 | 1388.22 | 9100.6 | 179.74 | 2757.22 |  | 76.7477 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg Top Slab Chemical W/P + Screeding Work | Screeding W/P-BCo | Sq.Ft | 383 | 15 | 5745 | 1034.1 | 6779.1 | 10 | 246 | 3690 | 0 | 3690 | 137 | 3089.1 |  | 64.2298 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | Chemical W/P-DLd | Sq.Ft | 2866 | 22 | 63052 | 11349.36 | 74401.36 | 10 | 0 | 0 | 0 | 0 | 2866 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg Top Slab Chemical W/P + Screeding Work | Chemical W/P-DLd | Sq.Ft | 383 | 22 | 8426 | 1516.68 | 9942.68 | 10 | 135 | 2970 | 0 | 2970 | 248 | 6972.68 |  | 35.248 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP-Top Slab Chemical W/P + Screeding work (L) | Chemical Waterproofing (M+L).Sq.ft | Sq.Ft | 427 | 22 | 9394 | 1690.92 | 11084.92 | 10 | 427 | 9394 | 0 | 9394 | 0 | 1690.92 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP-Top Slab Chemical W/P + Screeding work (L) | Screeding W/P-BCo | Sq.Ft | 427 | 15 | 6405 | 1152.9 | 7557.9 | 10 | 193.6 | 2904 | 0 | 2904 | 233.4 | 4653.9 |  | 45.3396 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP-Int Chemical Waterproofing+Ghotai Plaster | Cement Ghotai Plaster | Sq.Ft | 2360.98 | 15 | 35414.7 | 6374.64 | 41789.34 | 10 | 1888.784 | 28331.76 | 5099.72 | 33431.48 | 472.196 | 8357.86 |  | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | Cement Ghotai Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 07 Dec 2022 |  | S OH Infrastructure | Cancelled | DUSHANT GORE | 07 Feb 2023
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP Ext Waterproofing Work | Membrane Horizontal Waterproofing (L) | Sq.Ft | 723 | 13 | 9399 | 1691.82 | 11090.82 | 10 | 0 | 0 | 0 | 0 | 723 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP-Int Chemical Waterproofing+Ghotai Plaster | Screeding W/P-BCo | Sq.Ft | 378 | 15 | 5670 | 1020.6 | 6690.6 | 10 | 0 | 0 | 0 | 0 | 378 | 0 |  | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | Cement Ghotai Plaster | Sq.Ft | 2388 | 15 | 35820 | 6447.6 | 42267.6 | 10 | 1910.4 | 28656 | 5158.08 | 33814.08 | 477.6 | 8453.52 |  | 80 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP-Int Chemical Waterproofing+Ghotai Plaster | Chemical Waterproofing (M+L).Sq.ft | Sq.Ft | 2738.98 | 22 | 60257.56 | 10846.36 | 71103.92 | 10 | 0 | 0 | 0 | 0 | 2738.98 | 0 |  | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | Screeding W/P-BCo | Sq.Ft | 478 | 15 | 7170 | 1290.6 | 8460.6 | 10 | 382.4 | 5736 | 1032.48 | 6768.48 | 95.6 | 1692.12 |  | 80 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP Ext Waterproofing Work | Membrane Vertical Waterproofing (L) | Sq.Ft | 1096 | 15 | 16440 | 2959.2 | 19399.2 | 10 | 876.8 | 13152 | 2367.36 | 15519.36 | 219.2 | 3879.84 |  | 80 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 555 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP External Waterproofing Work | Membrane Vertical Waterproofing (L) | Sq.Ft | 908 | 15 | 13620 | 2451.6 | 16071.6 | 10 | 726.4 | 10896 | 1961.28 | 12857.28 | 181.6 | 3214.32 |  | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 556 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP Ext Waterproofing Work | Membrane Vertical Waterproofing (M) | Sq.Ft | 1096 | 40 | 43840 | 7891.2 | 51731.2 | 0 | 876.8 | 35072 | 6312.96 | 41384.96 | 219.2 | 10346.24 |  | 80 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 556 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP External Waterproofing Work | Membrane Vertical Waterproofing (M) | Sq.Ft | 908 | 40 | 36320 | 6537.6 | 42857.6 | 0 | 726.4 | 29056 | 5230.08 | 34286.08 | 181.6 | 8571.52 |  | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 556 | 1 | 13 Oct 2022 | AQUARIUS WATERPROOFING | F-Bldg ETP Ext Waterproofing Work | Membrane Horizontal Waterproofing (M) | Sq.Ft | 723 | 34 | 24582 | 4424.76 | 29006.76 | 0 | 0 | 0 | 0 | 0 | 723 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 556 | 0 | 13 Oct 2022 | AQUARIUS WATERPROOFING | STP External Waterproofing Work | Membrane Horizontal Waterproofing (M) | Sq.Ft | 773 | 34 | 26282 | 4730.76 | 31012.76 | 0 | 0 | 0 | 0 | 0 | 773 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Dec 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 559 | 0 | 19 Oct 2022 | VECTOR SURVEYORS | UGWT- Surveying Work by total station | Total Statiotn Survey | Day | 3 | 4500 | 13500 | 0 | 13500 | 0 | 1 | 4500 | 0 | 4500 | 2 | 9000 |  | 33.3333 |  | Dushant Gore | Swapnil Erande | construction open | 10 Nov 2022 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 574 | 0 | 25 Nov 2022 | VEDANT CONSTRUCTION | STP - 265 KLD Slab Cutting work | Lumpsum work- DCW | No. | 1 | 65000 | 65000 | 11700 | 76700 | 0 | 1 | 65000 | 11700 | 76700 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Dec 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 575 | 0 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Pile Concreting Work | Mtrs | 12.25 | 100 | 1225 | 220.5 | 1445.5 | 2.5 | 12.25 | 1225 | 0 | 1225 | 0 | 220.5 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | skmishra | 10 Nov 2023
GANGA ALTUS | 575 | 0 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Reinforcement for Piling-BC | Mtrs | 57.97 | 100 | 5797 | 1043.46 | 6840.46 | 2.5 | 57.97 | 5797 | 0 | 5797 | 0 | 1043.46 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Foreclose | skmishra | 10 Nov 2023
GANGA ALTUS | 575 | 1 | 28 Nov 2022 | MASKE PILE FOUNDATION | Near Well Pile Work-Near Well (L) - 1 No. | Reinforcement for Piling-BC | Mtrs | 72 | 100 | 7200 | 1296 | 8496 | 2.5 | 71.64 | 7164 | 0 | 7164 | 0.36 | 1332 |  | 99.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 575 | 2 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Reinforcement for Piling-BC | Mtrs | 11.55 | 100 | 1155 | 207.9 | 1362.9 | 2.5 | 11.55 | 1155 | 207.9 | 1362.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 575 | 2 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Mobilisation - DEn | No. | 2 | 35000 | 70000 | 12600 | 82600 | 0 | 2 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | DEV. Entrance Gate | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 575 | 0 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Mobilisation - DEn | No. | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Entrance Gate | Foreclose | skmishra | 10 Nov 2023
GANGA ALTUS | 575 | 0 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Reinforcement for Piling-BC | Mtrs | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | B.C. RCC Substructure | Cancelled | ADITYA CHOUGULE | 28 Nov 2022
GANGA ALTUS | 575 | 1 | 28 Nov 2022 | MASKE PILE FOUNDATION | Near Well Pile Work-Near Well (L) - 1 No. | Chiseling work for Piling - DEn | Hrs | 40 | 500 | 20000 | 3600 | 23600 | 2.5 | 40 | 20000 | 0 | 20000 | 0 | 3600 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 575 | 1 | 28 Nov 2022 | MASKE PILE FOUNDATION | Near Well Pile Work-Near Well (L) - 1 No. | Pile Concreting Work | Mtrs | 60 | 100 | 6000 | 1080 | 7080 | 2.5 | 27.88 | 2788 | 0 | 2788 | 32.12 | 4292 |  | 46.4667 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 575 | 0 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Chiseling work for Piling - DEn | Hrs | 0 | 400 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Entrance Gate | Foreclose | skmishra | 10 Nov 2023
GANGA ALTUS | 575 | 2 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Chiseling work for Piling - DEn | Hrs | 35.77 | 400 | 14308 | 2575.44 | 16883.44 | 0 | 35.77 | 14308 | 2575.44 | 16883.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | DEV. Entrance Gate | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 575 | 2 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Pile Concreting Work | Mtrs | 57.2 | 100 | 5720 | 1029.6 | 6749.6 | 2.5 | 57.2 | 5720 | 1029.6 | 6749.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 575 | 1 | 28 Nov 2022 | MASKE PILE FOUNDATION | Near Well Pile Work-Near Well (L) - 1 No. | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 60 | 1000 | 60000 | 10800 | 70800 | 2.5 | 54.95 | 54950 | 0 | 54950 | 5.05 | 15850 |  | 91.5833 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 575 | 1 | 28 Nov 2022 | MASKE PILE FOUNDATION | Near Well Pile Work-Near Well (L) - 1 No. | Transport Charges | No. | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 575 | 2 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Piling Work 500mm dia rate diff. | No. | 10 | 26079 | 260790 | 46942.2 | 307732.2 | 2.5 | 10 | 260790 | 46942.2 | 307732.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 575 | 0 | 28 Nov 2022 | MASKE PILE FOUNDATION | Transformer Room- Pile Excavation Work | Piling Work 500mm Dia. - ULT | Mtrs | 43.57 | 900 | 39213 | 7058.34 | 46271.34 | 2.5 | 43.57 | 39213 | 1782 | 40995 | 0 | 5276.34 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Foreclose | skmishra | 10 Nov 2023
GANGA ALTUS | 579 | 0 | 08 Dec 2022 | GREEN PLANET SOLUTION | Organic Waste Composter | Organic Waste Composter Machine (M+L) | No. | 1 | 835000 | 835000 | 100200 | 935200 | 0 | 0.8 | 668000 | 80160 | 748160 | 0.2 | 187040 |  | 80 |  | Dushant Gore | Swapnil Erande | construction open | 08 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 584 | 0 | 10 Dec 2022 | SHIVAM ENTERPRISES | LG Floor- Excavation Work for Service line | Backfilling - UDR | Cu.Ft | 8475.36 | 3.5 | 29663.76 | 0 | 29663.76 | 0 | 7107.7143 | 24877 | 0 | 24877 | 1367.6457 | 4786.76 |  | 83.8633 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Dec 2022 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 584 | 0 | 10 Dec 2022 | SHIVAM ENTERPRISES | LG Floor- Excavation Work for Service line | Excavation Manually | Cu.Mtrs | 301 | 180 | 54180 | 0 | 54180 | 0 | 242.3778 | 43628 | 0 | 43628 | 58.6222 | 10552 |  | 80.5242 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Dec 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 585 | 0 | 12 Dec 2022 | DURGARAM CHANDURAM BHATEE | Drainage Chamber Cleaning Work | Chamber Cleaning Work | No. | 15 | 100 | 1500 | 0 | 1500 | 0 | 14 | 1400 | 0 | 1400 | 1 | 100 |  | 93.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Dec 2022 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 586 | 0 | 12 Dec 2022 | K B N FABRICATION | UGWT- MS Sleeves Work | Sleeve Fixing UWT | No. | 31 | 400 | 12400 | 0 | 12400 | 2.5 | 30 | 12000 | 0 | 12000 | 1 | 400 |  | 96.7742 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Dec 2022 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 1 | 1750 | 1750 | 315 | 2065 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand-Kartar/ Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 260 | 2100 | 546000 | 98280 | 644280 | 0 | 70 | 147000 | 26460 | 173460 | 190 | 470820 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 26.9231 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 3 | 1750 | 5250 | 945 | 6195 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand -Kartar/Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 3 | 1750 | 5250 | 945 | 6195 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand -Kartar/Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (M) | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand -Essel/Mercry | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 25 | 33000 | 825000 | 148500 | 973500 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-Essel | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (M) | set | 12 | 33000 | 396000 | 71280 | 467280 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supply of landing Hydrants a) Double headed (Type B) hydrant valve made of stainless steel with 63mm dia outlets & 80mm/100 mm dia flanged inlet,gunmetal blank caps,chain and hand wheels b) 2 L of 15 mtr long,63mm dia RRL hose. Brand-Essel/Mercury. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 360 | 2550 | 918000 | 165240 | 1083240 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 370 | 500 | 185000 | 33300 | 218300 | 0 | 113.618 | 56809 | 10225.62 | 67034.62 | 256.382 | 151265.38 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 30.7076 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 440 | 2550 | 1122000 | 201960 | 1323960 | 0 | 308 | 785400 | 141372 | 926772 | 132 | 397188 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 1 | 7263 | 7263 | 1307.34 | 8570.34 | 0 | 0.7 | 5084.1 | 915.14 | 5999.24 | 0.3 | 2571.1 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand- Zoloto / KARTAR | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 13 | 1450 | 18850 | 3393 | 22243 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 1027 | 1450 | 1489150 | 268047 | 1757197 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 20 | 1450 | 29000 | 5220 | 34220 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 25 | 275 | 6875 | 1237.5 | 8112.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 275 | 3300 | 594 | 3894 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 25 | 33000 | 825000 | 148500 | 973500 | 0 | 17.5 | 577500 | 103950 | 681450 | 7.5 | 292050 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-Essel | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Orifice Plate (M) | No. | 25 | 1400 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (M) | No. | 3 | 3280 | 9840 | 1771.2 | 11611.2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 79 | 2100 | 165900 | 29862 | 195762 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 79 | 2100 | 165900 | 29862 | 195762 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 1 | 1750 | 1750 | 315 | 2065 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand-Kartar/ Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 270 | 3240 | 583.2 | 3823.2 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 1788 | 350 | 625800 | 112644 | 738444 | 0 | 714 | 249900 | 44982 | 294882 | 1074 | 443562 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 39.9329 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 25 | 7500 | 187500 | 33750 | 221250 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 26 | 2010 | 52260 | 9406.8 | 61666.8 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand- Mercury | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 25 | 4500 | 112500 | 20250 | 132750 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand- Zoloto/Kartar. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 9 | 1000 | 9000 | 1620 | 10620 | 0 | 6.3 | 6300 | 1134 | 7434 | 2.7 | 3186 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 100 | 2650 | 265000 | 47700 | 312700 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 50mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 857 | 1450 | 1242650 | 223677 | 1466327 | 0 | 666.5504 | 966498.01 | 173969.64 | 1140467.65 | 190.4497 | 325859.35 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 77.7772 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 27 | 1450 | 39150 | 7047 | 46197 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 57 | 450 | 25650 | 4617 | 30267 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | Supply of Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. Brand- HD Fire | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 120 | 230 | 27600 | 4968 | 32568 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (M). | set | 8 | 18500 | 148000 | 26640 | 174640 | 0 | 5.6 | 103600 | 18648 | 122248 | 2.4 | 52392 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-KARTAR | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 1616 | 380 | 614080 | 110534.4 | 724614.4 | 0 | 685.8 | 260604 | 46908.72 | 307512.72 | 930.2 | 417101.68 | Supply of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002 Brand- HD Fire | 42.4381 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 25 | 275 | 6875 | 1237.5 | 8112.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 270 | 3240 | 583.2 | 3823.2 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 1 | 6640 | 6640 | 1195.2 | 7835.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 1 | 6640 | 6640 | 1195.2 | 7835.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 1788 | 350 | 625800 | 112644 | 738444 | 0 | 420 | 147000 | 26460 | 173460 | 1368 | 564984 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 23.4899 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 466 | 2100 | 978600 | 176148 | 1154748 | 0 | 0 | 0 | 0 | 0 | 466 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (M) | No. | 3 | 995 | 2985 | 537.3 | 3522.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 260 | 2100 | 546000 | 98280 | 644280 | 0 | 177.8 | 373380 | 67208.4 | 440588.4 | 82.2 | 203691.6 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 68.3846 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 270 | 3240 | 583.2 | 3823.2 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 3401 | 350 | 1190350 | 214263 | 1404613 | 0 | 1821.9429 | 637680 | 114782.4 | 752462.4 | 1579.0571 | 652150.6 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 53.5708 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (M) | No. | 8 | 1100 | 8800 | 1584 | 10384 | 0 | 5.6 | 6160 | 1108.8 | 7268.8 | 2.4 | 3115.2 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 302 | 650 | 196300 | 35334 | 231634 | 0 | 210 | 136500 | 24570 | 161070 | 92 | 70564 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 69.5364 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 1027 | 1450 | 1489150 | 268047 | 1757197 | 0 | 426.2304 | 618034.01 | 111246.12 | 729280.13 | 600.7697 | 1027916.87 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 41.5025 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 100 | 2650 | 265000 | 47700 | 312700 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 50mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 27 | 1450 | 39150 | 7047 | 46197 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 25 | 3600 | 90000 | 16200 | 106200 | 0 | 17.5 | 63000 | 11340 | 74340 | 7.5 | 31860 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 1 | 3600 | 3600 | 648 | 4248 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 2 | 3600 | 7200 | 1296 | 8496 | 0 | 1.4 | 5040 | 907.2 | 5947.2 | 0.6 | 2548.8 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 25 | 3600 | 90000 | 16200 | 106200 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 302 | 650 | 196300 | 35334 | 231634 | 0 | 180.6 | 117390 | 21130.2 | 138520.2 | 121.4 | 93113.8 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 59.8013 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 223 | 650 | 144950 | 26091 | 171041 | 0 | 140.8215 | 91534 | 16476.12 | 108010.12 | 82.1785 | 63030.88 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 63.1487 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 13 | 6500 | 84500 | 15210 | 99710 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand-Kartar/Quinn. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 12 | 8500 | 102000 | 18360 | 120360 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supply of Vane type water flow switch in 150 mm size with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (M) | No. | 1 | 639 | 639 | 115.02 | 754.02 | 0 | 0.7 | 447.3 | 80.52 | 527.82 | 0.3 | 226.2 | Supplying and installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 1508 | 450 | 678600 | 122148 | 800748 | 0 | 1018.6489 | 458392 | 82510.56 | 540902.56 | 489.3511 | 259845.44 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 67.5497 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 1536 | 500 | 768000 | 138240 | 906240 | 0 | 420 | 210000 | 37800 | 247800 | 1116 | 658440 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 27.3438 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(M) | No. | 3 | 3800 | 11400 | 2052 | 13452 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 1536 | 500 | 768000 | 138240 | 906240 | 0 | 999.6 | 499800 | 89964 | 589764 | 536.4 | 316476 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 65.0781 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 1 | 3200 | 3200 | 576 | 3776 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand -Kartar/Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (M) | No. | 398 | 450 | 179100 | 32238 | 211338 | 0 | 282.2 | 126990 | 22858.2 | 149848.2 | 115.8 | 61489.8 | Supply of Early Suppression Fast Response Upright sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. Brand- HD Fire | 70.9045 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 1340 | 350 | 469000 | 84420 | 553420 | 0 | 567 | 198450 | 35721 | 234171 | 773 | 319249 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 42.3134 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 1340 | 350 | 469000 | 84420 | 553420 | 0 | 350 | 122500 | 22050 | 144550 | 990 | 408870 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 26.1194 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 18 | 1000 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (M) | No. | 4 | 3000 | 12000 | 2160 | 14160 | 0 | 2.8 | 8400 | 1512 | 9912 | 1.2 | 4248 | Supplying and installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe (M) | Mtrs | 153 | 800 | 122400 | 22032 | 144432 | 0 | 115.22 | 92176 | 16591.68 | 108767.68 | 37.78 | 35664.32 | Supply of 65mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 75.3072 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 373 | 1000 | 373000 | 67140 | 440140 | 0 | 273.4 | 273400 | 49212 | 322612 | 99.6 | 117528 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 73.2976 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 40 | 1000 | 40000 | 7200 | 47200 | 0 | 28 | 28000 | 5040 | 33040 | 12 | 14160 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(M) | No. | 4 | 3400 | 13600 | 2448 | 16048 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 40 | 160 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand -Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 40 | 160 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand -Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 1 | 7263 | 7263 | 1307.34 | 8570.34 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand- Zoloto / KARTAR | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 14 | 1200 | 16800 | 3024 | 19824 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Supply of stainless steel single stage single hole restriction 80 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 200 | 340 | 68000 | 12240 | 80240 | 0 | 140 | 47600 | 8568 | 56168 | 60 | 24072 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 9 | 1200 | 10800 | 1944 | 12744 | 0 | 6.3 | 7560 | 1360.8 | 8920.8 | 2.7 | 3823.2 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 175 | 350 | 61250 | 11025 | 72275 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | No. | 3 | 5800 | 17400 | 3132 | 20532 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers CO2 type fire extinguishers of 4.5 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand-Marcury | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 4 Way 63mm,Fire Service inlet (M) | No. | 3 | 7200 | 21600 | 3888 | 25488 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supply of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand -Essel/Mercry | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(M) | No. | 18 | 3800 | 68400 | 12312 | 80712 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 357 | 450 | 160650 | 28917 | 189567 | 0 | 6.3 | 2835 | 510.3 | 3345.3 | 350.7 | 186221.7 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 1.7647 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 1 | 7540 | 7540 | 1357.2 | 8897.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of Vane type water flow switch in 100 mm size with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 12 | 2200 | 26400 | 4752 | 31152 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand-Marcury | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm.(M) | set | 7 | 56500 | 395500 | 71190 | 466690 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | Supply of Hydraulically operated sprinkler alarm valve 15mm with all accesories; 2 nos of pressure guages,2 nos isolation valves, 1 no of angle valve, 1 no of strainer, 1 no of non return valve, 1 no of alarm control valve, 1 no of alarm test valve etc.Brand-HD Fire | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(M) | No. | 14 | 3200 | 44800 | 8064 | 52864 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Supply of C.I. butterfly valves 80 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 1366 | 2100 | 2868600 | 516348 | 3384948 | 0 | 386.3105 | 811252.03 | 146025.36 | 957277.39 | 979.6895 | 2427670.61 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 28.2804 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 120 | 230 | 27600 | 4968 | 32568 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 100 | 2400 | 240000 | 43200 | 283200 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 100 | 2400 | 240000 | 43200 | 283200 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 12 | 1400 | 16800 | 3024 | 19824 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Orifice Plate (M) | No. | 25 | 1400 | 35000 | 6300 | 41300 | 0 | 17.5 | 24500 | 4410 | 28910 | 7.5 | 12390 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 20 | 1450 | 29000 | 5220 | 34220 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 8 | 1850 | 14800 | 2664 | 17464 | 0 | 7.7005 | 14246.01 | 2564.28 | 16810.29 | 0.2995 | 653.71 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 96.2563 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (M). | set | 14 | 19500 | 273000 | 49140 | 322140 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-Essel/Mercury. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (M) | No. | 21 | 1450 | 30450 | 5481 | 35931 | 0 | 20.7 | 30015 | 5402.7 | 35417.7 | 0.3 | 513.3 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 98.5714 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 200 | 340 | 68000 | 12240 | 80240 | 0 | 107.8 | 36652 | 6597.36 | 43249.36 | 92.2 | 36990.64 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 53.9 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 175 | 350 | 61250 | 11025 | 72275 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 1 | 3200 | 3200 | 576 | 3776 | 0 | 0.7 | 2240 | 403.2 | 2643.2 | 0.3 | 1132.8 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand -Kartar/Zoloto | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 24 | 350 | 8400 | 1512 | 9912 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 25 | 7500 | 187500 | 33750 | 221250 | 0 | 17.5 | 131250 | 23625 | 154875 | 7.5 | 66375 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 357 | 450 | 160650 | 28917 | 189567 | 0 | 249.9 | 112455 | 20241.9 | 132696.9 | 107.1 | 56870.1 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 26 | 2010 | 52260 | 9406.8 | 61666.8 | 0 | 17.5 | 35175 | 6331.5 | 41506.5 | 8.5 | 20160.3 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand- Mercury | 67.3077 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 25 | 4500 | 112500 | 20250 | 132750 | 0 | 17.5 | 78750 | 14175 | 92925 | 7.5 | 39825 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand- Zoloto/Kartar. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 2 | 3600 | 7200 | 1296 | 8496 | 0 | 1.4 | 5040 | 907.2 | 5947.2 | 0.6 | 2548.8 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (L) | No. | 21 | 200 | 4200 | 756 | 4956 | 0 | 19 | 3800 | 684 | 4484 | 2 | 472 | ITC 32mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 90.4762 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 27 | 550 | 14850 | 2673 | 17523 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (L) | No. | 4 | 350 | 1400 | 252 | 1652 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 20 | 550 | 11000 | 1980 | 12980 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 8 | 200 | 1600 | 288 | 1888 | 0 | 6.65 | 1330 | 239.4 | 1569.4 | 1.35 | 318.6 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 83.125 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Orifice Plate (L) | No. | 25 | 200 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (L) | Mtrs | 40 | 45 | 1800 | 324 | 2124 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | ITC earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. The strip shall run on floor / ceiling / walls ,from the equipment to the nearest earth pit with neccessory accessories as require | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (L) | No. | 14 | 200 | 2800 | 504 | 3304 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 80mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 857 | 550 | 471350 | 84843 | 556193 | 0 | 211.28 | 116204 | 20916.72 | 137120.72 | 645.72 | 419072.28 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 24.6534 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (L) | No. | 1 | 320 | 320 | 57.6 | 377.6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 370 | 300 | 111000 | 19980 | 130980 | 0 | 76.05 | 22815.01 | 4106.7 | 26921.71 | 293.95 | 104058.29 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 20.5541 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Double Hydrant Valve (L) | set | 25 | 1500 | 37500 | 6750 | 44250 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC of Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 4 way 63mm,Fire service inlet | No. | 3 | 250 | 750 | 135 | 885 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | ITC of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | UTI Fire fight. (underground) | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Double Hydrant Valve (L) | set | 25 | 1500 | 37500 | 6750 | 44250 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC of Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Air Release Valve 25mm (L) | No. | 3 | 220 | 660 | 118.8 | 778.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (L). | set | 8 | 1100 | 8800 | 1584 | 10384 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | Single headed (Type A) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet , gunmetal blank caps, chain and hand wheels etc complete. The installation must be carried out as per the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(L) | No. | 3 | 350 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 79 | 600 | 47400 | 8532 | 55932 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Brand-Jindal/Apollo.ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 260 | 600 | 156000 | 28080 | 184080 | 0 | 138.6 | 83160 | 14968.8 | 98128.8 | 121.4 | 85951.2 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 53.3077 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(L) | No. | 14 | 350 | 4900 | 882 | 5782 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (L) | Mtrs | 40 | 45 | 1800 | 324 | 2124 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | ITC earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. The strip shall run on floor / ceiling / walls ,from the equipment to the nearest earth pit with neccessory accessories as require | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass,with unions etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 16.1 | 5635 | 1014.3 | 6649.3 | 8.9 | 3675.7 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass,with unions etc. complete. The installation must be carried out as per EIC. | 64.4 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 1536 | 300 | 460800 | 82944 | 543744 | 0 | 0 | 0 | 0 | 0 | 1536 | 0 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 1536 | 300 | 460800 | 82944 | 543744 | 0 | 945 | 283500 | 51030 | 334530 | 591 | 209214 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 61.5234 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 25 | 100 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (L) | No. | 3 | 350 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 223 | 400 | 89200 | 16056 | 105256 | 0 | 63.03 | 25212 | 4538.16 | 29750.16 | 159.97 | 75505.84 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 28.2646 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm.Cable. (L) | Mtrs | 175 | 55 | 9625 | 1732.5 | 11357.5 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 50mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 13 | 850 | 11050 | 1989 | 13039 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass, with unions etc. complete. The installation must be carried out as per EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 40 | 500 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (L) | No. | 1616 | 200 | 323200 | 58176 | 381376 | 0 | 96.9 | 19380 | 3488.4 | 22868.4 | 1519.1 | 358507.6 | ITC Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 5.9963 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe | Mtrs | 153 | 450 | 68850 | 12393 | 81243 | 0 | 47.5311 | 21389 | 3850.02 | 25239.02 | 105.4689 | 56003.99 | ITC 65mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 31.0661 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 12 | 200 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs.Complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 357 | 250 | 89250 | 16065 | 105315 | 0 | 249.9 | 62475 | 11245.5 | 73720.5 | 107.1 | 31594.5 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 360 | 750 | 270000 | 48600 | 318600 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (L) | set | 12 | 1500 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 18 | 450 | 8100 | 1458 | 9558 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (L) | No. | 1 | 250 | 250 | 45 | 295 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 1340 | 200 | 268000 | 48240 | 316240 | 0 | 0 | 0 | 0 | 0 | 1340 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 373 | 500 | 186500 | 33570 | 220070 | 0 | 176.15 | 88075 | 15853.5 | 103928.5 | 196.85 | 116141.5 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 47.2252 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm (L) | No. | 7 | 2500 | 17500 | 3150 | 20650 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | ITC of Hydraulically operated sprinkler alarm valve with accesories; 2 nos of pressure guages,2 nos isolation valves.The installation must be carried out as per the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 9 | 600 | 5400 | 972 | 6372 | 0 | 3.64 | 2184 | 393.12 | 2577.12 | 5.36 | 3794.88 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 40.4444 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 357 | 250 | 89250 | 16065 | 105315 | 0 | 0 | 0 | 0 | 0 | 357 | 0 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 1508 | 250 | 377000 | 67860 | 444860 | 0 | 250.952 | 62738 | 11292.84 | 74030.84 | 1257.048 | 370829.16 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 16.6414 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(L) | No. | 18 | 350 | 6300 | 1134 | 7434 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Orifice Plate (L) | No. | 25 | 200 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 26 | 215 | 5590 | 1006.2 | 6596.2 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | ITC portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 26 | 215 | 5590 | 1006.2 | 6596.2 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | ITC portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Strainer "Y" (L) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I,of size and pressure rating as indicated below, with required flanges, nuts, bolts.The installation must be carried out as per the standard procedure of EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Strainer "Y" (L) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(L) | No. | 4 | 300 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (L) | No. | 12 | 200 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Air Release Valve 25mm (L) | No. | 1 | 200 | 200 | 36 | 236 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete.The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 260 | 600 | 156000 | 28080 | 184080 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 79 | 600 | 47400 | 8532 | 55932 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Brand-Jindal/Apollo.ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 466 | 600 | 279600 | 50328 | 329928 | 0 | 0 | 0 | 0 | 0 | 466 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (L) | No. | 1 | 200 | 200 | 36 | 236 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete.The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 1366 | 600 | 819600 | 147528 | 967128 | 0 | 205.515 | 123309 | 22195.62 | 145504.62 | 1160.485 | 821623.38 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 15.045 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 440 | 750 | 330000 | 59400 | 389400 | 0 | 303.0307 | 227273.03 | 40909.14 | 268182.17 | 136.9693 | 121217.84 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 68.8706 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(L) | No. | 3 | 200 | 600 | 108 | 708 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | ITC portable fire extinguisers CO2 type fire extinguishers 4.5 KG.Fitted with gun metal union, high pressure CO2 gas cartridge & wall mounting bracket etc.complete. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 1788 | 200 | 357600 | 64368 | 421968 | 0 | 1002.4 | 200480 | 36086.4 | 236566.4 | 785.6 | 185401.6 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 56.0626 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (L) | No. | 57 | 350 | 19950 | 3591 | 23541 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | ITC Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 24 | 200 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 16.1 | 5635 | 1014.3 | 6649.3 | 8.9 | 3675.7 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC | 64.4 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Brand-Zoloto/Kartar.ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Brand-Zoloto/Kartar.ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (L) | No. | 8 | 150 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | Design,installation,testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (L). | set | 14 | 1250 | 17500 | 3150 | 20650 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | ITC Single headed (Type A) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet , gunmetal blank caps, chain and hand wheels etc.complete.The installation must be carried out as per EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 1788 | 200 | 357600 | 64368 | 421968 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 1027 | 550 | 564850 | 101673 | 666523 | 0 | 544.2819 | 299355.02 | 53430.3 | 352785.32 | 482.7182 | 313737.68 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 52.9973 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 1027 | 550 | 564850 | 101673 | 666523 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 13 | 550 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (L) | No. | 398 | 350 | 139300 | 25074 | 164374 | 0 | 11.4 | 3990 | 718.2 | 4708.2 | 386.6 | 159665.8 | ITC Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 2.8643 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (L) | No. | 3 | 350 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 302 | 400 | 120800 | 21744 | 142544 | 0 | 0 | 0 | 0 | 0 | 302 | 0 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 302 | 400 | 120800 | 21744 | 142544 | 0 | 211.4 | 84560 | 15220.8 | 99780.8 | 90.6 | 42763.2 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 3401 | 200 | 680200 | 122436 | 802636 | 0 | 269.25 | 53850 | 9693 | 63543 | 3131.75 | 739093 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 7.9168 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 25 | 100 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 200 | 200 | 40000 | 7200 | 47200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 1340 | 200 | 268000 | 48240 | 316240 | 0 | 844.2 | 168840 | 30391.2 | 199231.2 | 495.8 | 117008.8 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 63 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 200 | 200 | 40000 | 7200 | 47200 | 0 | 128.8 | 25760 | 4636.8 | 30396.8 | 71.2 | 16803.2 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 64.4 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 9 | 450 | 4050 | 729 | 4779 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 12 | 350 | 4200 | 756 | 4956 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | ITC 150mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm.Cable. (L) | Mtrs | 175 | 55 | 9625 | 1732.5 | 11357.5 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Air Release Valve 25mm (L) | No. | 3 | 220 | 660 | 118.8 | 778.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Start/Stop push button station (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Erection of emergency start / stop push button station weather proof type for Booster pump. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Non Return Valve 100mm (L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I,of size and pressure rating as indicated below, with required flanges, nuts, bolts.The installation must be carried out as per the standard procedure of EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 3C x 1.5sqmm (L) | Mtrs | 120 | 45 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (L) | Mtrs | 120 | 45 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Start/Stop push button station (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Erection of emergency start / stop push button station weather proof type for Booster pump. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 20 | 550 | 11000 | 1980 | 12980 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 27 | 550 | 14850 | 2673 | 17523 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 606 | 0 | 03 Jan 2023 | MAHARASTRA NATURAL GAS LIMITED | E-Bldg MNGL Connection | Gas Connection & Activation | Flat | 200 | 6000 | 1200000 | 216000 | 1416000 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jan 2023 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 606 | 0 | 03 Jan 2023 | MAHARASTRA NATURAL GAS LIMITED | D-Bldg MNGL Connection | Gas Connection & Activation | Flat | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jan 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 04 Jan 2023
GANGA ALTUS | 606 | 0 | 03 Jan 2023 | MAHARASTRA NATURAL GAS LIMITED | D-Bldg MNGL Connection | Gas Connection & Activation | Flat | 200 | 6000 | 1200000 | 216000 | 1416000 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jan 2023 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 606 | 0 | 03 Jan 2023 | MAHARASTRA NATURAL GAS LIMITED | D-Bldg MNGL Connection | Gas Connection & Activation | Flat | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jan 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 04 Jan 2023
GANGA ALTUS | 606 | 0 | 03 Jan 2023 | MAHARASTRA NATURAL GAS LIMITED | E-Bldg MNGL Connection | Gas Connection & Activation | Flat | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jan 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 04 Jan 2023
GANGA ALTUS | 606 | 0 | 03 Jan 2023 | MAHARASTRA NATURAL GAS LIMITED | E-Bldg MNGL Connection | Gas Connection & Activation | Flat | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Jan 2023 |  | 14 MISC WORK | Cancelled | ADITYA CHOUGULE | 04 Jan 2023
GANGA ALTUS | 617 | 0 | 06 Feb 2023 | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | F-Bldg LG Fl-Electrical Cable pipe line work-Lift to M.Room | Chamber 24" x 24" (2.5ft Ht) - UDR | No. | 4 | 1000 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 617 | 0 | 06 Feb 2023 | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | F-Bldg LG Fl-Electrical Cable pipe line work-Lift to M.Room | 6" RCC Hume Pipe laying & fixing -UDR | R.Ft | 60.64 | 15 | 909.6 | 163.72 | 1073.32 | 2.5 | 0 | 0 | 0 | 0 | 60.64 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 625 | 0 | 24 Feb 2023 | RITU ENTERPRISES | ETP RCC Work (L) | RCC Work ETP | Ltrs | 116136 | 4 | 464544 | 83617.92 | 548161.92 | 2.5 | 65036.16 | 260144.64 | 46826.02 | 306970.66 | 51099.84 | 241191.26 |  | 56 |  | DUSHANT GORE | DUSHANT GORE | construction open | 26 May 2023 |  | 02 RCC WORK | Approved | DUSHANT GORE | 1900-01-01
GANGA ALTUS | 631 | 1 | 02 Mar 2023 | SS ENTERPRISES | STP-265 KLD Murum Backfilling Work - 1 No. | Murum Backfilling | Cu.Mtrs | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Murum Filling including loading, unloading including all leads and lifts, stacking with all tool, Equipments & machinery. Ensuring all required safety precautions etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Spreading & Levelling Work | Cu.Mtrs | 758 | 20 | 15160 | 2728.8 | 17888.8 | 0 | 758 | 15160 | 0 | 15160 | 0 | 2728.8 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Spreading & Levelling Work | Cu.Mtrs | 522.85 | 20 | 10457 | 1882.26 | 12339.26 | 0 | 522 | 10440 | 0 | 10440 | 0.85 | 1899.26 |  | 99.8374 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Excavation in Hard Rock | Cu.Mtrs | 309.39 | 210 | 64971.9 | 11694.94 | 76666.84 | 0 | 309.39 | 64971.9 | 0 | 64971.9 | 0 | 11694.94 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Backfilling | Cu.Mtrs | 289.04 | 60 | 17342.4 | 3121.64 | 20464.04 | 0 | 289.04 | 17342.4 | 0 | 17342.4 | 0 | 3121.64 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Backfilling | Cu.Mtrs | 758 | 60 | 45480 | 8186.4 | 53666.4 | 0 | 758 | 45480 | 0 | 45480 | 0 | 8186.4 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Backfilling | Cu.Mtrs | 522.85 | 60 | 31371 | 5646.78 | 37017.78 | 0 | 344.111 | 20646.66 | 0 | 20646.66 | 178.739 | 16371.12 |  | 65.8145 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Excavation in Soil- UST | Cu.Mtrs | 546.75 | 60 | 32805 | 5904.9 | 38709.9 | 0 | 546.75 | 32805 | 0 | 32805 | 0 | 5904.9 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | UTI. S.T.P | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Spreading & Levelling Work | Cu.Mtrs | 546.75 | 20 | 10935 | 1968.3 | 12903.3 | 0 | 546.75 | 10935 | 0 | 10935 | 0 | 1968.3 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Spreading & Levelling Work | Cu.Mtrs | 289.04 | 20 | 5780.8 | 1040.54 | 6821.34 | 0 | 289.04 | 5780.8 | 0 | 5780.8 | 0 | 1040.54 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 0 | 02 Mar 2023 | SS ENTERPRISES | Ramp footing Excavation & UGWT- Side Filling | Spreading & Levelling Work | Cu.Mtrs | 309.39 | 15 | 4640.85 | 835.36 | 5476.21 | 0 | 309 | 4635 | 0 | 4635 | 0.39 | 841.21 |  | 99.8739 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 631 | 1 | 02 Mar 2023 | SS ENTERPRISES | STP-265 KLD Murum Backfilling Work - 1 No. | Bobcat Hiring Charges | Hrs | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
GANGA ALTUS | 631 | 1 | 02 Mar 2023 | SS ENTERPRISES | STP-265 KLD Murum Backfilling Work - 1 No. | Spreading & Levelling Work | Cu.Mtrs | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Murum Spreading with available dumped earth material including Lifting, shifting & unloading at requird Place including all leads and lifts, stacking and spreading with all tool, Equipments etc. | 0 |  | ADITYA CHOUGULE |  | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 07 Apr 2023
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Signage Board (M) | No. | 10 | 225 | 2250 | 405 | 2655 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | This sign shall be used to Indicate the system for which pipe is used. It shall be accompanied: by an arrow.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (M). | Mtrs | 24 | 2400 | 57600 | 10368 | 67968 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Exhaust pipe 100mm for Diesel engine of M.S. medium grade with mineral wool insulation and aluminum sheet for protection | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (M) | No. | 2 | 25500 | 51000 | 9180 | 60180 | 0 | 1.4 | 35700 | 6426 | 42126 | 0.6 | 18054 | C.I. butterfly valves 200mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables (M) | Mtrs | 40 | 2950 | 118000 | 21240 | 139240 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(M) | Mtrs | 14 | 1500 | 21000 | 3780 | 24780 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 4 Way 63mm,Fire Service inlet (M) | No. | 2 | 7200 | 14400 | 2592 | 16992 | 0 | 1.4 | 10080 | 1814.4 | 11894.4 | 0.6 | 5097.6 | Fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry). | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(M) | No. | 2 | 7000 | 14000 | 2520 | 16520 | 0 | 0.95 | 6650 | 1197 | 7847 | 1.05 | 8673 | C.I. butterfly valves 80mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 47.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (M) | No. | 2 | 1450 | 2900 | 522 | 3422 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 25mm dia Automatic air release valve of approved makes with unions etc. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Rotameter (M) | No. | 1 | 10500 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Rotameter of approved make of flow range 2.5 to 40000 lph of approved make etc complete | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables (M) | Mtrs | 10 | 2950 | 29500 | 5310 | 34810 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 15 | 2200 | 33000 | 5940 | 38940 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 21 | 2200 | 46200 | 8316 | 54516 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Switch (M) | No. | 10 | 2350 | 23500 | 4230 | 27730 | 0 | 7 | 16450 | 2961 | 19411 | 3 | 8319 | Pressure switches of approved makes of suitable range for pumpsets. The quoted rates shall include needle valves, fittings like unions / collars / reducers etc. (Make- Danfors) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Service Inlet Connection (M) | set | 6 | 5200 | 31200 | 5616 | 36816 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Fire service inlet connection of 3 way with 3 nos. 63mm dia instantaneous coupling with built in non return valves(Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 2 Way 63mm,Fire Service inlet (M) | No. | 1 | 4200 | 4200 | 756 | 4956 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (M) | No. | 20 | 3200 | 64000 | 11520 | 75520 | 0 | 9.8 | 31360 | 5644.8 | 37004.8 | 10.2 | 38515.2 | Glyserene filled pressure gauges of approved makes and of 0-25 bar range , dial size 100 mm accuracy class 1.6, IP 65 class include isolation valves, siphon tubes, needle valves with inlet connections of required sizes, with unions, washers, gaskets etc.(H Guru) | 49 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(M) | No. | 14 | 12000 | 168000 | 30240 | 198240 | 0 | 9.8 | 117600 | 21168 | 138768 | 4.2 | 59472 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (M) | Mtrs | 20 | 650 | 13000 | 2340 | 15340 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports,anchor fasteners etc. complete.Maximum height of suspension shall not exceed 500 mm.Size of the tray shall be 150 mm x 50 mm | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(M) | No. | 4 | 12000 | 48000 | 8640 | 56640 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (M) | No. | 2 | 1375000 | 2750000 | 495000 | 3245000 | 0 | 1.4 | 1925000 | 346500 | 2271500 | 0.6 | 973500 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type and capable to deliver from 1st Take off 171Cum/Hr at 106mwc and 171 Cum/Hr at 150 mwc from 2nd take off (Make-Lubi/KSB/Kirlosakar) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Rate Diff. Control Panel (M) | No. | 1 | 290000 | 290000 | 52200 | 342200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (M) | No. | 2 | 16500 | 33000 | 5940 | 38940 | 0 | 1.4 | 23100 | 4158 | 27258 | 0.6 | 11682 | Swing check type non-return valves 200mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(M) | Mtrs | 16 | 1500 | 24000 | 4320 | 28320 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 20 x 3mm GI Strip (M) | Mtrs | 30 | 400 | 12000 | 2160 | 14160 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | GI earthing strips of size 20mmx3mm of approved makes confirming to I.S. 3043:1987. The strip shall run on floor / ceiling / walls , from the equipment to the nearest earth pit with neccessory accessories as required | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (M) | No. | 2 | 27000 | 54000 | 9720 | 63720 | 0 | 1.4 | 37800 | 6804 | 44604 | 0.6 | 19116 | Air Vessel with required standard connections & required it supports,anchor fastners & nut bolts etc.(Dia 300 x 1200mm Height) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables (M) | Mtrs | 150 | 95 | 14250 | 2565 | 16815 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(M) | Mtrs | 10 | 4400 | 44000 | 7920 | 51920 | 0 | 7 | 30800 | 5544 | 36344 | 3 | 15576 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Relief Valve (M) | No. | 1 | 2300 | 2300 | 414 | 2714 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Pressure relief valve 20mm dia. UL / FM approved, with required threaded adaptors, nuts, bolts. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe (M) | Mtrs | 29 | 3400 | 98600 | 17748 | 116348 | 0 | 20.3 | 69020 | 12423.6 | 81443.6 | 8.7 | 34904.4 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(M) | No. | 4 | 7500 | 30000 | 5400 | 35400 | 0 | 2.8 | 21000 | 3780 | 24780 | 1.2 | 10620 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Control Panel (M) | No. | 1 | 410000 | 410000 | 73800 | 483800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe (M) | Mtrs | 1 | 3400 | 3400 | 612 | 4012 | 0 | 0.7 | 2380 | 428.4 | 2808.4 | 0.3 | 1203.6 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Strainer "Y" (M) | No. | 2 | 5900 | 11800 | 2124 | 13924 | 0 | 1.4 | 8260 | 1486.8 | 9746.8 | 0.6 | 4177.2 | C.I.flanges "Y" type strainer 100mm with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (M) | No. | 2 | 29200 | 58400 | 10512 | 68912 | 0 | 1.4 | 40880 | 7358.4 | 48238.4 | 0.6 | 20673.6 | Sluice valves 200mm of approved makes rating confirming to IS:14846:2000, for suction side of the pumps and rising spindle type with flanges, bolts, nuts washers, gaskets etc.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket (M) | No. | 4 | 1000 | 4000 | 720 | 4720 | 0 | 2.8 | 2800 | 504 | 3304 | 1.2 | 1416 | Fire buckets round bottom type enamel painted,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket Stand (M) | No. | 1 | 2500 | 2500 | 450 | 2950 | 0 | 0.7 | 1750 | 315 | 2065 | 0.3 | 885 | Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables (M) | Mtrs | 40 | 1150 | 46000 | 8280 | 54280 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(M) | No. | 6 | 7500 | 45000 | 8100 | 53100 | 0 | 6 | 45000 | 8100 | 53100 | 0 | 0 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables (M) | Mtrs | 40 | 1150 | 46000 | 8280 | 54280 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables (M) | Mtrs | 20 | 350 | 7000 | 1260 | 8260 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 14 | 1000 | 14000 | 2520 | 16520 | 0 | 9.8 | 9800 | 1764 | 11564 | 4.2 | 4956 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 80mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables (M) | Mtrs | 10 | 350 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Poly | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (M) | No. | 6 | 10000 | 60000 | 10800 | 70800 | 0 | 4.2 | 42000 | 7560 | 49560 | 1.8 | 21240 | Swing check type non-return valves 150mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Extinguisher (M) | No. | 1 | 6700 | 6700 | 1206 | 7906 | 0 | 0.7 | 4690 | 844.2 | 5534.2 | 0.3 | 2371.8 | Portable fire extinguisers Mechanical foam type fire extinguishers 50 Lts. capacity with intial filling in brand new cylinder with powder coated finish, fitted with gun metal union, high pressure CO2 gas cartridge,etc | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 100mm (M) | No. | 4 | 6500 | 26000 | 4680 | 30680 | 0 | 3.1 | 20150 | 3627 | 23777 | 0.9 | 6903 | Swing check type non-return valves 100mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 77.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (M) | No. | 10 | 1550 | 15500 | 2790 | 18290 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Ball valve 50mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Diesel Engine Driven Pump (M) | No. | 1 | 1717410 | 1717410 | 309133.8 | 2026543.8 | 0 | 0.7 | 1202187 | 216393.66 | 1418580.66 | 0.3 | 607963.14 | Diesel engine driven stand-by pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 171Cum/Hr at 106 mwc and 171 Cum/Hr at 150 mwc from 2nd take off.(Make-Lubi/KSB/Kirlosakar) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (M) | No. | 2 | 205000 | 410000 | 73800 | 483800 | 0 | 1.4 | 287000 | 51660 | 338660 | 0.6 | 145140 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 10.8Cum/Hr at 106 mwc and 10.8 Cum/Hr at 150 mwc from 2nd take off.(Hydrant Jockey + Sprinkler Jockey) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (M) | No. | 1 | 17500 | 17500 | 3150 | 20650 | 0 | 0.7 | 12250 | 2205 | 14455 | 0.3 | 6195 | Foot valves 150mm with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 25 NB-(M) | Mtrs | 7 | 350 | 2450 | 441 | 2891 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 25mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Sprinkler Alarm Valve 150mm dia (M) | set | 7 | 43500 | 304500 | 54810 | 359310 | 0 | 2.1 | 91350 | 16443 | 107793 | 4.9 | 251517 | Hydraulically operated sprinkler alarm valve with accesories | 30 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | CI Strainer 150 mm (M) | No. | 3 | 8900 | 26700 | 4806 | 31506 | 0 | 2.1 | 18690 | 3364.2 | 22054.2 | 0.9 | 9451.8 | C.I. "Basket" type strainer 150mm nominal dia with SS mesh of approved makes, confirming to ASME 31 with suitable flanges, nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 25mm (M) | No. | 4 | 1250 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Ball valve 25mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(M) | Mtrs | 2 | 4400 | 8800 | 1584 | 10384 | 0 | 1.4 | 6160 | 1108.8 | 7268.8 | 0.6 | 3115.2 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables (M) | Mtrs | 50 | 95 | 4750 | 855 | 5605 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | CI Strainer 150 mm (L) | No. | 3 | 320 | 960 | 172.8 | 1132.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | C.I. "Basket" type strainer 150mm nominal dia with SS mesh of approved makes, confirming to ASME 31 with suitable flanges, nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(L) | Mtrs | 16 | 500 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 21 | 600 | 12600 | 2268 | 14868 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 15 | 600 | 9000 | 1620 | 10620 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (L) | No. | 2 | 320 | 640 | 115.2 | 755.2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Sluice valves 200mm of approved makes rating confirming to IS:14846:2000, for suction side of the pumps and rising spindle type with flanges, bolts, nuts washers, gaskets etc.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket Stand (L) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 2 Way 63mm,Fire Service inlet (L) | No. | 1 | 250 | 250 | 45 | 295 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (L) | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Swing check type non-return valves 200mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 4 way 63mm,Fire service inlet | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | UTI Fire fight. (underground) | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket (L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Fire buckets round bottom type enamel painted,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables | Mtrs | 20 | 50 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (L) | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I. butterfly valves 200mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (L). | Mtrs | 24 | 600 | 14400 | 2592 | 16992 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Exhaust pipe 100mm for Diesel engine of M.S. medium grade with mineral wool insulation and aluminum sheet for protection | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables | Mtrs | 10 | 50 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Poly | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(L) | No. | 6 | 250 | 1500 | 270 | 1770 | 0 | 5.7 | 1425 | 256.5 | 1681.5 | 0.3 | 88.5 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 95 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (L) | No. | 2 | 15000 | 30000 | 5400 | 35400 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 10.8Cum/Hr at 106 mwc and 10.8 Cum/Hr at 150 mwc from 2nd take off.(Hydrant Jockey + Sprinkler Jockey) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Exstingusher (L) | No. | 1 | 150 | 150 | 27 | 177 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Portable fire extinguisers Mechanical foam type fire extinguishers 50 Lts. capacity with intial filling in brand new cylinder with powder coated finish, fitted with gun metal union, high pressure CO2 gas cartridge,etc | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe | Mtrs | 1 | 800 | 800 | 144 | 944 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe | Mtrs | 29 | 800 | 23200 | 4176 | 27376 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 25mm (L) | No. | 4 | 120 | 480 | 86.4 | 566.4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Ball valve 25mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (L) | No. | 2 | 30000 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type and capable to deliver from 1st Take off 171Cum/Hr at 106mwc and 171 Cum/Hr at 150 mwc from 2nd take off (Make-Lubi/KSB/Kirlosakar) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Signage Board (L) | No. | 10 | 100 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | This sign shall be used to Indicate the system for which pipe is used. It shall be accompanied: by an arrow.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(L) | Mtrs | 10 | 1000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Diesel Engine Driven Pump | No. | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Diesel engine driven stand-by pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 171Cum/Hr at 106 mwc and 171 Cum/Hr at 150 mwc from 2nd take off.(Make-Lubi/KSB/Kirlosakar) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables | Mtrs | 50 | 50 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Rotameter | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Rotameter of approved make of flow range 2.5 to 40000 lph of approved make etc complete | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (L) | No. | 6 | 250 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Swing check type non-return valves 150mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(L) | Mtrs | 14 | 500 | 7000 | 1260 | 8260 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(L) | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0.952 | 238 | 42.84 | 280.84 | 1.048 | 309.16 | C.I. butterfly valves 80mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 47.6 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 14 | 425 | 5950 | 1071 | 7021 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 80mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 100mm (L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0.952 | 238 | 42.84 | 280.84 | 3.048 | 899.16 | Swing check type non-return valves 100mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 23.8 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Sprinkler Alarm Valve 150mm dia (L) | set | 7 | 1500 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | Hydraulically operated sprinkler alarm valve with accesories | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (L) | Mtrs | 20 | 120 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports,anchor fasteners etc. complete.Maximum height of suspension shall not exceed 500 mm.Size of the tray shall be 150 mm x 50 mm | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Strainer "Y" (L) | No. | 2 | 320 | 640 | 115.2 | 755.2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I.flanges "Y" type strainer 100mm with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(L) | Mtrs | 2 | 1000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (L) | No. | 2 | 150 | 300 | 54 | 354 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 25mm dia Automatic air release valve of approved makes with unions etc. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 25 NB-(L) | Mtrs | 7 | 150 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 25mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (L) | No. | 1 | 320 | 320 | 57.6 | 377.6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Foot valves 150mm with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 20 x 3mm GI Strip (L) | Mtrs | 30 | 120 | 3600 | 648 | 4248 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | GI earthing strips of size 20mmx3mm of approved makes confirming to I.S. 3043:1987. The strip shall run on floor / ceiling / walls , from the equipment to the nearest earth pit with neccessory accessories as required | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Control Panel (L) | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (L) | No. | 10 | 120 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Ball valve 50mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables | Mtrs | 10 | 50 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables | Mtrs | 150 | 50 | 7500 | 1350 | 8850 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Relief Valve (L) | No. | 1 | 250 | 250 | 45 | 295 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Pressure relief valve 20mm dia. UL / FM approved, with required threaded adaptors, nuts, bolts. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(L) | No. | 14 | 250 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Switch (L) | No. | 10 | 120 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Pressure switches of approved makes of suitable range for pumpsets. The quoted rates shall include needle valves, fittings like unions / collars / reducers etc. (Make- Danfors) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Service Inlet Connection (L) | set | 6 | 250 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Fire service inlet connection of 3 way with 3 nos. 63mm dia instantaneous coupling with built in non return valves(Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (L) | No. | 2 | 1100 | 2200 | 396 | 2596 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Air Vessel with required standard connections & required it supports,anchor fastners & nut bolts etc.(Dia 300 x 1200mm Height) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (L) | No. | 20 | 120 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Glyserene filled pressure gauges of approved makes and of 0-25 bar range , dial size 100 mm accuracy class 1.6, IP 65 class include isolation valves, siphon tubes, needle valves with inlet connections of required sizes, with unions, washers, gaskets etc.(H Guru) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 0 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | Schedule & Quality | Sq.Ft | 1078.94 | 10 | 10789.4 | 0 | 10789.4 | 2.5 | 0 | 0 | 0 | 0 | 1078.94 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 1 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | Pile Breaking -DCW | No. | 10 | 500 | 5000 | 0 | 5000 | 0 | 10 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 18 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 0 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | Hacking Work | Sq.Ft | 1078.94 | 10 | 10789.4 | 0 | 10789.4 | 2.5 | 0 | 0 | 0 | 0 | 1078.94 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 1 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | RCC Superstructure (B-up area) | Sq.Ft | 817.15 | 145 | 118486.75 | 0 | 118486.75 | 2.5 | 817.15 | 118486.75 | 0 | 118486.75 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 18 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 0 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | RCC Superstructure (B-up area) | Sq.Ft | 1078.94 | 290 | 312892.6 | 0 | 312892.6 | 2.5 | 989.4185 | 286931.37 | 6050.66 | 292982.03 | 89.5215 | 19910.58 |  | 91.7028 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 0 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | RCC Substructure Labour (B-up area)- BC | Sq.Ft | 1078.94 | 100 | 107894 | 0 | 107894 | 2.5 | 1062.29 | 106229 | 0 | 106229 | 16.65 | 1665 |  | 98.4568 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Mar 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 638 | 0 | 18 Mar 2023 | VIJAY MOHITE | Transformer Room-RCC Work (L) | RCC Substructure Labour (B-up area)- BC | Sq.Ft | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 18 Mar 2023 |  | B.C. RCC Substructure | Cancelled | ADITYA CHOUGULE | 18 Mar 2023
GANGA ALTUS | 641 | 1 | 25 Mar 2023 | MEGAPOWER SOLUTION PVT LTD | 40kva DG servicing kit | AMC Charges | Month | 12 | 736 | 8832 | 1589.76 | 10421.76 | 0 | 3.9998 | 2943.88 | 529.92 | 3473.8 | 8.0002 | 6947.96 |  | 33.3317 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Mar 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 641 | 1 | 25 Mar 2023 | MEGAPOWER SOLUTION PVT LTD | 40kva DG servicing kit | AMC Charges | Month | 0 | 8832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 25 Mar 2023 |  | Admin. Indirect Expenses | Cancelled | MONALI CHAUDHAR | 03 Feb 2024
GANGA ALTUS | 642 | 1 | 25 Mar 2023 | MEGAPOWER SOLUTION PVT LTD | 82.5 kva DG servicing kit | AMC Charges | Month | 0 | 897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 25 Mar 2023 |  | SOC. M. Maintenace of Utilitie | Cancelled | MONALI CHAUDHAR | 03 Feb 2024
GANGA ALTUS | 642 | 1 | 25 Mar 2023 | MEGAPOWER SOLUTION PVT LTD | 82.5 kva DG servicing kit | AMC Charges | Month | 12 | 897 | 10764 | 1937.52 | 12701.52 | 0 | 3.9984 | 3586.56 | 645.6 | 4232.16 | 8.0016 | 8469.36 |  | 33.32 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Mar 2023 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 643 | 1 | 25 Mar 2023 | MEGAPOWER SOLUTION PVT LTD | 125kva DG servicing kit | AMC Charges | Month | 12 | 920 | 11040 | 1987.2 | 13027.2 | 0 | 3.9984 | 3678.53 | 662.16 | 4340.69 | 8.0016 | 8686.51 |  | 33.32 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 25 Mar 2023 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Cable Laying 22/300 | Mtrs | 0 | 168 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Outdoor Jointing Kit (M+L) | No. | 0 | 7560 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Excavation & Filling. | Mtrs | 0 | 192 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300sqmm x 3.5C Cable Laying (L) | Mtrs | 400 | 99 | 39600 | 7128 | 46728 | 2.5 | 400 | 39600 | 7128 | 46728 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 4 Way Feeder Pillar | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Touchproof Jointing Kit (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | RMU Installation | No. | 2 | 7000 | 14000 | 2520 | 16520 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | RMU Installation | No. | 0 | 7000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | HT Earthing Set (m+l) | No. | 10 | 4400 | 44000 | 7920 | 51920 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Straight through Jointing Kit (L) | No. | 3 | 3300 | 9900 | 1782 | 11682 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | LT Earthing Set (m+l) | No. | 0 | 4800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Excavation by breaker. | Mtrs | 100 | 385 | 38500 | 6930 | 45430 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Outdoor Jointing Kit (M+L) | No. | 4 | 6930 | 27720 | 4989.6 | 32709.6 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Indoor Jointing Kit (M+L) | No. | 4 | 6930 | 27720 | 4989.6 | 32709.6 | 2.5 | 1.083 | 7505.19 | 1350.94 | 8856.13 | 2.917 | 23853.47 |  | 27.075 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Touchproof Jointing Kit (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 50x5 GI Earthing Strip (M+L) | Mtrs | 150 | 258.5 | 38775 | 6979.5 | 45754.5 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Stepthrough Jointing Kit (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT GORE | 01 Apr 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Half round pipe | No. | 0 | 36 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Excavation & Filling. | Mtrs | 300 | 176 | 52800 | 9504 | 62304 | 2.5 | 146 | 25696 | 190.08 | 25886.08 | 154 | 36417.92 |  | 48.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Excavation & Filling. | Mtrs | 0 | 176 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 06 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Cable Laying (L) | Mtrs | 1150 | 154 | 177100 | 31878 | 208978 | 2.5 | 725 | 111650 | 8454.6 | 120104.6 | 425 | 88873.4 |  | 63.0435 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 35x5 GI Earthing Strip (M+L) | Mtrs | 400 | 198 | 79200 | 14256 | 93456 | 2.5 | 0 | 0 | 0 | 0 | 400 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Straight through Jointing Kit (L) | No. | 0 | 3600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Straight through Jointing Kit (L) | No. | 3 | 2750 | 8250 | 1485 | 9735 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 3Cx95 sqmm Cable Laying | Mtrs | 80 | 121 | 9680 | 1742.4 | 11422.4 | 2.5 | 40 | 4840 | 871.2 | 5711.2 | 40 | 5711.2 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | LT Earthing Set (m+l) | No. | 22 | 4400 | 96800 | 17424 | 114224 | 2.5 | 7 | 30800 | 5544 | 36344 | 15 | 77880 |  | 31.8182 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Full round pipe | No. | 50 | 55 | 2750 | 495 | 3245 | 2.5 | 25 | 1375 | 0 | 1375 | 25 | 1870 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | End Termination 300sqmm X 3.5 core cable (M+L) | No. | 24 | 1870 | 44880 | 8078.4 | 52958.4 | 2.5 | 24 | 44880 | 8078.4 | 52958.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 35x5 GI Earthing Strip (M+L) | Mtrs | 0 | 216 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 50x5 GI Earthing Strip (M+L) | Mtrs | 0 | 282 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Transformer Installation | No. | 3 | 6930 | 20790 | 3742.2 | 24532.2 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Transformer Installation | No. | 0 | 7560 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 4 Way Feeder Pillar | No. | 2 | 2750 | 5500 | 990 | 6490 | 2.5 | 1 | 2750 | 495 | 3245 | 1 | 3245 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Cable Laying 22/300 | Mtrs | 300 | 154 | 46200 | 8316 | 54516 | 2.5 | 0 | 0 | 0 | 0 | 300 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | End Termination 300sqmm X 3.5 core cable (M+L) | No. | 0 | 2040 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Indoor Jointing Kit (M+L) | No. | 0 | 7560 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Gland Plate Hole Making (L) | No. | 30 | 100 | 3000 | 540 | 3540 | 2.5 | 14 | 1400 | 252 | 1652 | 16 | 1888 |  | 46.6667 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 6 way Feeder Piller (L) | No. | 2 | 3300 | 6600 | 1188 | 7788 | 2.5 | 2 | 6600 | 1188 | 7788 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Half round pipe | No. | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT GORE | 01 Apr 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300sqmm x 3.5C Cable Laying (L) | Mtrs | 0 | 108 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Touchproof Jointing Kit (L) | No. | 8 | 2750 | 22000 | 3960 | 25960 | 2.5 | 3 | 8250 | 1485 | 9735 | 5 | 16225 |  | 37.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Touchproof Jointing Kit (L) | No. | 2 | 2750 | 5500 | 990 | 6490 | 2.5 | 2 | 5500 | 990 | 6490 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Stepthrough Jointing Kit (L) - No. | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT GORE | 01 Apr 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 6 way Feeder Piller (L) | No. | 0 | 3600 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 3Cx95 sqmm Cable Laying | Mtrs | 0 | 132 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Full round pipe | No. | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Excavation & Filling. | Mtrs | 0 | 192 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | DTC Meter Fixing | No. | 3 | 2000 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Excavation by breaker. | Mtrs | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | Half round pipe | No. | 400 | 33 | 13200 | 2376 | 15576 | 2.5 | 0 | 0 | 0 | 0 | 400 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 95 sqmm Straight through Jointing Kit (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | HT Earthing Set (m+l) | No. | 0 | 4800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 645 | 0 | 30 Mar 2023 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Electrical Labour work for Transformer Room | 300 sqmm Cable Laying (L) | Mtrs | 0 | 168 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ALTUS | 650 | 0 | 06 Apr 2023 | HARISH CHANDRA JADHAV ELECTRICALS | F Building Earthing Work(Temporary earthing work) 1 No. | Earthing work(m+l)- BC | No. | 2 | 4800 | 9600 | 1728 | 11328 | 2.5 | 2 | 9600 | 1728 | 11328 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 650 | 0 | 06 Apr 2023 | HARISH CHANDRA JADHAV ELECTRICALS | F Building Earthing Work(Temporary earthing work) 1 No. | Earthing work(m+l)- BC | No. | 4 | 4800 | 19200 | 3456 | 22656 | 2.5 | 4 | 19200 | 3456 | 22656 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 652 | 0 | 07 Apr 2023 | GANESH MAHADU LONDHE | STP-265 KLD Murum Backfilling Work - 1 No. | Spreading & Levelling Work | Cu.Mtrs | 465.4 | 15 | 6981 | 0 | 6981 | 0 | 465 | 6975 | 0 | 6975 | 0.4 | 6 | Murum Spreading with available dumped earth material including Lifting, shifting & unloading at requird Place including all leads and lifts, stacking and spreading with all tool, Equipments etc. | 99.9141 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 652 | 0 | 07 Apr 2023 | GANESH MAHADU LONDHE | STP-265 KLD Murum Backfilling Work - 1 No. | Murum Backfilling | Cu.Mtrs | 465.4 | 60 | 27924 | 0 | 27924 | 0 | 0 | 0 | 0 | 0 | 465.4 | 0 | Murum Filling including loading, unloading including all leads and lifts, stacking with all tool, Equipments & machinery. Ensuring all required safety precautions etc. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 652 | 0 | 07 Apr 2023 | GANESH MAHADU LONDHE | STP-265 KLD Murum Backfilling Work - 1 No. | Bobcat Hiring Charges | Hrs | 40 | 850 | 34000 | 0 | 34000 | 0 | 28 | 23800 | 0 | 23800 | 12 | 10200 |  | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 653 | 0 | 08 Apr 2023 | VIJAY MOHITE | STP-265 KLD RCC Work (L) | RCC Work - DCH | No. | 0 | 150000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Apr 2023 |  | DEV. Club House | Cancelled | ADITYA.CHOUGULE | 09 Aug 2023
GANGA ALTUS | 653 | 0 | 08 Apr 2023 | VIJAY MOHITE | STP-265 KLD RCC Work (L) | Labour Lumsum | No. | 0 | 150000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 08 Apr 2023
GANGA ALTUS | 653 | 0 | 08 Apr 2023 | VIJAY MOHITE | STP-265 KLD RCC Work (L) | RCC Work - DCH | No. | 1 | 400000 | 400000 | 0 | 400000 | 2.5 | 1 | 400000 | 0 | 400000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Apr 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 676 | 2 | 08 May 2023 | K RAMU RATHOD | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 8" Blockwork Rate Diff. | Sq.Ft | 794.93 | 1 | 794.93 | 0 | 794.93 | 2.5 | 794.444 | 794.44 | 143 | 937.44 | 0.486 | -142.51 |  | 99.9389 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 676 | 2 | 08 May 2023 | K RAMU RATHOD | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 8" Blockwork Rate Diff. | Sq.Ft | 613.66 | 1 | 613.66 | 0 | 613.66 | 2.5 | 490.928 | 490.93 | 88.36 | 579.29 | 122.732 | 34.37 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 676 | 0 | 08 May 2023 | K RAMU RATHOD | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | Blockwork 8" - BC | Sq.Ft | 794.93 | 20 | 15898.6 | 0 | 15898.6 | 2.5 | 794.444 | 15888.88 | 570.6 | 16459.48 | 0.486 | -560.88 |  | 99.9389 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 676 | 2 | 08 May 2023 | K RAMU RATHOD | F-Bldg STP- 8" Blockwork & Plaster Work (L) | Sand Face Plaster Rate Diff. - DCH | Sq.Ft | 1219.56 | 5 | 6097.8 | 0 | 6097.8 | 2.5 | 0 | 0 | 0 | 0 | 1219.56 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 676 | 2 | 08 May 2023 | K RAMU RATHOD | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | Sand Face Plaster Rate Diff. - DCH | Sq.Ft | 1592.26 | 5 | 7961.3 | 0 | 7961.3 | 2.5 | 1273.808 | 6369.04 | 1146.42 | 7515.46 | 318.452 | 445.84 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 676 | 0 | 08 May 2023 | K RAMU RATHOD | F-Bldg STP- 8" Blockwork & Plaster Work (L) | Blockwork 8" - BC | Sq.Ft | 613.66 | 20 | 12273.2 | 0 | 12273.2 | 2.5 | 613.65 | 12273 | 769.14 | 13042.14 | 0.01 | -768.94 |  | 99.9984 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 676 | 0 | 08 May 2023 | K RAMU RATHOD | F-Bldg STP- 8" Blockwork & Plaster Work (L) | Sand Face Plaster - UTR | Sq.Ft | 1219.56 | 20 | 24391.2 | 0 | 24391.2 | 2.5 | 1219.548 | 24390.96 | 4390.38 | 28781.34 | 0.012 | -4390.14 |  | 99.999 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | UTI. Rainwater harvesting | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 676 | 0 | 08 May 2023 | K RAMU RATHOD | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | Sand Face Plaster - UTR | Sq.Ft | 1592.26 | 20 | 31845.2 | 0 | 31845.2 | 2.5 | 1592.258 | 31845.16 | 5732.12 | 37577.28 | 0.002 | -5732.08 |  | 99.9999 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | UTI. Rainwater harvesting | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 676 | 1 | 08 May 2023 | K RAMU RATHOD | Transformer Room- Brickwork & Plaster Above Plinth Beam (L) | Sand Face Plaster - ULT | Sq.Ft | 572.37 | 20 | 11447.4 | 0 | 11447.4 | 2.5 | 0 | 0 | 0 | 0 | 572.37 | 0 | Sand face plaster (Single Coat) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 May 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 676 | 1 | 08 May 2023 | K RAMU RATHOD | Transformer Room- Brickwork & Plaster Above Plinth Beam (L) | Brickwork 9" - ULT | Sq.Ft | 483.7 | 21 | 10157.7 | 0 | 10157.7 | 2.5 | 290.22 | 6094.62 | 1097.04 | 7191.66 | 193.48 | 2966.04 | 9" Brick Work with 1:6 Cement mortar with Fly ash Brick,Cement,Sand & water etc.with Plumb (Valamba) & Right angle (Gunya) at corner,with proper joint filling.Loading,shifting & unloading of material from store to required place to be done by contractor. | 60 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 May 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 684 | 0 | 27 May 2023 | AJAY KUMAR GUPTA | Transformer Room- Trench Int. Face Ghotai Work | Int. Ghotai Plaster- UWR | Sq.Ft | 1505.57 | 15 | 22583.55 | 0 | 22583.55 | 10 | 499.76 | 7496.4 | 1349.36 | 8845.76 | 1005.81 | 13737.79 | Cement plaster Ghotai with 1:4 cement mortar mixing with chemical (Dr. Fixit/ Fosroc/ SBRE etc.) chemical in contractors scope proportion of 100 ml for 1 bag of cement, with broom finish including cleaning, scrubbing, vacuum cleaning etc. | 33.1941 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 02 Jun 2023 |  | UTI. Water Supply | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 684 | 0 | 27 May 2023 | AJAY KUMAR GUPTA | Transformer Room- Floor IPS Waterproofing | IPS W/P | Sq.Ft | 350.2 | 15 | 5253 | 0 | 5253 | 10 | 350.2 | 5253 | 945.54 | 6198.54 | 0 | -945.54 | IPS Waterproofing with concrete, including laying with proper line level & slope, ghotai with dry cement & broom/brush finish etc. Loading, shifting & unloading of estimated raw material from store to required place to be done by contractor. | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 02 Jun 2023 |  | 06 WATERPROOFING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 684 | 0 | 27 May 2023 | AJAY KUMAR GUPTA | Transformer Room- Terrace Brickbat W/P Work | Brickbat W/P-ULT | Sq.Ft | 685.13 | 24 | 16443.12 | 0 | 16443.12 | 10 | 522.3431 | 12536.23 | 0 | 12536.23 | 162.7869 | 3906.89 | Brick Bat Waterproofing work with red clay 4" thick bricks including base coat with C:M 1:4 proportion up to 15 mm thick, Laying red bricks above base coat with proper line level & slope of 100:1 to 120:1. | 76.24 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 02 Jun 2023 |  | UTI. Electricity Infrastructur | Approved | chetan jewalikar | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fire Repeater Panel (L) | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card (LPCB / UL, FM Approved).Make- Ravel,Model-RE-517 RP | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 32mm dia.(L) | Mtrs | 380 | 250 | 95000 | 17100 | 112100 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | G.I.Pipe 32mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Amplifier (L) | No. | 1 | 12500 | 12500 | 2250 | 14750 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 480W Power Amplifier with Rated output wattage - 480W Make- Ravel,Model-RE-250 | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 80mm dia.(L) | Mtrs | 60 | 450 | 27000 | 4860 | 31860 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | G.I.Pipe 80mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Signage Fire Hose Reel (L) | No. | 0 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 10 Aug 2023 |  | No category | Cancelled | MONALI CHAUDHAR | 24 Jan 2024
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1.2mtr length) (L) | No. | 30 | 188 | 5640 | 1015.2 | 6655.2 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1200 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(L) | No. | 2 | 200 | 400 | 72 | 472 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | CO2 Type Extinguisher 4.5 kg- Mercury | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 294 | 40 | 11760 | 2116.8 | 13876.8 | 2.5 | 0 | 0 | 0 | 0 | 294 | 0 | Laying of 2 Core x 1.5 Sq.mm,Multistrand Copper,Shielded,Twisted pair,FRLS PVC insulated UnArmoured cable, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.5 meters interval.Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 40mm (L) | No. | 6 | 300 | 1800 | 324 | 2124 | 0 | 4.75 | 1425 | 256.5 | 1681.5 | 1.25 | 442.5 | C.I.Butterfly Valve 40 mm- Kartar | 79.1667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 50 | 40 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 | Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated armoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Control Module (L) | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power.active Modes - Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MC | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 40mm dia.(L) | Mtrs | 120 | 300 | 36000 | 6480 | 42480 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | G.I.Pipe 40mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 25 NB | Mtrs | 300 | 282 | 84600 | 15228 | 99828 | 0 | 280.1525 | 79003 | 14220.54 | 93223.54 | 19.8475 | 6604.46 | Installation And Removing G.I.Pipe 25 mm for Rework | 93.3842 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Side wall (L) | No. | 10 | 200 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Sidewall Sprinkler 68 Deg - Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 80mm-(L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I.Butterfly Valve 80 mm- Kartar | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI C Class Pipe 100mm dia.(L) | Mtrs | 264 | 550 | 145200 | 26136 | 171336 | 0 | 0 | 0 | 0 | 0 | 264 | 0 | G.I.Pipe 100 mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Electrical Starter (L) | No. | 1 | 1410 | 1410 | 253.8 | 1663.8 | 0 | 0.95 | 1339.5 | 241.12 | 1580.62 | 0.05 | 83.18 | Electrical Starter-STD | 95 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | GI Single Fire Hose Box (L) | No. | 5 | 1034 | 5170 | 930.6 | 6100.6 | 0 | 4.75 | 4911.5 | 884.08 | 5795.58 | 0.25 | 305.02 | S.S.Fire Hydrant Valve single headed,Fire Hose Box with powder coating ,Fire Hose Pipe 63 mm dia 15mtr long,Branch Pipe Nozzel- Essel/Padma | 95 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Air Release Valve 25mm (L) | No. | 2 | 200 | 400 | 72 | 472 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Air Release Valve- STD | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 25mm dia-(L) | Mtrs | 660 | 200 | 132000 | 23760 | 155760 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | G.I.Pipe 25mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (L) | Mtrs | 1508 | 40 | 60320 | 10857.6 | 71177.6 | 2.5 | 660.45 | 26418 | 4755.24 | 31173.24 | 847.55 | 40004.36 | Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Ploycab | 43.7964 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Back Box (L) | No. | 17 | 100 | 1700 | 306 | 2006 | 2.5 | 0 | 0 | 0 | 0 | 17 | 0 | ITC of back box for 6 Watt Ceiling Speakers.Make- STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (L) | Mtrs | 350 | 40 | 14000 | 2520 | 16520 | 2.5 | 0 | 0 | 0 | 0 | 350 | 0 | Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated UnArmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval (Red in Colour)(Only LPCB approved) Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talk Back System (L) | No. | 10 | 250 | 2500 | 450 | 2950 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 | ITC of Fire Fighter (talk back) jack module.Make- Ravel,Model-EK 750J | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fault Isolator Base / Module (L) | No. | 10 | 300 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 | ITC of Zonal Short Circuit Loop Isolator, (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MI | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 150mm -(L) | No. | 6 | 300 | 1800 | 324 | 2124 | 0 | 0.95 | 285 | 51.3 | 336.3 | 5.05 | 1787.7 | C.I.Butterfly Valve 150 mm - Kartar | 15.8333 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Upright (L) | No. | 30 | 350 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Upright Sprinkler 68 Deg- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 100mm-(L) | No. | 6 | 350 | 2100 | 378 | 2478 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | C.I.Butterfly Valve 100 mm- Kartar | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Rack 6 U (L) | No. | 1 | 2500 | 2500 | 450 | 2950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 6U Wall mount Rack with Front Glass Door, Fan Tray on Top, Perforated Rear Doors, Openable Entry at the Bottom for the Cable entry, Cable Basket for Cable Dressing & Vertical Power Strip with all necessary accessories & hardware.Make-STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler Alarm Valve 150mm dia (L) | set | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Sprinkler Alarm Valve 150 mm dia- HD | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 65mm dia.(L) | Mtrs | 60 | 375 | 22500 | 4050 | 26550 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | G.I.Pipe 65mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 32 NB | Mtrs | 60 | 352.5 | 21150 | 3807 | 24957 | 0 | 52.6298 | 18552 | 3339.36 | 21891.36 | 7.3702 | 3065.64 | Installation And Removing G.I.Pipe 32 mm for Rework | 87.7163 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talkback Panel (L) | No. | 1 | 12000 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 8 Zone Talkback Panel.Make- Ravel,Model-EK 740 | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 150mm dia.(L) | Mtrs | 90 | 600 | 54000 | 9720 | 63720 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 150 mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 6W Ceiling Speakers (L) | No. | 17 | 350 | 5950 | 1071 | 7021 | 2.5 | 0 | 0 | 0 | 0 | 17 | 0 | ITC of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps Make- Ravel,Model-RE-LS 6C | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Telephone Jack/Receiver (L) | No. | 1 | 150 | 150 | 27 | 177 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Fire Fighter (talk back) Telephone handset.Make- Ravel,Model-EK705H | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Signal Based Voice Alarm Controller (L) | No. | 1 | 15000 | 15000 | 2700 | 17700 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 8 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 8 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller.Make- Ravel,Model-Escape-250W | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Rossete Plate (L) | No. | 370 | 45 | 16650 | 2997 | 19647 | 0 | 204.2667 | 9192 | 1654.56 | 10846.56 | 165.7333 | 8800.44 | Rossete plate- STD | 55.2072 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 50mm dia.(L) | Mtrs | 90 | 400 | 36000 | 6480 | 42480 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 50mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Fire Alarm Panel (L) | No. | 1 | 20000 | 20000 | 3600 | 23600 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC Flush or Surface Mounting Modularized Panel with 4 loops.Having inbuilt 1 loops,Maximum 4 Loops (4 with Network ),Max Capacity with 4 Loops =1524 Addressable Devices. Make-Ravel ,Model-Avani-LCS | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Signage Fire Hose Reel (L) | No. | 5 | 329 | 1645 | 296.1 | 1941.1 | 0 | 3.7994 | 1249.99 | 225 | 1474.99 | 1.2006 | 466.11 | Fire Hose Reel with 30 mtrs rubber hose- Essel/Padma | 75.988 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | No. | 370 | 188 | 69560 | 12520.8 | 82080.8 | 0 | 204.25 | 38399 | 6911.82 | 45310.82 | 165.75 | 36769.98 | Flexible Hose Pipe 1000 mm- Newage /Hd | 55.2027 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Cable 2.5 sqmm (L) | Mtrs | 70 | 42.3 | 2961 | 532.98 | 3493.98 | 0 | 37.9906 | 1607 | 289.26 | 1896.26 | 32.0095 | 1597.72 | Cable 2.5sqr mm X 4 core- Polycab | 54.2723 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Conventional Sounder cum Strobe (L) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 | ITC of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool. Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 M | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher ABC 4Kg (L) | No. | 6 | 188 | 1128 | 203.04 | 1331.04 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | ABC Type Fire Extinguisher 4 Kg- Mercury | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 50 NB | Mtrs | 30 | 564 | 16920 | 3045.6 | 19965.6 | 0 | 21.8493 | 12323.01 | 2218.14 | 14541.15 | 8.1507 | 5424.45 | Installation And Removing G.I.Pipe 50 mm for Rework | 72.831 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | 7.5 HP Booster Pump- (L) | No. | 1 | 3290 | 3290 | 592.2 | 3882.2 | 0 | 0.95 | 3125.5 | 562.6 | 3688.1 | 0.05 | 194.1 | Booster Pump 7.5 Hp- CRI/Kirlosakar | 95 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 1500 mm with Bushing (L) | No. | 30 | 188 | 5640 | 1015.2 | 6655.2 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1500 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Heat Detector (L) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 | ITC of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D HL | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 100 NB | Mtrs | 90 | 775.5 | 69795 | 12563.1 | 82358.1 | 0 | 80.1805 | 62179.97 | 11192.4 | 73372.37 | 9.8195 | 8985.73 | Sprinkler Alarm Valve 150 mm dia- HD | 89.0894 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Pendent (L) | No. | 440 | 200 | 88000 | 15840 | 103840 | 0 | 123.5 | 24700 | 4446 | 29146 | 316.5 | 74694 | Pendent Sprinkler 68 Deg- Newage /Hd | 28.0682 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 40 NB | Mtrs | 12 | 423 | 5076 | 913.68 | 5989.68 | 0 | 8.7399 | 3697 | 665.46 | 4362.46 | 3.2601 | 1627.22 | Installation And Removing G.I.Pipe 40 mm for Rework | 72.8325 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Non Return Valve 100mm (L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Installation And Removing G.I.Pipe 100 mm for Rework | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Handheld Microphone (L) | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Handheld Microphone with stand and cable of Microphone (corded).(Freq. response: 20Hz to 18kHz S/N: 1.6mV-4.5mV. Model-Goose Neck Microphone | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable smoke detector (L) | No. | 105 | 300 | 31500 | 5670 | 37170 | 2.5 | 0 | 0 | 0 | 0 | 105 | 0 | ITC of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D SL | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Manual call point (L) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 | ITC of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool. Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 M | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI C Class Pipe 100mm dia.(M) | Mtrs | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT.GORE | 25 Jan 2024
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 80mm dia.(M) | Mtrs | 60 | 1000 | 60000 | 10800 | 70800 | 0 | 24.5 | 24500 | 4410 | 28910 | 35.5 | 41890 | G.I.Pipe 80mm dia- Apollo | 40.8333 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Manual call point (M) | No. | 5 | 2850 | 14250 | 2565 | 16815 | 0 | 0.7 | 1995 | 359.1 | 2354.1 | 4.3 | 14460.9 | Supply of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool. Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 M | 14 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Signal Based Voice Alarm Controller (M) | No. | 1 | 51653 | 51653 | 9297.54 | 60950.54 | 0 | 0.7 | 36157.1 | 6508.28 | 42665.38 | 0.3 | 18285.16 | Supply of 8 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 8 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller.Make- Ravel,Model-Escape-250W | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talkback Panel (M) | No. | 1 | 66504 | 66504 | 11970.72 | 78474.72 | 0 | 0.7 | 46552.8 | 8379.5 | 54932.3 | 0.3 | 23542.42 | Supply of 8 Zone Talkback Panel.Make- Ravel,Model-EK 740 | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Control Module (M) | No. | 1 | 3300 | 3300 | 594 | 3894 | 0 | 0.7 | 2310 | 415.8 | 2725.8 | 0.3 | 1168.2 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power.active Modes - Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MC | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 40mm dia.(M) | Mtrs | 120 | 500 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | G.I.Pipe 40mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 150mm dia.(M) | Mtrs | 90 | 2100 | 189000 | 34020 | 223020 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 150 mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Telephone Jack/Receiver (M) | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 0.7 | 3850 | 693 | 4543 | 0.3 | 1947 | Supply of Fire Fighter (talk back) Telephone handset.Make- Ravel,Model-EK705H | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 40mm (M) | No. | 6 | 2650 | 15900 | 2862 | 18762 | 0 | 5.0004 | 13251.03 | 2385.18 | 15636.21 | 0.9996 | 3125.79 | C.I.Butterfly Valve 40 mm- Kartar | 83.34 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Electrical Starter (M) | No. | 1 | 6241 | 6241 | 1123.38 | 7364.38 | 0 | 1 | 6241 | 1123.36 | 7364.36 | 0 | 0.02 | Electrical Starter-STD | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Non Return Valve 100mm (M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 0.7 | 2240 | 403.2 | 2643.2 | 1.3 | 4908.8 | C.I.NRV 100 mm- Kartar | 35 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1.2mtr length) (M) | No. | 30 | 1222 | 36660 | 6598.8 | 43258.8 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1200 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Side wall (M) | No. | 10 | 350 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Sidewall Sprinkler 68 Deg - Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 32mm dia.(M) | Mtrs | 380 | 450 | 171000 | 30780 | 201780 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | G.I.Pipe 32mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 50 | 80 | 4000 | 720 | 4720 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated armoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Fire Alarm Panel (M) | No. | 1 | 215000 | 215000 | 38700 | 253700 | 0 | 0.7 | 150500 | 27090 | 177590 | 0.3 | 76110 | Supply Flush or Surface Mounting Modularized Panel with 4 loops.Having inbuilt 1 loops,Maximum 4 Loops (4 with Network ),Max Capacity with 4 Loops =1524 Addressable Devices. Make-Ravel ,Model-Avani-LCS | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 294 | 80 | 23520 | 4233.6 | 27753.6 | 0 | 0 | 0 | 0 | 0 | 294 | 0 | Supply of 2 Core x 1.5 Sq.mm,Multistrand Copper,Shielded,Twisted pair,FRLS PVC insulated UnArmoured cable, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.5 meters interval.Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable smoke detector (M) | No. | 105 | 2400 | 252000 | 45360 | 297360 | 0 | 73.5 | 176400 | 31752 | 208152 | 31.5 | 89208 | Supply of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D SL | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Rack 6 U (M) | No. | 1 | 17059 | 17059 | 3070.62 | 20129.62 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of 6U Wall mount Rack with Front Glass Door, Fan Tray on Top, Perforated Rear Doors, Openable Entry at the Bottom for the Cable entry, Cable Basket for Cable Dressing & Vertical Power Strip with all necessary accessories & hardware.Make-STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | GI Single Fire Hose Box (M) | No. | 5 | 17930 | 89650 | 16137 | 105787 | 0 | 5 | 89650 | 16137.02 | 105787.02 | 0 | -0.02 | S.S.Fire Hydrant Valve single headed,Fire Hose Box with powder coating ,Fire Hose Pipe 63 mm dia 15mtr long,Branch Pipe Nozzel- Essel/Padma | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (M) | Mtrs | 1508 | 80 | 120640 | 21715.2 | 142355.2 | 0 | 917.7 | 73416 | 13214.88 | 86630.88 | 590.3 | 55724.32 | Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Ploycab | 60.8554 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Conventional Sounder cum Strobe (M) | No. | 5 | 1900 | 9500 | 1710 | 11210 | 0 | 3.5 | 6650 | 1197 | 7847 | 1.5 | 3363 | Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-25 SS | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1mtr length) (M) | No. | 370 | 1034 | 382580 | 68864.4 | 451444.4 | 0 | 271.001 | 280214.99 | 50438.7 | 330653.69 | 98.999 | 120790.71 | Flexible Hose Pipe 1000 mm- Newage /Hd | 73.2435 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Handheld Microphone (M) | No. | 1 | 2150 | 2150 | 387 | 2537 | 0 | 0.7 | 1505 | 270.9 | 1775.9 | 0.3 | 761.1 | Supply of Handheld Microphone with stand and cable of Microphone (corded).(Freq. response: 20Hz to 18kHz S/N: 1.6mV-4.5mV. Model-Goose Neck Microphone | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Rossete Plate (M) | No. | 370 | 90 | 33300 | 5994 | 39294 | 0 | 271.0111 | 24391 | 4390.38 | 28781.38 | 98.9889 | 10512.62 | Rossete plate- STD | 73.2462 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fire Repeater Panel (M) | No. | 1 | 45000 | 45000 | 8100 | 53100 | 0 | 0.7 | 31500 | 5670 | 37170 | 0.3 | 15930 | Supply of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card (LPCB / UL, FM Approved).Make- Ravel,Model-RE-517 RP | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | No. | 2 | 5800 | 11600 | 2088 | 13688 | 0 | 1.4 | 8120 | 1461.6 | 9581.6 | 0.6 | 4106.4 | CO2 Type Extinguisher 4.5 kg- Mercury | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Signage Fire Hose Reel (M) | No. | 5 | 6392 | 31960 | 5752.8 | 37712.8 | 0 | 4 | 25568.03 | 4602.24 | 30170.27 | 1 | 7542.53 | Fire Hose Reel with 30 mtrs rubber hose- Essel/Padma | 80 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 6W Ceiling Speakers (M) | No. | 17 | 1250 | 21250 | 3825 | 25075 | 0 | 10.5 | 13125 | 2362.5 | 15487.5 | 6.5 | 9587.5 | Supply of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps Make- Ravel,Model-RE-LS 6C | 61.7647 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 150mm -(M) | No. | 6 | 3800 | 22800 | 4104 | 26904 | 0 | 1 | 3800 | 684 | 4484 | 5 | 22420 | C.I.Butterfly Valve 150 mm - Kartar | 16.6667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (M) | Mtrs | 350 | 80 | 28000 | 5040 | 33040 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated UnArmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval (Red in Colour)(Only LPCB approved) Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fault Isolator Base / Module (M) | No. | 10 | 2500 | 25000 | 4500 | 29500 | 0 | 2.8 | 7000 | 1260 | 8260 | 7.2 | 21240 | Supply of Zonal Short Circuit Loop Isolator, (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MI | 28 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler Alarm Valve 150mm dia (M) | set | 1 | 43500 | 43500 | 7830 | 51330 | 0 | 0.7 | 30450 | 5481 | 35931 | 0.3 | 15399 | Sprinkler Alarm Valve 150 mm dia- HD | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 80mm-(M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I.Butterfly Valve 80 mm- Kartar | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talk Back System (M) | No. | 10 | 800 | 8000 | 1440 | 9440 | 0 | 2.8 | 2240 | 403.2 | 2643.2 | 7.2 | 6796.8 | Supply of Fire Fighter (talk back) jack module.Make- Ravel,Model-EK 750J | 28 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Back Box (M) | No. | 17 | 350 | 5950 | 1071 | 7021 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Supply of back box for 6 Watt Ceiling Speakers.Make- STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Upright (M) | No. | 30 | 450 | 13500 | 2430 | 15930 | 0 | 21 | 9450 | 1701 | 11151 | 9 | 4779 | Upright Sprinkler 68 Deg- Newage /Hd | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Cable 2.5 sqmm (M) | Mtrs | 70 | 122 | 8540 | 1537.2 | 10077.2 | 0 | 40 | 4880 | 878.4 | 5758.4 | 30 | 4318.8 | Cable 2.5sqr mm X 4 core- Polycab | 57.1429 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Heat Detector (M) | No. | 5 | 2350 | 11750 | 2115 | 13865 | 0 | 0.7 | 1645 | 296.1 | 1941.1 | 4.3 | 11923.9 | Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D HL | 14 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Pendent (M) | No. | 440 | 380 | 167200 | 30096 | 197296 | 0 | 186 | 70680 | 12722.4 | 83402.4 | 254 | 113893.6 | Pendent Sprinkler 68 Deg- Newage /Hd | 42.2727 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 1500 mm with Bushing (M) | No. | 30 | 1504 | 45120 | 8121.6 | 53241.6 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1500 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 50mm dia.(M) | Mtrs | 90 | 650 | 58500 | 10530 | 69030 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 50mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI C Class Pipe 100mm dia.(M) | Mtrs | 264 | 1439.83 | 380115.12 | 68420.72 | 448535.84 | 0 | 0 | 0 | 0 | 0 | 264 | 0 | G.I.Pipe 100mm Dia-Brand-Apollo | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 100mm-(M) | No. | 6 | 3600 | 21600 | 3888 | 25488 | 0 | 4.2 | 15120 | 2721.6 | 17841.6 | 1.8 | 7646.4 | C.I.Butterfly Valve 100 mm- Kartar | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Amplifier (M) | No. | 1 | 38000 | 38000 | 6840 | 44840 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of 480W Power Amplifier with Rated output wattage - 480W Make- Ravel,Model-RE-250 | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher ABC 4Kg (M) | No. | 6 | 1645 | 9870 | 1776.6 | 11646.6 | 0 | 4.2 | 6909 | 1243.62 | 8152.62 | 1.8 | 3493.98 | ABC Type Fire Extinguisher 4 Kg- Mercury | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | 7.5 HP Booster Pump- (M) | No. | 1 | 45590 | 45590 | 8206.2 | 53796.2 | 0 | 1 | 45590 | 8206.22 | 53796.22 | 0 | -0.02 | Booster Pump 7.5 Hp- CRI/Kirlosakar | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 25mm dia.(M) | Mtrs | 660 | 350 | 231000 | 41580 | 272580 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | G.I.Pipe 25mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 65mm dia.(M) | Mtrs | 60 | 800 | 48000 | 8640 | 56640 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | G.I.Pipe 65mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Air Release Valve 25mm (M) | No. | 2 | 1750 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Air Release Valve- STD | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 693 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room-External Single Coat-Sand Face Plaster Work | Sand Face Plaster - ULT | Sq.Ft | 2129.33 | 20 | 42586.6 | 0 | 42586.6 | 2.5 | 836.96 | 16739.2 | 3013.06 | 19752.26 | 1292.37 | 22834.34 |  | 39.3063 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 693 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room-Internal Single Coat-Sand Face Plaster Work | Sand Face Plaster - ULT | Sq.Ft | 1390.24 | 20 | 27804.8 | 0 | 27804.8 | 2.5 | 1331.73 | 26634.6 | 4794.22 | 31428.82 | 58.51 | -3624.02 |  | 95.7914 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 693 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room-Internal Single Coat-Sand Face Plaster Work | Sand Face Plaster - ULT | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 10 Jun 2023
GANGA ALTUS | 694 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room- Cable Trench Ext. Face Rough Plaster Work | Rough Plaster- ULT | Sq.Ft | 776.3 | 15 | 11644.5 | 0 | 11644.5 | 2.5 | 759.19 | 11387.85 | 2049.82 | 13437.67 | 17.11 | -1793.17 |  | 97.796 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jun 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 694 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room G Fl. to 1st Slab & Parapet -8" Blockwork | Blockwork 8" - BC | Sq.Ft | 1531 | 20 | 30620 | 0 | 30620 | 2.5 | 771.81 | 15436.2 | 2778.52 | 18214.72 | 759.19 | 12405.28 |  | 50.4121 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 694 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room- Cable Trench 15" Thk Brickwork | Brickwork 15" -DLd | Sq.Ft | 776.28 | 24 | 18630.72 | 0 | 18630.72 | 2.5 | 680.83 | 16339.92 | 2941.18 | 19281.1 | 95.45 | -650.38 |  | 87.7042 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jun 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 694 | 0 | 07 Jun 2023 | K RAMU RATHOD | Transformer Room- Cable Trench Int. Face Rough Plaster Work | Rough Plaster- ULT | Sq.Ft | 1505.6 | 15 | 22584 | 0 | 22584 | 2.5 | 790.73 | 11860.95 | 2134.98 | 13995.93 | 714.87 | 8588.07 |  | 52.5193 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Jun 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 1 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Screeding work- BC | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 28 Jul 2023 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 19 Dec 2023
GANGA ALTUS | 733 | 1 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Cement Ghotai-ULT | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 28 Jul 2023 |  | UTI. Electricity Infrastructur | Cancelled | ADITYA.CHOUGULE | 19 Dec 2023
GANGA ALTUS | 733 | 0 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Cement Ghotai-ULT | Sq.Ft | 2214.87 | 15 | 33223.05 | 5980.14 | 39203.19 | 10 | 1181 | 17715 | 0 | 17715 | 1033.87 | 21488.19 |  | 53.3214 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 0 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Screeding work- BC | Sq.Ft | 504.29 | 15 | 7564.35 | 1361.58 | 8925.93 | 10 | 290.5333 | 4358 | 0 | 4358 | 213.7567 | 4567.93 |  | 57.6123 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 0 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Top Slab Chemical W/P & Screeding Work | Screeding W/P-BCo | Sq.Ft | 625.01 | 15 | 9375.15 | 1687.52 | 11062.67 | 10 | 0 | 0 | 0 | 0 | 625.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 0 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Chemical W/P-DLd | Sq.Ft | 504.29 | 22 | 11094.38 | 1996.98 | 13091.36 | 10 | 290.5 | 6391 | 0 | 6391 | 213.79 | 6700.36 |  | 57.6057 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 1 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Chemical W/P-DLd | Sq.Ft | 290.53 | 22 | 6391.66 | 1150.5 | 7542.16 | 10 | 290.53 | 6391.66 | 0 | 6391.66 | 0 | 1150.5 | Chemical waterproofing with proper cleaning,scrubbing,ghadai,vacuum cleaning then chemical 2 coat for floor area plus 6" height on wallif sunk is 2" & 12" height if sunk is 6" above chemical coat 1" to 1.5" thick screeding with C:M 1:4 with 10mm metal. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 2 | 21 Jul 2023 | GANGAPRASAD K VARMA | OWC Unit-IPS Work | IPS W/P | Sq.Ft | 2109.26 | 15 | 31638.9 | 5695 | 37333.9 | 5 | 0 | 0 | 0 | 0 | 2109.26 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 28 Jul 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 1 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Bottom & Vertical Pardi- W/P Work | Chemical W/P-DLd | Sq.Ft | 681.97 | 22 | 15003.34 | 2700.6 | 17703.94 | 10 | 681.97 | 15003.34 | 0 | 15003.34 | 0 | 2700.6 | Chemical waterproofing with proper cleaning,scrubbing,ghadai,vacuum cleaning then chemical 2 coat for floor area plus 6" height on wallif sunk is 2" & 12" height if sunk is 6" above chemical coat 1" to 1.5" thick screeding with C:M 1:4 with 10mm metal. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 733 | 0 | 21 Jul 2023 | GANGAPRASAD K VARMA | 265 KLD STP Top Slab Chemical W/P & Screeding Work | Chemical W/P-DLd | Sq.Ft | 625.01 | 22 | 13750.22 | 2475.04 | 16225.26 | 10 | 0 | 0 | 0 | 0 | 625.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 736 | 0 | 25 Jul 2023 | S. V. ENTERPRISES | Rain Water Harvesting System | Rainwater Harvesting System-UTR | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 25 Jul 2023 |  | UTI. Rainwater harvesting | Cancelled | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ALTUS | 736 | 0 | 25 Jul 2023 | S. V. ENTERPRISES | Rain Water Harvesting System | Rainwater Harvesting System-UTR | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 25 Jul 2023 |  | UTI. Rainwater harvesting | Cancelled | ADITYA.CHOUGULE | 31 Jul 2023
GANGA ALTUS | 737 | 0 | 31 Jul 2023 | S.V. ASSOCIATES | Rain Water Harvesting System | Rainwater Harvesting System-UTR | Sq.Ft | 78500 | 1.75 | 137375 | 24727.5 | 162102.5 | 0 | 23549.9966 | 41212.49 | 7418.24 | 48630.73 | 54950.0034 | 113471.77 |  | 30 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Aug 2023 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 745 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room Internal Face- Cement Paint Work Wall+Ceili | Cement Paint (L)- BC | Sq.Ft | 2075.35 | 2 | 4150.7 | 747.12 | 4897.82 | 2.5 | 0 | 0 | 0 | 0 | 2075.35 | 0 | 2 Coat Cement Paint | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ALTUS | 746 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room Internal Face- Cement Paint Work Wall+Ceili | Cement Paint (M)- BC | Sq.Ft | 2075.35 | 2 | 4150.7 | 747.12 | 4897.82 | 0 | 0 | 0 | 0 | 0 | 2075.35 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 02 Aug 2023
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | Texture Paint (L) | Sq.Ft | 0 | 7.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 17 Feb 2024
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Aug 2023
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 2129.33 | 1.5 | 3194 | 574.92 | 3768.92 | 2.5 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 2129.33 | 1 | 2129.33 | 383.28 | 2512.61 | 2.5 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 2129.33 | 0.5 | 1064.67 | 191.64 | 1256.31 | 2.5 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Aug 2023
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 2129.33 | 1.5 | 3194 | 574.92 | 3768.92 | 2.5 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 747 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | Scaffolding Fixing Work - DER | Sq.Ft | 2129.33 | 3.5 | 7452.66 | 1341.48 | 8794.14 | 2.5 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ALTUS | 748 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | Texture Paint (M) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 17 Feb 2024
GANGA ALTUS | 748 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 2129.33 | 2.25 | 4790.99 | 862.38 | 5653.37 | 0 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 748 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 2129.33 | 2.5 | 5323.33 | 958.2 | 6281.53 | 0 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 748 | 0 | 02 Aug 2023 | ANIL MAHTO ENTERPRISES | Transformer Room External Face- Acrylic Texture Paint Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 2129.33 | 1 | 2129.33 | 383.28 | 2512.61 | 0 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 760 | 1 | 25 Aug 2023 | PRABHURAM VERMA | UGWT-Pump Room-Chemical Grouting Work | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Sep 2023 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 12 Dec 2023
GANGA ALTUS | 760 | 1 | 25 Aug 2023 | PRABHURAM VERMA | UGWT-Pump Room-Chemical Grouting Work | Cement Ghotai - DCH | Sq.Ft | 2801.18 | 15 | 42017.7 | 0 | 42017.7 | 10 | 0 | 0 | 0 | 0 | 2801.18 | 0 | Cement plaster Ghotai with 1:4 cement mortar mixing with chemical (Dr. Fixit/ Fosroc/ SBRE etc.) chemical in contractors scope proportion of 100 ml for 1 bag of cement, with broom finish including cleaning, scrubbing, vacuum cleaning etc. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 760 | 2 | 25 Aug 2023 | PRABHURAM VERMA | STP 265KLD Waterproofing work due to RCC Changes | Chemical W/ P AIE | Sq.Ft | 1347.2 | 22 | 29638.4 | 0 | 29638.4 | 10 | 0 | 0 | 0 | 0 | 1347.2 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Sep 2023 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ALTUS | 760 | 2 | 25 Aug 2023 | PRABHURAM VERMA | STP 265KLD Waterproofing work due to RCC Changes | IPS W/P | Sq.Ft | 162.691 | 15 | 2440.37 | 0 | 2440.37 | 10 | 0 | 0 | 0 | 0 | 162.691 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Sep 2023 |  | 06 WATERPROOFING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 760 | 1 | 25 Aug 2023 | PRABHURAM VERMA | UGWT-Pump Room-Chemical Grouting Work | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Sep 2023 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 30 Jan 2024
GANGA ALTUS | 760 | 0 | 25 Aug 2023 | PRABHURAM VERMA | UGWT- D&E Internal waterproofing work | Chemical W/P-UWT- | Sq.Ft | 15451 | 22 | 339922 | 0 | 339922 | 10 | 12360.8 | 271937.6 | 0 | 271937.6 | 3090.2 | 67984.4 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 760 | 0 | 25 Aug 2023 | PRABHURAM VERMA | UGWT- D&E Internal waterproofing work | Cement Ghotai inside W/P-UWT- | Sq.Ft | 15451 | 15 | 231765 | 0 | 231765 | 10 | 12360.8 | 185412 | 0 | 185412 | 3090.2 | 46353 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 760 | 2 | 25 Aug 2023 | PRABHURAM VERMA | STP 265KLD Waterproofing work due to RCC Changes | Brickbat W/P | Sq.Ft | 14.28 | 24 | 342.72 | 0 | 342.72 | 10 | 0 | 0 | 0 | 0 | 14.28 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Sep 2023 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ALTUS | 771 | 1 | 11 Sep 2023 | GUFRAN GULZAR SHAIKH | STP-265 KLD Grinding Work near 265KLD STP | Chipping & Grinding Work - DER | Sq.Ft | 4219.4 | 4.5 | 18987.3 | 0 | 18987.3 | 0 | 4219.4 | 18987.3 | 0 | 18987.3 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 12 Sep 2023 |  | DEV. Extrawork/Rework | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 776 | 0 | 16 Sep 2023 | JAI SEVALAL CONSTRUCTION | OWC Unit- 8" Blockwork (L) | Blockwork 8" - BC | Sq.Ft | 659.29 | 26 | 17141.54 | 3085.48 | 20227.02 | 2.5 | 0 | 0 | 0 | 0 | 659.29 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 776 | 1 | 16 Sep 2023 | JAI SEVALAL CONSTRUCTION | Transformer Room G Fl. to 1st Slab & Parapet -8" Blockwork | 8" Blockwork Rate Diff. | Sq.Ft | 880 | 5 | 4400 | 792 | 5192 | 2.5 | 0 | 0 | 0 | 0 | 880 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Sep 2023 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 776 | 0 | 16 Sep 2023 | JAI SEVALAL CONSTRUCTION | OWC Unit- Single Coat Sand Face Plaster Work (L) | Sand Face Plaster - UTR | Sq.Ft | 6159.06 | 20 | 123181.2 | 22172.62 | 145353.82 | 2.5 | 81.41 | 1628.2 | 293.08 | 1921.28 | 6077.65 | 143432.54 |  | 1.3218 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Sep 2023 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 776 | 0 | 16 Sep 2023 | JAI SEVALAL CONSTRUCTION | OWC Unit- 8" Blockwork (L) | Blockwork 8" - BC | Sq.Ft | 1130.23 | 22 | 24865.06 | 4475.72 | 29340.78 | 2.5 | 0 | 0 | 0 | 0 | 1130.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 809 | 1 | 17 Nov 2023 | AVCON TECHNICS PVT LTD | 265KLD STP Rebaring Work | Rebarring work 10mm dia- BC | No. | 1316 | 200 | 263200 | 47376 | 310576 | 2.5 | 549 | 109800 | 19764 | 129564 | 767 | 181012 |  | 41.7173 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 809 | 0 | 17 Nov 2023 | AVCON TECHNICS PVT LTD | RCC Work Rebaring-Tie Beam-Transformer Room | Rebaring work 16mm- cc | No. | 60 | 450 | 27000 | 4860 | 31860 | 0 | 60 | 27000 | 4860 | 31860 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | B.C. Customer Changes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 809 | 0 | 17 Nov 2023 | AVCON TECHNICS PVT LTD | RCC Work Rebaring-Tie Beam-Transformer Room | Rebaring work 12mm- cc | No. | 40 | 230 | 9200 | 1656 | 10856 | 0 | 28 | 6440 | 1159.2 | 7599.2 | 12 | 3256.8 |  | 70 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | B.C. Customer Changes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 809 | 0 | 17 Nov 2023 | AVCON TECHNICS PVT LTD | RCC Work Rebaring-Tie Beam-Transformer Room | Rebarring work 10mm dia-UWT | No. | 60 | 180 | 10800 | 1944 | 12744 | 0 | 45 | 8100 | 1458 | 9558 | 15 | 3186 |  | 75 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | UTI. U.G.W.T | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 809 | 1 | 17 Nov 2023 | AVCON TECHNICS PVT LTD | 265KLD STP Rebaring Work | Rebaring work 16mm- cc | No. | 77 | 500 | 38500 | 6930 | 45430 | 2.5 | 0 | 0 | 0 | 0 | 77 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 829 | 0 | 30 Nov 2023 | PATIL CONSTRUCTION | STP-265 KLD Cutting of RCC Wall near 265KLD STP | Cutting Work-BRE | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Dec 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 837 | 0 | 07 Dec 2023 | SHITOLE ENGINEERING SERVICES | UGWT-Pump Room-MS Railing Work | M.S. Railing (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 07 Dec 2023 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Dec 2023
GANGA ALTUS | 839 | 1 | 08 Dec 2023 | SURESH RANGNATH SHITOLE | Transformer Room-Fabrication work for RMU-II Stand | Labour Lumpsum | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Dec 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 839 | 0 | 08 Dec 2023 | SURESH RANGNATH SHITOLE | UGWT-Pump Room-MS Railing Work | M.S. Railing (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Dec 2023 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Dec 2023
GANGA ALTUS | 839 | 0 | 08 Dec 2023 | SURESH RANGNATH SHITOLE | UGWT-Pump Room-MS Railing Work | M.S. Railing (L) | Sq.Ft | 226 | 25 | 5650 | 0 | 5650 | 2.5 | 203.14 | 5078.5 | 0 | 5078.5 | 22.86 | 571.5 |  | 89.885 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 840 | 0 | 08 Dec 2023 | JAISAN | STP-265KLD-Breaking of RCC Partition Wall at Top Slab | Breaking & Removing Work -AIE | No. | 0 | 8500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Dec 2023 |  | Admin. Indirect Expenses | Cancelled | MONALI CHAUDHAR | 14 Dec 2023
GANGA ALTUS | 840 | 0 | 08 Dec 2023 | JAISAN | STP-265KLD-Breaking of RCC Partition Wall at Top Slab | Breaking & Removing Work -AIE | No. | 1 | 85000 | 85000 | 0 | 85000 | 2.5 | 1 | 85000 | 0 | 85000 | 0 | 0 | With Debris Shifting & Cleaning. | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Dec 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 851 | 0 | 12 Dec 2023 | VIJAY MOHITE | OWC Unit-Plum Concrete in 265KLD STP & OWC | Shuttering Work-Mkt | Sq.m. | 8.23 | 550 | 4526.5 | 0 | 4526.5 | 2.5 | 8.23 | 4526.5 | 0 | 4526.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Dec 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 851 | 0 | 12 Dec 2023 | VIJAY MOHITE | OWC Unit-Plum Concrete in 265KLD STP & OWC | Plum Concrete | Cu.Mtrs | 35.94 | 300 | 10782 | 0 | 10782 | 2.5 | 35.94 | 10782 | 0 | 10782 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Dec 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 851 | 0 | 12 Dec 2023 | VIJAY MOHITE | OWC Unit-Plum Concrete in 265KLD STP & OWC | Plum Concrete | Cu.Mtrs | 7.41 | 300 | 2223 | 0 | 2223 | 2.5 | 7.41 | 2223 | 0 | 2223 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Dec 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 852 | 0 | 12 Dec 2023 | VIJAY MOHITE | OWC Unit-PCC Work near 265KLD STP | PCC Work | Sq.Ft | 2123 | 8 | 16984 | 0 | 16984 | 2.5 | 2123 | 16984 | 0 | 16984 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 864 | 0 | 15 Dec 2023 | YOGESH SANTOSH GAIKWAD | Excavation Work-PMC Pipeline Connection to UGWT F Bldg. | Labour Lumpsum | No. | 1 | 21000 | 21000 | 0 | 21000 | 0 | 1 | 21000 | 0 | 21000 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 866 | 0 | 16 Dec 2023 | PRABHURAM VERMA | Transformer Room- Terrace Brickbat W/P Work | Brickbat W/P-ULT | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | UTI. Electricity Infrastructur | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 866 | 0 | 16 Dec 2023 | PRABHURAM VERMA | Transformer Room- Terrace Brickbat W/P Work | Brickbat W/P-ULT | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | UTI. Electricity Infrastructur | Cancelled | MONALI CHAUDHAR | 22 Dec 2023
GANGA ALTUS | 866 | 0 | 16 Dec 2023 | PRABHURAM VERMA | Transformer Room- Terrace Brickbat W/P Work | Brickbat W/P-ULT | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | UTI. Electricity Infrastructur | Cancelled | ADITYA.CHOUGULE | 21 Dec 2023
GANGA ALTUS | 866 | 0 | 16 Dec 2023 | PRABHURAM VERMA | Transformer Room- Terrace Brickbat W/P Work | Brickbat W/P-ULT | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | UTI. Electricity Infrastructur | Cancelled | ADITYA.CHOUGULE | 25 Dec 2023
GANGA ALTUS | 866 | 0 | 16 Dec 2023 | PRABHURAM VERMA | Transformer Room- Terrace Brickbat W/P Work | Brickbat W/P-ULT | Sq.Ft | 49.482 | 24 | 1187.57 | 0 | 1187.57 | 10 | 0 | 0 | 0 | 0 | 49.482 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 2nd Coat Primer (water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 2nd Coat Primer (water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 2nd Coat Primer (water Base) (L) | Sq.Ft | 4288.55 | 1 | 4288.55 | 0 | 4288.55 | 2.5 | 0 | 0 | 0 | 0 | 4288.55 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 4288.55 | 1 | 4288.55 | 0 | 4288.55 | 2.5 | 0 | 0 | 0 | 0 | 4288.55 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 868 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 870 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 870 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 4288.55 | 1 | 4288.55 | 0 | 4288.55 | 0 | 0 | 0 | 0 | 0 | 4288.55 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 870 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 2nd Coat Primer (water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 870 | 0 | 16 Dec 2023 | BUDDHRAJ MANJHI | UGWT-Pump Room-Internal Paint Work | 2nd Coat Primer (water Base) (M) | Sq.Ft | 4288.55 | 1 | 4288.55 | 0 | 4288.55 | 0 | 0 | 0 | 0 | 0 | 4288.55 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 873 | 1 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Fabrication work-Dld. | R.Ft | 93.5 | 40 | 3740 | 673.2 | 4413.2 | 2.5 | 93.5 | 3740 | 673.2 | 4413.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 873 | 1 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 596.74 | 80 | 47739.2 | 8593.06 | 56332.26 | 2.5 | 596.74 | 47739.2 | 8593.06 | 56332.26 | 0 | 0 | 1. Rolling Shutter size- 10.5ft x 15.5ft = 162.75 Sqft. 2. Rolling Shutter size- 9ft 9inch x 15.5ft= 151.12 Sqft. 3. Rolling Shutter size- 9ft 9inch x 15.5ft= 151.12 Sqft. 4. Rolling Shutter size- 8.5 ft x 15.5 ft= 131.75 Sqft. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 873 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 873 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 873 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 873 | 1 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Gear Box (L) | No. | 4 | 1800 | 7200 | 1296 | 8496 | 2.5 | 4 | 7200 | 1296 | 8496 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 874 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | ETP-15KLD-Rolling Shutter Fab.Work | Rolling Shutter (L) | Sq.Ft | 48.735 | 70 | 3411.45 | 614.06 | 4025.51 | 2.5 | 48.735 | 3411.45 | 614.06 | 4025.51 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 874 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | STP-45KLD-Rolling Shutter Fab.Work | Rolling Shutter (L) | Sq.Ft | 49.64 | 70 | 3474.8 | 625.46 | 4100.26 | 2.5 | 49.64 | 3474.8 | 625.46 | 4100.26 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 875 | 1 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 596.74 | 180 | 107413.2 | 19334.38 | 126747.58 | 0 | 596.74 | 107413.2 | 19334.38 | 126747.58 | 0 | 0 | 1. Rolling Shutter size- 10.5ft x 15.5ft = 162.75 Sqft. 2. Rolling Shutter size- 9ft 9inch x 15.5ft= 151.12 Sqft. 3. Rolling Shutter size- 9ft 9inch x 15.5ft= 151.12 Sqft. 4. Rolling Shutter size- 8.5 ft x 15.5 ft= 131.75 Sqft. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 875 | 1 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Gear Box (M) | No. | 4 | 4200 | 16800 | 3024 | 19824 | 0 | 4 | 16800 | 3024 | 19824 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 875 | 1 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Fabrication work (M)- Rft | R.Ft | 93.5 | 95 | 8882.5 | 1598.86 | 10481.36 | 0 | 93.5 | 8882.5 | 1598.86 | 10481.36 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 875 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | Transformer Room-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 16 Dec 2023
GANGA ALTUS | 876 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | ETP-15KLD-Rolling Shutter Fab.Work | Rolling Shutter (M) | Sq.Ft | 48.735 | 155 | 7553.93 | 1359.7 | 8913.63 | 0 | 48.735 | 7553.93 | 1359.7 | 8913.63 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 876 | 0 | 16 Dec 2023 | BHAGYALAXMI ENTERPRISES | STP-45KLD-Rolling Shutter Fab.Work | Rolling Shutter (M) | Sq.Ft | 49.64 | 155 | 7694.2 | 1384.96 | 9079.16 | 0 | 49.64 | 7694.2 | 1384.96 | 9079.16 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 880 | 0 | 16 Dec 2023 | JAI SEVALAL CONSTRUCTION | STP-45KLD- Int Single Coat Sandface Plaster | Sand Face Plaster DJT | Sq.Ft | 699.28 | 25 | 17482 | 3146.76 | 20628.76 | 2.5 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Jan 2024 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 880 | 0 | 16 Dec 2023 | JAI SEVALAL CONSTRUCTION | ETP-15KLD-Ext Sandface Single Coat Plaster | Sand Face Plaster DJT | Sq.Ft | 997.64 | 25 | 24941 | 4489.38 | 29430.38 | 2.5 | 0 | 0 | 0 | 0 | 997.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Jan 2024 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 880 | 0 | 16 Dec 2023 | JAI SEVALAL CONSTRUCTION | STP- 45KLD-Ext Single Coat Sandface Plaster Work | Sand Face Plaster DJT | Sq.Ft | 661.04 | 25 | 16526 | 2974.68 | 19500.68 | 2.5 | 0 | 0 | 0 | 0 | 661.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Jan 2024 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 880 | 0 | 16 Dec 2023 | JAI SEVALAL CONSTRUCTION | ETP-15KLD- Int Sandface Single Coat Plaster | Sand Face Plaster DJT | Sq.Ft | 990.84 | 25 | 24771 | 4458.78 | 29229.78 | 2.5 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Jan 2024 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 889 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Fabrication work-Dld. | R.Ft | 46.5 | 40 | 1860 | 334.8 | 2194.8 | 2.5 | 46.5 | 1860 | 334.8 | 2194.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Feb 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 889 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 889 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 889 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 20 Dec 2023
GANGA ALTUS | 889 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (L) | Sq.Ft | 142.715 | 80 | 11417.2 | 2055.1 | 13472.3 | 2.5 | 142.715 | 11417.2 | 2055.1 | 13472.3 | 0 | 0 | 1. Rolling Shutter size- 6ft 4inch x 11.5ft= 72.8 Sqft. 2. Rolling Shutter size- 6ft 1inch x 11.5ft= 69.9 Sqft. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 889 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Gear Box (L) | No. | 2 | 1800 | 3600 | 648 | 4248 | 2.5 | 2 | 3600 | 648 | 4248 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 889 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Gear Box (L) | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 22 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 890 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 20 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 890 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 20 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 20 Dec 2023
GANGA ALTUS | 890 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 20 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | MONALI CHAUDHAR | 20 Dec 2023
GANGA ALTUS | 890 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Fabrication work (M)- Rft | R.Ft | 46.5 | 95 | 4417.5 | 795.16 | 5212.66 | 0 | 46.5 | 4417.5 | 795.16 | 5212.66 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 890 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 142.715 | 180 | 25688.7 | 4623.96 | 30312.66 | 0 | 142.715 | 25688.7 | 4623.96 | 30312.66 | 0 | 0 | 1. Rolling Shutter size- 6ft 4inch x 11.5ft= 72.8 Sqft. 2. Rolling Shutter size- 6ft 1inch x 11.5ft= 69.9 Sqft. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 890 | 1 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Gear Box (M) | No. | 2 | 4200 | 8400 | 1512 | 9912 | 0 | 2 | 8400 | 1512 | 9912 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 890 | 0 | 20 Dec 2023 | BHAGYALAXMI ENTERPRISES | Altus-OWC-MS Rolling Shutter Work | Rolling Shutter (M) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 20 Dec 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 22 Feb 2024
GANGA ALTUS | 902 | 0 | 03 Jan 2024 | GURUDATTA KRUPA ENTERPRISES | TransformerRoom-Fabrication of RMC Stand | ISMC 125 (L) - Kgs | Kgs | 119.325 | 12 | 1431.9 | 257.74 | 1689.64 | 2.5 | 0 | 0 | 0 | 0 | 119.325 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jan 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 907 | 0 | 15 Jan 2024 | JAI SEVALAL CONSTRUCTION | Transformer Room-Internal Single Coat-Sand Face Plaster Work | Single Coat Plaster Rate Diff. (L) | Sq.Ft | 1390.24 | 5 | 6951.2 | 1251.22 | 8202.42 | 2.5 | 0 | 0 | 0 | 0 | 1390.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jan 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 907 | 0 | 15 Jan 2024 | JAI SEVALAL CONSTRUCTION | Transformer Room-External Single Coat-Sand Face Plaster Work | Single Coat Plaster Rate Diff. (L) | Sq.Ft | 2129.33 | 5 | 10646.65 | 1916.4 | 12563.05 | 2.5 | 0 | 0 | 0 | 0 | 2129.33 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jan 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 907 | 0 | 15 Jan 2024 | JAI SEVALAL CONSTRUCTION | Transformer Room-External Single Coat-Sand Face Plaster Work | Single Coat Plaster Rate Diff. (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Jan 2024 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 30 Jan 2024
GANGA ALTUS | 907 | 0 | 15 Jan 2024 | JAI SEVALAL CONSTRUCTION | Transformer Room-Internal Single Coat-Sand Face Plaster Work | Single Coat Plaster Rate Diff. (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Jan 2024 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 30 Jan 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 07 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Schedule- BC | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 2nd Coat Cement Paint (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Schedule- BC | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Scaffolding work | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1st Coat Cement Paint (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Scaffolding work | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1st Coat Cement Paint (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 2nd Coat Cement Paint (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 909 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Texture Paint (M) | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Texture Paint (M) | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1st Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1st Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 912 | 1 | 19 Jan 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Jan 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Power Supply unit (M) | No. | 6 | 8500 | 51000 | 9180 | 60180 | 0 | 4.2 | 35700 | 6426 | 42126 | 1.8 | 18054 | Model No-RE-5APS.Make-Ravel.Supply of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 6 zone Voice Alarm controller (M) | No. | 2 | 165000 | 330000 | 59400 | 389400 | 0 | 1.4 | 231000 | 41580 | 272580 | 0.6 | 116820 | Model No-RE-2AS.Supply of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station).Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Surface Mounting Modularized Panel (M) | No. | 2 | 325000 | 650000 | 117000 | 767000 | 0 | 1.4 | 455000 | 81900 | 536900 | 0.6 | 230100 | Model No-Aaral x8.Make-Ravel.Supply of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 20 Watt Cabinet Speakers (M) | No. | 76 | 2500 | 190000 | 34200 | 224200 | 0 | 53.2 | 133000 | 23940 | 156940 | 22.8 | 67260 | Model no-RE-LS20W.Supply of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable smoke detector (M) | No. | 857 | 2340 | 2005380 | 360968.4 | 2366348.4 | 0 | 599.9 | 1403766 | 252677.88 | 1656443.88 | 257.1 | 709904.52 | Model NoAR-LC.Make-Ravel.Supply of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Heat Detector (M) | No. | 207 | 2300 | 476100 | 85698 | 561798 | 0 | 144.9 | 333270 | 59988.6 | 393258.6 | 62.1 | 168539.4 | Model No-RE357S.Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | Telephone Jack/Receiver (M) | No. | 2 | 5200 | 10400 | 1872 | 12272 | 0 | 1.4 | 7280 | 1310.4 | 8590.4 | 0.6 | 3681.6 | Model No-EK- 750 H.Make- Ravel.Supply of Fire Fighter (talk back) Telephone handset. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Manual call point (M) | No. | 34 | 5000 | 170000 | 30600 | 200600 | 0 | 23.8 | 119000 | 21420 | 140420 | 10.2 | 60180 | Model No-RE-557PS.Make Ravel.Supply of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 955 | 75 | 71625 | 12892.5 | 84517.5 | 0 | 668.5 | 50137.5 | 9024.76 | 59162.26 | 286.5 | 25355.24 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | Mtrs | 10638 | 45 | 478710 | 86167.8 | 564877.8 | 0 | 7420 | 333900 | 60102 | 394002 | 3218 | 170875.8 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 69.75 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 1 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Monitor Module (M) | No. | 25 | 3135 | 78375 | 14107.5 | 92482.5 | 0 | 17.5 | 54862.5 | 9875.26 | 64737.76 | 7.5 | 27744.74 | Monitor Module (RE 757M) | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 600 | 75 | 45000 | 8100 | 53100 | 0 | 31.5 | 2362.5 | 425.26 | 2787.76 | 568.5 | 50312.24 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 5.25 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Push to talk Microphone (M) | No. | 2 | 16500 | 33000 | 5940 | 38940 | 0 | 1.4 | 23100 | 4158 | 27258 | 0.6 | 11682 | Model No-RE-2AS-PTT.Supply of Push to Talk microphone. Make:RAVEL | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Combined sounder (M) | No. | 34 | 4200 | 142800 | 25704 | 168504 | 0 | 23.8 | 99960 | 17992.8 | 117952.8 | 10.2 | 50551.2 | Model No-RE-658SS.Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Wall Mounting Kit (M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 1.4 | 4480 | 806.4 | 5286.4 | 0.6 | 2265.6 | Model No-RE-2AS WMK.Supply of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 1 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 1C x 1sqmm Wire (M) | Mtrs | 10000 | 33.25 | 332500 | 59850 | 392350 | 0 | 7000 | 232750 | 41895 | 274645 | 3000 | 117705 | 1 Sqmm x 1 Core Copper wire | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Zone Module (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 140 | 504000 | 90720 | 594720 | 60 | 254880 | Model No-RE - 386LP.Make Ravel.Supply of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Battery update & activation card (M) | No. | 2 | 42000 | 84000 | 15120 | 99120 | 0 | 1.4 | 58800 | 10584 | 69384 | 0.6 | 29736 | Model No-RE-2AS BC.Supply of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 2083 | 75 | 156225 | 28120.5 | 184345.5 | 0 | 1400 | 105000 | 18900 | 123900 | 683 | 60445.5 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, Twisted pair, FRLS PVC insulated Armoured cable, laid on wall / slab or structure with necessary GI saddles & spacer at 0.5 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. | 67.2108 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 8 Zone FFT Panel (M) | No. | 1 | 68915 | 68915 | 12404.7 | 81319.7 | 0 | 0.7 | 48240.5 | 8683.3 | 56923.8 | 0.3 | 24395.9 | Model No-EK - 740.Make- Ravel.Supply of 8 Zone FFT Panel. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | SITC Fireman's Phone Jack (M) | No. | 34 | 3300 | 112200 | 20196 | 132396 | 0 | 23.8 | 78540 | 14137.2 | 92677.2 | 10.2 | 39718.8 | Model No-EK-751J(For Aaral).Make- Ravel.Supply of Fire Fighter (talk back) jack module | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Fault Isolator Base / Module (M) | No. | 52 | 3100 | 161200 | 29016 | 190216 | 0 | 36.4 | 112840 | 20311.2 | 133151.2 | 15.6 | 57064.8 | Model No-RE-757I.Make Ravel.Supply ofFault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Signal initiating devices (M) | No. | 112 | 750 | 84000 | 15120 | 99120 | 0 | 78.4 | 58800 | 10584 | 69384 | 33.6 | 29736 | Model No-RE-LS6C.Supply & Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Gas Leakage Detector (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 140 | 504000 | 90720 | 594720 | 60 | 254880 | Model No-RE357HMake-Ravel.Supply of Gas Leak Detector with Power Supply(standalone system) | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Network Active Repeater (M) | No. | 1 | 42500 | 42500 | 7650 | 50150 | 0 | 0.7 | 29750 | 5355 | 35105 | 0.3 | 15045 | Make-Ravel.Supply of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 1 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Relay Module (M) | No. | 4 | 3135 | 12540 | 2257.2 | 14797.2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 1 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 1C x 1sqmm Wire (L) | Mtrs | 10000 | 23.75 | 237500 | 42750 | 280250 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 Sqmm x 1 Core Copper wire | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Wall Mounting Kit (L) | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | SITC Fireman's Phone Jack (L) | No. | 34 | 250 | 8500 | 1530 | 10030 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) jack module | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Push to talk Microphone (L) | No. | 2 | 4200 | 8400 | 1512 | 9912 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of Push to Talk microphone. Make:RAVEL | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 600 | 35 | 21000 | 3780 | 24780 | 2.5 | 0 | 0 | 0 | 0 | 600 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 1 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Monitor Module (L) | No. | 25 | 332.5 | 8312.5 | 1496.26 | 9808.76 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Monitor Module (RE 757M) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 20 Watt Cabinet Speakers (L) | No. | 76 | 300 | 22800 | 4104 | 26904 | 2.5 | 0 | 0 | 0 | 0 | 76 | 0 | Installation of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Signal initiating devices (L) | No. | 112 | 200 | 22400 | 4032 | 26432 | 2.5 | 0 | 0 | 0 | 0 | 112 | 0 | Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable smoke detector (L) | No. | 857 | 300 | 257100 | 46278 | 303378 | 0 | 0 | 0 | 0 | 0 | 857 | 0 | Make-Ravel.Installation of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Network Active Repeater (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | Make-Ravel.Installation of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 8 Zone FFT Panel (L) | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | Make- Ravel.Installation of 8 Zone FFT Panel. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Manual call point (L) | No. | 34 | 300 | 10200 | 1836 | 12036 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 | Make Ravel.Instalation of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Power Supply unit (L) | No. | 6 | 180 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 | Make-Ravel.Installation of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (L) | Mtrs | 10638 | 35 | 372330 | 67019.4 | 439349.4 | 2.5 | 0 | 0 | 0 | 0 | 10638 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Zone Module (L) | No. | 200 | 300 | 60000 | 10800 | 70800 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make Ravel.Installation of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Fault Isolator Base / Module (L) | No. | 52 | 300 | 15600 | 2808 | 18408 | 2.5 | 0 | 0 | 0 | 0 | 52 | 0 | Make Ravel.Installation of Fault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Heat Detector (L) | No. | 207 | 300 | 62100 | 11178 | 73278 | 2.5 | 0 | 0 | 0 | 0 | 207 | 0 | Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | Telephone Jack/Receiver (L) | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) Telephone handset. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 1 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Relay Module (L) | No. | 4 | 332.5 | 1330 | 239.4 | 1569.4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Gas Leakage Detector (L) | No. | 200 | 250 | 50000 | 9000 | 59000 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make-Ravel.Installation of Gas Leak Detector with Power Supply(standalone system) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Battery update & activation card (L) | No. | 2 | 12000 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 6 zone Voice Alarm controller (L) | No. | 2 | 23500 | 47000 | 8460 | 55460 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 2083 | 35 | 72905 | 13122.9 | 86027.9 | 2.5 | 0 | 0 | 0 | 0 | 2083 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 955 | 35 | 33425 | 6016.5 | 39441.5 | 2.5 | 0 | 0 | 0 | 0 | 955 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Combined sounder (L) | No. | 34 | 300 | 10200 | 1836 | 12036 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 | Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Surface Mounting Modularized Panel (L) | No. | 2 | 35000 | 70000 | 12600 | 82600 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make-Ravel.Installation of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 2610 | 75 | 195750 | 35235 | 230985 | 0 | 0 | 0 | 0 | 0 | 2610 | 0 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 1C x 1sqmm Wire (M) | Mtrs | 10000 | 33.25 | 332500 | 59850 | 392350 | 0 | 1680 | 55860 | 10054.8 | 65914.8 | 8320 | 326435.2 | 1 Sqmm x 1 Core Copper wire | 16.8 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Surface Mounting Modularized Panel (M) | No. | 2 | 325000 | 650000 | 117000 | 767000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-Aaral x8.Make-Ravel.Supply of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Manual call point (M) | No. | 40 | 5000 | 200000 | 36000 | 236000 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Model No-RE-557PS.Make Ravel.Supply of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable smoke detector (M) | No. | 866 | 2340 | 2026440 | 364759.2 | 2391199.2 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | Model NoAR-LC.Make-Ravel.Supply of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Zone Module (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | Model No-RE - 386LP.Make Ravel.Supply of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Heat Detector (M) | No. | 216 | 2300 | 496800 | 89424 | 586224 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | Model No-RE357S.Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Wall Mounting Kit (M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS WMK.Supply of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 20 Watt Cabinet Speakers (M) | No. | 49 | 2500 | 122500 | 22050 | 144550 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | Model no-RE-LS20W.Supply of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 2.8571 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 6 zone Voice Alarm controller (M) | No. | 2 | 165000 | 330000 | 59400 | 389400 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS.Supply of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station).Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Power Supply unit (M) | No. | 6 | 8500 | 51000 | 9180 | 60180 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Model No-RE-5APS.Make-Ravel.Supply of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Gas Leakage Detector (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | Model No-RE357HMake-Ravel.Supply of Gas Leak Detector with Power Supply(standalone system) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Push to talk Microphone (M) | No. | 2 | 16500 | 33000 | 5940 | 38940 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS-PTT.Supply of Push to Talk microphone. Make:RAVEL | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | Telephone Jack/Receiver (M) | No. | 2 | 5200 | 10400 | 1872 | 12272 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-EK- 750 H.Make- Ravel.Supply of Fire Fighter (talk back) Telephone handset. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | Mtrs | 10134 | 45 | 456030 | 82085.4 | 538115.4 | 0 | 3500 | 157500 | 28350 | 185850 | 6634 | 352265.4 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 34.5372 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Fault Isolator Base / Module (M) | No. | 54 | 3100 | 167400 | 30132 | 197532 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | Model No-RE-757I.Make Ravel.Supply ofFault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Monitor Module (M) | No. | 25 | 3135 | 78375 | 14107.5 | 92482.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Monitor Module (RE 757M) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 610 | 75 | 45750 | 8235 | 53985 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 820 | 75 | 61500 | 11070 | 72570 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Battery update & activation card (M) | No. | 2 | 42000 | 84000 | 15120 | 99120 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS BC.Supply of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 8 Zone FFT Panel (M) | No. | 1 | 68915 | 68915 | 12404.7 | 81319.7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Model No-EK - 740.Make- Ravel.Supply of 8 Zone FFT Panel. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Combined sounder (M) | No. | 40 | 4200 | 168000 | 30240 | 198240 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Model No-RE-658SS.Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Signal initiating devices (M) | No. | 112 | 750 | 84000 | 15120 | 99120 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | Model No-RE-LS6C.Supply & Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | SITC Fireman's Phone Jack (M) | No. | 39 | 3300 | 128700 | 23166 | 151866 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | Model No-EK-751J(For Aaral).Make- Ravel.Supply of Fire Fighter (talk back) jack module | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Relay Module (M) | No. | 4 | 3135 | 12540 | 2257.2 | 14797.2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 1C x 1sqmm Wire (L) | Mtrs | 10000 | 23.75 | 237500 | 42750 | 280250 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 Sqmm x 1 Core Copper wire | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Zone Module (L) | No. | 200 | 300 | 60000 | 10800 | 70800 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make Ravel.Installation of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 6 zone Voice Alarm controller (L) | No. | 2 | 23500 | 47000 | 8460 | 55460 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Manual call point (L) | No. | 40 | 300 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 | Make Ravel.Instalation of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Manual call point (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 27 Jan 2024
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 20 Watt Cabinet Speakers (L) | No. | 49 | 300 | 14700 | 2646 | 17346 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 | Installation of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Fault Isolator Base / Module (L) | No. | 54 | 300 | 16200 | 2916 | 19116 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 | Make Ravel.Installation of Fault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 8 Zone FFT Panel (L) | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | Make- Ravel.Installation of 8 Zone FFT Panel. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Gas Leakage Detector (L) | No. | 200 | 250 | 50000 | 9000 | 59000 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make-Ravel.Installation of Gas Leak Detector with Power Supply(standalone system) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Relay Module (L) | No. | 4 | 332.5 | 1330 | 239.4 | 1569.4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Wall Mounting Kit (L) | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Monitor Module (L) | No. | 25 | 332.5 | 8312.5 | 1496.26 | 9808.76 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Monitor Module (RE 757M) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Surface Mounting Modularized Panel (L) | No. | 2 | 35000 | 70000 | 12600 | 82600 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make-Ravel.Installation of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable smoke detector (L) | No. | 866 | 300 | 259800 | 46764 | 306564 | 2.5 | 0 | 0 | 0 | 0 | 866 | 0 | Make-Ravel.Installation of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Signal initiating devices (L) | No. | 112 | 200 | 22400 | 4032 | 26432 | 2.5 | 0 | 0 | 0 | 0 | 112 | 0 | Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Push to talk Microphone (L) | No. | 2 | 4200 | 8400 | 1512 | 9912 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of Push to Talk microphone. Make:RAVEL | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Battery update & activation card (L) | No. | 2 | 12000 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 820 | 35 | 28700 | 5166 | 33866 | 2.5 | 0 | 0 | 0 | 0 | 820 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Combined sounder (L) | No. | 40 | 300 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 | Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 610 | 35 | 21350 | 3843 | 25193 | 2.5 | 0 | 0 | 0 | 0 | 610 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Heat Detector (L) | No. | 216 | 300 | 64800 | 11664 | 76464 | 2.5 | 0 | 0 | 0 | 0 | 216 | 0 | Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | SITC Fireman's Phone Jack (L) | No. | 39 | 250 | 9750 | 1755 | 11505 | 2.5 | 0 | 0 | 0 | 0 | 39 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) jack module | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (L) | Mtrs | 10134 | 35 | 354690 | 63844.2 | 418534.2 | 2.5 | 0 | 0 | 0 | 0 | 10134 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 2610 | 35 | 91350 | 16443 | 107793 | 2.5 | 0 | 0 | 0 | 0 | 2610 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Power Supply unit (L) | No. | 6 | 180 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 | Make-Ravel.Installation of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | Telephone Jack/Receiver (L) | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) Telephone handset. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 921 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | Transformer Room Trench covering with Jali | MS Angle. (M) | Kgs | 287.28 | 59 | 16949.52 | 3050.92 | 20000.44 | 0 | 0 | 0 | 0 | 0 | 287.28 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 922 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | Transformer Room Trench covering with Jali | Fabrication (L) - Mkt | Kgs | 682.56 | 20 | 13651.2 | 2457.22 | 16108.42 | 2.5 | 0 | 0 | 0 | 0 | 682.56 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Feb 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 922 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | Transformer Room Trench covering with Jali | MS Angle. (L) | Kgs | 287.28 | 23.6 | 6779.81 | 1220.36 | 8000.17 | 2.5 | 0 | 0 | 0 | 0 | 287.28 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Feb 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 931 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 40kva DG servicing kit | Air Filter element | No. | 0 | 7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Feb 2024 |  | 18. Maintenance & Repair Work | Cancelled | MONALI CHAUDHAR | 03 Feb 2024
GANGA ALTUS | 931 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 40kva DG servicing kit | Air Filter element | No. | 2 | 2047 | 4094 | 736.92 | 4830.92 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 03 Feb 2024 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 931 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 40kva DG servicing kit | Transport Charges | No. | 4 | 736 | 2944 | 529.92 | 3473.92 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 03 Feb 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 931 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 40kva DG servicing kit | B Check Service Kit | set | 4 | 7455 | 29820 | 5367.6 | 35187.6 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 03 Feb 2024 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 932 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 82.5 kva DG servicing kit | B Check Service Kit | set | 8 | 9062 | 72496 | 13049.28 | 85545.28 | 0 | 4 | 36248 | 6524.64 | 42772.64 | 4 | 42772.64 |  | 50 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 932 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 82.5 kva DG servicing kit | Transport Charges | No. | 8 | 736 | 5888 | 1059.84 | 6947.84 | 0 | 4 | 2944 | 529.92 | 3473.92 | 4 | 3473.92 |  | 50 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 932 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 82.5 kva DG servicing kit | Air Filter element | No. | 2 | 2971.6 | 5943.2 | 1069.78 | 7012.98 | 0 | 1 | 2971.6 | 534.88 | 3506.48 | 1 | 3506.5 |  | 50 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 933 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 125kva DG servicing kit | Air Filter element | No. | 2 | 4404.04 | 8808.08 | 1585.46 | 10393.54 | 0 | 1 | 4404.04 | 792.72 | 5196.76 | 1 | 5196.78 |  | 50 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 933 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 125kva DG servicing kit | B Check Service Kit | set | 6 | 11132 | 66792 | 12022.56 | 78814.56 | 0 | 1 | 11132 | 2003.76 | 13135.76 | 5 | 65678.8 |  | 16.6667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 933 | 0 | 03 Feb 2024 | MEGAPOWER SOLUTION PVT LTD | 125kva DG servicing kit | Transport Charges | No. | 6 | 736 | 4416 | 794.88 | 5210.88 | 0 | 1 | 736 | 132.48 | 868.48 | 5 | 4342.4 |  | 16.6667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 997.64 | 1.75 | 1745.87 | 314.26 | 2060.13 | 2.5 | 0 | 0 | 0 | 0 | 997.64 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 661.04 | 1.75 | 1156.82 | 208.22 | 1365.04 | 2.5 | 0 | 0 | 0 | 0 | 661.04 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1st Coat Cement Paint (L) | Sq.Ft | 699.28 | 1 | 699.28 | 125.88 | 825.16 | 2.5 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Texture Paint (L) | Sq.Ft | 661.04 | 7.5 | 4957.8 | 892.4 | 5850.2 | 2.5 | 661.04 | 4957.8 | 892.4 | 5850.2 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Texture Paint (L) | Sq.Ft | 997.64 | 7.5 | 7482.3 | 1346.82 | 8829.12 | 2.5 | 997.64 | 7482.3 | 1346.82 | 8829.12 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Scaffolding work | Sq.Ft | 661.04 | 3.5 | 2313.64 | 416.46 | 2730.1 | 2.5 | 661.04 | 2313.64 | 416.46 | 2730.1 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Scaffolding work | Sq.Ft | 997.64 | 3.5 | 3491.74 | 628.52 | 4120.26 | 2.5 | 997.64 | 3491.74 | 628.52 | 4120.26 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Scaffolding work | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 990.64 | 0.5 | 495.32 | 89.16 | 584.48 | 0 | 990.64 | 495.32 | 89.16 | 584.48 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 2nd Coat Cement Paint (L) | Sq.Ft | 699.28 | 1 | 699.28 | 125.88 | 825.16 | 2.5 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 661.04 | 1.5 | 991.56 | 178.48 | 1170.04 | 2.5 | 0 | 0 | 0 | 0 | 661.04 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Schedule- BC | Sq.Ft | 997.64 | 1 | 997.64 | 179.58 | 1177.22 | 2.5 | 997.64 | 997.64 | 179.58 | 1177.22 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1st Coat Cement Paint (L) | Sq.Ft | 990.84 | 1 | 990.84 | 178.36 | 1169.2 | 2.5 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 661.04 | 0.5 | 330.52 | 59.5 | 390.02 | 0 | 661.04 | 330.52 | 59.5 | 390.02 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Schedule- BC | Sq.Ft | 661.04 | 1 | 661.04 | 118.98 | 780.02 | 2.5 | 661.04 | 661.04 | 118.98 | 780.02 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 990.84 | 1 | 990.84 | 178.36 | 1169.2 | 2.5 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 997.64 | 1.5 | 1496.46 | 269.36 | 1765.82 | 2.5 | 0 | 0 | 0 | 0 | 997.64 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 2nd Coat Cement Paint (L) | Sq.Ft | 990.84 | 1 | 990.84 | 178.36 | 1169.2 | 2.5 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 699.28 | 1 | 699.28 | 125.88 | 825.16 | 2.5 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 661.04 | 1 | 661.04 | 118.98 | 780.02 | 2.5 | 0 | 0 | 0 | 0 | 661.04 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 935 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 997.64 | 1 | 997.64 | 179.58 | 1177.22 | 2.5 | 0 | 0 | 0 | 0 | 997.64 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 661.04 | 1 | 661.04 | 118.98 | 780.02 | 0 | 661.04 | 661.04 | 118.98 | 780.02 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 997.64 | 2.5 | 2494.1 | 448.94 | 2943.04 | 0 | 997.64 | 2494.1 | 448.94 | 2943.04 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 997.64 | 2.25 | 2244.69 | 404.04 | 2648.73 | 0 | 997.64 | 2244.69 | 404.04 | 2648.73 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 699.28 | 1 | 699.28 | 125.88 | 825.16 | 0 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 990.84 | 1 | 990.84 | 178.36 | 1169.2 | 0 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 2nd Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 699.28 | 1 | 699.28 | 125.88 | 825.16 | 0 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1st Coat Cement Paint (M) | Sq.Ft | 990.84 | 1 | 990.84 | 178.36 | 1169.2 | 0 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 661.04 | 2.5 | 1652.6 | 297.46 | 1950.06 | 0 | 661.04 | 1652.6 | 297.46 | 1950.06 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 661.04 | 2.25 | 1487.34 | 267.72 | 1755.06 | 0 | 661.04 | 1487.34 | 267.72 | 1755.06 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-Internal Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 990.84 | 1 | 990.84 | 178.36 | 1169.2 | 0 | 0 | 0 | 0 | 0 | 990.84 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 997.64 | 1 | 997.64 | 179.58 | 1177.22 | 0 | 997.64 | 997.64 | 179.58 | 1177.22 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1st Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-External Painting Work | Texture Paint (M) | Sq.Ft | 661.04 | 8 | 5288.32 | 951.9 | 6240.22 | 0 | 661.04 | 5288.32 | 951.9 | 6240.22 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | ETP-15KLD-External Painting Work | Texture Paint (M) | Sq.Ft | 997.64 | 8 | 7981.12 | 1436.6 | 9417.72 | 0 | 997.64 | 7981.12 | 1436.6 | 9417.72 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1st Coat Cement Paint (M) | Sq.Ft | 699.28 | 1 | 699.28 | 125.88 | 825.16 | 0 | 0 | 0 | 0 | 0 | 699.28 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 936 | 0 | 08 Feb 2024 | RAHUL PATIL | STP-45KLD-Internal Painting Work | 1st Coat Cement Paint (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 08 Feb 2024
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | F Bldg. Side Storm water line (L) | 12" RCC Hume Pipe laying & fixing -UTR - | R.Ft | 40 | 30 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Electrical Line-Transformer to Common Meter (L) | 12" RCC Hume Pipe laying & fixing -UDR | R.Ft | 1181 | 30 | 35430 | 6377.4 | 41807.4 | 2.5 | 0 | 0 | 0 | 0 | 1181 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Drainage Line (L) | Round Chamber- UDR | No. | 4 | 4000 | 16000 | 2880 | 18880 | 2.5 | 3 | 12000 | 2160 | 14160 | 1 | 4720 |  | 75 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Storm water line (L) | Chamber 24" x 24" (4ft Ht) - USL | No. | 3 | 2100 | 6300 | 1134 | 7434 | 2.5 | 2 | 4200 | 756 | 4956 | 1 | 2478 |  | 66.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Strom Line | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 16'' RCC Hume Pipe Laying & Fixing work | R.Ft | 27 | 35 | 945 | 170.1 | 1115.1 | 2.5 | 0 | 0 | 0 | 0 | 27 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | F Bldg. Side Storm water line (L) | Round Chamber- UDR | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 10" RCC Hume Pipe laying & fixing -UDR | R.Ft | 132 | 28 | 3696 | 665.28 | 4361.28 | 2.5 | 132 | 3696 | 665.28 | 4361.28 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Drainage Line-For Club House Additionall | 10" RCC Hume Pipe laying & fixing -UDR | R.Ft | 181 | 28 | 5068 | 912.24 | 5980.24 | 2.5 | 0 | 0 | 0 | 0 | 181 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Storm water line (L) | Round Chamber- UDR | No. | 4 | 4000 | 16000 | 2880 | 18880 | 2.5 | 4 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Storm water line (L) | Round Chamber- UDR | No. | 0 | 4000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | UTI. Drainage | Cancelled | ADITYA.CHOUGULE | 27 Feb 2024
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Drainage Line (L) | Chamber 24" x 36" (4ft Ht) - UTI | No. | 2 | 2600 | 5200 | 936 | 6136 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Overflow Line (From 265KLD to Na | Chamber 24" x 36" (4ft Ht) - UTI | No. | 4 | 2600 | 10400 | 1872 | 12272 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Drainage Line.-Side of F Bldg.-As per Site Condition | 10" RCC Hume Pipe laying & fixing -UST - | R.Ft | 171 | 28 | 4788 | 861.84 | 5649.84 | 2.5 | 76.916 | 2153.65 | 387.66 | 2541.31 | 94.084 | 3108.53 |  | 44.9801 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. S.T.P | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 12" RCC Hume Pipe laying & fixing -UDR | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | UTI. Drainage | Cancelled | DUSHANT.GORE | 02 Mar 2024
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Storm water line (L) | Chamber 24" x 36" (4ft Ht) - UTI | No. | 9 | 2600 | 23400 | 4212 | 27612 | 2.5 | 2 | 5200 | 936 | 6136 | 7 | 21476 |  | 22.2222 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Overflow Line (From 265KLD to Na | Round Chamber- UDR | No. | 3 | 4000 | 12000 | 2160 | 14160 | 2.5 | 2 | 8000 | 1440 | 9440 | 1 | 4720 |  | 66.6667 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | STP Overflow line-265KLD to Nala Line-(L) | 10" RCC Hume Pipe laying & fixing -UDR | R.Ft | 417 | 28 | 11676 | 2101.68 | 13777.68 | 2.5 | 183.6726 | 5142.83 | 925.72 | 6068.55 | 233.3274 | 7709.13 |  | 44.0462 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 12" RCC Hume Pipe laying & fixing -UDR | R.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | UTI. Drainage | Cancelled | MONALI CHAUDHAR | 22 Feb 2024
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 12" RCC Hume Pipe laying & fixing -UDR | R.Ft | 427 | 30 | 12810 | 2305.8 | 15115.8 | 2.5 | 427 | 12810 | 2305.8 | 15115.8 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Drainage Line (Club House) | Round Chamber- UDR | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 1 | 17 Feb 2024 | SAI PLUMBING WORKS | Blockwork & Plaster Work for Rainwater Harvesting Chamber | Chamber Making -USL | No. | 4 | 10000 | 40000 | 7200 | 47200 | 2.5 | 2 | 20000 | 3600 | 23600 | 2 | 23600 |  | 50 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. D.G.Set | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Construction of Chamber for Storm water line (L) | Chamber 36" x 18" (4ft Ht) - UDR | No. | 2 | 2200 | 4400 | 792 | 5192 | 2.5 | 1 | 2200 | 396 | 2596 | 1 | 2596 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 14" RCC Hume Pipe laying & fixing | R.Ft | 165 | 32 | 5280 | 950.4 | 6230.4 | 2.5 | 0 | 0 | 0 | 0 | 165 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 8" RCC Hume Pipe laying & fixing -UDR | R.Ft | 99 | 26 | 2574 | 463.32 | 3037.32 | 2.5 | 0 | 0 | 0 | 0 | 99 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 938 | 0 | 17 Feb 2024 | SAI PLUMBING WORKS | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 8" RCC Hume Pipe laying & fixing -UDR | R.Ft | 214 | 26 | 5564 | 1001.52 | 6565.52 | 2.5 | 0 | 0 | 0 | 0 | 214 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 120sqmm X 3.5 core cable (M+L) | No. | 24 | 990 | 23760 | 4276.8 | 28036.8 | 2.5 | 20 | 19800 | 3564 | 23364 | 4 | 4672.8 |  | 83.3333 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 95sqmm X 3.5 core cable (M+L) | No. | 4 | 990 | 3960 | 712.8 | 4672.8 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 120sqmm-UTI | Mtrs | 800 | 71.5 | 57200 | 10296 | 67496 | 2.5 | 394 | 28171 | 5070.78 | 33241.78 | 406 | 34254.22 |  | 49.25 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 185 Sqmm x 3.5 Core cable (M+L) | No. | 4 | 1540 | 6160 | 1108.8 | 7268.8 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 50sqmm-UTI | Mtrs | 80 | 55 | 4400 | 792 | 5192 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 300sqmm X 3.5 core cable (M+L) | No. | 54 | 1870 | 100980 | 18176.4 | 119156.4 | 2.5 | 8 | 14960 | 2692.8 | 17652.8 | 46 | 101503.6 |  | 14.8148 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 95sqmm-UTI | Mtrs | 120 | 60.5 | 7260 | 1306.8 | 8566.8 | 2.5 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | 120 Sqmm x 3.5 Core Alu. Armoud jointing kit (M+L) | No. | 3 | 2800 | 8400 | 1512 | 9912 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | DTC Meter Fixing | No. | 4 | 2420 | 9680 | 1742.4 | 11422.4 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 300sqmm-UTI | Mtrs | 2270 | 99 | 224730 | 40451.4 | 265181.4 | 2.5 | 2039 | 201861 | 36334.98 | 238195.98 | 231 | 26985.42 |  | 89.8238 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | 300 Sqmm x 3.5 core Alu. Armoud Jointing kit (M+L) | No. | 4 | 3300 | 13200 | 2376 | 15576 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Meter Panel (L) | No. | 32 | 3000 | 96000 | 17280 | 113280 | 2.5 | 14 | 42000 | 7560 | 49560 | 18 | 63720 |  | 43.75 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 50 Sqmm x 3.5 Core cable (M+L) | No. | 18 | 660 | 11880 | 2138.4 | 14018.4 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | 185 Sqmm x 3.5 Core Alu. Armoud jointing kit (M+L) | No. | 2 | 2800 | 5600 | 1008 | 6608 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 1 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Pumproom UGWT D&E Foundation work for Fire Pump | Concrete - M25 | Cu.Mtrs | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 23 Apr 2024 |  | 02 RCC WORK | Cancelled | MONALI CHAUDHAR | 06 Jul 2024
GANGA ALTUS | 968 | 0 | 24 Apr 2024 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | Core Cutting Work-Pump Room-D&E & Ret.Wall | Horizontal Core Cutting 150mm | No. | 6 | 265 | 1590 | 286.2 | 1876.2 | 0 | 6 | 1590 | 0 | 1590 | 0 | 286.2 | For Fire Hydrant line, Fire loop, Rising Main to Bldg. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 968 | 0 | 24 Apr 2024 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | Core Cutting Work-Pump Room-D&E & Ret.Wall | Horizontal Core Cutting 75mm | No. | 2 | 265 | 530 | 95.4 | 625.4 | 0 | 2 | 530 | 0 | 530 | 0 | 95.4 | For Corporation Line. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Apr 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 968 | 0 | 24 Apr 2024 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | Core Cutting Work-Pump Room-D&E & Ret.Wall | Horizontal Core Cutting 100mm | No. | 4 | 265 | 1060 | 190.8 | 1250.8 | 0 | 2 | 530 | 47.7 | 577.7 | 2 | 673.1 | For Utility, Overflow | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Apr 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 968 | 0 | 24 Apr 2024 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | Core Cutting Work-Pump Room-D&E & Ret.Wall | Horizontal Core Cutting 125mm | No. | 2 | 265 | 530 | 95.4 | 625.4 | 0 | 2 | 530 | 0 | 530 | 0 | 95.4 | For CT Meter LT & HT Line | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Apr 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 968 | 0 | 24 Apr 2024 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | Core Cutting Work-Pump Room-D&E & Ret.Wall | Horizontal Core Cutting 125mm | No. | 4 | 265 | 1060 | 190.8 | 1250.8 | 0 | 4 | 1060 | 0 | 1060 | 0 | 190.8 | For Water Tank Inlet, Flushing & Domestic Line. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Apr 2024 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-1216) (M) | Mtrs | 290 | 248 | 71920 | 12945.6 | 84865.6 | 0 | 203 | 50344 | 9061.92 | 59405.92 | 87 | 25459.68 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 1216 | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-2025) (M) | Mtrs | 370 | 361 | 133570 | 24042.6 | 157612.6 | 0 | 259 | 93499 | 16829.82 | 110328.82 | 111 | 47283.78 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 2025 | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Pressure Relief Valve 15mm (M) | No. | 4 | 3800 | 15200 | 2736 | 17936 | 0 | 2.8 | 10640 | 1915.2 | 12555.2 | 1.2 | 5380.8 | Supply Pressure Relief Valve 15mm inclusive of GI Fittings for Pressure Systems Make: OR | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of MS Fabricated Support (M) | Kgs | 179.9 | 80 | 14392 | 2590.56 | 16982.56 | 0 | 125.93 | 10074.4 | 1813.4 | 11887.8 | 53.97 | 5094.76 | Supply of MS Fabricated support with necessary fittings for holding GI Air Pipe with one coat of Red oxide & 2 Coats of Enamel Paint | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Air Vent 15mm (M) | No. | 4 | 950 | 3800 | 684 | 4484 | 0 | 2.8 | 2660 | 478.8 | 3138.8 | 1.2 | 1345.2 | Supply of Air vent Valve inclusive of GI Fittings Make: DRP/OR Size 15mm | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Ball Valve 15mm (M) | No. | 150 | 353 | 52950 | 9531 | 62481 | 0 | 105 | 37065 | 6671.7 | 43736.7 | 45 | 18744.3 | Supply of Ball Valves with necessary GI Fittings Make: Zoloto. Size 15 mm. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Solar water heating system1500LPD (M) | No. | 4 | 281500 | 1126000 | 135120 | 1261120 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of Solar Water Heating System Pressure Type of capacity 1500 LPD,Solar Hot Water Tank 1125 L, Material SS 304 , suitable for working pressure 3.5 bar Rock wool Insulation & Aluminium Cladding for Hot Water Mixing tank Flat Plate Collectors 12 Nos. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-2532) (M) | Mtrs | 420 | 460 | 193200 | 34776 | 227976 | 0 | 294 | 135240 | 24343.2 | 159583.2 | 126 | 68392.8 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 2532 | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Solar water heating system ETC500 (M) | No. | 24 | 38000 | 912000 | 109440 | 1021440 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Supply of Solar Water Heating System , Non-Pressure Type, of capacity ETC 500, Model GGES, ETC Tubes of Dia. 58 mm x L 2100 mm 32 Nos. per system Supporting stands & accessories. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Ball Valve 20mm (M) | No. | 54 | 440 | 23760 | 4276.8 | 28036.8 | 0 | 37.8 | 16632 | 2993.76 | 19625.76 | 16.2 | 8411.04 | Supply of Ball Valves with necessary GI Fittings Make: Zoloto. Size 20 mm. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of NRV 15mm (M) | No. | 140 | 1660 | 232400 | 41832 | 274232 | 0 | 98 | 162680 | 29282.4 | 191962.4 | 42 | 82269.6 | Supply of NRV withe necessary GI Fittings, Make:Zoloto.Size 15mm | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of NRV 32mm (M) | No. | 10 | 3060 | 30600 | 5508 | 36108 | 0 | 7 | 21420 | 3855.6 | 25275.6 | 3 | 10832.4 | Supply of NRV withe necessary GI Fittings, Make:Zoloto.Size 32mm | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Ball Valve 32mm (M) | No. | 20 | 1960 | 39200 | 7056 | 46256 | 0 | 14 | 27440 | 4939.2 | 32379.2 | 6 | 13876.8 | Supply of Ball Valves with necessary GI Fittings Make: Zoloto. Size 32 mm. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Spring NRV 25mm (M) | No. | 4 | 2400 | 9600 | 1728 | 11328 | 0 | 2.8 | 6720 | 1209.6 | 7929.6 | 1.2 | 3398.4 | Supply of NRV withe necessary GI Fittings, Make:Zoloto.Size 25mm Spring NRV | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-1620) (M) | Mtrs | 110 | 295 | 32450 | 5841 | 38291 | 0 | 77 | 22715 | 4088.7 | 26803.7 | 33 | 11487.3 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 1620 | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of GI Air Pipe 15mm (M) | No. | 70 | 2000 | 140000 | 25200 | 165200 | 0 | 49 | 98000 | 17640 | 115640 | 21 | 49560 | Supply of GI Air Pipe 15 mm for ETC Solar Water Heating System | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 992 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Supply of Pressure reducing valve (M) | No. | 20 | 5400 | 108000 | 19440 | 127440 | 0 | 14 | 75600 | 13608 | 89208 | 6 | 38232 | Supply of Pressure Reducing Valve with necessary GI Fittings & as per requirement of PRV Station & PRV at Auto Drain. Size 20mm | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-2532) (M) | Mtrs | 420 | 460 | 193200 | 34776 | 227976 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 2532 | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-1216) (M) | Mtrs | 290 | 248 | 71920 | 12945.6 | 84865.6 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 1216 | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Pressure Relief Valve 15mm (M) | No. | 4 | 3800 | 15200 | 2736 | 17936 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply Pressure Relief Valve 15mm inclusive of GI Fittings for Pressure Systems Make: OR | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Air Vent 15mm (M) | No. | 4 | 950 | 3800 | 684 | 4484 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of Air vent Valve inclusive of GI Fittings Make: DRP/OR Size 15mm | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Ball Valve 20mm (M) | No. | 54 | 440 | 23760 | 4276.8 | 28036.8 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | Supply of Ball Valves with necessary GI Fittings Make: Zoloto. Size 20mm. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of NRV 15mm (M) | No. | 140 | 1660 | 232400 | 41832 | 274232 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | Supply of NRV withe necessary GI Fittings, Make:Zoloto.Size 15mm | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Ball Valve 15mm (M) | No. | 150 | 353 | 52950 | 9531 | 62481 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | Supply of Ball Valves with necessary GI Fittings Make: Zoloto. Size 15 mm. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Solar water heating system1500LPD (M) | No. | 4 | 281500 | 1126000 | 135120 | 1261120 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of Solar Water Heating System Pressure Type of capacity 1500 LPD,Solar Hot Water Tank 1125 L, Material SS 304 , suitable for working pressure 3.5 bar Rock wool Insulation & Aluminium Cladding for Hot Water Mixing tank Flat Plate Collectors 12 Nos. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-2025) (M) | Mtrs | 370 | 361 | 133570 | 24042.6 | 157612.6 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 2025 | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of NRV 32mm (M) | No. | 10 | 3060 | 30600 | 5508 | 36108 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Supply of NRV withe necessary GI Fittings, Make:Zoloto.Size 32mm | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Pressure reducing valve (M) | No. | 20 | 5400 | 108000 | 19440 | 127440 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Supply of Pressure Reducing Valve with necessary GI Fittings & as per requirement of PRV Station & PRV at Auto Drain. Size 20mm | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of MS Fabricated Support (M) | Kgs | 179.9 | 80 | 14392 | 2590.56 | 16982.56 | 0 | 0 | 0 | 0 | 0 | 179.9 | 0 | Supply of MS Fabricated support with necessary fittings for holding GI Air Pipe with one coat of Red oxide & 2 Coats of Enamel Paint | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-1620) (M) | Mtrs | 110 | 295 | 32450 | 5841 | 38291 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | Supply of Composite Pipe with all necessary kitec & GI Fittings, Make: Kitec.Size 1620 | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of GI Air Pipe 15mm (M) | No. | 70 | 2000 | 140000 | 25200 | 165200 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | Supply of GI Air Pipe 15 mm for ETC Solar Water Heating System | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Spring NRV 25mm (M) | No. | 4 | 2400 | 9600 | 1728 | 11328 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of NRV withe necessary GI Fittings, Make:Zoloto.Size 25mm Spring NRV | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Supply of Ball Valve 32mm (M) | No. | 20 | 1960 | 39200 | 7056 | 46256 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Supply of Ball Valves with necessary GI Fittings Make: Zoloto. Size 32mm. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 995 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Solar water heating system ETC500 (M) | No. | 24 | 38000 | 912000 | 109440 | 1021440 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Supply of Solar Water Heating System , Non-Pressure Type, of capacity ETC 500, Model GGES, ETC Tubes of Dia. 58 mm x L 2100 mm 32 Nos. per system Supporting stands & accessories. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | DUSHANT.GORE | 17 Jun 2024
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Ball Valve 32mm (L) | No. | 20 | 300 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of NRV 15mm (L) | No. | 140 | 300 | 42000 | 7560 | 49560 | 2.5 | 0 | 0 | 0 | 0 | 140 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Ball Valve 15mm (L) | No. | 150 | 160 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-2025) (L) | Mtrs | 370 | 80 | 29600 | 5328 | 34928 | 2.5 | 0 | 0 | 0 | 0 | 370 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Solar water heating system ETC500 (L) | No. | 24 | 3500 | 84000 | 15120 | 99120 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Pressure reducing valve (L) | No. | 20 | 680 | 13600 | 2448 | 16048 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Spring NRV 25mm (L) | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Ball Valve 20mm (L) | No. | 54 | 140 | 7560 | 1360.8 | 8920.8 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-1620) (L) | Mtrs | 110 | 80 | 8800 | 1584 | 10384 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of GI Air Pipe 15mm(L) | No. | 70 | 500 | 35000 | 6300 | 41300 | 2.5 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-2532) (L) | Mtrs | 420 | 80 | 33600 | 6048 | 39648 | 2.5 | 0 | 0 | 0 | 0 | 420 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Composite Pipe (Size-1216) (L) | Mtrs | 290 | 80 | 23200 | 4176 | 27376 | 2.5 | 0 | 0 | 0 | 0 | 290 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Pressure Relief Valve 15mm(L) | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation NRV 32mm (L) | No. | 10 | 400 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of Air Vent15mm (L) | No. | 4 | 300 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Solar water heating system1500LPD (L) | No. | 4 | 10500 | 42000 | 7560 | 49560 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 | Supporting stands for Solar Hot Water Tank & Solar Collectors | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 996 | 0 | 25 May 2024 | SARV ENTERPRISES | D-Solar Water Heating System | Installation of MS Fabricated Support (L) | Kgs | 179.9 | 20 | 3598 | 647.64 | 4245.64 | 2.5 | 0 | 0 | 0 | 0 | 179.9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of GI Air Pipe 15mm(L) | No. | 70 | 500 | 35000 | 6300 | 41300 | 2.5 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-1620) (L) | Mtrs | 110 | 80 | 8800 | 1584 | 10384 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation NRV 32mm (L) | No. | 10 | 400 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Air Vent15mm (L) | No. | 4 | 300 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Solar water heating system ETC500 (L) | No. | 24 | 3500 | 84000 | 15120 | 99120 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Pressure reducing valve (L) | No. | 20 | 680 | 13600 | 2448 | 16048 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-2025) (L) | Mtrs | 370 | 80 | 29600 | 5328 | 34928 | 2.5 | 0 | 0 | 0 | 0 | 370 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Pressure Relief Valve 15mm(L) | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Ball Valve 32mm (L) | No. | 20 | 300 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of NRV 15mm (L) | No. | 140 | 300 | 42000 | 7560 | 49560 | 2.5 | 0 | 0 | 0 | 0 | 140 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Ball Valve 15mm (L) | No. | 150 | 160 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 150 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-1216) (L) | Mtrs | 290 | 80 | 23200 | 4176 | 27376 | 2.5 | 0 | 0 | 0 | 0 | 290 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Composite Pipe (Size-2532) (L) | Mtrs | 420 | 80 | 33600 | 6048 | 39648 | 2.5 | 0 | 0 | 0 | 0 | 420 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of MS Fabricated Support (L) | Kgs | 179.9 | 20 | 3598 | 647.64 | 4245.64 | 2.5 | 0 | 0 | 0 | 0 | 179.9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Solar water heating system1500LPD (L) | No. | 4 | 10500 | 42000 | 7560 | 49560 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 | Supporting stands for Solar Hot Water Tank & Solar Collectors | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Ball Valve 20mm (L) | No. | 54 | 140 | 7560 | 1360.8 | 8920.8 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 997 | 0 | 25 May 2024 | SARV ENTERPRISES | E -Solar Water Heating System | Installation of Spring NRV 25mm (L) | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1000 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (L) - Mtrs | Mtrs | 120 | 42 | 5040 | 907.2 | 5947.2 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1000 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (L) | No. | 1 | 6045 | 6045 | 1088.1 | 7133.1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Booster Pump 12.5 HP.Brand- CRI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1000 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | Electrical Starter (L) | No. | 1 | 2325 | 2325 | 418.5 | 2743.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1001 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | Electrical Starter (M) | No. | 1 | 9765 | 9765 | 1757.7 | 11522.7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1001 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (M) | No. | 1 | 63705 | 63705 | 11466.9 | 75171.9 | 0 | 0.7 | 44593.5 | 8026.84 | 52620.34 | 0.3 | 22551.56 | Booster Pump 12.5 HP.Brand- CRI | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1001 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (M) - Mtrs | Mtrs | 120 | 289 | 34680 | 6242.4 | 40922.4 | 0 | 70 | 20230 | 3641.4 | 23871.4 | 50 | 17051 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 58.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1002 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (L) - Mtrs | Mtrs | 120 | 42 | 5040 | 907.2 | 5947.2 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1002 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (L) | No. | 1 | 6045 | 6045 | 1088.1 | 7133.1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Booster Pump 12.5 HP.Brand- CRI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1002 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | Electrical Starter (L) | No. | 1 | 2325 | 2325 | 418.5 | 2743.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1003 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (M) | No. | 1 | 63705 | 63705 | 11466.9 | 75171.9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Booster Pump 12.5 HP.Brand- CRI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1003 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | Electrical Starter (M) | No. | 1 | 9765 | 9765 | 1757.7 | 11522.7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1003 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (M) - Mtrs | Mtrs | 120 | 289 | 34680 | 6242.4 | 40922.4 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1012 | 0 | 11 Jun 2024 | ANAND PUNDLIK JADHAV | Electricity Infrastructure | RMU Installation | No. | 1 | 65000 | 65000 | 0 | 65000 | 0 | 1 | 65000 | 0 | 65000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1026 | 0 | 25 Jun 2024 | UPRISEN CONSTRUCTION | Making of Foundation for D.G Set Near F Bldg. | Shuttering Work-Dev | Sq.m. | 18.6 | 550 | 10230 | 1841.4 | 12071.4 | 2.5 | 17.05 | 9377.5 | 1687.96 | 11065.46 | 1.55 | 1005.94 |  | 91.6667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Jul 2024 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1026 | 0 | 25 Jun 2024 | UPRISEN CONSTRUCTION | Making of Foundation for D.G Set Near F Bldg. | Concreting Work | Cu.Mtrs | 25.2 | 300 | 7560 | 1360.8 | 8920.8 | 2.5 | 23.1 | 6930 | 1247.4 | 8177.4 | 2.1 | 743.4 |  | 91.6667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Slab | Sq.Ft | 140.1 | 200 | 28020 | 5043.6 | 33063.6 | 2.5 | 0 | 0 | 0 | 0 | 140.1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | PCC Work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 26 Jun 2024 |  | 02 RCC WORK | Cancelled | MONALI CHAUDHAR | 26 Jun 2024
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Work - Mkt | Sq.Ft | 434.7 | 160 | 69552 | 12519.36 | 82071.36 | 2.5 | 0 | 0 | 0 | 0 | 434.7 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | PCC Work | Sq.Ft | 67.79 | 10 | 677.9 | 122.02 | 799.92 | 2.5 | 0 | 0 | 0 | 0 | 67.79 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Retaining Wall - Dld | Sq.Ft | 79.62 | 160 | 12739.2 | 2293.06 | 15032.26 | 2.5 | 0 | 0 | 0 | 0 | 79.62 | 0 | Including Reinforcement, Shuttering & Casting | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Retaining Wall - Dld | Sq.Ft | 385.1 | 160 | 61616 | 11090.88 | 72706.88 | 2.5 | 0 | 0 | 0 | 0 | 385.1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Beam - BRE | R.Ft | 92 | 250 | 23000 | 4140 | 27140 | 2.5 | 0 | 0 | 0 | 0 | 92 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Raft -UWT | Sq.Ft | 49.07 | 120 | 5888.4 | 1059.92 | 6948.32 | 2.5 | 0 | 0 | 0 | 0 | 49.07 | 0 | Including Reinforcement, Shuttering & Casting | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1037 | 0 | 03 Jul 2024 | TEJASHREE ENTERPRISES | OWC Unit-Internal Painting Work-Ceiling | 2 Coat Primer (L) | Sq.Ft | 2935.01 | 2 | 5870.02 | 1056.6 | 6926.62 | 2.5 | 0 | 0 | 0 | 0 | 2935.01 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1037 | 0 | 03 Jul 2024 | TEJASHREE ENTERPRISES | OWC Unit-Internal Painting Work-Walls | 2 Coat Primer (L) | Sq.Ft | 2805.42 | 2 | 5610.84 | 1009.96 | 6620.8 | 2.5 | 0 | 0 | 0 | 0 | 2805.42 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1038 | 0 | 03 Jul 2024 | TEJASHREE ENTERPRISES | OWC Unit-Internal Painting Work-Walls | 2 Coat Primer (M) | Sq.Ft | 2805.42 | 2 | 5610.84 | 1009.96 | 6620.8 | 0 | 0 | 0 | 0 | 0 | 2805.42 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Jul 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1038 | 0 | 03 Jul 2024 | TEJASHREE ENTERPRISES | OWC Unit-Internal Painting Work-Ceiling | 2 Coat Primer (M) | Sq.Ft | 2935.01 | 2 | 5870.02 | 1056.6 | 6926.62 | 0 | 0 | 0 | 0 | 0 | 2935.01 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Jul 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1044 | 0 | 06 Jul 2024 | UPRISEN CONSTRUCTION | Pumproom UGWT D&E Foundation work for Fire Pump | Concrete - M25 | Cu.Mtrs | 3.4 | 300 | 1020 | 183.6 | 1203.6 | 2.5 | 0 | 0 | 0 | 0 | 3.4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 12 Jul 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1044 | 0 | 06 Jul 2024 | UPRISEN CONSTRUCTION | Pumproom UGWT D&E Foundation work for Fire Pump | Shuttering Work-Dev | Sq.m. | 14.77 | 500 | 7385 | 1329.3 | 8714.3 | 2.5 | 0 | 0 | 0 | 0 | 14.77 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 12 Jul 2024 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1048 | 0 | 06 Jul 2024 | SAI PLUMBING WORKS | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 12" RCC Pipe Laying-USL | R.Ft | 422.75 | 30 | 12682.5 | 2282.86 | 14965.36 | 2.5 | 391.9696 | 11759.09 | 2116.64 | 13875.73 | 30.7804 | 1089.63 |  | 92.719 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Strom Line | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1048 | 0 | 06 Jul 2024 | SAI PLUMBING WORKS | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | Chamber 24" x 24" (3ft Ht) USL | No. | 10 | 2100 | 21000 | 3780 | 24780 | 2.5 | 3 | 6300 | 1134 | 7434 | 7 | 17346 |  | 30 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. S.T.P | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1048 | 0 | 06 Jul 2024 | SAI PLUMBING WORKS | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | Chamber 36" x 18" (3ft Ht) - UDR | No. | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | UTI. Drainage | Cancelled | MONALI CHAUDHAR | 09 Jul 2024
GANGA ALTUS | 1048 | 0 | 06 Jul 2024 | SAI PLUMBING WORKS | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | Chamber 36" x 18" (3ft Ht) - UDR | No. | 9 | 2200 | 19800 | 3564 | 23364 | 2.5 | 2 | 4400 | 792 | 5192 | 7 | 18172 |  | 22.2222 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1048 | 0 | 06 Jul 2024 | SAI PLUMBING WORKS | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | Chamber 48" x 48" (5ft Ht) - UTI | No. | 6 | 4000 | 24000 | 4320 | 28320 | 2.5 | 3 | 12000 | 2160 | 14160 | 3 | 14160 |  | 50 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1048 | 0 | 06 Jul 2024 | SAI PLUMBING WORKS | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | Chamber 24" x 24" (3ft Ht) USL | No. | 0 | 2300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | UTI. S.T.P | Cancelled | MONALI CHAUDHAR | 09 Jul 2024
GANGA ALTUS | 1057 | 0 | 19 Jul 2024 | TEJASHREE ENTERPRISES | Transformer Room-MS Rolling Shutter Painting Work | 2 Coat oil Paint (L) | Sq.Ft | 1222.53 | 5 | 6112.65 | 1100.28 | 7212.93 | 2.5 | 0 | 0 | 0 | 0 | 1222.53 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1057 | 0 | 19 Jul 2024 | TEJASHREE ENTERPRISES | OWC Unit-MS Rolling Shutter Painting Work | 2 Coat oil Paint (L) | Sq.Ft | 325.93 | 5 | 1629.65 | 293.34 | 1922.99 | 2.5 | 0 | 0 | 0 | 0 | 325.93 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1057 | 0 | 19 Jul 2024 | TEJASHREE ENTERPRISES | STP-45KLD,ETP-15KLD-MS Rolling Shutter Painting Work | 2 Coat oil Paint (L) | Sq.Ft | 229.04 | 5 | 1145.2 | 206.14 | 1351.34 | 2.5 | 0 | 0 | 0 | 0 | 229.04 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1058 | 0 | 19 Jul 2024 | TEJASHREE ENTERPRISES | OWC Unit-MS Rolling Shutter Painting Work | 2 Coat oil paint (M) | Sq.Ft | 325.93 | 5 | 1629.65 | 293.34 | 1922.99 | 0 | 0 | 0 | 0 | 0 | 325.93 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1058 | 0 | 19 Jul 2024 | TEJASHREE ENTERPRISES | STP-45KLD,ETP-15KLD-MS Rolling Shutter Painting Work | 2 Coat oil paint (M) | Sq.Ft | 229.04 | 5 | 1145.2 | 206.14 | 1351.34 | 0 | 0 | 0 | 0 | 0 | 229.04 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1058 | 0 | 19 Jul 2024 | TEJASHREE ENTERPRISES | Transformer Room-MS Rolling Shutter Painting Work | 2 Coat oil paint (M) | Sq.Ft | 1222.53 | 5 | 6112.65 | 1100.28 | 7212.93 | 0 | 0 | 0 | 0 | 0 | 1222.53 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01