## Project_Work_Order6385872213506
Project Work Order
From 01 Jan 2000 To 31 Jul 2024
Page 1 of 1
Total Records: 425 Records 1 To 425
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 21 | 2 | 13 Mar 2020 | SS ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 862.06 | 225 | 193963.5 | 34913.44 | 228876.94 | 0 | 862.06 | 193963.5 | 34913.44 | 228876.94 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 77.17 | 225 | 17363.25 | 3125.38 | 20488.63 | 0 | 77.17 | 17363.25 | 3125.38 | 20488.63 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | SKMISHRA | 11 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 16 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 13 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 16 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | SKMISHRA | 11 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 244.63 | 225 | 55041.75 | 9907.52 | 64949.27 | 0 | 244.63 | 55041.75 | 9907.52 | 64949.27 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ALTUS | 21 | 0 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SHUBHAM GIRI |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 03 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 13 Jun 2020
GANGA ALTUS | 21 | 0 | 13 Mar 2020 | SS ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SHUBHAM GIRI |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 03 Jun 2020
GANGA ALTUS | 21 | 2 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 1398.52 | 225 | 314667 | 56640.06 | 371307.06 | 0 | 1398.52 | 314667 | 56640.06 | 371307.06 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 13 Jun 2020
GANGA ALTUS | 21 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 210.43 | 75 | 15782.25 | 2840.8 | 18623.05 | 0 | 210.1467 | 15761 | 2836.98 | 18597.98 | 0.2833 | 25.07 |  | 99.8654 |  | chetan | chetan | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ALTUS | 22 | 1 | 13 Mar 2020 | SS ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 03 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 03 Jun 2020
GANGA ALTUS | 39 | 0 | 11 Jun 2020 | VARSHA ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 13 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 16 Jun 2020
GANGA ALTUS | 39 | 0 | 11 Jun 2020 | VARSHA ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 13 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 13 Jun 2020
GANGA ALTUS | 39 | 0 | 11 Jun 2020 | VARSHA ENTERPRISES | Driveway & Ramp Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 297.84 | 225 | 67014 | 12062.52 | 79076.52 | 0 | 297.84 | 67014 | 12062.52 | 79076.52 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 13 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ALTUS | 39 | 0 | 11 Jun 2020 | VARSHA ENTERPRISES | Podium Excavation, Shifting, Levelling | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 13 Jun 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 13 Jun 2020
GANGA ALTUS | 50 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | Planter Brickwork & Plaster | Brickwork 6" -DLd | Sq.Ft | 147 | 12 | 1764 | 0 | 1764 | 2.5 | 147 | 1764 | 0 | 1764 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 17 Aug 2020 |  | DEV. Landscape/Equipment | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 50 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | Planter Brickwork & Plaster | Sand Face Plaster DLd | Sq.Ft | 220 | 12 | 2640 | 0 | 2640 | 2.5 | 220 | 2640 | 0 | 2640 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 17 Aug 2020 |  | DEV. Landscape/Equipment | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 50 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | Paving Block fixing near Main Gate | Paving Block Fixing -DTR- (L) | Sq.Ft | 12 | 10 | 120 | 0 | 120 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | GANDHI | chetan | construction open | 17 Aug 2020 |  | DEV. Trimix Road | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 50 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | Paving Block fixing near Main Gate | Paving Block Fixing -DTR- (L) | Sq.Ft | 45 | 10 | 450 | 0 | 450 | 2.5 | 0 | 0 | 0 | 0 | 45 | 0 |  | 0 |  | GANDHI | chetan | construction open | 17 Aug 2020 |  | DEV. Trimix Road | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 50 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | Pathway Kerb stone fixing | Kerb stone fixing - Dld | R.Ft | 27 | 25 | 675 | 0 | 675 | 2.5 | 27 | 675 | 0 | 675 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 17 Aug 2020 |  | DEV. Landscape/Equipment | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 50 | 0 | 28 Jul 2020 | SURESH KUMAR MURALIDHAR | Pathway Plaster near main gate | Sand Face Plaster - Mkt | Sq.Ft | 12 | 10 | 120 | 0 | 120 | 2.5 | 12 | 120 | 0 | 120 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 17 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | GANDHI | 28 Jul 2020
GANGA ALTUS | 102 | 0 | 26 Sep 2020 | AMFEW AND CO | Eshan Tower AC Work | Lumpsum work- DCW | No. | 1 | 6450 | 6450 | 1161 | 7611 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | DEV. Compound Wall | Un-Approved |  | 1900-01-01
GANGA ALTUS | 102 | 0 | 26 Sep 2020 | AMFEW AND CO | Eshan Tower AC Work | Lumpsum work- DCW | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | DEV. Compound Wall | Un-Approved |  | 1900-01-01
GANGA ALTUS | 141 | 0 | 17 Feb 2021 | SS ENTERPRISES | Substructure Road Murum filling work | Spreading & Levelling Work | Cu.Mtrs | 5924.36 | 15 | 88865.4 | 15995.78 | 104861.18 | 0 | 5863.3333 | 87950 | 5751 | 93701 | 61.0267 | 11160.18 |  | 98.9699 |  | tausif | tausif | construction open | 24 Feb 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ALTUS | 141 | 0 | 17 Feb 2021 | SS ENTERPRISES | Substructure Road Murum filling work | Murum Filling-DLD | Cu.Mtrs | 5924.36 | 60 | 355461.6 | 63983.08 | 419444.68 | 0 | 4213.33 | 252799.8 | 23004 | 275803.8 | 1711.03 | 143640.88 |  | 71.1187 |  | tausif | tausif | construction open | 24 Feb 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ALTUS | 141 | 0 | 17 Feb 2021 | SS ENTERPRISES | Substructure Road Murum filling work | Murum Filling (with avail earth - Dev | Cu.Ft | 0 | 2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Feb 2021 |  | DEV. Murum Filling | Cancelled | tausif | 24 Feb 2021
GANGA ALTUS | 204 | 1 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road Bldg D to F Shops & Gate- front area road work | Dressing & Levelling Rate Diff. -DTR | Sq.Ft | 10308 | 2.5 | 25770 | 4638.6 | 30408.6 | 0 | 8570 | 21425 | 3856.5 | 25281.5 | 1738 | 5127.1 | Rate Difference. | 83.1393 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | DEV. Trimix Road | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 204 | 0 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road Bldg D to F Shops & Gate- front area road work | Levelling, Dressing- DR | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | DEV. Ramp | Cancelled | tausif | 26 May 2021
GANGA ALTUS | 204 | 2 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | Groove Cutting & Bituminous filling | Mtrs | 117.89 | 40 | 4715.6 | 848.8 | 5564.4 | 2.5 | 97.2 | 3888 | 699.84 | 4587.84 | 20.69 | 976.56 |  | 82.4497 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 204 | 2 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | Groove Cutting & Bituminous filling | Mtrs | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | B.C. RCC Substructure | Cancelled | Dushant Gore | 20 May 2022
GANGA ALTUS | 204 | 0 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road Bldg D to F Shops & Gate- front area road work | Compaction - DER | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | DEV. Extrawork/Rework | Cancelled | tausif | 26 May 2021
GANGA ALTUS | 204 | 2 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | Dressing,Levelling, Watering & Rolling | Sq.Ft | 4075.49 | 2.75 | 11207.6 | 2017.36 | 13224.96 | 0 | 2542.1818 | 6991 | 1258.38 | 8249.38 | 1533.3082 | 4975.58 |  | 62.3773 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 204 | 0 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road Bldg D to F Shops & Gate- front area road work | Trimix Work-SO | Sq.Ft | 10308 | 10 | 103080 | 18554.4 | 121634.4 | 0 | 9609 | 96090 | 17296.2 | 113386.2 | 699 | 8248.2 |  | 93.2189 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 204 | 0 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road Bldg D to F Shops & Gate- front area road work | Levelling, Dressing- DR | Sq.Ft | 10308 | 2.5 | 25770 | 4638.6 | 30408.6 | 0 | 10308 | 25770 | 4638.6 | 30408.6 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | DEV. Ramp | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 204 | 0 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road Bldg D to F Shops & Gate- front area road work | Groove Cutting & Bituminous filling | Mtrs | 253 | 40 | 10120 | 1821.6 | 11941.6 | 0 | 252.875 | 10115 | 1820.7 | 11935.7 | 0.125 | 5.9 |  | 99.9506 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ALTUS | 204 | 3 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Betn Podium,E-Bldg Grid Slab-Trimix Road Groove Cutting & Fi | Groove Cutting & Bitumen Filling -DTR - | Mtrs | 194.62 | 40 | 7784.8 | 1401.26 | 9186.06 | 2.5 | 0 | 0 | 0 | 0 | 194.62 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 204 | 2 | 20 May 2021 | JAI SAIRAM CONSTRUCTION | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | Trimix Work | Sq.Ft | 4075.49 | 10 | 40754.9 | 7335.88 | 48090.78 | 2.5 | 2542 | 25420 | 4575.6 | 29995.6 | 1533.49 | 18095.18 |  | 62.3729 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 262 | 0 | 08 Sep 2021 | S S ENTERISES (PROP. SOBRAN SINGH) | Well- Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 271 | 15 | 4065 | 731.7 | 4796.7 | 0 | 271 | 4065 | 731.7 | 4796.7 | 0 | 0 |  | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 09 Sep 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 262 | 0 | 08 Sep 2021 | S S ENTERISES (PROP. SOBRAN SINGH) | Well- Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 271 | 60 | 16260 | 2926.8 | 19186.8 | 0 | 271 | 16260 | 2926.8 | 19186.8 | 0 | 0 | Ensuring all required safety precautions e.g. shoring and struting. (O.G.L & Excavated R.L. to be maintened properly) | 100 |  | Runal Kindalkar | chetan.jewalikar | construction open | 09 Sep 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 263 | 0 | 14 Sep 2021 | VNE INFRA PROJECTS P LTD | Well RCC Work | Labour Lumpsum-cc | No. | 0 | 250000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 14 Sep 2021 |  | B.C. Customer Changes | Cancelled | skmishra | 14 Sep 2021
GANGA ALTUS | 263 | 0 | 14 Sep 2021 | VNE INFRA PROJECTS P LTD | Well RCC Work | Labour Lumpsum-cc | No. | 1 | 250000 | 250000 | 45000 | 295000 | 2.5 | 1 | 250000 | 45000 | 295000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 14 Sep 2021 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 271 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Fabrication work (L) | Kgs | 1394.4 | 17 | 23704.8 | 4266.86 | 27971.66 | 2.5 | 1394.4 | 23704.8 | 4266.86 | 27971.66 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 271 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Fabrication work (L) | Kgs | 710.24 | 17 | 12074.08 | 2173.34 | 14247.42 | 2.5 | 710.24 | 12074.08 | 2173.34 | 14247.42 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 271 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Fabrication work (L) | Kgs | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | skmishra | 25 Sep 2021
GANGA ALTUS | 271 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Deck Sheet Fixing | Sq.Ft | 500 | 7 | 3500 | 630 | 4130 | 2.5 | 500 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | UTI. U.G.W.T | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 271 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Crane Charges - | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 272 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Fabrication work (M) | Kgs | 1394.4 | 55 | 76692 | 13804.56 | 90496.56 | 0 | 1394.4 | 76692 | 13804.56 | 90496.56 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 272 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Fabrication work (M) | Kgs | 710.24 | 55 | 39063.2 | 7031.38 | 46094.58 | 0 | 710.24 | 39063.2 | 7031.38 | 46094.58 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 272 | 0 | 25 Sep 2021 | R.T.S. STEEL SERVICES | Well Top Slab Fabrication Work | Fabrication work (M) | Kgs | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | skmishra | 25 Sep 2021
GANGA ALTUS | 295 | 0 | 08 Dec 2021 | RAJSAN ENTERPRISES | Goel House Rennovation New Extension-Roofing Work | Tensile Canopy | Sq.Ft | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jewalikar |  | Construction | 28 Mar 2022 |  | DEV. Swimming Pool | Cancelled | skmishra | 28 Mar 2022
GANGA ALTUS | 296 | 0 | 08 Dec 2021 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation New window-Extension work | Partly fix/openable window | Sq.Ft | 144.83 | 145.5 | 21072.77 | 3793.1 | 24865.87 | 0 | 144.83 | 21072.77 | 3793.1 | 24865.87 | 0 | 0 |  | 100 |  | chetan.jewalikar | Swapnil Erande | Construction | 08 Apr 2024 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 296 | 0 | 08 Dec 2021 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation New window-Extension work | Aluminium Sliding Window (L) | Sq.Ft | 272.69 | 97 | 26450.93 | 4761.16 | 31212.09 | 0 | 272.69 | 26450.93 | 4761.16 | 31212.09 | 0 | 0 |  | 100 |  | chetan.jewalikar | Swapnil Erande | Construction | 08 Apr 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 296 | 0 | 08 Dec 2021 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation New window-Extension work | Partition Work | Sq.Ft | 570.92 | 145.5 | 83068.86 | 14952.4 | 98021.26 | 0 | 570.92 | 83068.86 | 14952.4 | 98021.26 | 0 | 0 |  | 100 |  | chetan.jewalikar | Swapnil Erande | Construction | 08 Apr 2024 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 297 | 0 | 09 Dec 2021 | GREENCON INFRATECH SOLUTION | Goel House Rennovation Aerocon Panel work | Aerocon Partition (M+L) BC | Sq.Ft | 864 | 150 | 129600 | 23328 | 152928 | 0 | 864 | 129600 | 23328 | 152928 | 0 | 0 |  | 100 |  | runal kindalkar | chetan.jewalikar | Construction | 13 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 297 | 0 | 09 Dec 2021 | GREENCON INFRATECH SOLUTION | Goel House Rennovation Aerocon Panel work | Aerocon Partition (M+L) BC | Sq.Ft | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | RUNAL KINDALKAR |  | Construction | 13 Dec 2021 |  | B.C. Internal Finishing Itmes | Cancelled | runal kindalkar | 13 Dec 2021
GANGA ALTUS | 307 | 0 | 09 Dec 2021 | JAI SAIRAM CONSTRUCTION | Road Rolling in front of D,E,podium,F-shops | Roller- BC | Day | 4 | 4000 | 16000 | 2880 | 18880 | 0 | 4 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 309 | 0 | 09 Dec 2021 | SS ENTERPRISES | Well side back filling work | Spreading & Levelling Work | Cu.Mtrs | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 10 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | Avinash Padmanabha | 10 Dec 2021
GANGA ALTUS | 309 | 0 | 09 Dec 2021 | SS ENTERPRISES | Well side back filling work | Spreading & Levelling Work | Cu.Mtrs | 244 | 15 | 3660 | 658.8 | 4318.8 | 0 | 244 | 3660 | 658.8 | 4318.8 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 10 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 309 | 0 | 09 Dec 2021 | SS ENTERPRISES | Well side back filling work | Murum Shifting work | Cu.Mtrs | 244 | 60 | 14640 | 2635.2 | 17275.2 | 0 | 244 | 14640 | 2635.2 | 17275.2 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 10 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 316 | 0 | 10 Dec 2021 | SS ENTERPRISES | Compound wall excavation work | Backfilling | Cu.Mtrs | 1136.17 | 60 | 68170.2 | 12270.64 | 80440.84 | 0 | 1136.1667 | 68170 | 6474.78 | 74644.78 | 0.0033 | 5796.06 |  | 99.9997 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 316 | 1 | 10 Dec 2021 | SS ENTERPRISES | Amenity Plot Excavation Murum, Levelling,& Dressing Work | Murum Shifting, Levelling, Compaction | Cu.Mtrs | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 27 Aug 2022
GANGA ALTUS | 316 | 1 | 10 Dec 2021 | SS ENTERPRISES | Amenity Plot Excavation Murum, Levelling,& Dressing Work | Murum Shifting, Levelling, Compaction | Cu.Mtrs | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 27 Aug 2022
GANGA ALTUS | 316 | 0 | 10 Dec 2021 | SS ENTERPRISES | Compound wall excavation work | Spreading & Levelling Work | Cu.Mtrs | 1234.08 | 15 | 18511.2 | 3332.02 | 21843.22 | 0 | 0 | 0 | 0 | 0 | 1234.08 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 316 | 1 | 10 Dec 2021 | SS ENTERPRISES | Amenity Plot Excavation Murum, Levelling,& Dressing Work | Murum Dressing & Levelling - Cu.Mtrs | Cu.Mtrs | 1228 | 15 | 18420 | 3315.6 | 21735.6 | 0 | 1228 | 18420 | 0 | 18420 | 0 | 3315.6 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 316 | 0 | 10 Dec 2021 | SS ENTERPRISES | Compound wall excavation work | Spreading & Levelling Work | Cu.Mtrs | 1136.17 | 15 | 17042.55 | 3067.66 | 20110.21 | 0 | 0 | 0 | 0 | 0 | 1136.17 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 316 | 0 | 10 Dec 2021 | SS ENTERPRISES | Compound wall excavation work | Excavation work-SO | Cu.Mtrs | 1234.08 | 60 | 74044.8 | 13328.06 | 87372.86 | 0 | 1234 | 74040 | 12009.6 | 86049.6 | 0.08 | 1323.26 |  | 99.9935 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 324 | 0 | 17 Dec 2021 | MMAK PROPERTY MANAGEMENT SERVICES | Goel House Housekeeping Work | Housekeeping Work- | Day | 90 | 466.67 | 42000.3 | 7560.06 | 49560.36 | 0 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 17 Dec 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 324 | 0 | 17 Dec 2021 | MMAK PROPERTY MANAGEMENT SERVICES | Goel House Housekeeping Work | Housekeeping Work- | Day | 90 | 466.67 | 42000.3 | 7560.06 | 49560.36 | 0 | 88.0001 | 41067.01 | 7392.06 | 48459.07 | 1.9999 | 1101.29 |  | 97.7779 |  | chetan.jewalikar | chetan.jewalikar | construction open | 17 Dec 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 324 | 0 | 17 Dec 2021 | MMAK PROPERTY MANAGEMENT SERVICES | Goel House Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 78.0009 | 35225.99 | 6340.68 | 41566.67 | 14.9991 | 7993.02 |  | 83.8719 |  | chetan.jewalikar | chetan.jewalikar | construction open | 17 Dec 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 324 | 0 | 17 Dec 2021 | MMAK PROPERTY MANAGEMENT SERVICES | Goel House Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 0 | 0 | 0 | 0 | 93 | 0 |  | 0 |  | chetan.jewalikar | chetan.jewalikar | construction open | 17 Dec 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | Shuttering Work-Dev | Sq.m. | 723.01 | 500 | 361505 | 65070.9 | 426575.9 | 0 | 544.756 | 272378 | 39110.04 | 311488.04 | 178.254 | 115087.86 |  | 75.3456 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | Reinforcement- Ded | Kgs | 526 | 8 | 4208 | 757.44 | 4965.44 | 0 | 345 | 2760 | 496.8 | 3256.8 | 181 | 1708.64 |  | 65.5894 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Ext Development | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | Reinforcement- Ded | Kgs | 10907 | 8 | 87256 | 15706.08 | 102962.08 | 0 | 7281 | 58248 | 8478.72 | 66726.72 | 3626 | 36235.36 |  | 66.7553 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Ext Development | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | Shuttering Work-Dev | Sq.m. | 220.12 | 450 | 99054 | 17829.72 | 116883.72 | 0 | 108.7 | 48915 | 8804.7 | 57719.7 | 111.42 | 59164.02 |  | 49.3822 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | PCC Work.- | Cu.Mtrs | 6.99 | 300 | 2097 | 377.46 | 2474.46 | 0 | 5.7267 | 1718.01 | 309.24 | 2027.25 | 1.2633 | 447.21 |  | 81.927 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | Concreting Work | Cu.Mtrs | 93.01 | 300 | 27903 | 5022.54 | 32925.54 | 0 | 90.76 | 27228 | 4253.04 | 31481.04 | 2.25 | 1444.5 |  | 97.5809 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 326 | 0 | 23 Dec 2021 | VNE INFRA PROJECTS P LTD | RCC Work Compound wall RCC Work | Plum Concrete | Cu.Mtrs | 65.68 | 300 | 19704 | 3546.72 | 23250.72 | 0 | 33.76 | 10128 | 1823.04 | 11951.04 | 31.92 | 11299.68 |  | 51.4007 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 329 | 0 | 28 Dec 2021 | K RAMU RATHOD | Compound wall Brickwork,Plaster,Coping - (L) | External Plaster DEn- | Sq.Ft | 4112.39 | 28 | 115146.92 | 0 | 115146.92 | 2.5 | 3949 | 110572 | 0 | 110572 | 163.39 | 4574.92 |  | 96.0269 |  | Aniket Mohite | chetan.jewalikar | construction open | 28 Dec 2021 |  | DEV. Entrance Gate | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 329 | 1 | 28 Dec 2021 | K RAMU RATHOD | 4" Flyash brickwork & Plaster work infront of shop | Plaster Work - BRE | Sq.Ft | 594 | 15 | 8910 | 0 | 8910 | 2.5 | 475.2 | 7128 | 0 | 7128 | 118.8 | 1782 |  | 80 |  | Dushant Gore | Swapnil Erande | construction open | 28 Dec 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 329 | 0 | 28 Dec 2021 | K RAMU RATHOD | Compound wall Brickwork,Plaster,Coping - (L) | Brickwork 6" --DEn | Sq.Ft | 1724.55 | 18 | 31041.9 | 0 | 31041.9 | 2.5 | 1724 | 31032 | 0 | 31032 | 0.55 | 9.9 |  | 99.9681 |  | Aniket Mohite | chetan.jewalikar | construction open | 28 Dec 2021 |  | DEV. Entrance Gate | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 329 | 0 | 28 Dec 2021 | K RAMU RATHOD | Compound wall Brickwork,Plaster,Coping - (L) | Brickwork 6" --DEn | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 28 Dec 2021 |  | DEV. Entrance Gate | Cancelled | Aniket Mohite | 28 Dec 2021
GANGA ALTUS | 329 | 0 | 28 Dec 2021 | K RAMU RATHOD | Compound wall Brickwork,Plaster,Coping - (L) | Copping Work DCH | R.Ft | 318.49 | 12 | 3821.88 | 0 | 3821.88 | 2.5 | 275.5 | 3306 | 0 | 3306 | 42.99 | 515.88 |  | 86.5019 |  | Aniket Mohite | chetan.jewalikar | construction open | 28 Dec 2021 |  | DEV. Club House | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 329 | 1 | 28 Dec 2021 | K RAMU RATHOD | 4" Flyash brickwork & Plaster work infront of shop | Brickwork 4" - SO | Sq.Ft | 235.5 | 11 | 2590.5 | 0 | 2590.5 | 2.5 | 235.5 | 2590.5 | 0 | 2590.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 28 Dec 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 339 | 0 | 08 Jan 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Sliding Window Work | 3 Track Sliding Window | Sq.Ft | 0 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar |  | construction open | 15 Mar 2022 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 15 Mar 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | AC Installation & Commissioning (L) | No. | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | hard Copper 18 Guage Ref Piping (L) | Mtrs | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | AC Installation & Commissioning (L) | No. | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | SITC of Drain Pipe (L) | Mtrs | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 22 Guage Gi Ducting (L) | Sq.m. | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | M.S. Stand | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | B.C. Internal Finishing Itmes | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Nitrogen Pressure & Leak Testing (L) | No. | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Soft Copper 22 Guage Ref Piping (L) | Mtrs | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 2.5 Sqmm 4 Core Cable (L) | Mtrs | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 3C x 2.5sqmm (L) | Mtrs | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Canvas Connection (L) | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 340 | 0 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Thermal Insulation (L) | Sq.m. | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 22 Guage GI Ducting (M) | Sq.m. | 0 | 1010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 3C x 2.5sqmm (M) | Mtrs | 0 | 160.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | SITC of Drain Pipe (M) | Mtrs | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 2.5 Sqmm 4 Core Cable (M) | Mtrs | 0 | 119.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Canvas Connection (M) | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Soft Copper 22 Guage Ref Piping (M) | Mtrs | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Gas Charging (M). | Kgs | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Nitrogen Pressure & Leak Testing (M) | No. | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | M.S. Stand | No. | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Vaibhav Biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | B.C. Internal Finishing Itmes | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Thermal Insulation (M) | Sq.m. | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 341 | 1 | 11 Jan 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Hard Copper 18 Guage Ref Piping (M) | Mtrs | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar | Swapnil Erande | construction open | 10 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 12 Dec 2022
GANGA ALTUS | 342 | 1 | 12 Jan 2022 | PRAKASH CONTRACTOR | Goel House- New Extension work soling & PCC | Labour Lumpsum | No. | 1 | 65000 | 65000 | 0 | 65000 | 0 | 1 | 65000 | 0 | 65000 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 12 Jan 2022 |  | Land Cost | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 342 | 0 | 12 Jan 2022 | PRAKASH CONTRACTOR | Goel House Bedroom 4,5,6,7 Floor Breaking | Tile Removing work-BRE | No. | 1 | 65000 | 65000 | 0 | 65000 | 0 | 0.8 | 52000 | 0 | 52000 | 0.2 | 13000 |  | 80 |  | chetan.jewalikar | chetan.jewalikar | construction open | 12 Jan 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 343 | 0 | 12 Jan 2022 | KADAVATH VENKAT ENTERPRISES | Goel House Bedroom 5&4 Brickwork & Plaster | Labour Lumpsum - BC | No. | 1 | 150000 | 150000 | 0 | 150000 | 2.5 | 1 | 150000 | 0 | 150000 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 12 Jan 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ALTUS | 345 | 0 | 15 Jan 2022 | NISAR AHMAD ANSARI | Goel House- Bedroom 1 Ceiling Painting Work | Premium Emulsion - BRE | Sq.Ft | 219 | 18 | 3942 | 709.56 | 4651.56 | 2.5 | 0 | 0 | 0 | 0 | 219 | 0 |  | 0 |  | chetan.jewalikar |  | construction open | 15 Jan 2022 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ALTUS | 345 | 0 | 15 Jan 2022 | NISAR AHMAD ANSARI | Goel House- Bedroom 1 Ceiling Painting Work | Premium Emulsion - BRE | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 15 Jan 2022 |  | B.C. Rework/Extrawork | Cancelled | skmishra | 15 Jan 2022
GANGA ALTUS | 351 | 0 | 19 Jan 2022 | PRAKASH CONTRACTOR | Goel House Kitchen- PCC Work | PCC Work | Sq.Ft | 468 | 6 | 2808 | 0 | 2808 | 2.5 | 0 | 0 | 0 | 0 | 468 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 358 | 0 | 21 Jan 2022 | PRAKASH CONTRACTOR | Goel House Excavation & RCC Work | RCC Work lumpsum- SOS | No. | 1 | 12000 | 12000 | 0 | 12000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | DEV. Ext Development | Un-Approved |  | 1900-01-01
GANGA ALTUS | 363 | 2 | 24 Jan 2022 | SNEHA GARDEN DEVELOPERS | Divider Plantation Work(Main+Inside Road | Old Shrub removing & shifting | Sq.Ft | 10000 | 9 | 90000 | 16200 | 106200 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 363 | 2 | 24 Jan 2022 | SNEHA GARDEN DEVELOPERS | Divider Plantation Work(Main+Inside Road | Old Shrub removing & shifting | Sq.Ft | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 15 Feb 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 21 Nov 2023
GANGA ALTUS | 363 | 2 | 24 Jan 2022 | SNEHA GARDEN DEVELOPERS | Divider Plantation Work(Main+Inside Road | Bouganvelia -DRD | No. | 10000 | 50 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | DEV. Ext Development | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 363 | 1 | 24 Jan 2022 | SNEHA GARDEN DEVELOPERS | Plantation Work | Plantation Work | No. | 2300 | 9 | 20700 | 3726 | 24426 | 0 | 2300 | 20700 | 3726 | 24426 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 364 | 0 | 24 Jan 2022 | PRAKASH CONTRACTOR | Goel House Excavation,Soling and PCC Work | Labour Lumpsum - SOS | No. | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | S OH Infrastructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 385 | 1 | 21 Feb 2022 | DEEP MAN ENTERPRISES | D&E Bldg.Road-Bore drilling for Rainwater Harvesting work | PVC Casing Work - UTR | R.Ft | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 09 Mar 2022 |  | UTI. Rainwater harvesting | Cancelled | ADITYA.CHOUGULE | 14 Feb 2024
GANGA ALTUS | 385 | 1 | 21 Feb 2022 | DEEP MAN ENTERPRISES | D&E Bldg.Road-Bore drilling for Rainwater Harvesting work | Drilling Work (Rft) | R.Ft | 800 | 95 | 76000 | 0 | 76000 | 0 | 445 | 42275 | 7609.5 | 49884.5 | 355 | 26115.5 | 4Nos x 200 Ft.= 800 R.ft | 55.625 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 09 Mar 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 385 | 1 | 21 Feb 2022 | DEEP MAN ENTERPRISES | D&E Bldg.Road-Bore drilling for Rainwater Harvesting work | PVC Casing Work - UTR | R.Ft | 160 | 350 | 56000 | 0 | 56000 | 0 | 55 | 19250 | 3465 | 22715 | 105 | 33285 | 4Nos x 40 Ft.= 160 R.ft | 34.375 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 09 Mar 2022 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 385 | 1 | 21 Feb 2022 | DEEP MAN ENTERPRISES | D&E Bldg.Road-Bore drilling for Rainwater Harvesting work | Drilling Work (Rft) | R.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 09 Mar 2022 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 14 Feb 2024
GANGA ALTUS | 439 | 2 | 04 Jun 2022 | PAPPU BAGELA | D,E,F Bldg.Main Road-Paver Block Fixing | Paving Block Fixing - AIE | Sq.Ft | 3523.365 | 13 | 45803.75 | 0 | 45803.75 | 2.5 | 659.5105 | 8573.64 | 0 | 8573.64 | 2863.8545 | 37230.11 |  | 18.7182 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 439 | 1 | 04 Jun 2022 | PAPPU BAGELA | F Bldg.-Road Work-Paver Block Fixing | Paving block fixing - ULT | Sq.Ft | 925.704 | 10 | 9257.04 | 0 | 9257.04 | 2.5 | 925.704 | 9257.04 | 0 | 9257.04 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 08 Jun 2022 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 439 | 0 | 04 Jun 2022 | PAPPU BAGELA | Paving Block Fixing work-In front of shops | Paving Block Fixing - AIE | Sq.Ft | 1248 | 12 | 14976 | 2695.68 | 17671.68 | 2.5 | 0 | 0 | 0 | 0 | 1248 | 0 | D Building Front side shops to F Building Front Side Shops. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 451 | 0 | 28 Jun 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House 125KVA- Stalilizer | AMC Charges | Month | 0 | 1187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 28 Jun 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 28 Jun 2022
GANGA ALTUS | 451 | 0 | 28 Jun 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House 125KVA- Stalilizer | AMC Charges | Month | 12 | 1187.5 | 14250 | 2565 | 16815 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 28 Jun 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ALTUS | 468 | 0 | 06 Jul 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House 30 KVA -Online UPS System | AMC Charges | Month | 12 | 1218.75 | 14625 | 2632.5 | 17257.5 | 0 | 12 | 14625 | 2632.44 | 17257.44 | 0 | 0.06 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jul 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 469 | 0 | 06 Jul 2022 | TECHNOVISION ENERGY PVT.LTD. | AMC Charges for 125KVA Stabilizer | AMC Charges | Month | 12 | 1187.5 | 14250 | 2565 | 16815 | 0 | 12 | 14250 | 2564.98 | 16814.98 | 0 | 0.02 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jul 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 483 | 0 | 11 Jul 2022 | K RAMU RATHOD | Compound wall-9" brickwork,plaster,coping (L) | Brickwork 9" --DEn | Sq.Ft | 1419.72 | 18 | 25554.96 | 0 | 25554.96 | 2.5 | 576 | 10368 | 0 | 10368 | 843.72 | 15186.96 |  | 40.5714 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 483 | 0 | 11 Jul 2022 | K RAMU RATHOD | Compound wall-9" brickwork,plaster,coping (L) | Brick Pillar Work-SOf | R.Ft | 30.504 | 50 | 1525.2 | 0 | 1525.2 | 2.5 | 0 | 0 | 0 | 0 | 30.504 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 483 | 0 | 11 Jul 2022 | K RAMU RATHOD | Compound wall-9" brickwork,plaster,coping (L) | Coping Work -DCH | Sq.Ft | 288.41 | 10 | 2884.1 | 0 | 2884.1 | 2.5 | 0 | 0 | 0 | 0 | 288.41 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 483 | 0 | 11 Jul 2022 | K RAMU RATHOD | Compound wall-9" brickwork,plaster,coping (L) | External Plaster DEn- | Sq.Ft | 2971.94 | 20 | 59438.8 | 0 | 59438.8 | 2.5 | 0 | 0 | 0 | 0 | 2971.94 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 558 | 0 | 19 Oct 2022 | VECTOR SURVEYORS | Amenity Plot- Surveying Work by Total Station | Total Statiotn Survey | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Oct 2022 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 558 | 0 | 19 Oct 2022 | VECTOR SURVEYORS | Amenity Plot- Surveying Work by Total Station | Total Statiotn Survey | Day | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 19 Oct 2022 |  | Land Cost | Cancelled | Dushant Gore | 19 Oct 2022
GANGA ALTUS | 559 | 1 | 19 Oct 2022 | VECTOR SURVEYORS | Club House-Survey work by Total Station | Total Statiotn Survey | Day | 3 | 4500 | 13500 | 0 | 13500 | 0 | 3 | 13500 | 0 | 13500 | 0 | 0 | (Setting out-1 Day, Pile Making-1 Day, After Pile Casting Column Center-1 Day) | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Nov 2022 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 568 | 1 | 07 Nov 2022 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Rolling,Compaction,Levelling | Sq.Ft | 2761 | 4 | 11044 | 1987.92 | 13031.92 | 2.5 | 2761 | 11044 | 1987.92 | 13031.92 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Nov 2022 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 568 | 1 | 07 Nov 2022 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Dry Lean Concrete (L) | Sq.Ft | 0 | 5.11 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Nov 2022 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 568 | 1 | 07 Nov 2022 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Wet Mix Macadam (L) | Sq.Ft | 1200.9785 | 5.11 | 6137 | 1104.66 | 7241.66 | 2.5 | 1200.9785 | 6137 | 1104.66 | 7241.66 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Nov 2022 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 568 | 1 | 07 Nov 2022 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Pavement Quality Concrete (L) | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Nov 2022 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 568 | 0 | 07 Nov 2022 | AMAN ASSOCIATES | Kharadi DP Road Work Rate Difference | Rate Difference | No. | 1 | 2644988 | 2644988 | 476097.84 | 3121085.84 | 0 | 1 | 2644988 | 476097.84 | 3121085.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Dushant Gore | construction open | 07 Nov 2022 |  | No category | Approved | Dushant Gore | 1900-01-01
GANGA ALTUS | 568 | 1 | 07 Nov 2022 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | GSB 2nd Layer (L) | Sq.Ft | 2761.0568 | 5.11 | 14109 | 2539.62 | 16648.62 | 2.5 | 2761.0568 | 14109 | 2539.62 | 16648.62 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Nov 2022 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 568 | 1 | 07 Nov 2022 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | GSB 1st Layer (L) | Sq.Ft | 2761.0568 | 5.11 | 14109 | 2539.62 | 16648.62 | 2.5 | 2761.0568 | 14109 | 2539.62 | 16648.62 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Nov 2022 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 587 | 0 | 12 Dec 2022 | SHIVAM ENTERPRISES | Filling & Leveling for STP Access road | JCB Charges. | Day | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Dec 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 13 Dec 2022
GANGA ALTUS | 587 | 0 | 12 Dec 2022 | SHIVAM ENTERPRISES | Filling & Leveling for STP Access road | JCB Charges | Hrs | 16 | 850 | 13600 | 0 | 13600 | 0 | 16 | 13600 | 0 | 13600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Dec 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 587 | 1 | 12 Dec 2022 | SHIVAM ENTERPRISES | F Bldg.-Road Excavation Work | Excavation by Bucket | Cu.Mtrs | 647.79 | 60 | 38867.4 | 0 | 38867.4 | 0 | 647.79 | 38867.4 | 0 | 38867.4 | 0 | 0 | Excavation by Bucket & Shifting inside | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Dec 2022 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 587 | 1 | 12 Dec 2022 | SHIVAM ENTERPRISES | F Bldg.-Road Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 647.79 | 20 | 12955.8 | 0 | 12955.8 | 0 | 647.79 | 12955.8 | 0 | 12955.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Dec 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 594 | 1 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Zebra Crossing marking | Sq.m. | 161.71 | 580 | 93791.8 | 16882.52 | 110674.32 | 0 | 153.15 | 88827 | 15988.86 | 104815.86 | 8.56 | 5858.46 | 1.LOCATION- AMRUT GANGA CHOWK BEAUTIFICATION 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 94.7066 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 594 | 0 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Zebra Crossing marking | Sq.m. | 104 | 580 | 60320 | 10857.6 | 71177.6 | 0 | 104 | 60320 | 10857.6 | 71177.6 | 0 | 0 | 1.LOCATION- AMRUT GANGA CHOWK BEAUTIFICATION 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 594 | 0 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Yellow Box Marking | Sq.m. | 200 | 580 | 116000 | 20880 | 136880 | 0 | 200 | 116000 | 20880 | 136880 | 0 | 0 | 1.LOCATION- AMRUT GANGA CHOWK BEAUTIFICATION 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 594 | 1 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Yellow Box Marking | Sq.m. | 167.08 | 580 | 96906.4 | 17443.16 | 114349.56 | 0 | 167 | 96860 | 17434.8 | 114294.8 | 0.08 | 54.76 | 1.LOCATION- AMRUT GANGA CHOWK BEAUTIFICATION 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 99.9521 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 595 | 1 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Zebra Crossing marking | Sq.m. | 9.55 | 580 | 5539 | 997.02 | 6536.02 | 0 | 0 | 0 | 0 | 0 | 9.55 | 0 | 1.LOCATION- P.L. DESHPANDE GARDEN BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 595 | 0 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Yellow Box Marking | Sq.m. | 231 | 580 | 133980 | 24116.4 | 158096.4 | 0 | 231 | 133980 | 24116.4 | 158096.4 | 0 | 0 | 1.LOCATION- P.L. DESHPANDE GARDEN BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 595 | 0 | 19 Dec 2022 | AVS TRAFEIC SYSTEMS | Zebra Crossing & Yellow Box marking work | Zebra Crossing marking | Sq.m. | 116 | 580 | 67280 | 12110.4 | 79390.4 | 0 | 26.57 | 15410.6 | 2773.9 | 18184.5 | 89.43 | 61205.9 | 1.LOCATION- P.L. DESHPANDE GARDEN BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 22.9052 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 596 | 0 | 19 Dec 2022 | PRAKASH CONTRACTOR | Road Beautification - Civil work | Labour Lumpsum | No. | 1 | 55000 | 55000 | 0 | 55000 | 0 | 0.8691 | 47800.5 | 0 | 47800.5 | 0.1309 | 7199.5 | 1.LOCATION- P.L. DESHPANDE GARDEN BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 86.91 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 596 | 0 | 19 Dec 2022 | PRAKASH CONTRACTOR | Road Beautification - Civil work | Tractor Trip - DCW | Trips | 25 | 1000 | 25000 | 0 | 25000 | 0 | 9.2 | 9200 | 0 | 9200 | 15.8 | 15800 | 1.LOCATION- P.L. DESHPANDE GARDEN BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 36.8 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 597 | 0 | 19 Dec 2022 | LAXMI ELECTRICALS | Street Light Pole fixing work | 4C 6 sqmm Alu. Cable (L) | Mtrs | 150 | 40 | 6000 | 0 | 6000 | 2.5 | 20 | 800 | 0 | 800 | 130 | 5200 |  | 13.3333 |  | Dushant Gore | Swapnil Erande | construction open | 19 Dec 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 597 | 0 | 19 Dec 2022 | LAXMI ELECTRICALS | Street Light Pole fixing work | Street Light Pole fixing (L) | No. | 7 | 1000 | 7000 | 0 | 7000 | 2.5 | 7 | 7000 | 0 | 7000 | 0 | 0 | Safety of all workers, public & Vehicles is of contractors responsbility. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Dec 2022 |  | DEV. Street Lighting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 597 | 0 | 19 Dec 2022 | LAXMI ELECTRICALS | Street Light Pole fixing work | Street Light Foundation Work - DSL | No. | 7 | 1500 | 10500 | 1890 | 12390 | 2.5 | 7 | 10500 | 0 | 10500 | 0 | 1890 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Dec 2022 |  | DEV. Street Lighting | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 597 | 0 | 19 Dec 2022 | LAXMI ELECTRICALS | Street Light Pole fixing work | Labour Charges. | No. | 4 | 600 | 2400 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Safety of all workers, public & Vehicles is of contractors responsbility. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Dec 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 598 | 0 | 19 Dec 2022 | ABHISHREE LOGISTICS & SERVICES | Vertical Artificial Green Wall Work | Supply Vertical Green Wall | Sq.Ft | 2012.62 | 235 | 472965.7 | 85133.82 | 558099.52 | 0 | 2012.62 | 472965.7 | 85133.82 | 558099.52 | 0 | 0 | 1.LOCATION- WADGAON FLYOVER BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 598 | 0 | 19 Dec 2022 | ABHISHREE LOGISTICS & SERVICES | Vertical Artificial Green Wall Work | Installation Charges | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 | 1.LOCATION- WADGAON FLYOVER BEAUTIFICATION. 2.Safety of all workers, public & Vehicles is of contractors responsbility. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 07 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | Plantation Work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 14 Mar 2023
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ALTUS | 637 | 0 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 550 | 4400 | 0 | 4400 | 0 | 8 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 637 | 1 | 14 Mar 2023 | PRAKASH CONTRACTOR | P.L. Deshpande Garden Maintenance work | Male Coolie | No. | 8 | 650 | 5200 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 14 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 665 | 1 | 12 Apr 2023 | MASKE PILE FOUNDATION | Club House-Pile Steel Work | Reinforcement for Piling-BC | Mtrs | 256 | 200 | 51200 | 9216 | 60416 | 2.5 | 235.25 | 47050 | 8469 | 55519 | 20.75 | 4897 |  | 91.8945 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 665 | 1 | 12 Apr 2023 | MASKE PILE FOUNDATION | Club House-Pile Steel Work | Piling Work 500mm Dia. - ULT | Mtrs | 48 | 2400 | 115200 | 20736 | 135936 | 2.5 | 48 | 115200 | 20736 | 135936 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 665 | 1 | 12 Apr 2023 | MASKE PILE FOUNDATION | Club House-Pile Steel Work | Mobilisation - DEn | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 665 | 1 | 12 Apr 2023 | MASKE PILE FOUNDATION | Club House-Pile Steel Work | Pile Concreting Work | Mtrs | 256 | 200 | 51200 | 9216 | 60416 | 2.5 | 235.25 | 47050 | 8469 | 55519 | 20.75 | 4897 |  | 91.8945 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 665 | 1 | 12 Apr 2023 | MASKE PILE FOUNDATION | Club House-Pile Steel Work | Piling Work 500mm Dia. - ULT | Mtrs | 208 | 1600 | 332800 | 59904 | 392704 | 2.5 | 208 | 332800 | 59904 | 392704 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 751 | 0 | 03 Aug 2023 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Granular Sub Base (M) | Sq.Ft | 2760.9965 | 37.33 | 103068 | 18552.24 | 121620.24 | 0 | 2760.9965 | 103068 | 18552.24 | 121620.24 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 18 Aug 2023 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 751 | 0 | 03 Aug 2023 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Wet Mix Macadam (M) | Sq.Ft | 1201.0138 | 21.7 | 26062 | 4691.16 | 30753.16 | 0 | 1201.0138 | 26062 | 4691.16 | 30753.16 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 18 Aug 2023 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 751 | 0 | 03 Aug 2023 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Dry Lean Concrete (M) | Sq.Ft | 0 | 39.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 18 Aug 2023 |  | No category | Foreclose | DUSHANT.GORE | 06 Nov 2023
GANGA ALTUS | 772 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | M30 PQC (M) | Cu.Mtrs | 0 | 5432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Cancelled | DUSHANT.GORE | 07 Nov 2023
GANGA ALTUS | 772 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Dowel Bars (M) | No. | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Cancelled | DUSHANT.GORE | 07 Nov 2023
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | F-Bldg Side Road Work -PQC Road | Dowel Bars (L) | No. | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Cancelled | DUSHANT.GORE | 07 Nov 2023
GANGA ALTUS | 803 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (L) | Sq.Ft | 0 | 18.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 803 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (L) | Sq.Ft | 0 | 5.7 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 803 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ALTUS | 803 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 2nd Layer (L) | Sq.Ft | 0 | 3.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 803 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Wet Mix Macadam (L) | Sq.Ft | 0 | 4.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 803 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 1st Layer (L) | Sq.Ft | 0 | 3.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 804 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Granular Sub Base (M) | Sq.Ft | 0 | 42.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 804 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (M) | Sq.Ft | 0 | 32.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 804 | 0 | 04 Nov 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Wet Mix Macadam (M) | Sq.Ft | 0 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 25 May 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Pavement Quality Concrete (L) | Sq.Ft | 7159.78 | 18.75 | 134245.88 | 24164.26 | 158410.14 | 2.5 | 4053 | 75993.75 | 13678.88 | 89672.63 | 3106.78 | 68737.51 |  | 56.6079 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Dry Lean Concrete (L) | Sq.Ft | 7159.78 | 5.7 | 40810.75 | 7345.94 | 48156.69 | 2.5 | 5468 | 31167.6 | 5610.16 | 36777.76 | 1691.78 | 11378.93 |  | 76.3711 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Rolling,Compaction,Levelling | Sq.Ft | 4398.78 | 4 | 17595.12 | 3167.12 | 20762.24 | 2.5 | 2558 | 10232 | 1841.76 | 12073.76 | 1840.78 | 8688.48 |  | 58.1525 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | GSB 2nd Layer (L) | Sq.Ft | 4398.7232 | 3.75 | 16495.21 | 2969.14 | 19464.35 | 2.5 | 2558 | 9592.5 | 1726.66 | 11319.16 | 1840.7232 | 8145.19 |  | 58.1532 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Groove Cutting & Bitumen Filling -DTR - | Mtrs | 700 | 80 | 56000 | 10080 | 66080 | 2.5 | 0 | 0 | 0 | 0 | 700 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Trimix Road | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | GSB 1st Layer (L) | Sq.Ft | 4398.7232 | 3.75 | 16495.21 | 2969.14 | 19464.35 | 2.5 | 2558 | 9592.5 | 1726.66 | 11319.16 | 1840.7232 | 8145.19 |  | 58.1532 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 805 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Wet Mix Macadam (L) | Sq.Ft | 5958.8015 | 4.5 | 26814.61 | 4826.62 | 31641.23 | 2.5 | 5468 | 24606 | 4429.08 | 29035.08 | 490.8015 | 2606.15 |  | 91.7634 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 806 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | M25 PQC (M) | Sq.Ft | 7159.78 | 106.25 | 760726.63 | 136930.8 | 897657.43 | 0 | 4053 | 430631.25 | 77513.62 | 508144.87 | 3106.78 | 389512.56 |  | 56.6079 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 806 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Wet Mix Macadam (M) | Sq.Ft | 5958.7662 | 25.5 | 151948.54 | 27350.74 | 179299.28 | 0 | 5468 | 139434 | 25098.12 | 164532.12 | 490.7662 | 14767.16 |  | 91.764 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 806 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Dry Lean Concrete (M) | Sq.Ft | 7159.78 | 32.3 | 231260.89 | 41626.96 | 272887.85 | 0 | 5468 | 176616.4 | 31790.96 | 208407.36 | 1691.78 | 64480.49 |  | 76.3711 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 806 | 0 | 06 Nov 2023 | VIRAJ ENTERPRISES | F-Bldg Side Road Work -PQC Road | Granular Sub Base (M) | Sq.Ft | 4398.7835 | 42.5 | 186948.3 | 33650.7 | 220599 | 0 | 2558 | 108715 | 19568.7 | 128283.7 | 1840.7835 | 92315.3 |  | 58.1524 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 813 | 0 | 21 Nov 2023 | SNEHA GARDEN DEVELOPERS | Divider Plantation Work(Main+Inside Road | Old Shrub removing & shifting | Sq.Ft | 1000 | 9 | 9000 | 1620 | 10620 | 0 | 1000 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 813 | 0 | 21 Nov 2023 | SNEHA GARDEN DEVELOPERS | Divider Plantation Work(Main+Inside Road | Euphorbia Mili | No. | 1000 | 50 | 50000 | 9000 | 59000 | 0 | 1000 | 50000 | 9000 | 59000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 15 LANDSCAPE & GARDEN WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 821 | 0 | 24 Nov 2023 | SURESH RANGNATH SHITOLE | Removing of GI Sheet,Channels&Angle (Store&Steel Yard Area) | G.I. Sheet Removing - SOI | Sq.Ft | 1957.17 | 6 | 11743.02 | 0 | 11743.02 | 0 | 1448 | 8688 | 0 | 8688 | 509.17 | 3055.02 |  | 73.9844 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 822 | 0 | 24 Nov 2023 | SURESH RANGNATH SHITOLE | Removing & fixing of GI Sheet (Steel Yard & Store) | G.I. Sheet Removing - SOI | Sq.Ft | 8388.81 | 6 | 50332.86 | 0 | 50332.86 | 0 | 5072.3791 | 30434.27 | 0 | 30434.27 | 3316.4309 | 19898.59 |  | 60.466 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 822 | 1 | 24 Nov 2023 | SURESH RANGNATH SHITOLE | D,E,Podium Ramp Hand Barrication-No. | Baricating Removing Work(L) - SOSB | Kgs | 2171 | 6 | 13026 | 0 | 13026 | 0 | 0 | 0 | 0 | 0 | 2171 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 822 | 0 | 24 Nov 2023 | SURESH RANGNATH SHITOLE | Removing & fixing of GI Sheet (Steel Yard & Store) | G.I. Sheet Fixing - BC | Sq.Ft | 7144 | 13 | 92872 | 0 | 92872 | 2.5 | 2783.804 | 36189.45 | 0 | 36189.45 | 4360.196 | 56682.55 |  | 38.967 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 1900-01-01
GANGA ALTUS | 822 | 1 | 24 Nov 2023 | SURESH RANGNATH SHITOLE | D,E,Podium Ramp Hand Barrication-No. | MS Pipe Fixing (L) | Kgs | 2171 | 14 | 30394 | 0 | 30394 | 2.5 | 0 | 0 | 0 | 0 | 2171 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 1 | 29 Nov 2023 | SHIVAM ENTERPRISES | D,E&F Bldg.-Road Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 1711.29 | 20 | 34225.8 | 0 | 34225.8 | 0 | 1711.29 | 34225.8 | 0 | 34225.8 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 0 | 29 Nov 2023 | SHIVAM ENTERPRISES | D&E-Ent.Gate-Excavation & Backfilling | Spreading & Levelling Work | Cu.Mtrs | 109.824 | 20 | 2196.48 | 0 | 2196.48 | 0 | 109.824 | 2196.48 | 0 | 2196.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 0 | 29 Nov 2023 | SHIVAM ENTERPRISES | F-Ent.Gate-Excavation & Backfilling | Spreading & Levelling Work | Cu.Mtrs | 175.032 | 20 | 3500.64 | 0 | 3500.64 | 0 | 175.032 | 3500.64 | 0 | 3500.64 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 2 | 29 Nov 2023 | SHIVAM ENTERPRISES | Excavation & Backfilling Work-East Side Compound Wall | Backfilling | Cu.Mtrs | 591.69 | 60 | 35501.4 | 0 | 35501.4 | 0 | 587.895 | 35273.7 | 0 | 35273.7 | 3.795 | 227.7 |  | 99.3586 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 0 | 29 Nov 2023 | SHIVAM ENTERPRISES | D&E-Ent.Gate-Excavation & Backfilling | Backfilling | Cu.Mtrs | 100.542 | 60 | 6032.52 | 0 | 6032.52 | 0 | 100.542 | 6032.52 | 0 | 6032.52 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 1 | 29 Nov 2023 | SHIVAM ENTERPRISES | D,E&F Bldg.-Road Excavation Work | Excavation Work | Cu.Mtrs | 1711.29 | 60 | 102677.4 | 0 | 102677.4 | 0 | 1711.29 | 102677.4 | 0 | 102677.4 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 0 | 29 Nov 2023 | SHIVAM ENTERPRISES | F-Ent.Gate-Excavation & Backfilling | Backfilling | Cu.Mtrs | 160.608 | 60 | 9636.48 | 0 | 9636.48 | 0 | 160.608 | 9636.48 | 0 | 9636.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 0 | 29 Nov 2023 | SHIVAM ENTERPRISES | F-Ent.Gate-Excavation & Backfilling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 175.032 | 60 | 10501.92 | 0 | 10501.92 | 0 | 175.032 | 10501.92 | 0 | 10501.92 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 828 | 0 | 29 Nov 2023 | SHIVAM ENTERPRISES | D&E-Ent.Gate-Excavation & Backfilling | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 109.824 | 60 | 6589.44 | 0 | 6589.44 | 0 | 109.824 | 6589.44 | 0 | 6589.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 834 | 0 | 02 Dec 2023 | VIRAJ ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 0 | 6.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 25 May 2024
GANGA ALTUS | 846 | 0 | 09 Dec 2023 | NITIN D PARDESHI | GBT Electricity expenses | Electricity Bills | No. | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Jan 2024 |  | SOC. M. Maintenace Overheads | Cancelled | ADITYA.CHOUGULE | 11 Jan 2024
GANGA ALTUS | 850 | 0 | 12 Dec 2023 | VEER BHADRA ENTERPRISES | Altus& Arcadia-Divider-Paint Work | Painting work (M+L) -BC | Sq.Ft | 2028.81 | 10 | 20288.1 | 3651.86 | 23939.96 | 2.5 | 2028.81 | 20288.1 | 3651.86 | 23939.96 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Dec 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 867 | 0 | 16 Dec 2023 | ROHIT CONSTRUCTION | RCC Work D& E-Entrance Gate RCC Labour | RCC Work - DCH | No. | 1 | 300000 | 300000 | 54000 | 354000 | 2.5 | 1 | 300000 | 54000 | 354000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Dec 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 867 | 0 | 16 Dec 2023 | ROHIT CONSTRUCTION | RCC Work F-Entrance Gate RCC Labour | RCC Work - DEn | No. | 1 | 300000 | 300000 | 54000 | 354000 | 2.5 | 0.88 | 264000 | 47520 | 311520 | 0.12 | 42480 |  | 88 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Dec 2023 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 872 | 0 | 16 Dec 2023 | JAISAN | Excavation & Backfilling Work-East Side Compound Wall | Excavation (manually)- DPo | Cu.Ft | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | DEV. Podium | Cancelled | ADITYA.CHOUGULE | 09 Jan 2024
GANGA ALTUS | 872 | 0 | 16 Dec 2023 | JAISAN | Club House-Pile Top Breaking Work | Breaking Work - Dld | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 26 Dec 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 12 Apr 2024
GANGA ALTUS | 896 | 1 | 29 Dec 2023 | AVCON TECHNICS PVT LTD | D&F Bldg. Entrance Gate Rebaring Work | Rebaring work 12mm- cc | No. | 0 | 260 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Customer Changes | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ALTUS | 896 | 1 | 29 Dec 2023 | AVCON TECHNICS PVT LTD | D&F Bldg. Entrance Gate Rebaring Work | Rebaring work 12mm- cc | No. | 18 | 260 | 4680 | 842.4 | 5522.4 | 2.5 | 18 | 4680 | 842.4 | 5522.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 896 | 1 | 29 Dec 2023 | AVCON TECHNICS PVT LTD | D&F Bldg. Entrance Gate Rebaring Work | Rebaring work 16mm- cc | No. | 0 | 500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Customer Changes | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ALTUS | 896 | 1 | 29 Dec 2023 | AVCON TECHNICS PVT LTD | D&F Bldg. Entrance Gate Rebaring Work | Rebaring work 16mm- cc | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 2 | 09 Jan 2024 | VIJAY MOHITE | Excavation & Backfilling Work-East Side Compound Wall | Excavation Manually | Cu.Mtrs | 139.02 | 575 | 79936.5 | 0 | 79936.5 | 0 | 139.02 | 79936.5 | 0 | 79936.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 0 | 09 Jan 2024 | VIJAY MOHITE | Altus-Retaining Wall -RCC-East Side Compound Wall | RCC Work - Mkt | Sq.Ft | 1936.8 | 210 | 406728 | 0 | 406728 | 2.5 | 649.28 | 136348.8 | 0 | 136348.8 | 1287.52 | 270379.2 |  | 33.5233 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 1 | 09 Jan 2024 | VIJAY MOHITE | RCC Chajja-East Side Compound Wall | RCC Chajja - Mkt | Sq.Ft | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Cancelled | MONALI CHAUDHAR | 06 Jul 2024
GANGA ALTUS | 903 | 0 | 09 Jan 2024 | VIJAY MOHITE | Altus-Retaining Wall -RCC-East Side Compound Wall | RCC Work - Mkt | Sq.Ft | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA.CHOUGULE | 09 Jan 2024
GANGA ALTUS | 903 | 0 | 09 Jan 2024 | VIJAY MOHITE | Altus-Raft-RCC-East Side Compound Wall | RCC Work - Mkt | Sq.Ft | 1614 | 105 | 169470 | 0 | 169470 | 2.5 | 1049.4908 | 110196.53 | 0 | 110196.53 | 564.5092 | 59273.47 |  | 65.0242 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 1 | 09 Jan 2024 | VIJAY MOHITE | RCC Column-East Side Compound Wall | RCC Column - DSP | No. | 0 | 3500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | DEV. Swimming Pool | Cancelled | MONALI CHAUDHAR | 06 Jul 2024
GANGA ALTUS | 903 | 1 | 09 Jan 2024 | VIJAY MOHITE | RCC Column-East Side Compound Wall | RCC Column - DSP | No. | 13 | 3500 | 45500 | 0 | 45500 | 2.5 | 0 | 0 | 0 | 0 | 13 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 0 | 09 Jan 2024 | VIJAY MOHITE | Excavation & Backfilling Work-East Side Compound Wall | Excavation Manually | Cu.Mtrs | 534.5 | 625 | 334062.5 | 0 | 334062.5 | 0 | 534.5 | 334062.5 | 0 | 334062.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 1 | 09 Jan 2024 | VIJAY MOHITE | RCC Chajja-East Side Compound Wall | RCC Chajja - Mkt | Sq.Ft | 318.5 | 300 | 95550 | 0 | 95550 | 2.5 | 318.5 | 95550 | 0 | 95550 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 0 | 09 Jan 2024 | VIJAY MOHITE | Altus-Retaining Wall -RCC-East Side Compound Wall | RCC Work - Mkt | Sq.Ft | 1323.972 | 210 | 278034.12 | 0 | 278034.12 | 2.5 | 1124.73 | 236193.3 | 0 | 236193.3 | 199.242 | 41840.82 |  | 84.9512 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 903 | 0 | 09 Jan 2024 | VIJAY MOHITE | Altus-PCC- Work-East Side Compound Wall | PCC Work | Sq.Ft | 1711.476 | 8 | 13691.81 | 0 | 13691.81 | 2.5 | 1220.634 | 9765.07 | 0 | 9765.07 | 490.842 | 3926.74 |  | 71.3205 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 939 | 0 | 19 Feb 2024 | ITORRENT INDUSTRIES PVT LTD | Borewell Earthing Work | Transport Charges | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 81 | 8100 | 1458 | 9558 | 19 | 2242 | For GI Earthing- 90 Nos, Copper Bonded Electrode- 10Nos. | 81 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Feb 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 939 | 0 | 19 Feb 2024 | ITORRENT INDUSTRIES PVT LTD | Borewell Earthing Work | Earthing Work (M) | No. | 90 | 1700 | 153000 | 27540 | 180540 | 0 | 75 | 127500 | 22950 | 150450 | 15 | 30090 | Including Loading,Unloading,shifting,wastage,Profit & all other compliance etc. | 83.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 939 | 0 | 19 Feb 2024 | ITORRENT INDUSTRIES PVT LTD | Borewell Earthing Work | EPC Pit Cover (Green) (M) | No. | 100 | 300 | 30000 | 5400 | 35400 | 0 | 81 | 24300 | 4374 | 28674 | 19 | 6726 | For GI Earthing- 90 Nos, Copper Bonded Electrode- 10Nos. | 81 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Feb 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 939 | 0 | 19 Feb 2024 | ITORRENT INDUSTRIES PVT LTD | Borewell Earthing Work | Earthing Work (M) | No. | 10 | 2900 | 29000 | 5220 | 34220 | 0 | 6 | 17400 | 3132 | 20532 | 4 | 13688 | Including Loading,Unloading,shifting,wastage,Profit & all other compliance etc. | 60 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 940 | 0 | 19 Feb 2024 | ITORRENT INDUSTRIES PVT LTD | Borewell Earthing Work | Earthing Work (L) | No. | 90 | 1700 | 153000 | 27540 | 180540 | 2.5 | 75 | 127500 | 22950 | 150450 | 15 | 30090 |  | 83.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 940 | 0 | 19 Feb 2024 | ITORRENT INDUSTRIES PVT LTD | Borewell Earthing Work | Earthing Work (L) | No. | 10 | 1700 | 17000 | 3060 | 20060 | 2.5 | 6 | 10200 | 1836 | 12036 | 4 | 8024 |  | 60 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Feb 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 100mm dia. (L) | Mtrs | 0 | 400 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | ADITYA.CHOUGULE | 28 Feb 2024
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 65mm dia.(L) | Mtrs | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA.CHOUGULE | 28 Feb 2024
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 40mm dia.(L) | Mtrs | 82 | 175 | 14350 | 2583 | 16933 | 2.5 | 0 | 0 | 0 | 0 | 82 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 65mm dia.(L) | Mtrs | 64 | 250 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 64 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 80mm dia.(L) | Mtrs | 78 | 300 | 23400 | 4212 | 27612 | 2.5 | 0 | 0 | 0 | 0 | 78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | IWL Coating with Bitumin liquid (L) | Mtrs | 415 | 125 | 51875 | 9337.5 | 61212.5 | 2.5 | 0 | 0 | 0 | 0 | 415 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 100mm dia. (L) | Mtrs | 48 | 400 | 19200 | 3456 | 22656 | 2.5 | 0 | 0 | 0 | 0 | 48 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 100mm dia. (L) | Mtrs | 94 | 400 | 37600 | 6768 | 44368 | 2.5 | 0 | 0 | 0 | 0 | 94 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 942 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 50mm dia.(L) | Mtrs | 78 | 200 | 15600 | 2808 | 18408 | 2.5 | 0 | 0 | 0 | 0 | 78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 50mm dia.(M) | Mtrs | 78 | 574 | 44772 | 8058.96 | 52830.96 | 0 | 0 | 0 | 0 | 0 | 78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 80mm dia.(M) | Mtrs | 78 | 912 | 71136 | 12804.48 | 83940.48 | 0 | 0 | 0 | 0 | 0 | 78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 40mm dia.(M) | Mtrs | 82 | 418 | 34276 | 6169.68 | 40445.68 | 0 | 0 | 0 | 0 | 0 | 82 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 65mm dia.(M) | Mtrs | 64 | 734 | 46976 | 8455.68 | 55431.68 | 0 | 0 | 0 | 0 | 0 | 64 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 100mm dia. (M) | Mtrs | 48 | 1308 | 62784 | 11301.12 | 74085.12 | 0 | 0 | 0 | 0 | 0 | 48 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | IWL Coating with Bitumin liquid (M) | Mtrs | 415 | 300 | 124500 | 22410 | 146910 | 0 | 0 | 0 | 0 | 0 | 415 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 945 | 0 | 28 Feb 2024 | SAFETY ENGINEERS & CONSULTANTS | Development-GI Pipe Supply & installation for Rising main | SITC GI Pipe C Class 100mm dia. (M) | Mtrs | 94 | 1308 | 122952 | 22131.36 | 145083.36 | 0 | 0 | 0 | 0 | 0 | 94 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Mar 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 960 | 1 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | GI Earthing Patti 25x3 (M) | Kgs | 0 | 101.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Apr 2024 |  | 04 ELECTRICAL WORK | Cancelled | MONALI CHAUDHAR | 09 Apr 2024
GANGA ALTUS | 961 | 0 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | GI Earthing Patti 25x3 (M) | Kgs | 60 | 101.2 | 6072 | 1092.96 | 7164.96 | 0 | 54.31 | 5496.17 | 989.32 | 6485.49 | 5.69 | 679.47 |  | 90.5167 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 961 | 0 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | Earthing Patti 25x3 (L) | Mtrs | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Cancelled | MONALI CHAUDHAR | 09 Apr 2024
GANGA ALTUS | 961 | 0 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | GI Earthing Patti 50x6 (M) | Kgs | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Cancelled | MONALI CHAUDHAR | 09 Apr 2024
GANGA ALTUS | 961 | 0 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | GI Earthing Patti 50x6 (M) | Kgs | 2987.5 | 101.2 | 302335 | 54420.3 | 356755.3 | 0 | 334.125 | 33813.45 | 6086.42 | 39899.87 | 2653.375 | 316855.43 |  | 11.1841 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 962 | 0 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | GI Earthing Patti 50 x 6mm (L) | Mtrs | 1195 | 80 | 95600 | 17208 | 112808 | 2.5 | 133.65 | 10692 | 1924.56 | 12616.56 | 1061.35 | 100191.44 |  | 11.1841 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 962 | 0 | 09 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | D,E, F & Development-Earthing Patti Work | Earthing Patti 25x3 (L) | Mtrs | 100 | 50 | 5000 | 900 | 5900 | 2.5 | 90.52 | 4526 | 814.68 | 5340.68 | 9.48 | 559.32 |  | 90.52 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 15 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-Plinth Level Slab- RCC-BUA | RCC Superstructure (B-up area) | Sq.Ft | 1619.94 | 140 | 226791.6 | 40822.48 | 267614.08 | 2.5 | 0 | 0 | 0 | 0 | 1619.94 | 0 | Pile Cap Bottom- PCC, Pile Cap Casting, Column upto 1 - 1.5 mtr plinth beam, Grid slab, Compaction, soling & Grid slab with steel (Regular 8mm dia bar) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-F.F Top Slab- RCC-BUA | Schedule- BC | Sq.Ft | 1120.24 | 10 | 11202.4 | 2016.44 | 13218.84 | 0 | 0 | 0 | 0 | 0 | 1120.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-OHWT (Top & Bottom) - RCC-BUA | Schedule- BC | Sq.Ft | 257.24 | 10 | 2572.4 | 463.04 | 3035.44 | 0 | 0 | 0 | 0 | 0 | 257.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-Ground Floor Top Slab- RCC-BUA | Schedule- BC | Sq.Ft | 1496.15 | 10 | 14961.5 | 2693.08 | 17654.58 | 0 | 0 | 0 | 0 | 0 | 1496.15 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-Pile Top Breaking Work | Breaking Work - Dld | No. | 32 | 750 | 24000 | 4320 | 28320 | 0 | 0 | 0 | 0 | 0 | 32 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-Plinth Level Slab- RCC-BUA | Schedule- BC | Sq.Ft | 1619.94 | 10 | 16199.4 | 2915.9 | 19115.3 | 0 | 0 | 0 | 0 | 0 | 1619.94 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-Ground Floor Top Slab- RCC-BUA | RCC Superstructure (B-up area) | Sq.Ft | 1496.15 | 225 | 336633.75 | 60594.08 | 397227.83 | 2.5 | 0 | 0 | 0 | 0 | 1496.15 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-F.F Top Slab- RCC-BUA | RCC Superstructure (B-up area) | Sq.Ft | 1120.24 | 225 | 252054 | 45369.72 | 297423.72 | 2.5 | 0 | 0 | 0 | 0 | 1120.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 963 | 0 | 12 Apr 2024 | UPRISEN CONSTRUCTION | Club House-OHWT (Top & Bottom) - RCC-BUA | RCC Superstructure (B-up area) | Sq.Ft | 257.24 | 225 | 57879 | 10418.22 | 68297.22 | 2.5 | 0 | 0 | 0 | 0 | 257.24 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 993 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (M) | Sq.Ft | 8958.29 | 60.8 | 544664.03 | 98039.52 | 642703.55 | 0 | 0 | 0 | 0 | 0 | 8958.29 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 993 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Granular Sub Base (M) | Sq.Ft | 0 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 993 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Granular Sub Base (M) | Sq.Ft | 600 | 20.9 | 12540 | 2257.2 | 14797.2 | 0 | 0 | 0 | 0 | 0 | 600 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved | Aditya.chougule | 27 Jul 2024
GANGA ALTUS | 993 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (M) | Sq.Ft | 0 | 60.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (L) | Sq.Ft | 0 | 5.11 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (L) | Sq.Ft | 8958.28 | 5.11 | 45776.81 | 8239.82 | 54016.63 | 2.5 | 0 | 0 | 0 | 0 | 8958.28 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (L) | Sq.Ft | 7889.42 | 16 | 126230.72 | 22721.52 | 148952.24 | 2.5 | 0 | 0 | 0 | 0 | 7889.42 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Wet Mix Macadam (L) | Sq.Ft | 0 | 5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Reinforcement Work - BC | Sq.Ft | 0 | 7 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Reinforcement Work - BC | Sq.Ft | 7889.42 | 7 | 55225.94 | 9940.66 | 65166.6 | 2.5 | 0 | 0 | 0 | 0 | 7889.42 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 1st Layer (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 1st Layer (L) | Sq.Ft | 3238.56 | 5 | 16192.8 | 2914.7 | 19107.5 | 0 | 0 | 0 | 0 | 0 | 3238.56 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 3238.56 | 3 | 9715.68 | 0 | 9715.68 | 0 | 0 | 0 | 0 | 0 | 3238.56 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 2nd Layer (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (L) | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2024
GANGA ALTUS | 1011 | 0 | 08 Jun 2024 | PRAKASH CONTRACTOR | D,E,F Bldg. Periphery Road-PCC Work below Paver Block | PCC Work | Sq.Ft | 3523.65 | 4 | 14094.6 | 0 | 14094.6 | 2.5 | 0 | 0 | 0 | 0 | 3523.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1027 | 0 | 25 Jun 2024 | SHIVAM ENTERPRISES | Backfilling Work for Club House | Murum Backfilling | Cu.Mtrs | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 26 Jun 2024 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 26 Jun 2024
GANGA ALTUS | 1027 | 0 | 25 Jun 2024 | SHIVAM ENTERPRISES | Backfilling Work for Club House | Murum Backfilling | Cu.Mtrs | 303.78 | 60 | 18226.8 | 0 | 18226.8 | 0 | 0 | 0 | 0 | 0 | 303.78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Jun 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1027 | 0 | 25 Jun 2024 | SHIVAM ENTERPRISES | Backfilling Work for Club House | Spreading & Levelling Work | Cu.Mtrs | 303.78 | 30 | 9113.4 | 0 | 9113.4 | 0 | 0 | 0 | 0 | 0 | 303.78 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 26 Jun 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 1 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Rework for Club House | Reinforcement (L) | Kgs | 720 | 8 | 5760 | 1036.8 | 6796.8 | 2.5 | 0 | 0 | 0 | 0 | 720 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Jun 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1028 | 1 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Rework for Club House | Shuttering Work-Mkt | Sq.m. | 17.81 | 550 | 9795.5 | 1763.2 | 11558.7 | 2.5 | 0 | 0 | 0 | 0 | 17.81 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Jun 2024 |  | MKT. Marketing Infrastructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1028 | 1 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Rework for Club House | Labour Lumpsum | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Jun 2024 |  | DEV. Ext Development | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 5.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 5.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Labour lumpsum | No. | 1 | 48000 | 48000 | 8640 | 56640 | 2.5 | 0.5 | 24000 | 4320 | 28320 | 0.5 | 28320 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Labour lumpsum | No. | 1 | 48000 | 48000 | 8640 | 56640 | 2.5 | 0.75 | 36000 | 6480 | 42480 | 0.25 | 14160 |  | 75 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 11.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 11.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.63 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.63 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Schedule work- BC | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Schedule work- BC | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.25 | 3867.14 | 696.08 | 4563.22 | 0 | 1539.65 | 3464.21 | 623.56 | 4087.77 | 179.08 | 475.45 |  | 89.5807 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.5 | 4296.83 | 773.42 | 5070.25 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.5 | 4296.83 | 773.42 | 5070.25 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1718.73 | 1 | 1718.73 | 309.38 | 2028.11 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1718.73 | 1 | 1718.73 | 309.38 | 2028.11 | 0 | 1539.65 | 1539.65 | 277.14 | 1816.79 | 179.08 | 211.32 |  | 89.5807 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.25 | 3867.14 | 696.08 | 4563.22 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | Texture Paint (M) | Sq.Ft | 1718.73 | 8 | 13749.84 | 2474.98 | 16224.82 | 0 | 1539.65 | 12317.2 | 2217.1 | 14534.3 | 179.08 | 1690.52 |  | 89.5807 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | Texture Paint (M) | Sq.Ft | 1718.73 | 8 | 13749.84 | 2474.98 | 16224.82 | 0 | 1718.73 | 13749.84 | 2474.98 | 16224.82 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1039 | 0 | 04 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | East Side Compound Wall Brickwork & Plaster (L) | Patli Work DCH | R.Ft | 127.92 | 15 | 1918.8 | 345.38 | 2264.18 | 2.5 | 0 | 0 | 0 | 0 | 127.92 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Jul 2024 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1039 | 0 | 04 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | East Side Compound Wall Brickwork & Plaster (L) | Sand face Plaster- BC | Sq.Ft | 2354.2 | 20 | 47084 | 8475.12 | 55559.12 | 2.5 | 0 | 0 | 0 | 0 | 2354.2 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Jul 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1039 | 0 | 04 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | East Side Compound Wall Brickwork & Plaster (L) | Blockwork 8" - BC | Sq.Ft | 776.62 | 22 | 17085.64 | 3075.42 | 20161.06 | 2.5 | 0 | 0 | 0 | 0 | 776.62 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Jul 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1049 | 0 | 09 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | Front Side Compound Wall Brickwork | Brickwork 6" | Sq.Ft | 126.58 | 22 | 2784.76 | 501.26 | 3286.02 | 2.5 | 0 | 0 | 0 | 0 | 126.58 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1049 | 0 | 09 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | Front Side Compound Wall Single Coat Sand Face Plaster | Sand face Plaster- BC | Sq.Ft | 2051.3 | 20 | 41026 | 7384.68 | 48410.68 | 2.5 | 0 | 0 | 0 | 0 | 2051.3 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1049 | 0 | 09 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | Front Side Compound Wall Brickwork | Brickwork 15" - SOS | Sq.Ft | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | MONALI CHAUDHAR | 10 Jul 2024
GANGA ALTUS | 1049 | 0 | 09 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | Front Side Compound Wall Brickwork | Brickwork 15" - SOS | Sq.Ft | 152.58 | 35 | 5340.3 | 961.26 | 6301.56 | 2 | 0 | 0 | 0 | 0 | 152.58 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1049 | 0 | 09 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | Front Side Compound Wall Brickwork | Brickwork Pillar | R.Ft | 48.03 | 60 | 2881.8 | 518.72 | 3400.52 | 2.5 | 12 | 720 | 129.6 | 849.6 | 36.03 | 2550.92 |  | 24.9844 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1049 | 0 | 09 Jul 2024 | SHUBHAM SURENDRA BAHADUR SINGH | Front Side Compound Wall Brickwork | Brickwork 9" DCW | Sq.Ft | 561.4 | 24 | 13473.6 | 2425.24 | 15898.84 | 2.5 | 189.4203 | 4546.09 | 818.3 | 5364.39 | 371.9797 | 10534.45 |  | 33.7407 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Riser (L)- BCE | R.Ft | 46.33 | 40 | 1853.2 | 0 | 1853.2 | 2.5 | 0 | 0 | 0 | 0 | 46.33 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (L)- BCE | Sq.Ft | 169.1 | 45 | 7609.5 | 0 | 7609.5 | 2.5 | 84.07 | 3783.15 | 0 | 3783.15 | 85.03 | 3826.35 |  | 49.7161 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (L)- BCE | Sq.Ft | 169.1 | 45 | 7609.5 | 0 | 7609.5 | 2.5 | 0 | 0 | 0 | 0 | 169.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Riser (L)- BCE | R.Ft | 46.33 | 40 | 1853.2 | 0 | 1853.2 | 2.5 | 22.83 | 913.2 | 0 | 913.2 | 23.5 | 940 |  | 49.2769 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Vertical Patta (L) | R.Ft | 21.67 | 45 | 975.15 | 0 | 975.15 | 2.5 | 10.67 | 480.15 | 0 | 480.15 | 11 | 495 |  | 49.2386 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Vertical Patta (L) | R.Ft | 21.67 | 45 | 975.15 | 0 | 975.15 | 2.5 | 0 | 0 | 0 | 0 | 21.67 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Tread | R.Ft | 22.92 | 40 | 916.8 | 0 | 916.8 | 2.5 | 11.42 | 456.8 | 0 | 456.8 | 11.5 | 460 |  | 49.8255 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Edge Polish (L) | R.Ft | 39.17 | 10 | 391.7 | 0 | 391.7 | 2.5 | 19.58 | 195.8 | 0 | 195.8 | 19.59 | 195.9 |  | 49.9872 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Edge Polish (L) | R.Ft | 39.17 | 10 | 391.7 | 0 | 391.7 | 2.5 | 0 | 0 | 0 | 0 | 39.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Tread | R.Ft | 22.92 | 40 | 916.8 | 0 | 916.8 | 2.5 | 0 | 0 | 0 | 0 | 22.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1052 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (M)- BCE | Sq.Ft | 247.52 | 110.7 | 27400.46 | 0 | 27400.46 | 0 | 0 | 0 | 0 | 0 | 247.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1052 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (M)- BCE | Sq.Ft | 247.52 | 110.7 | 27400.46 | 0 | 27400.46 | 0 | 120.8 | 13372.56 | 0 | 13372.56 | 126.72 | 14027.9 |  | 48.8041 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1053 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES | Front Side Compound Wall Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 742.75 | 1.75 | 1299.81 | 233.96 | 1533.77 | 2.5 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1053 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES | Front Side Compound Wall Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 742.75 | 1 | 742.75 | 133.7 | 876.45 | 2.5 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1053 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES | Front Side Compound Wall Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 742.75 | 1.5 | 1114.13 | 200.54 | 1314.67 | 2.5 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1053 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES | Front Side Compound Wall Texture Work | Texture Paint (L) | Sq.Ft | 742.75 | 7.5 | 5570.63 | 1002.72 | 6573.35 | 2.5 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1053 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES | Front Side Compound Wall Texture Work | Scaffolding work | Sq.Ft | 742.75 | 0.5 | 371.38 | 66.84 | 438.22 | 2.5 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1053 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES | Front Side Compound Wall Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 742.75 | 0.5 | 371.38 | 66.84 | 438.22 | 0 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1054 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | Front Side Compound Wall Texture Work | Texture Paint (M) | Sq.Ft | 742.75 | 8 | 5942 | 1069.56 | 7011.56 | 0 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1054 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | Front Side Compound Wall Texture Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 742.75 | 2.25 | 1671.19 | 300.82 | 1972.01 | 0 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1054 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | Front Side Compound Wall Texture Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 742.75 | 2.5 | 1856.88 | 334.24 | 2191.12 | 0 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1054 | 0 | 12 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | Front Side Compound Wall Texture Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 742.75 | 1 | 742.75 | 133.7 | 876.45 | 0 | 0 | 0 | 0 | 0 | 742.75 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1060 | 0 | 24 Jul 2024 | BHAGWAT CONSTRUCTION | D,E,F-Bldg Side- PQC Road Work(Main Road | Wet Mix Macadam (L) | Sq.Ft | 8776.93 | 5.11 | 44850.11 | 8073.02 | 52923.13 | 0 | 0 | 0 | 0 | 0 | 8776.93 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1060 | 0 | 24 Jul 2024 | BHAGWAT CONSTRUCTION | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 10017.02 | 3 | 30051.06 | 5409.2 | 35460.26 | 0 | 0 | 0 | 0 | 0 | 10017.02 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1061 | 0 | 24 Jul 2024 | BHAGWAT CONSTRUCTION | D,E,F-Bldg Side- PQC Road Work(Main Road | Wet Mix Macadam (M) | Sq.Ft | 8776.93 | 21.32 | 187124.15 | 33682.34 | 220806.49 | 0 | 0 | 0 | 0 | 0 | 8776.93 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | 12mm Toughned Glass work (M) | Sq.Ft | 183 | 155 | 28365 | 5105.7 | 33470.7 | 0 | 0 | 0 | 0 | 0 | 183 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | EPF 703P Overpanel Patch | No. | 1 | 2035 | 2035 | 366.3 | 2401.3 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Silicon | No. | 8 | 250 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Twin Pro section 10ft. (M+L) | No. | 3 | 1500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Doorset FH 943 (M+L) | No. | 2 | 10200 | 20400 | 3672 | 24072 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Handle hole to Hole 600mm | No. | 2 | 1900 | 3800 | 684 | 4484 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Cutout | No. | 7 | 150 | 1050 | 189 | 1239 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Hole Making | No. | 3 | 100 | 300 | 54 | 354 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | 12mm Toughned Glass work (L) | Sq.Ft | 183 | 50 | 9150 | 1647 | 10797 | 2.5 | 0 | 0 | 0 | 0 | 183 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | ESH 412 | No. | 2 | 429 | 858 | 154.44 | 1012.44 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Hole Making | No. | 11 | 50 | 550 | 99 | 649 | 2.5 | 0 | 0 | 0 | 0 | 11 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Un-Approved |  | 1900-01-01