## Project_Work_Order6385872308649
Project Work Order
From 01 Jul 2020 To 09 Aug 2024
Page 1 of 1
Total Records: 20 Records 1 To 20
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Completion Conduiting in Electrical Duct | No. | 55 | 1375 | 75625 | 13612.5 | 89237.5 | 2.5 | 0 | 0 | 0 | 0 | 55 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Meter Room RCCB, Busbar,Wiring, Earthing | No. | 46 | 1650 | 75900 | 13662 | 89562 | 2.5 | 0 | 0 | 0 | 0 | 46 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Meter Work Completed | No. | 55 | 275 | 15125 | 2722.5 | 17847.5 | 2.5 | 0 | 0 | 0 | 0 | 55 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Meter Room RCCB, Busbar,Wiring, Earthing | No. | 55 | 1650 | 90750 | 16335 | 107085 | 2.5 | 0 | 0 | 0 | 0 | 55 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Meter Work Completed | No. | 46 | 275 | 12650 | 2277 | 14927 | 2.5 | 0 | 0 | 0 | 0 | 46 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Main Line Wiring Bldg to Main Meter | No. | 50 | 1750 | 87500 | 15750 | 103250 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Meter Room RCCB, Busbar,Wiring, Earthing | No. | 50 | 1500 | 75000 | 13500 | 88500 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Completion Conduiting in Electrical Duct | No. | 50 | 1250 | 62500 | 11250 | 73750 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Meter Room RCCB, Busbar,Wiring, Earthing | No. | 49 | 1800 | 88200 | 15876 | 104076 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Main Line Wiring Bldg to Main Meter | No. | 49 | 2100 | 102900 | 18522 | 121422 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Testing | No. | 50 | 250 | 12500 | 2250 | 14750 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Completion Conduiting in Electrical Duct | No. | 49 | 1500 | 73500 | 13230 | 86730 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Meter Work Completed | No. | 49 | 300 | 14700 | 2646 | 17346 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Completion Conduiting in Electrical Duct | No. | 46 | 1375 | 63250 | 11385 | 74635 | 2.5 | 0 | 0 | 0 | 0 | 46 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Meter Work Completed | No. | 50 | 250 | 12500 | 2250 | 14750 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Testing | No. | 49 | 300 | 14700 | 2646 | 17346 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Testing | No. | 55 | 275 | 15125 | 2722.5 | 17847.5 | 2.5 | 0 | 0 | 0 | 0 | 55 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | After Testing | No. | 46 | 275 | 12650 | 2277 | 14927 | 2.5 | 0 | 0 | 0 | 0 | 46 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Main Line Wiring Bldg to Main Meter | No. | 55 | 1925 | 105875 | 19057.5 | 124932.5 | 2.5 | 0 | 0 | 0 | 0 | 55 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 491 | 0 | 16 Jul 2022 | HARISH CHANDRA JADHAV ELECTRICALS | D-Bldg Main Line Electrical Work | Main Line Wiring Bldg to Main Meter | No. | 46 | 1925 | 88550 | 15939 | 104489 | 2.5 | 0 | 0 | 0 | 0 | 46 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Aug 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01