## Project_Work_Order6385880190282
Project Work Order
From 01 Jan 2000 To 31 Jul 2024
Page 1 of 1
Total Records: 239 Records 1 To 239
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ARCADIA - A BUILDING | 9 | 0 | 21 Jul 2021 | RITU ENTERPRISES | A-PCC | PCC Work | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | Construction | 23 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 23 Mar 2023
GANGA ARCADIA - A BUILDING | 9 | 0 | 21 Jul 2021 | RITU ENTERPRISES | A-Excavation & Cleaning | Dressing, Levelling & Cleaning | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | Construction | 23 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT GORE | 23 Mar 2023
GANGA ARCADIA - A BUILDING | 20 | 1 | 22 Apr 2022 | SS ENTERPRISES | Excavation work by needle | Excavation By Needle | Cu.Mtrs | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 25 May 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 07 Nov 2023
GANGA ARCADIA - A BUILDING | 20 | 1 | 22 Apr 2022 | SS ENTERPRISES | Excavation work by needle | Excavation By Needle | Cu.Mtrs | 5937 | 210 | 1246770 | 224418.6 | 1471188.6 | 0 | 5937 | 1246770 | 224418.6 | 1471188.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 25 May 2022 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ARCADIA - A BUILDING | 20 | 0 | 22 Apr 2022 | SS ENTERPRISES | Excavation work by needle | Excavation By Needle | Cu.Mtrs | 2477.5 | 210 | 520275 | 93649.5 | 613924.5 | 0 | 2402.8619 | 504601 | 90828.18 | 595429.18 | 74.6381 | 18495.32 |  | 96.9874 |  | Dushant Gore | Swapnil Erande | construction open | 25 May 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 22 | 0 | 29 Aug 2022 | Kone Elevator (I) Pvt. Ltd | Supply & Installation of Lifts - A Bldg. | Lift Supply & Installaion BC | No. | 0 | 1864406.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | Construction | 29 Aug 2022 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 29 Aug 2022
GANGA ARCADIA - A BUILDING | 22 | 0 | 29 Aug 2022 | Kone Elevator (I) Pvt. Ltd | Supply & Installation of Lifts - A Bldg. | Lift Supply & Installaion BC | No. | 1 | 2033898.3 | 2033898.3 | 366101.7 | 2400000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | Construction | 29 Aug 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 23 | 0 | 29 Aug 2022 | Kone Elevator (I) Pvt. Ltd | Supply & Installation of Lifts - A Bldg. | Lift Supply & Installaion BC | No. | 1 | 1864406.78 | 1864406.78 | 335593.22 | 2200000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | Construction | 29 Aug 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 24 | 0 | 19 Oct 2022 | VECTOR SURVEYORS | Survey work | Total Statiotn Survey | Day | 3 | 4500 | 13500 | 0 | 13500 | 0 | 1 | 4500 | 0 | 4500 | 2 | 9000 |  | 33.3333 |  | Dushant Gore | Swapnil Erande | construction open | 10 Nov 2022 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Footing & Column | Footing & Column | Sq.Ft | 0 | 90 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10045.078 | 165 | 1657437.87 | 298338.82 | 1955776.69 | 2.5 | 0 | 0 | 0 | 0 | 10045.078 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -Terrace - RCC 18th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | Hacking Work | Sq.Ft | 11647.529 | 2.5 | 29118.82 | 5241.38 | 34360.2 | 2.5 | 0 | 0 | 0 | 0 | 11647.529 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | Hacking Work | Sq.Ft | 10045.078 | 2.5 | 25112.7 | 4520.28 | 29632.98 | 2.5 | 0 | 0 | 0 | 0 | 10045.078 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Soling & PCC | Soling & PCC | Sq.Ft | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 135 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Plinth Beam | RCC Beam | Sq.Ft | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 155 | 1552012.68 | 279362.28 | 1831374.96 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | LMR (Top/Bottom Slab) & OHWT (Top/Bottom Slab) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | Hacking Work | Sq.Ft | 12655.012 | 2.5 | 31637.53 | 5694.76 | 37332.29 | 2.5 | 0 | 0 | 0 | 0 | 12655.012 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 135 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Soling & PCC | Soling & PCC | Sq.Ft | 18375.17 | 60 | 1102510.2 | 198451.84 | 1300962.04 | 2.5 | 14891 | 893460 | 160822.8 | 1054282.8 | 3484.17 | 246679.24 |  | 87.7053 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | LMR (Top/Bottom Slab) & OHWT (Top/Bottom Slab) | Hacking Work | Sq.Ft | 3375.954 | 2.5 | 8439.89 | 1519.18 | 9959.07 | 2.5 | 0 | 0 | 0 | 0 | 3375.954 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -Terrace - RCC 18th Slab BUA (L) | Hacking Work | Sq.Ft | 10037.813 | 2.5 | 25094.53 | 4517.02 | 29611.55 | 2.5 | 0 | 0 | 0 | 0 | 10037.813 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 145 | 1451882.83 | 261338.9 | 1713221.73 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | LMR (Top/Bottom Slab) & OHWT (Top/Bottom Slab) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 11647.529 | 135 | 1572416.42 | 283034.96 | 1855451.38 | 2.5 | 0 | 0 | 0 | 0 | 11647.529 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Plinth Beam | RCC Beam | Sq.Ft | 18375.17 | 70 | 1286261.9 | 231527.14 | 1517789.04 | 2.5 | 14891 | 1042370 | 187626.6 | 1229996.6 | 3484.17 | 287792.44 |  | 87.7053 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | Schedule- BC | Sq.Ft | 10045.078 | 10 | 100450.78 | 18081.14 | 118531.92 | 2.5 | 0 | 0 | 0 | 0 | 10045.078 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | LMR (Top/Bottom Slab) & OHWT (Top/Bottom Slab) | Schedule- BC | Sq.Ft | 3375.954 | 10 | 33759.54 | 6076.72 | 39836.26 | 2.5 | 0 | 0 | 0 | 0 | 3375.954 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | Schedule- BC | Sq.Ft | 11647.529 | 10 | 116475.29 | 20965.56 | 137440.85 | 2.5 | 0 | 0 | 0 | 0 | 11647.529 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 145 | 1451882.83 | 261338.9 | 1713221.73 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Excavation & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 7 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Excavation & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 18375.17 | 6 | 110251.02 | 19845.18 | 130096.2 | 2.5 | 18375 | 110250 | 15638.4 | 125888.4 | 0.17 | 4207.8 |  | 99.9991 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Footing & Column | Footing & Column | Sq.Ft | 0 | 90 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 145 | 1451882.83 | 261338.9 | 1713221.73 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Plinth Beam | RCC Beam | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | Schedule- BC | Sq.Ft | 12655.012 | 10 | 126550.12 | 22779.02 | 149329.14 | 2.5 | 0 | 0 | 0 | 0 | 12655.012 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 3 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Raft & Retaining Wall-(External)-RCC Work(L) | Shuttering Work-Mkt | Sq.m. | 41.68 | 600 | 25008 | 4501.44 | 29509.44 | 2.5 | 15 | 9000 | 1620 | 10620 | 26.68 | 18889.44 |  | 59.9808 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 18375.172 | 135 | 2480648.22 | 446516.68 | 2927164.9 | 2.5 | 12680 | 1711800 | 308124 | 2019924 | 5695.172 | 907240.9 |  | 69.0062 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Footing & Column | Footing & Column | Sq.Ft | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 3 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Raft & Retaining Wall-(External)-RCC Work(L) | Shuttering Work-Mkt | Sq.m. | 453.59 | 600 | 272154 | 48987.72 | 321141.72 | 2.5 | 307.55 | 184530 | 33215.4 | 217745.4 | 146.04 | 103396.32 |  | 84.5587 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 30 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 12655.012 | 135 | 1708426.62 | 307516.8 | 2015943.42 | 2.5 | 0 | 0 | 0 | 0 | 12655.012 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-PCC | PCC Work | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 135 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 135 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 16th Floor RCC 17th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 145 | 1451882.83 | 261338.9 | 1713221.73 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 16th Floor RCC 17th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 175 | 1752272.38 | 315409.02 | 2067681.4 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 155 | 1552012.68 | 279362.28 | 1831374.96 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Footing & Column | Footing & Column | Sq.Ft | 18375.17 | 80 | 1470013.6 | 264602.44 | 1734616.04 | 2.5 | 14891 | 1191280 | 214430.4 | 1405710.4 | 3484.17 | 328905.64 |  | 87.7053 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-PCC | PCC Work | Sq.Ft | 18375.17 | 8 | 147001.36 | 26460.24 | 173461.6 | 2.5 | 15264 | 122112 | 21980.16 | 144092.16 | 3111.17 | 29369.44 |  | 83.0686 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 3 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Raft & Retaining Wall-(External)-RCC Work(L) | Reinforcement BC | Kgs | 3286 | 8 | 26288 | 4731.84 | 31019.84 | 2.5 | 2243 | 17944 | 3229.92 | 21173.92 | 1043 | 9845.92 |  | 86.5186 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 15th Floor RCC 16th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -Terrace - RCC 18th Slab BUA (L) | Schedule- BC | Sq.Ft | 10037.813 | 10 | 100378.13 | 18068.06 | 118446.19 | 2.5 | 0 | 0 | 0 | 0 | 10037.813 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 165 | 1652142.53 | 297385.66 | 1949528.19 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-PCC | PCC Work | Sq.Ft | 0 | 9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Soling & PCC | Soling & PCC | Sq.Ft | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | Hacking Work | Sq.Ft | 18375.172 | 2.5 | 45937.93 | 8268.82 | 54206.75 | 2.5 | 0 | 0 | 0 | 0 | 18375.172 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | Schedule- BC | Sq.Ft | 10045.078 | 10 | 100450.78 | 18081.14 | 118531.92 | 2.5 | 0 | 0 | 0 | 0 | 10045.078 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | Schedule- BC | Sq.Ft | 18375.172 | 10 | 183751.72 | 33075.3 | 216827.02 | 2.5 | 0 | 0 | 0 | 0 | 18375.172 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 15th Floor RCC 16th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -Terrace - RCC 18th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 211.9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 15th Floor RCC 16th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 175 | 1752272.38 | 315409.02 | 2067681.4 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | LMR (Top/Bottom Slab) & OHWT (Top/Bottom Slab) | RCC Superstructure (B-up area) | Sq.Ft | 3375.954 | 285 | 962146.89 | 173186.44 | 1135333.33 | 2.5 | 0 | 0 | 0 | 0 | 3375.954 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -Terrace - RCC 18th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | LMR (Top/Bottom Slab) & OHWT (Top/Bottom Slab) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 1 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Bldg RCC Work & Shuttering Work | RCC Work lumpsum- SOS | No. | 1 | 350000 | 350000 | 63000 | 413000 | 2.5 | 1 | 350000 | 63000 | 413000 | 0 | 0 | Construction of RCC Footing of specified grade of concrete including all Reinforcement, shuttering, strutting, propping, concreting with compaction and removal of form etc. for PCC & Footing etc.(All raw material / RMC will be provided by GGG) | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 3 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Raft & Retaining Wall-(External)-RCC Work(L) | Reinforcement BC | Kgs | 11914.33 | 8 | 95314.64 | 17156.64 | 112471.28 | 2.5 | 7361.3 | 58890.4 | 10600.28 | 69490.68 | 4553.03 | 42980.6 |  | 74.3751 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 8th Floor RCC 9th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10045.078 | 155 | 1556987.09 | 280257.68 | 1837244.77 | 2.5 | 0 | 0 | 0 | 0 | 10045.078 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 135 | 1351752.98 | 243315.54 | 1595068.52 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 175 | 1752272.38 | 315409.02 | 2067681.4 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 3 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Raft & Retaining Wall-(External)-RCC Work(L) | Concreting DPo | Cu.Mtrs | 64.603 | 300 | 19380.9 | 3488.56 | 22869.46 | 2.5 | 25 | 7500 | 1350 | 8850 | 39.603 | 14019.46 |  | 46.4375 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 30 Mar 2023 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 2nd Floor RCC 3rd Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 135 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10012.985 | 165 | 1652142.53 | 297385.66 | 1949528.19 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 3 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Raft & Retaining Wall-(External)-RCC Work(L) | Concreting DPo | Cu.Mtrs | 118.597 | 300 | 35579.1 | 6404.24 | 41983.34 | 2.5 | 64 | 19200 | 3456 | 22656 | 54.597 | 19327.34 |  | 60.7098 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 30 Mar 2023 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -Terrace - RCC 18th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 10037.813 | 196.4 | 1971426.47 | 354856.76 | 2326283.23 | 2.5 | 0 | 0 | 0 | 0 | 10037.813 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 7th Floor RCC 8th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 4th Floor RCC 5th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A -10th Floor RCC 11th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-PCC | PCC Work | Sq.Ft | 0 | 9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Plinth Beam | RCC Beam | Sq.Ft | 0 | 80 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 12th Floor RCC 13th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Soling & PCC | Soling & PCC | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | Hacking Work | Sq.Ft | 10045.078 | 2.5 | 25112.7 | 4520.28 | 29632.98 | 2.5 | 0 | 0 | 0 | 0 | 10045.078 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 9th Floor RCC 10th Slab BUA (L) | Hacking Work | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 13th Floor RCC 14th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 5th Floor RCC 6th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 3rd Floor RCC 4th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 16th Floor RCC 17th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Excavation & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 7 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A-Excavation & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - Ground Floor RCC - 1st Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 135 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A11th Floor RCC 12th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 1st Floor RCC 2nd Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 0 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | Schedule- BC | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | Schedule- BC | Sq.Ft | 10012.985 | 10 | 100129.85 | 18023.38 | 118153.23 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A 14th Floor RCC 15th Slab BUA (L) | Hacking Work | Sq.Ft | 10012.985 | 2.5 | 25032.46 | 4505.84 | 29538.3 | 2.5 | 0 | 0 | 0 | 0 | 10012.985 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 25 | 2 | 23 Mar 2023 | ROHIT CONSTRUCTION | A - 6th Floor RCC 7th Slab BUA (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Mar 2023 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 11 Oct 2023
GANGA ARCADIA - A BUILDING | 46 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Waterproofing Lift Waterproofing | Membrane Horizontal Waterproofing (L) | Sq.Ft | 3273.81 | 13 | 42559.53 | 7660.72 | 50220.25 | 10 | 2793 | 36309 | 6535.62 | 42844.62 | 480.81 | 7375.63 |  | 85.3134 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Oct 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 46 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Retaining Wall Retaining Wall External Waterproofing | Membrane Vertical Waterproofing (L) | Sq.Ft | 5780.68 | 15 | 86710.2 | 15607.84 | 102318.04 | 10 | 2111.5333 | 31673 | 5701.14 | 37374.14 | 3669.1467 | 64943.9 |  | 36.5274 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Oct 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 46 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Waterproofing Lift Waterproofing | Membrane Horizontal Waterproofing (L) | Sq.Ft | 0 | 13 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 02 Oct 2023 |  | 06 WATERPROOFING WORK | Cancelled | ADITYA.CHOUGULE | 02 Oct 2023
GANGA ARCADIA - A BUILDING | 46 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Waterproofing Lift Waterproofing | Membrane Vertical Waterproofing (L) | Sq.Ft | 2587 | 15 | 38805 | 6984.9 | 45789.9 | 10 | 1979.2667 | 29689 | 5344.02 | 35033.02 | 607.7333 | 10756.88 |  | 76.5082 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Oct 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 47 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Retaining Wall Retaining Wall External Waterproofing | Membrane Vertical Waterproofing (M) | Sq.Ft | 5780.68 | 40 | 231227.2 | 41620.9 | 272848.1 | 0 | 2111.5 | 84460 | 15202.8 | 99662.8 | 3669.18 | 173185.3 |  | 36.5268 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Oct 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 47 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Waterproofing Lift Waterproofing | Membrane Horizontal Waterproofing (M) | Sq.Ft | 3273.81 | 34 | 111309.54 | 20035.72 | 131345.26 | 0 | 2313 | 78642 | 14155.56 | 92797.56 | 960.81 | 38547.7 |  | 70.6516 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Oct 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 47 | 0 | 02 Oct 2023 | AQUARIUS WATERPROOFING | Waterproofing Lift Waterproofing | Membrane Vertical Waterproofing (M) | Sq.Ft | 2587 | 40 | 103480 | 18626.4 | 122106.4 | 0 | 2309.275 | 92371 | 16626.78 | 108997.78 | 277.725 | 13108.62 |  | 89.2646 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Oct 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 50 | 0 | 19 Oct 2023 | S.R.Enterprises | Anti-Termite Treatment-Arcadia | Antitermite Treatment - BC] | Sq.Ft | 20783.56 | 4 | 83134.24 | 14964.16 | 98098.4 | 0 | 10680 | 42720 | 5169.6 | 47889.6 | 10103.56 | 50208.8 |  | 51.3868 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 69 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | B Bldg.-Slab Strengthening work | MS Plate (L) | Kgs | 90 | 30.4 | 2736 | 492.48 | 3228.48 | 2.5 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Un-Approved |  | 1900-01-01
GANGA ARCADIA - A BUILDING | 69 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | B Bldg.-Slab Strengthening work | ISMC 150 (L) | Kgs | 153.66 | 25 | 3841.5 | 691.48 | 4532.98 | 2.5 | 0 | 0 | 0 | 0 | 153.66 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ARCADIA - A BUILDING | 69 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | B Bldg.-Slab Strengthening work | ISMC 200 (L) | Kgs | 423.4 | 25 | 10585 | 1905.3 | 12490.3 | 2.5 | 0 | 0 | 0 | 0 | 423.4 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ARCADIA - A BUILDING | 69 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | B Bldg.-Slab Strengthening work | Chemical Fastner 16mm (L) | No. | 48 | 182.4 | 8755.2 | 1575.94 | 10331.14 | 2.5 | 0 | 0 | 0 | 0 | 48 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ARCADIA - A BUILDING | 70 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | B Bldg.-Slab Strengthening work | Chemical Fastener 16mm (M) | No. | 48 | 480 | 23040 | 4147.2 | 27187.2 | 0 | 0 | 0 | 0 | 0 | 48 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Un-Approved |  | 1900-01-01
GANGA ARCADIA - A BUILDING | 70 | 0 | 01 Feb 2024 | R.T.S. STEEL SERVICES | B Bldg.-Slab Strengthening work | MS Plate (M) | Kgs | 90 | 80 | 7200 | 1296 | 8496 | 0 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Un-Approved |  | 1900-01-01
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Varun (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Vasturaviraj Copper Strip (Pyramid) | No. | 0 | 561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | SKS (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | VDDN (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Mandal Remedy | No. | 0 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | MMY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | NG Treatment (L) | No. | 0 | 28050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | HY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Vishwakarma (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | RRY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Vasturaviraj Pyramid Clear Quartz WB - No. | No. | 0 | 1028.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Vasturaviraj Pyramid (with crystal) | No. | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | DB (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | BPBN (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | MSY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | PT/L | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | NY(L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Special Yantra (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | BY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | BM (XL) | No. | 0 | 7012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | SSY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Kamakhya Yantra (XL) | No. | 0 | 7012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | DY (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | GY | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Kamakhya Yantra (Large) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | Navranta 50K | No. | 0 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 83 | 0 | 24 May 2024 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | A-Bldg Vastu Pyramid | GMY | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 08 Jun 2024 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | GMY | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Varun (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | HY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Mandal Remedy | No. | 1 | 108000 | 108000 | 19440 | 127440 | 0 | 1 | 108000 | 280.8 | 108280.8 | 0 | 19159.2 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | PT/L | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Vasturaviraj Pyramid (with crystal) | No. | 174 | 255 | 44370 | 7986.6 | 52356.6 | 0 | 174 | 44370 | 7986.6 | 52356.6 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | SSY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | VDDN (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | NG Treatment (L) | No. | 1 | 28050 | 28050 | 5049 | 33099 | 0 | 1 | 28050 | 5049 | 33099 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | MSY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Vasturaviraj Pyramid Clear Quartz WB - No. | No. | 80 | 1028.5 | 82280 | 14810.4 | 97090.4 | 0 | 80 | 82280 | 14810.4 | 97090.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Kamakhya Yantra (Large) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Kamakhya Yantra (XL) | No. | 1 | 7012.5 | 7012.5 | 1262.26 | 8274.76 | 0 | 1 | 7012.5 | 1262.26 | 8274.76 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Vishwakarma (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | SKS (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | BM (XL) | No. | 1 | 7012.5 | 7012.5 | 1262.26 | 8274.76 | 0 | 1 | 7012.5 | 1262.26 | 8274.76 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | MMY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | DB (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Special Yantra (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Vasturaviraj Copper Strip (Pyramid) | No. | 241 | 561 | 135201 | 24336.18 | 159537.18 | 0 | 241 | 135201 | 24336.18 | 159537.18 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | NY(L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | BPBN (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | DY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | Navranta 50K | No. | 1 | 42500 | 42500 | 7650 | 50150 | 0 | 1 | 42500 | 110.5 | 42610.5 | 0 | 7539.5 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | BY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | RRY (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 88 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | A-Bldg Vastu Pyramid | GY | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 90 | 0 | 10 Jul 2024 | AVCON TECHNICS PVT LTD | A 1st to 2nd Column Rebaring Work | Rebaring work 16mm- cc | No. | 16 | 500 | 8000 | 1440 | 9440 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jul 2024 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 90 | 0 | 10 Jul 2024 | AVCON TECHNICS PVT LTD | A 1st to 2nd Column Rebaring Work | Rebaring work 16mm- cc | No. | 6 | 500 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jul 2024 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 90 | 0 | 10 Jul 2024 | AVCON TECHNICS PVT LTD | A 1st to 2nd Column Rebaring Work | Rebarring work 10mm dia- BC | No. | 6 | 160 | 960 | 172.8 | 1132.8 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 31 Jul 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 93 | 0 | 23 Jul 2024 | SHIVAM ENTERPRISES | Murum Filling Work | Murum Filling (avail earth in site) | Cu.Mtrs | 504 | 60 | 30240 | 0 | 30240 | 0 | 504 | 30240 | 0 | 30240 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 93 | 0 | 23 Jul 2024 | SHIVAM ENTERPRISES | Murum Filling Work | Spreading & Levelling Work | Cu.Mtrs | 2854 | 30 | 85620 | 0 | 85620 | 0 | 2854 | 85620 | 0 | 85620 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 93 | 0 | 23 Jul 2024 | SHIVAM ENTERPRISES | Murum Filling Work | Murum Filling (avail earth in site) | Cu.Mtrs | 241.2 | 60 | 14472 | 0 | 14472 | 0 | 0 | 0 | 0 | 0 | 241.2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 93 | 0 | 23 Jul 2024 | SHIVAM ENTERPRISES | Murum Filling Work | Murum Filling (avail earth in site) | Cu.Mtrs | 2854 | 60 | 171240 | 0 | 171240 | 0 | 2854 | 171240 | 0 | 171240 | 0 | 0 | For all Building area | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 93 | 0 | 23 Jul 2024 | SHIVAM ENTERPRISES | Murum Filling Work | Spreading & Levelling Work | Cu.Mtrs | 241.2 | 30 | 7236 | 0 | 7236 | 0 | 0 | 0 | 0 | 0 | 241.2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 93 | 0 | 23 Jul 2024 | SHIVAM ENTERPRISES | Murum Filling Work | Spreading & Levelling Work | Cu.Mtrs | 504 | 30 | 15120 | 0 | 15120 | 0 | 504 | 15120 | 0 | 15120 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01