## Project_Work_Order6385880311499
Project Work Order
From 01 Jan 2000 To 31 Jul 2024
Page 1 of 1
Total Records: 74 Records 1 To 74
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0.7333 | 4693.12 | 0 | 4693.12 | 0.2667 | 1706.88 |  | 73.33 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | tausif | 27 Mar 2021
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0.8666 | 5546.24 | 0 | 5546.24 | 0.1334 | 853.76 |  | 86.66 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0.9355 | 5987.2 | 0 | 5987.2 | 0.0645 | 412.8 |  | 93.55 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 3 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0.8065 | 5161.6 | 0 | 5161.6 | 0.1935 | 1238.4 |  | 80.65 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 4 | 0 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 0 | 5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 May 2021
GANGA ARCADIA - A BUILDING | 4 | 1 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 0 | 6400 | 0 | 1152 |  | 100 |  | tausif | tausif | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 4 | 2 | 27 Mar 2021 | RADHIKA ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 27 Mar 2021 |  | SOC. M. Maintenace of Aminitie | Approved | Dushant Gore | 08 Aug 2022
GANGA ARCADIA - A BUILDING | 6 | 0 | 08 May 2021 | VIJAY MOHITE | Compound Wall | Labour Lumpsum | No. | 1 | 70000 | 70000 | 0 | 70000 | 0 | 1 | 70000 | 0 | 70000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 11 May 2021 |  | DEV. Ext Development | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 61 | 0 | 29 Dec 2023 | HELIOS | A-Swimming Pool SS Railing Work | SS Railing (L) | R.Ft | 126.416 | 325 | 41085.2 | 7395.34 | 48480.54 | 2.5 | 0 | 0 | 0 | 0 | 126.416 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Jan 2024 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 62 | 0 | 29 Dec 2023 | HELIOS (Material) | A-Swimming Pool SS Railing Work | SS Railing (M) | R.Ft | 126.416 | 625 | 79010 | 14221.8 | 93231.8 | 0 | 0 | 0 | 0 | 0 | 126.416 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Jan 2024 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 68 | 0 | 01 Feb 2024 | SHREE ENTERPRISES | Swimming Pool Cleaning Work | Swimming Pool Cleaning work | Month | 1 | 6400 | 6400 | 0 | 6400 | 0 | 1 | 6400 | 0 | 6400 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Feb 2024 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | 300sqmm 3.5C Alu. Armoud Jointing Kit (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | Removal Of Pole - UTI | No. | 1 | 2200 | 2200 | 396 | 2596 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | 4 way Feeder Pillar fixing-UTI | No. | 1 | 2750 | 2750 | 495 | 3245 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | M.S. Plate (M+L) | No. | 2 | 4400 | 8800 | 1584 | 10384 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | End Termination 300sqmm X 3.5 core cable (M+L) | No. | 3 | 1870 | 5610 | 1009.8 | 6619.8 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | Labour Lumpsum | No. | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | Mtrs | 100 | 99 | 9900 | 1782 | 11682 | 2.5 | 100 | 9900 | 1782 | 11682 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | Pole fixing - UTI | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 78 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | 4 way Feeder Pillar fixing-UTI | No. | 0 | 3800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | MONALI CHAUDHAR | 02 Apr 2024
GANGA ARCADIA - A BUILDING | 79 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | Laying of Arm.Cables & Termination to Pannels | 300sqmm 3.5C Alu. Armoud Jointing Kit (M) | No. | 1 | 3800 | 3800 | 684 | 4484 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01