GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 105 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1503 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 3BHK 202 Kit, Toil, Utility, WB Count Dado | Dado Fixing | Sq.Ft | 479.52 | 23 | 11028.96 | 0 | 11028.96 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 15 | 519.75 | 0 | 519.75 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P5 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-- 204 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23 | 641.24 | 0 | 641.24 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1804 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 15 | 637.8 | 0 | 637.8 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 22 | 11700.26 | 2106.04 | 13806.3 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 202 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23 | 727.95 | 0 | 727.95 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 19.5 | 678.99 | 0 | 678.99 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 16.5 | 571.73 | 0 | 571.73 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1903 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 24.5 | 3921.47 | 0 | 3921.47 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 403 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 206 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23 | 713 | 0 | 713 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1003 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 16.5 | 574.53 | 0 | 574.53 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2701 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1701 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 3BHK 202 Kit, Toil, Utility, WB Count Dado | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2302 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1005 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 25.25 | 17659.6 | 3178.72 | 20838.32 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2201 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 18 | 641.88 | 0 | 641.88 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1001 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2005 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 25 | 11369.25 | 0 | 11369.25 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 16.5 | 1305.15 | 0 | 1305.15 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-- Flat 208 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23 | 641.24 | 0 | 641.24 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2305 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2101 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 207 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23 | 713 | 0 | 713 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1002 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2305 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1705 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.52 | 2 | 71.04 | 0 | 71.04 | 2.5 | 0 | 0 | 0 | 0 | 35.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2402 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 16.5 | 701.58 | 0 | 701.58 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 16 | 11190.24 | 0 | 11190.24 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 16.5 | 574.53 | 0 | 574.53 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 102 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 18 | 623.7 | 0 | 623.7 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 903 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1905 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 16 | 8509.28 | 0 | 8509.28 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2402 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 501 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 1837.26 | 12044.25 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 105 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 404 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 18 | 1229.4 | 0 | 1229.4 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1601 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 25.25 | 13428.71 | 2417.16 | 15845.87 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 16 | 11190.24 | 0 | 11190.24 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 701 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1801 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P3 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2301 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 16 | 11297.6 | 0 | 11297.6 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2201 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2703 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 16.5 | 943.47 | 0 | 943.47 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 35.52 | 2 | 71.04 | 0 | 71.04 | 2.5 | 0 | 0 | 0 | 0 | 35.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 304 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 19 | 8640.63 | 0 | 8640.63 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 2703 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P1 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 701 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1905 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 16 | 11378.08 | 0 | 11378.08 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 401 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 20 | 4309.8 | 0 | 4309.8 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1701 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 805 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 303 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 19 | 8841.46 | 0 | 8841.46 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 208 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 454.74 | 23 | 10459.02 | 0 | 10459.02 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2603 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 602 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2205 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 603 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 464.94 | 2 | 929.88 | 0 | 929.88 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 203 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 465.34 | 23 | 10702.82 | 0 | 10702.82 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1805 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2701 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 28.28 | 12908.1 | 0 | 12908.1 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1203 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 901 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 601 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing1 3BHK 206 Kit, Toil, Utility, WB Count Dado | Dado Fixing | Sq.Ft | 465.22 | 23 | 10700.06 | 0 | 10700.06 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2802 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 903 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 303 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 504 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1602 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1805 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-- Flat 209 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 24 | 3924.24 | 0 | 3924.24 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2401 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 803 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 20.5 | 9539.47 | 0 | 9539.47 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1501 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2702 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1105 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24 | 3947.76 | 0 | 3947.76 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2202 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2801 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2601 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 29.33 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1203 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P4 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 463 | 2 | 926 | 0 | 926 | 2.5 | 0 | 0 | 0 | 0 | 463 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P1 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 15 | 1024.5 | 0 | 1024.5 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 402 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 19 | 9110.88 | 0 | 9110.88 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1905 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2201 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1302 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P5 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1905 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 301 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 19 | 8673.88 | 0 | 8673.88 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P1 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2804 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 19 | 10205.85 | 1837.06 | 12042.91 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 19.5 | 675.68 | 0 | 675.68 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2603 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 29.25 | 4681.76 | 0 | 4681.76 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1703 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 23.5 | 670.69 | 0 | 670.69 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2101 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2004 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 904 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1605 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 22 | 11700.26 | 2106.04 | 13806.3 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P2 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 16.5 | 588.39 | 0 | 588.39 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1002 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1204 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.66 | 15 | 519.9 | 0 | 519.9 | 2.5 | 0 | 0 | 0 | 0 | 34.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1705 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1201 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2703 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 19.5 | 678.99 | 0 | 678.99 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 402 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 464.94 | 2 | 929.88 | 0 | 929.88 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 2703 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 16 | 11190.24 | 0 | 11190.24 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 31.64 | 15 | 474.6 | 0 | 474.6 | 2.5 | 0 | 0 | 0 | 0 | 31.64 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 503 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 21.5 | 3441.29 | 0 | 3441.29 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1902 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1705 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P2 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 22 | 15534.2 | 2796.16 | 18330.36 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2203 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 21.5 | 1229.59 | 0 | 1229.59 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 703 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 205 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1802 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 23.5 | 11268.72 | 0 | 11268.72 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 904 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 19.5 | 675.68 | 0 | 675.68 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 504 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1905 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2403 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 605 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1605 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1403 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 802 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2805 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 18 | 623.7 | 0 | 623.7 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1903 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 23.5 | 10935.49 | 0 | 10935.49 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 102 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2302 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-- 204 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 18 | 1029.24 | 0 | 1029.24 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1804 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1003 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 18 | 1029.42 | 0 | 1029.42 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 15 | 522.3 | 0 | 522.3 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 902 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1004 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 702 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 805 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No.1903 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1905 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 705 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2204 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2105 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 16.5 | 574.53 | 0 | 574.53 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1105 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2804 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 29.25 | 4811.33 | 0 | 4811.33 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2703 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 29.25 | 4681.76 | 0 | 4681.76 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1205 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2303 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2502 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 29.25 | 6365.39 | 0 | 6365.39 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 702 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1105 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 15 | 1056 | 0 | 1056 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2802 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 29.25 | 6365.39 | 0 | 6365.39 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2001 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 19 | 1375.79 | 0 | 1375.79 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 904 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 19 | 10205.85 | 1837.06 | 12042.91 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2405 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1405 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 0 | 662.72 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 802 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1704 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 16.5 | 1305.15 | 0 | 1305.15 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 602 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 803 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 20.5 | 585.07 | 0 | 585.07 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 103 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 19 | 542.26 | 0 | 542.26 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P3 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No.1903 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2202 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 502 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2002 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 401 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 22 | 11817.3 | 2127.12 | 13944.42 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 18 | 765.36 | 0 | 765.36 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1204 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 15 | 819.15 | 0 | 819.15 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 18 | 1423.8 | 0 | 1423.8 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1002 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 23 | 5005.26 | 0 | 5005.26 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 103 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 18 | 623.7 | 0 | 623.7 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2705 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1601 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2505 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1702 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2305 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 20.5 | 10902.52 | 1962.46 | 12864.98 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2703 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1005 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.6 | 1708.88 | 0 | 1708.88 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1502 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 19.5 | 1115.21 | 0 | 1115.21 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1701 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1705 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2602 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 19.5 | 1115.21 | 0 | 1115.21 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1504 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 23.6 | 1349.45 | 0 | 1349.45 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1504 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 19 | 10104.77 | 1818.86 | 11923.63 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1802 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2605 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1403 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 19.5 | 695.37 | 0 | 695.37 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1503 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 23.5 | 670.69 | 0 | 670.69 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 23.6 | 1611.88 | 0 | 1611.88 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2701 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 29.33 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1202 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 16.5 | 1194.77 | 0 | 1194.77 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 20.5 | 14337.5 | 2580.76 | 16918.26 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1401 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 23.6 | 817.74 | 0 | 817.74 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1101 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 23.6 | 1003.47 | 0 | 1003.47 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat 2502 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 29.33 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 17.5 | 12239.33 | 0 | 12239.33 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1805 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1001 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 23.6 | 1866.76 | 0 | 1866.76 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1204 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 23.6 | 1349.68 | 0 | 1349.68 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2205 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 23.6 | 1349.68 | 0 | 1349.68 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2603 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 29.33 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2601 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1201 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1203 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 23 | 3681.38 | 0 | 3681.38 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.6 | 823.17 | 0 | 823.17 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1301 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 101 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 18 | 1423.8 | 0 | 1423.8 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 103 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 20 | 3201.2 | 0 | 3201.2 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1101 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 16 | 8595.36 | 0 | 8595.36 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2203 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 25.5 | 727.77 | 0 | 727.77 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 109 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2701 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1905 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1101 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 402 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1905 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1205 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P2 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 804 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1802 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 20.5 | 14475.05 | 2605.5 | 17080.55 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2603 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 464.94 | 28.28 | 13146.18 | 0 | 13146.18 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1001 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1201 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 15 | 857.85 | 0 | 857.85 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2503 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1503 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 23.5 | 10935.49 | 0 | 10935.49 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20.5 | 11012.81 | 1982.3 | 12995.11 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2004 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 805 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 15 | 522.3 | 0 | 522.3 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 18 | 641.88 | 0 | 641.88 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 601 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 20.5 | 9358.66 | 0 | 9358.66 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1805 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1905 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 20.5 | 14337.5 | 2580.76 | 16918.26 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2702 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 21.5 | 1468.45 | 0 | 1468.45 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 18 | 1029.24 | 0 | 1029.24 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2702 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 28.28 | 13558.43 | 0 | 13558.43 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1402 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No.1903 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 20.5 | 10902.52 | 1962.46 | 12864.98 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 103 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21.5 | 1556.82 | 0 | 1556.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 304 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 101 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1403 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1405 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 20.5 | 10902.52 | 1962.46 | 12864.98 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21.5 | 749.92 | 0 | 749.92 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 15 | 857.7 | 0 | 857.7 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1105 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.66 | 2 | 69.32 | 0 | 69.32 | 2.5 | 0 | 0 | 0 | 0 | 34.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No.1903 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P1 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2105 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 705 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 19 | 13415.9 | 2414.86 | 15830.76 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 16 | 11297.6 | 0 | 11297.6 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 801 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2401 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 26 | 5602.74 | 0 | 5602.74 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2805 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 28.28 | 12858.62 | 0 | 12858.62 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 209 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 478.97 | 23 | 11016.31 | 0 | 11016.31 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 601 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1602 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 603 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 16.5 | 701.58 | 0 | 701.58 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 602 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 20.5 | 9830.16 | 0 | 9830.16 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)- 201 Kitchen, Toilet, Utility, WB Counter - D | Dado Fixing | Sq.Ft | 456.52 | 23 | 10499.96 | 0 | 10499.96 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 22 | 11817.3 | 2127.12 | 13944.42 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2504 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 29.25 | 4811.33 | 0 | 4811.33 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 503 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 16 | 8595.36 | 0 | 8595.36 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 305 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 902 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2704 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 28.28 | 12858.62 | 0 | 12858.62 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 17.5 | 9307.03 | 0 | 9307.03 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 405 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1803 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1403 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2703 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 17.5 | 12239.33 | 0 | 12239.33 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2602 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 29.25 | 6365.39 | 0 | 6365.39 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1902 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1202 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 704 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P4 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 17.5 | 9401.18 | 0 | 9401.18 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 405 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 17.5 | 9401.18 | 0 | 9401.18 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2002 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 17.5 | 9307.03 | 0 | 9307.03 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1601 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 23.5 | 10728.22 | 0 | 10728.22 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1504 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)- Flat 305 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 17.5 | 9400.13 | 0 | 9400.13 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 22 | 11700.26 | 2106.04 | 13806.3 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 203 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1101 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 39.93 | 2 | 79.86 | 0 | 79.86 | 2.5 | 0 | 0 | 0 | 0 | 39.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1304 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2105 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 206 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 24 | 5226.96 | 0 | 5226.96 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 302 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1303 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 23 | 3681.38 | 0 | 3681.38 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1402 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 22 | 10549.44 | 0 | 10549.44 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1802 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 602 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 22 | 11817.3 | 2127.12 | 13944.42 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 504 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 204 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23 | 10459.71 | 0 | 10459.71 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2705 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1202 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 23 | 5005.26 | 0 | 5005.26 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat 2502 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1603 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1002 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1201 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 23 | 4956.27 | 0 | 4956.27 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 202 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 24 | 5222.88 | 0 | 5222.88 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 305 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P2 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 20 | 4352.4 | 0 | 4352.4 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 501 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 603 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2305 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 207 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 24 | 5226.96 | 0 | 5226.96 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 803 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 21.5 | 744.98 | 0 | 744.98 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 904 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1702 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 23.5 | 11268.72 | 0 | 11268.72 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1503 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 24.5 | 3921.47 | 0 | 3921.47 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2505 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.6 | 769.49 | 0 | 769.49 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 905 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2204 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 25 | 11369.25 | 0 | 11369.25 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2503 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 28.28 | 13157.49 | 0 | 13157.49 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1904 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2603 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 27.6 | 787.7 | 0 | 787.7 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2501 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2303 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 25 | 11633.5 | 0 | 11633.5 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21.5 | 1556.82 | 0 | 1556.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 301 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2605 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1905 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 901 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19 | 646.19 | 0 | 646.19 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 15 | 1056 | 0 | 1056 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1302 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 22 | 10549.44 | 0 | 10549.44 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P4 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 15 | 1186.5 | 0 | 1186.5 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 802 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 20.5 | 9830.16 | 0 | 9830.16 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2303 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1901 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 15 | 510.15 | 0 | 510.15 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19 | 1472.5 | 0 | 1472.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 804 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 901 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 20.5 | 9358.66 | 0 | 9358.66 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 21.5 | 1229.37 | 0 | 1229.37 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1504 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 21.5 | 1468.45 | 0 | 1468.45 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 203 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 501 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 21.5 | 4633.04 | 0 | 4633.04 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1904 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 703 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 20.5 | 9539.47 | 0 | 9539.47 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 16 | 8509.28 | 0 | 8509.28 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2201 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 25 | 11413 | 0 | 11413 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2003 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1803 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 18 | 765.36 | 0 | 765.36 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 404 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1703 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 23.5 | 10935.49 | 0 | 10935.49 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 805 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1904 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2403 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 25 | 11633.5 | 0 | 11633.5 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1505 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 18 | 765.36 | 0 | 765.36 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 503 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21.5 | 1556.82 | 0 | 1556.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 106 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1904 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1804 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2603 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 19 | 661.58 | 0 | 661.58 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 703 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 18 | 641.88 | 0 | 641.88 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 21.5 | 744.98 | 0 | 744.98 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2301 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 25 | 11413 | 0 | 11413 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1901 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 15 | 1086.15 | 0 | 1086.15 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2101 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2502 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 27.6 | 873.54 | 0 | 873.54 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 21.5 | 748.63 | 0 | 748.63 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2702 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2804 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1202 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 21.5 | 1700.65 | 0 | 1700.65 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1803 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 18 | 626.76 | 0 | 626.76 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2401 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 25 | 11413 | 0 | 11413 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 18 | 1029.24 | 0 | 1029.24 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 801 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 603 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2201 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2203 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 25 | 11633.5 | 0 | 11633.5 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 805 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 502 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2705 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.6 | 769.49 | 0 | 769.49 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 107 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 704 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 16.5 | 1126.95 | 0 | 1126.95 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 20.5 | 14475.05 | 2605.5 | 17080.55 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 20.5 | 14337.5 | 2580.76 | 16918.26 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 16.5 | 1126.95 | 0 | 1126.95 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 805 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1302 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2003 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 26 | 4161.56 | 0 | 4161.56 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 16.5 | 943.64 | 0 | 943.64 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20.5 | 11012.81 | 1982.3 | 12995.11 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1003 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P5 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 20 | 4355.8 | 0 | 4355.8 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2702 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P1 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1304 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 801 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2204 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2805 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 1837.26 | 12044.25 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat 2502 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1502 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1805 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 18 | 1029.42 | 0 | 1029.42 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1504 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 902 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 19.5 | 829.14 | 0 | 829.14 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1704 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21.5 | 867.96 | 0 | 867.96 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 19.5 | 1115.01 | 0 | 1115.01 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 102 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1505 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1603 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 24.5 | 3921.47 | 0 | 3921.47 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 25.25 | 17829.03 | 3209.22 | 21038.25 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P2 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 477.1 | 2 | 954.2 | 0 | 954.2 | 2.5 | 0 | 0 | 0 | 0 | 477.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 21.5 | 1229.37 | 0 | 1229.37 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1001 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 106 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2602 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1103 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 22 | 627.88 | 0 | 627.88 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1401 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 601 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 21.5 | 4633.04 | 0 | 4633.04 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1302 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 402 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1704 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1005 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1405 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 603 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 20.5 | 585.07 | 0 | 585.07 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2205 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 107 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 19.5 | 695.37 | 0 | 695.37 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 19.5 | 675.68 | 0 | 675.68 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20 | 14222.6 | 0 | 14222.6 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 0 | 662.72 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1004 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.52 | 19 | 674.88 | 0 | 674.88 | 2.5 | 0 | 0 | 0 | 0 | 35.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 23.6 | 817.74 | 0 | 817.74 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.6 | 952.73 | 0 | 952.73 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 19 | 1086.42 | 0 | 1086.42 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.6 | 823.17 | 0 | 823.17 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.6 | 1708.88 | 0 | 1708.88 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.6 | 1661.44 | 0 | 1661.44 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 102 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2102 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 26 | 5658.12 | 0 | 5658.12 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19 | 767.03 | 0 | 767.03 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 304 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1901 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1301 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1501 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2301 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 106 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2402 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 16.5 | 1305.15 | 0 | 1305.15 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 16.5 | 588.39 | 0 | 588.39 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2704 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21.5 | 867.96 | 0 | 867.96 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 21.5 | 1468.45 | 0 | 1468.45 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 18 | 623.7 | 0 | 623.7 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1404 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2505 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 28.28 | 12858.62 | 0 | 12858.62 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 21.5 | 914.18 | 0 | 914.18 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 25.25 | 13428.71 | 2417.16 | 15845.87 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 905 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 18 | 765.36 | 0 | 765.36 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 801 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 20.5 | 9358.66 | 0 | 9358.66 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 21.5 | 1700.65 | 0 | 1700.65 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 505 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2601 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 18 | 1423.8 | 0 | 1423.8 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 904 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1403 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 23 | 3681.38 | 0 | 3681.38 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 902 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 20.5 | 9830.16 | 0 | 9830.16 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 503 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 19.5 | 1542.45 | 0 | 1542.45 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 22 | 15534.2 | 2796.16 | 18330.36 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 15 | 1186.5 | 0 | 1186.5 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 1837.26 | 12044.25 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1103 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 23 | 3681.38 | 0 | 3681.38 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 505 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1305 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1404 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 15 | 1186.5 | 0 | 1186.5 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2002 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1405 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 102 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 32.82 | 15 | 492.3 | 0 | 492.3 | 2.5 | 0 | 0 | 0 | 0 | 32.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2102 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 15 | 519.75 | 0 | 519.75 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 21.5 | 1229.59 | 0 | 1229.59 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2203 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2404 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2504 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 28.28 | 12858.62 | 0 | 12858.62 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 801 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2001 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 101 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 20 | 4309.8 | 0 | 4309.8 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 15 | 522.3 | 0 | 522.3 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1204 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P1 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 468.64 | 19 | 8904.16 | 0 | 8904.16 | 2.5 | 0 | 0 | 0 | 0 | 468.64 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 605 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2405 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 701 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 20.5 | 9358.66 | 0 | 9358.66 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1502 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 105 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 301 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 20 | 4309.8 | 0 | 4309.8 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1504 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24 | 3947.76 | 0 | 3947.76 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21.5 | 749.92 | 0 | 749.92 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2001 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2005 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1305 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2803 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2805 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2404 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 32.5 | 2 | 65 | 0 | 65 | 2.5 | 0 | 0 | 0 | 0 | 32.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1205 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2202 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2204 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1801 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 23.5 | 10728.22 | 0 | 10728.22 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 405 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1903 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1004 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20 | 10744.2 | 0 | 10744.2 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1901 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 24.5 | 5279.51 | 0 | 5279.51 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1403 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 22 | 10237.48 | 0 | 10237.48 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2405 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 805 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 403 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 19.5 | 829.14 | 0 | 829.14 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1301 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1402 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1301 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 22 | 10043.44 | 0 | 10043.44 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1901 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 23.5 | 10728.22 | 0 | 10728.22 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 25.25 | 13564.55 | 2441.62 | 16006.17 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P5 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1404 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1601 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2503 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 29.25 | 4681.76 | 0 | 4681.76 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2304 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1101 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 22 | 10043.44 | 0 | 10043.44 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 16.5 | 571.73 | 0 | 571.73 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 19.5 | 695.37 | 0 | 695.37 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2302 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 16.5 | 1126.95 | 0 | 1126.95 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 701 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2603 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 464.94 | 2 | 929.88 | 0 | 929.88 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 405 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 19 | 529.72 | 0 | 529.72 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 101 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.6 | 952.73 | 0 | 952.73 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)- Flat 305 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P1 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 23.6 | 1866.76 | 0 | 1866.76 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2001 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1705 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2802 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1205 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1203 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1503 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1201 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 22 | 10043.44 | 0 | 10043.44 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 25.25 | 17659.6 | 3178.72 | 20838.32 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1501 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P3 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1401 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1905 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2003 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 25.5 | 727.77 | 0 | 727.77 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1105 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1805 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1505 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1102 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 16.5 | 943.47 | 0 | 943.47 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 19.5 | 675.68 | 0 | 675.68 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 20 | 10743 | 0 | 10743 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 16.5 | 571.73 | 0 | 571.73 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 464.94 | 2 | 929.88 | 0 | 929.88 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 19.5 | 1331.85 | 0 | 1331.85 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1601 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1804 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2404 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 802 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 405 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 18 | 623.7 | 0 | 623.7 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 602 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 16.5 | 588.39 | 0 | 588.39 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2304 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 605 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 601 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19 | 1337.6 | 0 | 1337.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2403 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 26 | 4161.56 | 0 | 4161.56 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2203 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2803 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 504 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 209 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 16.5 | 571.73 | 0 | 571.73 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1703 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 24.5 | 3921.47 | 0 | 3921.47 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 464.94 | 2 | 929.88 | 0 | 929.88 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2203 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2304 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 16.5 | 1126.95 | 0 | 1126.95 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 16.5 | 943.64 | 0 | 943.64 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 802 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 21.5 | 4678.83 | 0 | 4678.83 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1204 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2303 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2202 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1002 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 19.5 | 1115.21 | 0 | 1115.21 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21.5 | 867.96 | 0 | 867.96 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1205 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 0 | 662.72 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1002 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 22 | 10549.44 | 0 | 10549.44 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2702 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 29.25 | 6365.39 | 0 | 6365.39 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21.5 | 867.96 | 0 | 867.96 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 103 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 464.94 | 19 | 8833.86 | 0 | 8833.86 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2204 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21.5 | 749.92 | 0 | 749.92 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 504 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2605 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 703 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2203 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1501 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 23.5 | 10728.22 | 0 | 10728.22 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1103 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 21.5 | 1700.65 | 0 | 1700.65 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1601 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 24.5 | 5279.51 | 0 | 5279.51 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 902 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2101 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2205 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21.5 | 749.92 | 0 | 749.92 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 804 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 32.82 | 2 | 65.64 | 0 | 65.64 | 2.5 | 0 | 0 | 0 | 0 | 32.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2404 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 20.5 | 11011.58 | 1982.08 | 12993.66 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 903 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2601 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 28.28 | 12908.1 | 0 | 12908.1 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 405 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 19.5 | 1412 | 0 | 1412 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2403 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No.1903 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 107 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P3 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 106 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 503 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 20.5 | 9539.47 | 0 | 9539.47 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 103 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 902 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 101 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2801 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 28.28 | 12908.1 | 0 | 12908.1 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 16 | 11297.6 | 0 | 11297.6 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 17.5 | 12356.75 | 0 | 12356.75 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 25.25 | 13564.55 | 2441.62 | 16006.17 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 38.75 | 2 | 77.5 | 0 | 77.5 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.6 | 823.17 | 0 | 823.17 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.6 | 952.73 | 0 | 952.73 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 23.6 | 841.58 | 0 | 841.58 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 16 | 8594.4 | 0 | 8594.4 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)- Flat 305 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 19 | 529.72 | 0 | 529.72 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 23.6 | 1611.88 | 0 | 1611.88 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 21.5 | 766.69 | 0 | 766.69 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2205 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2203 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 26 | 4161.56 | 0 | 4161.56 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P4 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 19 | 529.72 | 0 | 529.72 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 901 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 21.5 | 4633.04 | 0 | 4633.04 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1903 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 23.5 | 670.69 | 0 | 670.69 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 21.5 | 1468.45 | 0 | 1468.45 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 801 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 16.5 | 943.47 | 0 | 943.47 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P1 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 468.64 | 2 | 937.28 | 0 | 937.28 | 2.5 | 0 | 0 | 0 | 0 | 468.64 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 38.75 | 15 | 581.25 | 0 | 581.25 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 601 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2801 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 29.33 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 404 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 19 | 529.72 | 0 | 529.72 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 2703 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 19.5 | 1331.85 | 0 | 1331.85 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 21.5 | 748.63 | 0 | 748.63 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2001 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 25 | 11413 | 0 | 11413 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19 | 767.03 | 0 | 767.03 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 15 | 857.85 | 0 | 857.85 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 25.25 | 13563.04 | 2441.34 | 16004.38 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1901 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2602 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 27.6 | 873.54 | 0 | 873.54 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2101 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 26 | 5602.74 | 0 | 5602.74 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 19.5 | 1331.85 | 0 | 1331.85 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2102 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 25 | 11988 | 0 | 11988 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1802 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 101 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 15 | 637.8 | 0 | 637.8 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1804 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 16.5 | 1194.77 | 0 | 1194.77 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2504 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.6 | 769.49 | 0 | 769.49 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P3 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 20 | 3201.2 | 0 | 3201.2 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 19.5 | 678.99 | 0 | 678.99 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1102 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2803 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 27.6 | 787.7 | 0 | 787.7 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 16.5 | 588.39 | 0 | 588.39 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 402 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 20 | 4352.4 | 0 | 4352.4 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2301 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 26 | 5602.74 | 0 | 5602.74 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P4 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1102 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2303 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 26 | 4161.56 | 0 | 4161.56 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2205 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 25 | 11369.25 | 0 | 11369.25 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 702 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 505 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1004 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 25.25 | 13428.71 | 2417.16 | 15845.87 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 105 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P5 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 19 | 10104.77 | 1818.86 | 11923.63 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1203 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 22 | 627.88 | 0 | 627.88 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2704 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.6 | 769.49 | 0 | 769.49 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 19.5 | 829.14 | 0 | 829.14 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1201 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 19 | 10104.77 | 1818.86 | 11923.63 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1304 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2801 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 27.6 | 873.54 | 0 | 873.54 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 25.25 | 13563.04 | 2441.34 | 16004.38 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1304 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1402 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 23 | 5005.26 | 0 | 5005.26 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 905 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19 | 767.03 | 0 | 767.03 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 25.25 | 17659.6 | 3178.72 | 20838.32 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1102 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 23 | 5005.26 | 0 | 5005.26 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 505 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 22 | 15386.58 | 2769.58 | 18156.16 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P2 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 20 | 14122 | 0 | 14122 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P4 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2004 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 17.5 | 9400.13 | 0 | 9400.13 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 2127.36 | 13945.98 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 17.5 | 9401.18 | 0 | 9401.18 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1404 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20 | 14222.6 | 0 | 14222.6 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1004 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 18 | 765.36 | 0 | 765.36 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 22 | 15534.2 | 2796.16 | 18330.36 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2202 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 25 | 11988 | 0 | 11988 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21.5 | 749.92 | 0 | 749.92 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 21.5 | 1229.37 | 0 | 1229.37 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2702 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 27.6 | 873.54 | 0 | 873.54 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2405 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 25 | 11369.25 | 0 | 11369.25 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21.5 | 867.96 | 0 | 867.96 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2305 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 20 | 10704.2 | 0 | 10704.2 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 20 | 13987.8 | 0 | 13987.8 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2005 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1402 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 15 | 519.75 | 0 | 519.75 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 101 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 32.83 | 19 | 623.77 | 0 | 623.77 | 2.5 | 0 | 0 | 0 | 0 | 32.83 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 2127.36 | 13945.98 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2103 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 25.5 | 727.77 | 0 | 727.77 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 15 | 637.8 | 0 | 637.8 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P2 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P3 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 705 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 21.5 | 748.63 | 0 | 748.63 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1603 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1702 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 24.5 | 5331.69 | 0 | 5331.69 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 19 | 13288.41 | 2391.92 | 15680.33 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2503 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1505 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1603 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 464.94 | 2 | 929.88 | 0 | 929.88 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2002 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 26 | 5658.12 | 0 | 5658.12 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2005 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 16.5 | 943.47 | 0 | 943.47 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P3 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 19 | 542.26 | 0 | 542.26 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 15 | 534.9 | 0 | 534.9 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 20.5 | 14475.05 | 2605.5 | 17080.55 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2304 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2101 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 22 | 15386.58 | 2769.58 | 18156.16 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 18 | 626.76 | 0 | 626.76 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1703 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 16 | 8509.28 | 0 | 8509.28 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.52 | 15 | 532.8 | 0 | 532.8 | 2.5 | 0 | 0 | 0 | 0 | 35.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 18 | 1423.8 | 0 | 1423.8 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 21.5 | 766.69 | 0 | 766.69 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 20.5 | 10902.52 | 1962.46 | 12864.98 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2405 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1202 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 22 | 10549.44 | 0 | 10549.44 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2102 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 16 | 8595.36 | 0 | 8595.36 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 15 | 534.9 | 0 | 534.9 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1301 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 19.5 | 829.14 | 0 | 829.14 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 16 | 11297.6 | 0 | 11297.6 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1801 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2003 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1802 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 24.5 | 5331.69 | 0 | 5331.69 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1101 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1101 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 20.5 | 11011.58 | 1982.08 | 12993.66 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 16 | 8594.4 | 0 | 8594.4 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 405 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 15 | 1056 | 0 | 1056 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2605 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 28.28 | 12858.62 | 0 | 12858.62 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 21.5 | 748.63 | 0 | 748.63 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2005 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P5 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 20.5 | 14337.5 | 2580.76 | 16918.26 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)- 201 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2801 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 502 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 20.5 | 9830.16 | 0 | 9830.16 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1602 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 23.5 | 11268.72 | 0 | 11268.72 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1702 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 108 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 19 | 13288.41 | 2391.92 | 15680.33 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 20.5 | 11011.58 | 1982.08 | 12993.66 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)- Flat 304 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 25.25 | 17829.03 | 3209.22 | 21038.25 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 102 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 905 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 501 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 20.5 | 9358.66 | 0 | 9358.66 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 1837.26 | 12044.25 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19 | 767.03 | 0 | 767.03 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 25.25 | 13564.55 | 2441.62 | 16006.17 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 901 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 20.5 | 14337.5 | 2580.76 | 16918.26 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2204 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1402 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2705 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 28.28 | 12858.62 | 0 | 12858.62 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 19.5 | 695.37 | 0 | 695.37 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1804 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 20.5 | 11011.58 | 1982.08 | 12993.66 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 704 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 20.5 | 9322.79 | 0 | 9322.79 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 403 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 20 | 3201.2 | 0 | 3201.2 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 32.5 | 15 | 487.5 | 0 | 487.5 | 2.5 | 0 | 0 | 0 | 0 | 32.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1703 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 18 | 626.76 | 0 | 626.76 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 21.5 | 766.69 | 0 | 766.69 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 21.5 | 766.69 | 0 | 766.69 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 901 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 21.5 | 914.18 | 0 | 914.18 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 15 | 519.75 | 0 | 519.75 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 601 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 102 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 301 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P2 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 305 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 19 | 8640.63 | 0 | 8640.63 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 704 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 805 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2505 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 29.25 | 4811.33 | 0 | 4811.33 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 15 | 1024.5 | 0 | 1024.5 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2605 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 29.25 | 4811.33 | 0 | 4811.33 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 18 | 1029.42 | 0 | 1029.42 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat P1 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 20 | 4309.8 | 0 | 4309.8 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2601 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 29.25 | 6303.08 | 0 | 6303.08 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 21.5 | 766.69 | 0 | 766.69 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2102 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 401 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 703 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 21.5 | 3441.29 | 0 | 3441.29 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 15 | 1162.5 | 0 | 1162.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 302 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 20 | 4352.4 | 0 | 4352.4 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 18 | 626.76 | 0 | 626.76 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 32.82 | 2 | 65.64 | 0 | 65.64 | 2.5 | 0 | 0 | 0 | 0 | 32.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2802 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 502 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.6 | 823.17 | 0 | 823.17 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 15 | 522.3 | 0 | 522.3 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 23.6 | 1611.88 | 0 | 1611.88 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 903 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 17.5 | 12239.33 | 0 | 12239.33 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 107 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.6 | 1708.88 | 0 | 1708.88 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 19 | 1086.61 | 0 | 1086.61 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.6 | 1661.44 | 0 | 1661.44 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 505 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 19 | 1037.59 | 0 | 1037.59 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2103 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 15 | 534.9 | 0 | 534.9 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 19 | 807.88 | 0 | 807.88 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 403 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 19 | 542.26 | 0 | 542.26 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2405 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 19 | 10104.77 | 1818.86 | 11923.63 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 605 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2404 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 401 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 15 | 857.85 | 0 | 857.85 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2801 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2502 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1502 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 23.5 | 11268.72 | 0 | 11268.72 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1704 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1405 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 18 | 1229.4 | 0 | 1229.4 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P2 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2801 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 29.25 | 6303.08 | 0 | 6303.08 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1203 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 106 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 18 | 1029.42 | 0 | 1029.42 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 903 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2001 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 26 | 5602.74 | 0 | 5602.74 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2403 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 19 | 1502.9 | 0 | 1502.9 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 401 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1602 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 24.5 | 5331.69 | 0 | 5331.69 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1803 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2704 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P5 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 463.24 | 2 | 926.48 | 0 | 926.48 | 2.5 | 0 | 0 | 0 | 0 | 463.24 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1702 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1805 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1904 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1705 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 19.5 | 695.37 | 0 | 695.37 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 19.5 | 1412 | 0 | 1412 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1602 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 38.75 | 2 | 77.5 | 0 | 77.5 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 19.5 | 829.14 | 0 | 829.14 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 23.6 | 821.75 | 0 | 821.75 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1601 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)- 201 Kitchen, Toilet, Utility, WB Counter - D | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 205 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1501 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.6 | 1661.44 | 0 | 1661.44 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1603 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 23.5 | 670.69 | 0 | 670.69 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1301 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 23 | 4956.27 | 0 | 4956.27 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2503 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 23.6 | 841.58 | 0 | 841.58 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2605 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.6 | 769.49 | 0 | 769.49 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2804 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.6 | 769.49 | 0 | 769.49 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2103 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 464.94 | 25 | 11623.5 | 0 | 11623.5 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 16.5 | 701.58 | 0 | 701.58 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2101 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 25 | 11413 | 0 | 11413 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1904 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 23.6 | 1611.88 | 0 | 1611.88 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1904 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 23.6 | 817.74 | 0 | 817.74 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 16.5 | 943.64 | 0 | 943.64 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 701 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 502 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 504 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 204 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 502 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1801 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 203 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 109 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 34.66 | 2 | 69.32 | 0 | 69.32 | 2.5 | 0 | 0 | 0 | 0 | 34.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19 | 646.19 | 0 | 646.19 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 106 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1402 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 21.5 | 744.98 | 0 | 744.98 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 16.5 | 571.73 | 0 | 571.73 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 803 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 21.5 | 3441.29 | 0 | 3441.29 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 602 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 21.5 | 4678.83 | 0 | 4678.83 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.19 | 16.5 | 943.64 | 0 | 943.64 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 903 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 21.5 | 3441.29 | 0 | 3441.29 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1702 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1802 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2301 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2302 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 26 | 5658.12 | 0 | 5658.12 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2802 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)- Flat 303 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 20 | 3201.2 | 0 | 3201.2 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 101 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2601 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 29.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2004 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25.5 | 710.94 | 0 | 710.94 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P5 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 19 | 589 | 0 | 589 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1703 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1903 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat 2405 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1404 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1503 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 704 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 801 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 21.5 | 4633.04 | 0 | 4633.04 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 905 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 501 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 18 | 1229.4 | 0 | 1229.4 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 702 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 505 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2003 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 18 | 1229.4 | 0 | 1229.4 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 804 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 18 | 1229.4 | 0 | 1229.4 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1903 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 18 | 641.88 | 0 | 641.88 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 18 | 1423.8 | 0 | 1423.8 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 302 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1605 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 802 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 25.25 | 17829.03 | 3209.22 | 21038.25 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 16.5 | 701.58 | 0 | 701.58 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 16.5 | 1305.15 | 0 | 1305.15 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1305 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1704 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1003 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 22 | 627.88 | 0 | 627.88 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1203 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2005 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 27 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1204 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1402 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1001 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 22 | 10043.44 | 0 | 10043.44 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1201 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Balcony Flooring | Schedule & Quality | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1103 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 464.94 | 22 | 10228.68 | 0 | 10228.68 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1902 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 23.5 | 11268.72 | 0 | 11268.72 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1102 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 22 | 10549.44 | 0 | 10549.44 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2005 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)- 201 Kitchen, Toilet, Utility, WB Counter - D | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 109 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1705 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1905 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 301 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1205 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 19.5 | 678.99 | 0 | 678.99 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 802 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1003 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 23 | 3681.38 | 0 | 3681.38 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1103 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 605 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 2703 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 22 | 15534.2 | 2796.16 | 18330.36 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1505 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1105 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 803 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 902 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P4 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1701 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 24.5 | 5279.51 | 0 | 5279.51 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 901 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 17.5 | 9400.13 | 0 | 9400.13 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 17.5 | 9307.03 | 0 | 9307.03 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 106 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 17.5 | 12356.75 | 0 | 12356.75 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2405 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2101 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 25.5 | 807.08 | 0 | 807.08 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 404 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 905 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 702 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 801 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 704 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 19 | 13288.41 | 2391.92 | 15680.33 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 102 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1202 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 19 | 13415.9 | 2414.86 | 15830.76 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2803 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 903 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 20.5 | 9539.47 | 0 | 9539.47 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 209 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-- Flat 208 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24 | 3947.76 | 0 | 3947.76 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 20.5 | 14475.05 | 2605.5 | 17080.55 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2505 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 102 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 205 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19 | 1337.6 | 0 | 1337.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 701 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 3BHK 202 Kit, Toil, Utility, WB Count Dado | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 204 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2002 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2502 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 23.6 | 1866.76 | 0 | 1866.76 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.6 | 1661.44 | 0 | 1661.44 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 23.6 | 841.58 | 0 | 841.58 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2505 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.6 | 823.17 | 0 | 823.17 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 23.6 | 821.75 | 0 | 821.75 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 101 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 79.1 | 21.5 | 1700.65 | 0 | 1700.65 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1803 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 23.5 | 10935.49 | 0 | 10935.49 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2602 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 403 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 705 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 605 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1101 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 105 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 602 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 20.5 | 648.83 | 0 | 648.83 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1701 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 15 | 1086.15 | 0 | 1086.15 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1201 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 15 | 857.7 | 0 | 857.7 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1005 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2304 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)Flat No. 801 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1602 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2701 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1004 Flat Flooring | Schedule & Quality | Sq.Ft | 537.15 | 2 | 1074.3 | 0 | 1074.3 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2804 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21.5 | 1556.82 | 0 | 1556.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1102 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 603 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1403 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 22 | 627.88 | 0 | 627.88 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 206 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19 | 1472.5 | 0 | 1472.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P4 Kitchen Toilet Utility WB counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2601 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1405 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1403 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1605 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1901 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1902 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 24.5 | 5331.69 | 0 | 5331.69 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1703 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 39.93 | 2 | 79.86 | 0 | 79.86 | 2.5 | 0 | 0 | 0 | 0 | 39.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1005 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2402 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1202 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1501 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 24.5 | 5279.51 | 0 | 5279.51 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1302 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1904 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 801 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2401 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 705 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 19.5 | 1115.01 | 0 | 1115.01 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 109 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1903 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.34 | 2 | 930.68 | 0 | 930.68 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2203 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 19 | 1037.59 | 0 | 1037.59 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1303 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1704 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1501 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1003 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2403 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 21.5 | 914.18 | 0 | 914.18 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 2127.36 | 13945.98 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21.5 | 1513.6 | 0 | 1513.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 699.39 | 22 | 15386.58 | 2769.58 | 18156.16 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2204 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 22 | 11700.26 | 2106.04 | 13806.3 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 704 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 801 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1503 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2602 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1305 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 702 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 20.5 | 9830.16 | 0 | 9830.16 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2504 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2602 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 28.28 | 13558.43 | 0 | 13558.43 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | Swapnil Erande | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2705 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 30.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 105 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1505 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P3 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 801 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2205 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 402 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 479.52 | 2 | 959.04 | 0 | 959.04 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2002 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1401 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2404 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Utility Flooring | Schedule & Quality | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 503 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 20.5 | 585.07 | 0 | 585.07 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 804 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1002 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 601 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 207 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 302 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 19 | 677.54 | 0 | 677.54 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 16.5 | 943.47 | 0 | 943.47 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 702 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 21.5 | 4678.83 | 0 | 4678.83 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1502 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 19.5 | 1331.85 | 0 | 1331.85 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1605 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1303 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 22 | 627.88 | 0 | 627.88 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 16.5 | 701.58 | 0 | 701.58 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 705 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1801 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 19.5 | 1331.85 | 0 | 1331.85 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1404 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1205 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1202 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 405 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 204 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 304 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 101 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1303 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 403 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 19 | 8841.46 | 0 | 8841.46 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2705 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 29.25 | 4811.33 | 0 | 4811.33 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1001 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 18 | 1029.24 | 0 | 1029.24 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1902 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 23.5 | 743.78 | 0 | 743.78 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 305 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 531.83 | 19 | 10104.77 | 1818.86 | 11923.63 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1501 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 68.3 | 16.5 | 1126.95 | 0 | 1126.95 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1803 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 24.5 | 3921.47 | 0 | 3921.47 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 101 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 19 | 601.35 | 0 | 601.35 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 701 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2103 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 26 | 4161.56 | 0 | 4161.56 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 904 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20.5 | 11012.81 | 1982.3 | 12995.11 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1305 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1502 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 20.5 | 14475.05 | 2605.5 | 17080.55 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2004 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 57.18 | 21.5 | 1229.37 | 0 | 1229.37 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2202 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 22 | 15534.2 | 2796.16 | 18330.36 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21.5 | 867.96 | 0 | 867.96 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2001 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 2103 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 42.52 | 21.5 | 914.18 | 0 | 914.18 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1401 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 23 | 4956.27 | 0 | 4956.27 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 202 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1805 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1802 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 402 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 103 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 201 101 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 32.83 | 2 | 65.66 | 0 | 65.66 | 2.5 | 0 | 0 | 0 | 0 | 32.83 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat 2502 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 28.28 | 13558.43 | 0 | 13558.43 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 804 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 205 Kitchen, Toilet, Utility, WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23 | 10459.71 | 0 | 10459.71 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2704 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1904 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 23.5 | 10687.1 | 0 | 10687.1 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1203 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 204 Kitchen, Toilet, Utility, WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 208 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19 | 1337.6 | 0 | 1337.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2105 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2803 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 160.06 | 29.25 | 4681.76 | 0 | 4681.76 | 2.5 | 0 | 0 | 0 | 0 | 160.06 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK) Flat P2 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 477.1 | 19 | 9064.9 | 0 | 9064.9 | 2.5 | 0 | 0 | 0 | 0 | 477.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 1901 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2701 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 29.25 | 6303.08 | 0 | 6303.08 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2603 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 201 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 2303 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 28.54 | 25.5 | 727.77 | 0 | 727.77 | 2.5 | 0 | 0 | 0 | 0 | 28.54 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2501 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 29.25 | 6303.08 | 0 | 6303.08 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 25.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2402 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.62 | 26 | 5658.12 | 0 | 5658.12 | 2.5 | 0 | 0 | 0 | 0 | 217.62 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat P4 Kitchen Toilet Utility WB counter | Dado Fixing | Sq.Ft | 463 | 19 | 8797 | 0 | 8797 | 2.5 | 0 | 0 | 0 | 0 | 463 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 302 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 401 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 302 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 479.52 | 19 | 9110.88 | 0 | 9110.88 | 2.5 | 0 | 0 | 0 | 0 | 479.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 902 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 605 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P2 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2001 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 705 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2305 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)207 Kit, Toi, Utility, WB Count Dado | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2102 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1301 Flat Flooring | Schedule & Quality | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1902 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.19 | 2 | 114.38 | 0 | 114.38 | 2.5 | 0 | 0 | 0 | 0 | 57.19 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 702 Toilet Flooring | Schedule & Quality | Sq.Ft | 79.1 | 2 | 158.2 | 0 | 158.2 | 2.5 | 0 | 0 | 0 | 0 | 79.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1603 Utility Flooring | Schedule & Quality | Sq.Ft | 35.66 | 2 | 71.32 | 0 | 71.32 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1204 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1803 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1305 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 602 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2501 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31.65 | 27.6 | 873.54 | 0 | 873.54 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 1601 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.65 | 19.5 | 675.68 | 0 | 675.68 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 2004 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 25 | 11369.25 | 0 | 11369.25 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1504 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2601 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 501 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2802 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 26.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 903 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 16.5 | 1194.77 | 0 | 1194.77 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. P1 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 699.39 | 2 | 1398.78 | 0 | 1398.78 | 2.5 | 0 | 0 | 0 | 0 | 699.39 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 2401 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2302 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1404 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1603 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 464.94 | 23.5 | 10926.09 | 0 | 10926.09 | 2.5 | 0 | 0 | 0 | 0 | 464.94 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2803 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2801 Toilet Flooring | Schedule & Quality | Sq.Ft | 68.3 | 2 | 136.6 | 0 | 136.6 | 2.5 | 0 | 0 | 0 | 0 | 68.3 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 42.52 | 2 | 85.04 | 0 | 85.04 | 2.5 | 0 | 0 | 0 | 0 | 42.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2501 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 456.52 | 2 | 913.04 | 0 | 913.04 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1205 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 1837.26 | 12044.25 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 505 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 17 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 105 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 1101 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 215.49 | 23 | 4956.27 | 0 | 4956.27 | 2.5 | 0 | 0 | 0 | 0 | 215.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.15 | 25.25 | 13563.04 | 2441.34 | 16004.38 | 2.5 | 0 | 0 | 0 | 0 | 537.15 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2205 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 101 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 2401 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 0 | 26 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 1704 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2605 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1203 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 22 | 10237.48 | 0 | 10237.48 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2303 Flat Flooring | Schedule & Quality | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1003 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.34 | 22 | 10237.48 | 0 | 10237.48 | 2.5 | 0 | 0 | 0 | 0 | 465.34 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 304 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1405 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 501 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 1305 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 105 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 1105 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.77 | 22 | 10004.94 | 0 | 10004.94 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Flat No. 1304 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat P4 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1003 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 531.83 | 2 | 1063.66 | 0 | 1063.66 | 2.5 | 0 | 0 | 0 | 0 | 531.83 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-- 202 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2402 Flat Flooring | Schedule & Quality | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-- 203 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 603 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (3BHK)Flat 401 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 456.52 | 19 | 8673.88 | 0 | 8673.88 | 2.5 | 0 | 0 | 0 | 0 | 456.52 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK)Flat 404 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 504 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2501 Balcony Flooring | Schedule & Quality | Sq.Ft | 57.18 | 2 | 114.36 | 0 | 114.36 | 2.5 | 0 | 0 | 0 | 0 | 57.18 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat 704 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 703 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2705 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.6 | 823.17 | 0 | 823.17 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat 402 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 30 Apr 2024 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 30 Apr 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.6 | 1708.88 | 0 | 1708.88 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2805 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.6 | 952.73 | 0 | 952.73 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2703 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 35.66 | 23.6 | 841.58 | 0 | 841.58 | 2.5 | 0 | 0 | 0 | 0 | 35.66 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1005 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1403 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 108 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 11 May 2024
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Utility Flooring | Schedule & Quality | Sq.Ft | 34.82 | 2 | 69.64 | 0 | 69.64 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing -1 (2BHK) Flat 2105 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.77 | 2 | 909.54 | 0 | 909.54 | 2.5 | 0 | 0 | 0 | 0 | 454.77 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1105 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.82 | 16.5 | 574.53 | 0 | 574.53 | 2.5 | 0 | 0 | 0 | 0 | 34.82 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2702 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 706.1 | 25.25 | 17829.03 | 3209.22 | 21038.25 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 0 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1- 203 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Apr 2024 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.65 | 2 | 69.3 | 0 | 69.3 | 2.5 | 0 | 0 | 0 | 0 | 34.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 904 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 2005 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)Flat No. 105 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. P5 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (3BHK)-Flat No. 2302 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 706.1 | 2 | 1412.2 | 0 | 1412.2 | 2.5 | 0 | 0 | 0 | 0 | 706.1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 752 | 1 | 25 Apr 2024 | JUBAIR AHMAD | Wing 1 (2BHK)-Flat No. 1804 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Apr 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 5th Slab (P6 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 229.7 | 1381588.08 | 248685.86 | 1630273.94 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 210 | 1263097.5 | 227357.56 | 1490455.06 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 5th Slab (P6 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 229.7 | 1381588.08 | 248685.86 | 1630273.94 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 1st Slab (P2 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 5564.67 | 205 | 1140757.35 | 205336.32 | 1346093.67 | 2.5 | 0 | 0 | 0 | 0 | 5564.67 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Labour Wor | RCC Superstructure (B-up area) | Sq.Ft | 5953.035 | 229.7 | 1367412.14 | 246134.18 | 1613546.32 | 2.5 | 0 | 0 | 0 | 0 | 5953.035 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 205 | 1233023.75 | 221944.28 | 1454968.03 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 Plinth Work (RCC Labour) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 210 | 1263097.5 | 227357.56 | 1490455.06 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 4th Slab (P5 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 210 | 1263097.5 | 227357.56 | 1490455.06 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 1st Slab (P2 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 5564.67 | 205 | 1140757.35 | 205336.32 | 1346093.67 | 2.5 | 0 | 0 | 0 | 0 | 5564.67 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 205 | 1233023.75 | 221944.28 | 1454968.03 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 Plinth Work (RCC Labour) | RCC Substructure Labour (B-up area)- BC | Sq.Ft | 11129.34 | 215 | 2392808.1 | 430705.46 | 2823513.56 | 2.5 | 0 | 0 | 0 | 0 | 11129.34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 4th Slab (P5 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 6014.75 | 210 | 1263097.5 | 227357.56 | 1490455.06 | 2.5 | 0 | 0 | 0 | 0 | 6014.75 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 753 | 0 | 27 Apr 2024 | AJAY H SHARMA | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Labour Wor | RCC Superstructure (B-up area) | Sq.Ft | 5953.035 | 229.7 | 1367412.14 | 246134.18 | 1613546.32 | 2.5 | 0 | 0 | 0 | 0 | 5953.035 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 754 | 0 | 03 May 2024 | SACHIN SHANTARAM SONAR | Vastu Consultancy Visit Charges | Vastu Consultancy | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 755 | 0 | 04 May 2024 | SHREE SAI SAMARTH ENTERPRISES | New Labour Camp & Development Fabrication Work | Fabrication Work Fixing | Sq.Ft | 550 | 14 | 7700 | 0 | 7700 | 2.5 | 550 | 7700 | 0 | 7700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 755 | 0 | 04 May 2024 | SHREE SAI SAMARTH ENTERPRISES | New Labour Camp & Development Fabrication Work | Fabrication work Removing Sq.Ft | Sq.Ft | 1100 | 5 | 5500 | 0 | 5500 | 0 | 1050 | 5250 | 0 | 5250 | 50 | 250 |  | 95.4545 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 702 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1304 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1705 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2606 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1009 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 504 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1402 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2407 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1308 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1607 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 403 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 307 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 206 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 502 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2402 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 203 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1508 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 609 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1108 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2503 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1601 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2807 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 809 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1707 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2308 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2803 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 801 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2207 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 404 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2009 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1701 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 706 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1001 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 804 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2809 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2507 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 406 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2105 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1206 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 806 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No P2 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1409 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2504 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 209 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 803 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No P4 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 501 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1408 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 605 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 302 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2602 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2703 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 606 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2607 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1901 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2203 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1301 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2802 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1904 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 701 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2106 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1503 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2401 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2404 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 208 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2007 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1504 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2509 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1005 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2102 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 402 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2109 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 905 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1007 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2603 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 508 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1006 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 506 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1605 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 703 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1502 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2101 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 802 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1804 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 607 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2506 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 503 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1806 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2005 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2805 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2501 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 106 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 709 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 908 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 901 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 201 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 603 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2206 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1302 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1401 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1908 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2107 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1201 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No P5 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1608 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2006 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1609 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 704 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 906 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 303 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1109 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2108 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1105 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 101 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 105 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1406 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 207 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2605 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 907 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1204 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2302 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2608 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1903 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2202 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1407 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1704 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1002 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1909 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2103 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 401 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 904 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2701 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 205 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1207 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1907 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2804 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2209 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 408 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1703 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2508 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 109 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2502 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2704 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2309 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2706 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1905 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2808 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 902 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2609 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 708 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1203 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 108 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1506 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1103 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1404 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1306 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2705 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1702 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 507 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 301 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1004 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2205 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 306 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1003 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2001 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1307 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1106 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1208 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 202 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2008 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1303 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 308 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2305 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1802 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1403 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 505 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2306 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 409 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2406 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2405 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2601 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 107 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1405 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 407 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1107 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1808 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1509 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 309 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2801 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1101 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1602 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 707 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1803 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2709 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1709 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1309 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1708 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2505 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2307 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1507 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1305 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2708 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1205 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2003 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 909 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2806 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 509 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1902 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1202 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2707 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No P3 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2201 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 903 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 808 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 601 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1606 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2002 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1906 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2208 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 807 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2403 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1501 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1102 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2004 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1603 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 805 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 305 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 405 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2301 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1505 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1807 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 602 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2303 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2409 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 304 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2304 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 103 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 608 MS Window Grill | Window Grill (L) | Sq.Ft | 83.313 | 27.5 | 2291.11 | 412.4 | 2703.51 | 2.5 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1209 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1801 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No P1 MS Window Grill | Window Grill (L) | Sq.Ft | 112.376 | 27.5 | 3090.34 | 556.26 | 3646.6 | 2.5 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 204 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1809 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing.1 Flat No 102 MS Window Grill | Window Grill (L) | Sq.Ft | 129.814 | 27.5 | 3569.89 | 642.58 | 4212.47 | 2.5 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1706 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1008 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2408 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2702 MS Window Grill | Window Grill (L) | Sq.Ft | 129.81 | 27.5 | 3569.78 | 642.56 | 4212.34 | 2.5 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 2204 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 705 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 756 | 0 | 06 May 2024 | HELIOS | Wing-1 Flat No 1805 MS Window Grill | Window Grill (L) | Sq.Ft | 83.31 | 27.5 | 2291.03 | 412.38 | 2703.41 | 2.5 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1603 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 806 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2809 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1809 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1009 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1905 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2208 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 507 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2406 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1409 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1901 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1708 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 508 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1101 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2401 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 908 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1509 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2808 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 505 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2508 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2402 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1007 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2405 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2408 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2807 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1607 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 402 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1201 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 601 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 501 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 408 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 509 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1407 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2305 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 208 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 605 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2608 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 308 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1205 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1704 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2602 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2806 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 901 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2107 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2303 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1202 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1203 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1904 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2009 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1804 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2308 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2306 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1605 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 304 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No P3 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2301 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2003 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2004 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1105 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1909 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1503 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2503 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 809 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2103 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1506 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1107 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2108 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2106 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2109 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1801 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1005 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2409 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 705 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2705 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1601 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2805 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1208 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2702 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2005 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 603 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2201 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1806 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1209 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2607 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 203 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 102 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1906 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1307 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 704 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2506 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2505 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2606 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1609 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 108 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 406 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 204 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1803 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1207 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 405 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 207 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 209 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 503 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1302 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No P5 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 105 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 205 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1501 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1808 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 103 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2802 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 404 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2706 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2304 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 808 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1902 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2002 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2407 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1702 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 309 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1004 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1602 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1405 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1907 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 607 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 709 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2302 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2801 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1406 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2708 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1308 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 708 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2709 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 109 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1903 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 609 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1805 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 902 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 903 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2704 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 805 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2605 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1709 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2707 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2202 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2507 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1606 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2701 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2501 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 301 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1504 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2404 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2008 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1206 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 906 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 807 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 307 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 803 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1003 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1106 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2001 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1401 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2007 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2601 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 107 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 403 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 904 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 409 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 306 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1703 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1701 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2203 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1706 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 909 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 703 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No P2 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 106 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2803 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2504 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1002 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2205 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 202 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 707 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1204 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2309 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2101 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1306 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 801 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1006 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 907 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2509 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2403 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 706 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1502 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 502 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2804 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 602 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 506 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1108 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2703 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2204 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1908 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1508 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No P1 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1505 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 606 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1707 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1403 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2006 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 305 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 302 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1102 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2102 MS Window Grill | Window Grill (M) | Sq.Ft | 129.814 | 82.5 | 10709.66 | 1927.74 | 12637.4 | 0 | 0 | 0 | 0 | 0 | 129.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2502 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 407 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 201 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1608 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 702 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 206 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1807 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1802 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1309 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 701 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No P4 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2206 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1507 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 608 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1305 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2603 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1304 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 804 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1402 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 504 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1008 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1109 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2209 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2609 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1404 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1705 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1301 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 401 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1001 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 303 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 802 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2105 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2307 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1103 MS Window Grill | Window Grill (M) | Sq.Ft | 83.313 | 82.5 | 6873.32 | 1237.2 | 8110.52 | 0 | 0 | 0 | 0 | 0 | 83.313 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1408 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing.1 Flat No 101 MS Window Grill | Window Grill (M) | Sq.Ft | 112.376 | 82.5 | 9271.02 | 1668.78 | 10939.8 | 0 | 0 | 0 | 0 | 0 | 112.376 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 905 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 2207 MS Window Grill | Window Grill (M) | Sq.Ft | 129.81 | 82.5 | 10709.33 | 1927.68 | 12637.01 | 0 | 0 | 0 | 0 | 0 | 129.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 757 | 0 | 06 May 2024 | HELIOS (Material) | Wing-1 Flat No 1303 MS Window Grill | Window Grill (M) | Sq.Ft | 83.31 | 82.5 | 6873.08 | 1237.16 | 8110.24 | 0 | 0 | 0 | 0 | 0 | 83.31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 505 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1806 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 601 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 780.571 | 6 | 4683.43 | 843.02 | 5526.45 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2303 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2602 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2707 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 307 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2801 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1103 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 103 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 108 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.008 | 6 | 3606.05 | 649.08 | 4255.13 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1308 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1705 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1505 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2804 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1506 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1108 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2805 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 109 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.416 | 6 | 3602.5 | 648.46 | 4250.96 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2301 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1702 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2008 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 706 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 402 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 705 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2605 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 602 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.106 | 6 | 4728.64 | 851.16 | 5579.8 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 506 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1102 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2005 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2004 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2303 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 304 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1606 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 509 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.814 | 6 | 4720.88 | 849.76 | 5570.64 | 2.5 | 0 | 0 | 0 | 0 | 786.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2803 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2801 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2103 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.673 | 6 | 3598.04 | 647.64 | 4245.68 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2404 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 404 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 704 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 306 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 701 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 502 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 205 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2102 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.106 | 6 | 4728.64 | 851.16 | 5579.8 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2101 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2709 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 201 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2004 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 702 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 905 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 308 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1406 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2505 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1005 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2202 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2601 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 780.571 | 6 | 4683.43 | 843.02 | 5526.45 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2704 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1403 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1904 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1803 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 101 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2007 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 206 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2502 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2201 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 709 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1001 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1103 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.673 | 6 | 3598.04 | 647.64 | 4245.68 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1409 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1901 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1406 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1708 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1805 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 408 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2806 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 301 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 208 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 102 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.106 | 6 | 4728.64 | 851.16 | 5579.8 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 907 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 702 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2405 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1107 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 809 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2308 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1502 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2301 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P4 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1504 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 804 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2001 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1006 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2009 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2003 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2209 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2603 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1205 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 109 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2305 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1302 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1301 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1801 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2603 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.673 | 6 | 3598.04 | 647.64 | 4245.68 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 901 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2106 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 204 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2407 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1902 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2608 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.008 | 6 | 3606.05 | 649.08 | 4255.13 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2306 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1903 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 903 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2007 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1305 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1407 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 605 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1009 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1202 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2304 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No.902 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 108 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1302 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1403 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1405 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1609 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.416 | 6 | 3602.5 | 648.46 | 4250.96 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1505 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2403 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1109 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2208 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 503 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 301 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 908 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1308 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P5 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2203 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2108 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1701 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2606 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.213 | 6 | 4729.28 | 851.28 | 5580.56 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2206 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2005 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 202 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2408 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1706 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2702 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1607 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 802 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1507 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1202 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2407 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 205 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2708 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1802 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2807 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2109 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.416 | 6 | 3602.5 | 648.46 | 4250.96 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 609 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P2 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2501 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2403 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2808 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1502 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1605 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.662 | 6 | 3597.97 | 647.64 | 4245.61 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2304 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1105 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.662 | 6 | 3597.97 | 647.64 | 4245.61 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2402 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2706 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1607 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 787.88 | 6 | 4727.28 | 850.92 | 5578.2 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1601 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 802 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1008 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1503 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1109 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.416 | 6 | 3602.5 | 648.46 | 4250.96 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2002 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2207 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2601 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1907 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 809 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1204 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1005 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 708 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P1 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 783.413 | 6 | 4700.48 | 846.08 | 5546.56 | 2.5 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1808 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1209 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1106 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2607 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2607 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 787.88 | 6 | 4727.28 | 850.92 | 5578.2 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 805 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 405 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1709 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 208 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 204 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2406 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 909 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1602 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.106 | 6 | 4728.64 | 851.16 | 5579.8 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 502 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 209 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 707 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2408 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2006 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 107 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2308 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2802 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1009 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2805 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 507 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 107 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 787.88 | 6 | 4727.28 | 850.92 | 5578.2 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 302 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2609 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.416 | 6 | 3602.5 | 648.46 | 4250.96 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2508 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2704 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 408 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2605 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.662 | 6 | 3597.97 | 647.64 | 4245.61 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2505 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1107 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 787.88 | 6 | 4727.28 | 850.92 | 5578.2 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 105 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1602 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1609 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1201 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 407 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2003 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 405 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1508 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1008 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1804 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 406 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1007 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1207 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 608 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.008 | 6 | 3606.05 | 649.08 | 4255.13 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2207 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2307 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1208 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 501 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1907 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 506 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 704 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P4 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 602.267 | 6 | 3613.6 | 650.44 | 4264.04 | 2.5 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1801 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2705 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2105 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 406 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2102 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1904 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2503 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2201 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2008 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 401 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1408 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1608 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.008 | 6 | 3606.05 | 649.08 | 4255.13 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 608 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 309 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 803 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1004 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 808 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 106 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.213 | 6 | 4729.28 | 851.28 | 5580.56 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1603 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1404 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2202 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 908 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2001 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 203 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1001 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1203 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1301 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 703 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2806 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No.902 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 606 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 909 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 407 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1205 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 207 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1905 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2309 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1208 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 306 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2206 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 508 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1401 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2506 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1705 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 409 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2509 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 708 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 206 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2306 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1504 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 403 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P2 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 819.257 | 6 | 4915.54 | 884.8 | 5800.34 | 2.5 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 806 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2804 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P1 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 801 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1203 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2409 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 607 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 787.88 | 6 | 4727.28 | 850.92 | 5578.2 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1701 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 508 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1303 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 806 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1405 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2509 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1305 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2105 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.662 | 6 | 3597.97 | 647.64 | 4245.61 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2002 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1304 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1703 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1002 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2507 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1608 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 103 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.673 | 6 | 3598.04 | 647.64 | 4245.68 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 504 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1209 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 403 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 509 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 707 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2507 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 302 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 308 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1809 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1201 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2802 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1909 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1306 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1409 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1706 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1101 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 780.571 | 6 | 4683.43 | 843.02 | 5526.45 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 303 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1204 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1402 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2708 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1106 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.213 | 6 | 4729.28 | 851.28 | 5580.56 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 404 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2502 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1507 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1408 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 504 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P3 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 307 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2508 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 402 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 305 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1407 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2803 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2204 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2504 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 601 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1704 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 503 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2701 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1304 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 101 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 780.571 | 6 | 4683.43 | 843.02 | 5526.45 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1501 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2307 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1303 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 201 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 209 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2703 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 105 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.662 | 6 | 3597.97 | 647.64 | 4245.61 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1501 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1007 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1906 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2808 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2106 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.213 | 6 | 4729.28 | 851.28 | 5580.56 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1105 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1806 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1601 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 780.571 | 6 | 4683.43 | 843.02 | 5526.45 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1102 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.106 | 6 | 4728.64 | 851.16 | 5579.8 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1508 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1909 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1206 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 606 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.213 | 6 | 4729.28 | 851.28 | 5580.56 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 609 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.416 | 6 | 3602.5 | 648.46 | 4250.96 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2305 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1603 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.673 | 6 | 3598.04 | 647.64 | 4245.68 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 507 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2204 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 605 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.662 | 6 | 3597.97 | 647.64 | 4245.61 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1804 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 903 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1807 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 501 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1006 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1802 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2108 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.008 | 6 | 3606.05 | 649.08 | 4255.13 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1307 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 904 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1707 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2703 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 106 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2404 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 309 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2209 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 709 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1708 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1004 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2809 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1906 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1908 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1704 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2707 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1306 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1905 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 305 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2409 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2807 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1207 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2405 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2705 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 804 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1803 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2701 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1003 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 805 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1808 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 207 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 203 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1606 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.213 | 6 | 4729.28 | 851.28 | 5580.56 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 906 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1206 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 202 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2208 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P5 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2205 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2401 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2406 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1707 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1506 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1807 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1605 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2506 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2606 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 807 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 505 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2809 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P3 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 602.515 | 6 | 3615.09 | 650.72 | 4265.81 | 2.5 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1003 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1108 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.008 | 6 | 3606.05 | 649.08 | 4255.13 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2503 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1902 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1702 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 304 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1503 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.384 | 6 | 3602.3 | 648.42 | 4250.72 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2109 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 701 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2706 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2107 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 401 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1908 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 600.814 | 6 | 3604.88 | 648.88 | 4253.76 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 706 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2504 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 807 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1805 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2608 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1703 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1101 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2401 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 602 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2205 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.932 | 6 | 3599.59 | 647.92 | 4247.51 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 803 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 907 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2006 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1903 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2101 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 780.571 | 6 | 4683.43 | 843.02 | 5526.45 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1509 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 603 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 599.673 | 6 | 3598.04 | 647.64 | 4245.68 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 705 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 585.723 | 6 | 3514.34 | 632.58 | 4146.92 | 2.5 | 0 | 0 | 0 | 0 | 585.723 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2302 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2602 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.106 | 6 | 4728.64 | 851.16 | 5579.8 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2702 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 303 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1402 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2501 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2103 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1307 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2709 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2609 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 703 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2302 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1809 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1509 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 801 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 904 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 601.062 | 6 | 3606.37 | 649.14 | 4255.51 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1404 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1401 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2203 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1901 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1957.42 | 6 | 11744.52 | 2114.02 | 13858.54 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 603 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1469.63 | 6 | 8817.78 | 1587.2 | 10404.98 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 905 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 102 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2402 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2009 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 808 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1521.65 | 6 | 9129.9 | 1643.38 | 10773.28 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 906 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2309 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 901 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 746.244 | 6 | 4477.46 | 805.94 | 5283.4 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1309 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1309 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 409 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1530.02 | 6 | 9180.12 | 1652.42 | 10832.54 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1002 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 788.902 | 6 | 4733.41 | 852.02 | 5585.43 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 607 Internal Flat Gypsum Work | Patra Finish on wall (L) | Sq.Ft | 1953.37 | 6 | 11720.22 | 2109.64 | 13829.86 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2107 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 787.88 | 6 | 4727.28 | 850.92 | 5578.2 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 758 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1709 Internal Flat Gypsum Work | Patra Finish on Ceiling (L) | Sq.Ft | 786.644 | 6 | 4719.86 | 849.58 | 5569.44 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1901 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 409 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 805 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2502 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 609 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1605 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.662 | 4 | 2398.65 | 431.76 | 2830.41 | 0 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2404 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 506 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1109 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.416 | 4 | 2401.66 | 432.3 | 2833.96 | 0 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2107 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 904 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 508 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1402 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2009 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2706 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2302 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 108 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.008 | 4 | 2404.03 | 432.72 | 2836.75 | 0 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1108 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.008 | 4 | 2404.03 | 432.72 | 2836.75 | 0 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 408 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2408 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2201 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1304 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2109 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 402 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1109 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2503 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 903 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 503 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2205 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2002 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 802 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2709 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2707 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2107 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 787.88 | 4 | 3151.52 | 567.28 | 3718.8 | 0 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1408 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P5 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1206 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2308 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2106 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 403 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1405 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2003 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2704 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 509 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1205 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2103 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.673 | 4 | 2398.69 | 431.76 | 2830.45 | 0 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2809 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1408 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 106 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.213 | 4 | 3152.85 | 567.52 | 3720.37 | 0 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2804 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1904 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 401 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1702 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1909 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1201 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 704 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 303 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P2 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1307 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 603 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.673 | 4 | 2398.69 | 431.76 | 2830.45 | 0 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1403 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 501 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1705 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2806 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 605 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.662 | 4 | 2398.65 | 431.76 | 2830.41 | 0 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1902 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1603 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.673 | 4 | 2398.69 | 431.76 | 2830.45 | 0 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 709 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1309 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 508 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2808 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 307 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.664 | 4 | 3146.66 | 566.4 | 3713.06 | 0 | 0 | 0 | 0 | 0 | 786.664 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2108 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.008 | 4 | 2404.03 | 432.72 | 2836.75 | 0 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 707 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1301 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 501 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1507 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 401 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1209 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 608 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.008 | 4 | 2404.03 | 432.72 | 2836.75 | 0 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2601 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 780.571 | 4 | 3122.28 | 562.02 | 3684.3 | 0 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2202 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1407 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2801 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2509 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 809 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1505 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1606 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2306 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2303 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 509 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 602 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.106 | 4 | 3152.42 | 567.44 | 3719.86 | 0 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1706 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1302 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 906 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2702 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 305 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1805 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1904 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1106 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 404 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2508 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2403 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2401 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1804 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 704 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1803 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 505 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2704 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2206 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2308 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2204 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2101 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 780.571 | 4 | 3122.28 | 562.02 | 3684.3 | 0 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 801 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 603 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 502 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 807 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2609 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.416 | 4 | 2401.66 | 432.3 | 2833.96 | 0 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1906 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1401 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2707 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1807 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2706 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 507 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2807 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 208 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2506 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2606 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 804 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1406 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1101 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 780.571 | 4 | 3122.28 | 562.02 | 3684.3 | 0 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 504 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 706 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 502 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2605 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.662 | 4 | 2398.65 | 431.76 | 2830.41 | 0 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2609 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 309 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 805 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2303 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 407 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 905 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1208 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 505 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2007 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1707 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1504 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2504 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 406 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1902 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2307 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2507 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1606 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.213 | 4 | 3152.85 | 567.52 | 3720.37 | 0 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 206 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2005 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 102 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 302 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2402 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2209 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1102 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1405 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2403 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 605 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1907 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 405 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1506 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2705 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 703 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2607 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 787.88 | 4 | 3151.52 | 567.28 | 3718.8 | 0 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2305 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1103 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1404 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2801 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 804 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1504 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2004 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 403 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1501 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2808 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 208 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 408 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1901 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1003 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1304 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 601 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 780.571 | 4 | 3122.28 | 562.02 | 3684.3 | 0 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2101 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2809 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2802 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 204 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1308 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1305 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2302 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 705 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2409 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 801 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 702 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1108 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1703 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2106 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.213 | 4 | 3152.85 | 567.52 | 3720.37 | 0 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1706 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1801 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 203 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1701 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1201 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1001 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2601 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2208 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1601 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 780.571 | 4 | 3122.28 | 562.02 | 3684.3 | 0 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2207 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 705 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 585.723 | 4 | 2342.89 | 421.72 | 2764.61 | 0 | 0 | 0 | 0 | 0 | 585.723 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1509 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 904 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2004 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1004 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 803 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1005 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1203 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1803 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2602 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.106 | 4 | 3152.42 | 567.44 | 3719.86 | 0 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 903 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2108 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1802 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 708 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2304 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2001 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2705 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1002 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1105 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2602 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 406 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 402 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1805 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2505 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1508 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1207 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1809 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P3 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2804 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2702 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2807 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1702 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 108 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2203 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2102 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1908 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 901 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1705 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 807 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1207 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P2 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 819.257 | 4 | 3277.03 | 589.86 | 3866.89 | 0 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1703 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2208 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2503 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2708 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2501 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1009 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2703 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 202 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1308 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2105 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2301 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 209 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 304 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 601 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P4 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 602.267 | 4 | 2409.07 | 433.64 | 2842.71 | 0 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1808 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1603 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1608 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1001 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2608 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1508 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2304 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 206 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2402 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 109 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1601 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2802 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2204 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1609 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.416 | 4 | 2401.66 | 432.3 | 2833.96 | 0 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2803 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 109 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.416 | 4 | 2401.66 | 432.3 | 2833.96 | 0 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2306 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 706 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1704 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1708 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 102 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.106 | 4 | 3152.42 | 567.44 | 3719.86 | 0 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2005 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 809 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 101 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2502 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1806 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1507 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No.902 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2203 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2607 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 806 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1903 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2102 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.106 | 4 | 3152.42 | 567.44 | 3719.86 | 0 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1704 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2404 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1909 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1905 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 202 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1602 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.106 | 4 | 3152.42 | 567.44 | 3719.86 | 0 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1303 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 907 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2309 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 107 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 787.88 | 4 | 3151.52 | 567.28 | 3718.8 | 0 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2206 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1009 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1309 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2001 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 507 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1707 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P3 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 602.515 | 4 | 2410.06 | 433.82 | 2843.88 | 0 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1406 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1804 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2806 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1204 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 909 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 105 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 308 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2002 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1607 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 787.88 | 4 | 3151.52 | 567.28 | 3718.8 | 0 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2509 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 607 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2603 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1801 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1202 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2307 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1501 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1303 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1607 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1205 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 309 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2603 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.673 | 4 | 2398.69 | 431.76 | 2830.45 | 0 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 709 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 906 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 701 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1802 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2007 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2501 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2209 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2006 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1307 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 307 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 306 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No.902 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1401 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2605 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2608 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.008 | 4 | 2404.03 | 432.72 | 2836.75 | 0 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1102 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.106 | 4 | 3152.42 | 567.44 | 3719.86 | 0 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1908 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2003 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1204 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1208 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P1 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 783.413 | 4 | 3133.65 | 564.06 | 3697.71 | 0 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1709 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1503 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 305 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 207 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2205 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2408 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 302 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2606 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.213 | 4 | 3152.85 | 567.52 | 3720.37 | 0 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 907 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 703 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 301 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 205 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 909 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2207 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1202 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2406 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2405 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1003 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1402 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 101 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 780.571 | 4 | 3122.28 | 562.02 | 3684.3 | 0 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 407 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1605 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 103 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.673 | 4 | 2398.69 | 431.76 | 2830.45 | 0 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 201 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 808 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 506 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1409 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 609 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.416 | 4 | 2401.66 | 432.3 | 2833.96 | 0 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 303 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1502 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 105 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.662 | 4 | 2398.65 | 431.76 | 2830.41 | 0 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2109 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.416 | 4 | 2401.66 | 432.3 | 2833.96 | 0 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1509 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 708 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 503 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2301 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 103 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 209 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1305 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2401 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 608 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2006 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1306 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2701 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1907 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 901 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 746.244 | 4 | 2984.98 | 537.3 | 3522.28 | 0 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1206 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2803 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1906 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1006 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 203 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1302 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1403 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 606 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 106 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1005 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2701 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 404 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 808 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2407 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1301 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2508 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1905 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 205 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 207 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1502 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 107 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1505 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2504 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1808 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1101 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1107 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1103 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.673 | 4 | 2398.69 | 431.76 | 2830.45 | 0 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1004 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.062 | 4 | 2404.25 | 432.76 | 2837.01 | 0 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 602 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2105 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.662 | 4 | 2398.65 | 431.76 | 2830.41 | 0 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1903 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 702 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 802 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1709 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1203 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2505 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1006 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2103 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 908 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2708 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1708 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2008 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2407 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1008 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2709 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 806 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 908 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1602 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2201 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1007 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 905 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 308 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1506 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 405 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1609 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2506 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 504 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2805 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1106 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.213 | 4 | 3152.85 | 567.52 | 3720.37 | 0 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1209 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2805 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1503 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1105 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.662 | 4 | 2398.65 | 431.76 | 2830.41 | 0 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2305 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 599.932 | 4 | 2399.73 | 431.96 | 2831.69 | 0 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2507 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 707 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1306 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1807 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 304 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1008 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1409 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2406 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 301 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P1 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 2202 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 204 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 409 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1701 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2009 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P4 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2405 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 607 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 787.88 | 4 | 3151.52 | 567.28 | 3718.8 | 0 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1806 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 606 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.213 | 4 | 3152.85 | 567.52 | 3720.37 | 0 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2409 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1809 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 306 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1953.37 | 4 | 7813.48 | 1406.42 | 9219.9 | 0 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No P5 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1521.65 | 4 | 6086.6 | 1095.58 | 7182.18 | 0 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1404 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1530.02 | 4 | 6120.08 | 1101.62 | 7221.7 | 0 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 201 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 701 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1957.42 | 4 | 7829.68 | 1409.34 | 9239.02 | 0 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 803 Internal Flat Gypsum Work | Patra Finish on wall (M) | Sq.Ft | 1469.63 | 4 | 5878.52 | 1058.14 | 6936.66 | 0 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2008 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.814 | 4 | 2403.26 | 432.58 | 2835.84 | 0 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2703 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 600.384 | 4 | 2401.54 | 432.28 | 2833.82 | 0 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 2309 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1407 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No. 1002 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 788.902 | 4 | 3155.61 | 568 | 3723.61 | 0 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1007 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 786.644 | 4 | 3146.58 | 566.38 | 3712.96 | 0 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1608 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 601.008 | 4 | 2404.03 | 432.72 | 2836.75 | 0 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 759 | 0 | 06 May 2024 | GUDIYA ENTERPRISES | Flat No 1107 Internal Flat Gypsum Work | Patra Finish on Ceiling (M) | Sq.Ft | 787.88 | 4 | 3151.52 | 567.28 | 3718.8 | 0 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1003 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1302 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1602 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1204 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1306 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1708 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2107 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2605 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1301 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 705 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 209 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 404 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 507 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1703 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1401 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2702 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 808 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 801 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2204 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1004 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P1 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 909 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1304 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2701 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 109 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 807 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1609 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1709 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1806 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1702 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1805 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1708 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 209 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 701 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1703 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2603 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1405 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2702 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 508 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1905 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2303 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1207 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2809 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1404 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 501 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2509 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1806 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 603 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1407 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1203 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2509 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1904 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 707 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1602 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2408 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1502 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 707 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2009 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2503 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 705 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1906 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2807 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1802 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2202 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1103 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 803 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 904 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1407 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1505 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 607 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1107 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1102 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 608 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 308 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1704 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1309 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1308 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2505 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 804 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2804 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1005 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 906 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2609 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2101 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P5 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 602 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2701 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 907 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1305 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 305 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1304 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1107 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P1 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 306 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 902 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 402 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2003 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P2 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 606 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2408 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2103 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1206 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2002 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2209 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1509 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 307 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2602 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2508 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2107 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 901 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 704 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2705 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2503 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1106 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1002 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2208 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 903 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1101 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2808 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2608 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1006 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1106 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2502 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 509 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1606 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2002 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2809 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2205 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1801 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1908 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2708 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 105 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2203 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1408 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 405 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2806 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1807 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1601 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1009 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 804 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1206 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 809 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2008 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 704 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1109 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 709 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 106 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 204 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P2 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1501 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1307 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P5 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 706 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2403 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 703 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 502 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2105 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 409 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2406 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P3 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2103 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P4 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1608 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2506 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1306 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2309 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1906 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 301 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 509 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 203 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1603 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1008 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2301 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 806 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1904 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2008 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2609 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2505 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 205 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 501 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 809 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 905 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1209 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 309 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2706 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2306 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1204 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 602 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 708 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2303 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1308 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 201 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2709 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1105 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 908 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 507 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 102 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1909 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1408 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1002 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2204 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2507 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2805 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1601 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 808 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1508 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2407 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1506 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2703 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1007 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2708 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1706 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2004 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 505 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 508 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1506 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 702 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1205 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1901 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2001 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 202 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1705 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 505 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 101 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1201 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 605 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1403 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 108 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 106 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2007 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 409 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 103 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2207 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1108 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1902 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1103 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2801 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1809 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2404 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 805 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1907 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1108 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1409 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 408 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1504 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 302 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1302 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1202 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1704 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1201 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 406 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1702 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2704 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1309 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2106 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 306 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2009 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P3 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2207 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 807 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2205 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1505 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 903 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1808 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1406 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1507 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1405 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 202 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 203 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1609 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2501 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2102 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1404 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1008 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2005 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 806 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1808 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 407 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1701 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 802 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1502 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 706 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 204 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1507 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2301 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 909 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2402 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 702 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2801 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 303 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2306 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2402 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2403 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2706 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1508 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1101 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2504 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 802 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 801 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1105 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 304 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 207 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 609 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1805 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2506 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2406 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2608 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1401 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 107 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2003 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1202 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1608 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2603 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2405 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 902 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1208 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2707 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1307 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2607 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2305 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2404 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 307 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1905 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 201 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2508 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2309 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 503 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 606 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1207 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1303 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2108 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2202 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1503 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1706 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2409 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 108 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1804 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2302 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2302 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1803 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2006 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 301 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2106 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1001 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2802 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1607 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2704 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2206 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 603 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1707 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2307 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 406 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 304 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2108 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 906 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1503 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2308 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1205 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2208 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 904 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2304 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1006 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2703 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1007 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2307 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 401 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2607 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1909 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1504 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 205 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 305 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 601 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2805 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2705 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 207 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 107 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1705 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1509 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1709 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2102 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2804 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1605 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 504 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1903 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2201 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1209 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2803 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 105 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1003 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2606 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 308 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 101 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2401 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 403 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2502 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1809 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1701 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 506 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2806 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2808 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2606 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1603 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2007 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 608 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1907 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2004 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 601 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 703 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2507 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 109 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2006 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2305 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1102 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2405 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2501 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 907 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2803 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2209 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 206 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P4 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 503 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 208 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2304 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1605 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2709 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 302 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1303 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2605 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 905 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 504 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2504 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2203 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1707 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 408 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 708 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 103 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1606 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2308 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1403 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1908 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 803 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2807 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1009 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 102 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2407 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2707 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1109 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1406 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1402 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 404 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2206 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 208 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1409 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2409 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1903 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2005 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 709 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 506 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1001 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 405 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1802 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2802 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1005 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 502 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2601 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2109 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 402 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1203 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 403 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2602 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2201 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1301 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2001 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2401 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1004 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1902 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 609 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2105 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1803 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 401 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2601 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1804 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1402 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 901 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 303 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1208 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 607 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1801 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 908 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 206 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1501 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1901 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 309 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 701 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1807 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 407 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 605 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1607 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 43.6 | 15 | 654 | 117.72 | 771.72 | 2.5 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2101 C. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 805 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2109 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 760 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1305 M. Toilet Grid False Ceiling | Grid False Ceiling (L) | Sq.Ft | 38.76 | 15 | 581.4 | 104.66 | 686.06 | 2.5 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 106 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1408 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 507 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2608 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 903 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 207 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2703 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1703 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1007 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1506 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2302 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2706 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2206 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 108 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2208 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2703 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 207 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 904 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 209 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1306 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 905 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 402 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1203 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1703 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2207 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2203 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2103 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 903 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1201 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1309 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2505 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1407 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 201 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1006 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2705 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2605 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 702 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2609 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2006 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2103 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1809 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 806 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1306 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 806 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1802 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 205 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1901 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2702 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 303 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1301 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1308 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1607 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1507 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 103 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 804 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P2 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1805 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1102 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2009 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1103 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 607 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 103 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2202 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1403 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 601 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 803 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1106 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1905 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1606 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 303 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 902 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1701 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 708 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 708 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1709 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 707 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 704 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1802 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2506 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2406 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 302 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1108 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1406 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1103 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 703 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 302 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1005 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 109 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2006 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1609 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 706 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1204 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2306 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 508 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 701 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 704 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 301 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1008 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1105 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1903 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 809 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1908 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1204 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2205 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2701 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1508 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2607 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 809 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 204 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1409 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1907 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 807 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 501 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 504 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1705 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1502 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 305 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1509 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2602 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 906 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 109 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1303 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1005 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 802 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1903 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1402 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1302 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 805 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 208 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1006 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1505 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1908 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1209 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 108 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 907 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2003 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 409 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1102 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 807 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2106 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2808 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 902 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1207 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 802 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 401 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2205 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1807 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1805 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2001 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 703 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2108 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 505 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2809 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1307 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1902 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 503 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2005 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 705 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2407 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 906 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2806 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1807 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1803 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1806 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1302 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2603 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1003 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2102 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1605 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2707 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1101 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 403 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2508 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2106 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 404 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 909 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 605 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 601 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1405 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1506 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2502 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 908 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2109 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 502 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2108 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 803 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1603 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2708 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1909 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1706 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1501 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1601 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 105 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P2 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2606 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1101 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2004 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2105 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2501 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2302 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2204 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 609 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2105 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 509 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P4 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1409 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2008 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1305 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1504 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1707 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2802 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2102 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1107 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2204 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2504 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 606 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2402 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 904 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1501 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 505 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2803 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2408 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2704 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 204 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 202 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 506 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1407 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1602 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1704 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 203 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1702 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1705 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2505 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1901 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2209 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2503 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 202 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 306 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2708 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 709 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 405 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 407 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1806 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1504 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 306 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 602 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2304 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 206 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 402 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 106 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1105 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 602 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2201 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1307 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2307 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2606 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2802 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1709 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2405 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1305 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 304 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 209 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2206 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 701 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2107 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 403 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2307 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 507 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2804 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1404 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1308 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2808 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 506 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 309 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1301 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2005 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2201 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2002 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2002 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2502 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1403 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2807 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1602 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 606 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1208 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1004 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2305 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2203 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 407 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 909 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 801 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1108 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P1 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 406 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1003 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1803 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2404 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2608 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1208 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1508 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 702 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1808 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2701 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1507 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1201 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P1 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1009 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 502 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2403 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2704 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1603 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 404 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 408 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 504 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1402 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1708 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2401 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2308 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1609 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1906 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 608 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1008 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 805 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2309 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P5 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2009 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2705 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1607 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2507 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1401 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1304 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2304 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1904 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 706 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1002 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2805 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 801 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1206 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2208 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1106 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1408 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1608 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1503 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 107 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2303 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1109 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1509 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1109 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2603 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1801 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2003 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1907 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2209 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2308 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1304 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1107 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1309 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2501 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1706 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2605 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2509 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1503 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1606 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2508 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2402 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1702 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1804 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1205 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2602 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1209 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 905 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2509 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2406 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1001 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1205 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P5 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1206 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1704 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1906 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2803 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2506 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 907 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2301 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 205 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1405 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1007 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2207 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1203 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1905 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1207 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1404 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 307 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1002 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2007 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2401 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1601 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2301 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1009 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2309 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P3 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1809 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1902 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1808 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2202 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2709 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1202 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2507 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2109 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2407 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2609 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2408 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2405 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1505 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1708 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2101 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2706 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 908 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 304 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1707 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2306 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 709 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 808 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1608 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2504 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2601 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1202 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2403 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1303 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 804 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1004 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2305 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1502 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2007 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 705 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2503 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 105 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2702 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1801 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2004 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 308 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1904 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2008 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2804 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 101 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1605 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1909 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2806 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 201 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2707 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 901 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1701 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 308 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2303 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 901 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1406 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 401 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1401 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2607 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 203 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 609 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 301 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 808 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 607 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 707 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2409 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 608 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 208 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2601 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 101 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 1001 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 603 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2805 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 1804 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P3 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2809 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 102 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing.1 Flat No 2404 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 309 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2807 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 305 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2107 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 107 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2409 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2801 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2709 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2001 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 501 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2101 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 307 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No P4 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 409 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 405 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 605 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 2801 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 408 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 603 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 406 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 503 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 102 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 43.6 | 60 | 2616 | 470.88 | 3086.88 | 0 | 0 | 0 | 0 | 0 | 43.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 508 M. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 38.76 | 60 | 2325.6 | 418.6 | 2744.2 | 0 | 0 | 0 | 0 | 0 | 38.76 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 206 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 761 | 0 | 07 May 2024 | GUDIYA ENTERPRISES | Wing-1 Flat No 509 C. Toilet Grid False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 101 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 104 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 36.17 | 15 | 542.55 | 97.66 | 640.21 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 405 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 303 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 402 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 37.14 | 15 | 557.1 | 100.28 | 657.38 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 401 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 403 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 504 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 36.17 | 15 | 542.55 | 97.66 | 640.21 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 205 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 404 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 36.17 | 15 | 542.55 | 97.66 | 640.21 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 304 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 36.17 | 15 | 542.55 | 97.66 | 640.21 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 203 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 501 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 305 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 105 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 302 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 37.14 | 15 | 557.1 | 100.28 | 657.38 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 201 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 204 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 36.17 | 15 | 542.55 | 97.66 | 640.21 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 502 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 37.14 | 15 | 557.1 | 100.28 | 657.38 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 503 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 103 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 505 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 33.91 | 15 | 508.65 | 91.56 | 600.21 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 202 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 37.14 | 15 | 557.1 | 100.28 | 657.38 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 301 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 31.65 | 15 | 474.75 | 85.46 | 560.21 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 762 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 102 Toilet False Ceiling | Grid False Ceiling (L) | Sq.Ft | 37.14 | 15 | 557.1 | 100.28 | 657.38 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 402 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 37.14 | 60 | 2228.4 | 401.12 | 2629.52 | 0 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 501 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 105 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 303 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 104 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 36.17 | 60 | 2170.2 | 390.64 | 2560.84 | 0 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 202 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 37.14 | 60 | 2228.4 | 401.12 | 2629.52 | 0 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 503 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 103 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 403 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 201 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 101 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 401 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 404 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 36.17 | 60 | 2170.2 | 390.64 | 2560.84 | 0 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 203 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 304 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 36.17 | 60 | 2170.2 | 390.64 | 2560.84 | 0 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 205 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 305 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 505 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 301 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 31.65 | 60 | 1899 | 341.82 | 2240.82 | 0 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-1st Floor Flat No. 102 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 37.14 | 60 | 2228.4 | 401.12 | 2629.52 | 0 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 504 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 36.17 | 60 | 2170.2 | 390.64 | 2560.84 | 0 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-2nd Floor Flat No. 204 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 36.17 | 60 | 2170.2 | 390.64 | 2560.84 | 0 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-3rd Floor Flat No. 302 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 37.14 | 60 | 2228.4 | 401.12 | 2629.52 | 0 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-5th Floor Flat No. 502 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 37.14 | 60 | 2228.4 | 401.12 | 2629.52 | 0 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 763 | 0 | 08 May 2024 | GUDIYA ENTERPRISES | MHADA (Wing-1)-4th Floor Flat No. 405 Toilet False Ceiling | Grid False Ceiling (M) | Sq.Ft | 33.91 | 60 | 2034.6 | 366.22 | 2400.82 | 0 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.38 | 460 | 3394.8 | 0 | 3394.8 | 2.5 | 0 | 0 | 0 | 0 | 7.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P4 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.38 | 460 | 3394.8 | 0 | 3394.8 | 2.5 | 0 | 0 | 0 | 0 | 7.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -Flat P3 2BHK WB Counter | Wash Basin Counter-AIE | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 4.79 | 460 | 2203.4 | 0 | 2203.4 | 2.5 | 0 | 0 | 0 | 0 | 4.79 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P1 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P2 3BHK Window Sill Granite | Granite Edge Polish- Mkt. | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P2 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P2 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P2 3BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 59.04 | 45 | 2656.8 | 0 | 2656.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 5.18 | 460 | 2382.8 | 0 | 2382.8 | 2.5 | 0 | 0 | 0 | 0 | 5.18 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.71 | 460 | 3546.6 | 0 | 3546.6 | 2.5 | 0 | 0 | 0 | 0 | 7.71 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -Flat P2 3BHK WB Counter | Wash Basin Counter-AIE | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 5.28 | 460 | 2428.8 | 0 | 2428.8 | 2.5 | 0 | 0 | 0 | 0 | 5.28 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 207 3BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P5 2BHK Toilet Ventiltr Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 5.18 | 460 | 2382.8 | 0 | 2382.8 | 2.5 | 0 | 0 | 0 | 0 | 5.18 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.38 | 460 | 3394.8 | 0 | 3394.8 | 2.5 | 0 | 0 | 0 | 0 | 7.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 4.49 | 460 | 2065.4 | 0 | 2065.4 | 2.5 | 0 | 0 | 0 | 0 | 4.49 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-. 209 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 4.79 | 460 | 2203.4 | 0 | 2203.4 | 2.5 | 0 | 0 | 0 | 0 | 4.79 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P3 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P1 3BHK Toilet Ventiltr Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P3 2BHK Ledge Wall top | Chamfer Polish - BCE | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P4 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-1309 2BHK Window Sill Granite | Granite Edge Polish (L) | R.Ft | 59.04 | 10 | 590.4 | 0 | 590.4 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P3 2BHK Window Sill Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P5 2BHK Window Sill Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -Flat P1 3BHK WB Counter | Wash Basin Counter-AIE | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 4.79 | 460 | 2203.4 | 0 | 2203.4 | 2.5 | 0 | 0 | 0 | 0 | 4.79 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P3 2BHK Ledge Wall top | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 80.69 | 45 | 3631.05 | 0 | 3631.05 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 80.69 | 45 | 3631.05 | 0 | 3631.05 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P1 3BHK Window Sill Granite | Granite Edge Polish- Mkt. | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Window Sill Granite Work | Granite Chamfer Edge Polish -cc | R.Ft | 80.69 | 20 | 1613.8 | 0 | 1613.8 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P4 2BHK Toilet Ventiltr Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -Flat P4 2BHK WB Counter | Wash Basin Counter-AIE | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P1 3BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P4 2BHK Ledge Wall top | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 205 2BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 203 2BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Window Sill Granite Work | Granite Edge Polish- Mkt. | R.Ft | 80.69 | 10 | 806.9 | 0 | 806.9 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Window Sill Granite Work | Granite Champher Polish (L) | R.Ft | 59.04 | 20 | 1180.8 | 0 | 1180.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 204 2BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 4.79 | 460 | 2203.4 | 0 | 2203.4 | 2.5 | 0 | 0 | 0 | 0 | 4.79 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -Flat P5 2BHK WB Counter | Wash Basin Counter-AIE | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P5 2BHK Ledge Wall top | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 209 2BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Window Sill Granite Work | Granite Chamfer Edge Polish -cc | R.Ft | 80.69 | 20 | 1613.8 | 0 | 1613.8 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P2 3BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Window Sill Granite Work | Granite Champher Polish (L) | R.Ft | 59.04 | 20 | 1180.8 | 0 | 1180.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 80.69 | 45 | 3631.05 | 0 | 3631.05 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P5 2BHK Window Sill Granite | Granite Champher Polish (L) | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P5 2BHK Ledge Wall top | Chamfer Polish - BCE | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-1404 2BHK Window Sill Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 201 3BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.71 | 460 | 3546.6 | 0 | 3546.6 | 2.5 | 0 | 0 | 0 | 0 | 7.71 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P2 3BHK Window Sill Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P5 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P4 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P5 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 80.69 | 45 | 3631.05 | 0 | 3631.05 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 5.28 | 460 | 2428.8 | 0 | 2428.8 | 2.5 | 0 | 0 | 0 | 0 | 5.28 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P4 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P3 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P2 3BHK Ledge Wall top | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P2 3BHK Toilet Ventiltr Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Window Sill Granite Work | Granite Edge Polish (L) | R.Ft | 59.04 | 10 | 590.4 | 0 | 590.4 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P2 3BHK Ledge Wall top | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Window Sill Granite Work | Granite Chamfer Edge Polish -cc | R.Ft | 80.69 | 20 | 1613.8 | 0 | 1613.8 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P4 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P4 2BHK Toilet Ventiltr Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P3 2BHK Window Sill Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P3 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P4 2BHK Window Sill Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P1 3BHK Toilet Ventiltr Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P3 2BHK Window Sill Granite | Granite Champher Polish (L) | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P1 3BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P4 2BHK Ledge Wall top | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P1 3BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- P1 3BHK Ledge Wall top | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P3 2BHK Toilet Ventiltr Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.71 | 460 | 3546.6 | 0 | 3546.6 | 2.5 | 0 | 0 | 0 | 0 | 7.71 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Window Sill Granite Work | Granite Edge Polish- Mkt. | R.Ft | 80.69 | 10 | 806.9 | 0 | 806.9 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Window Sill Granite Work | Granite Chamfer Edge Polish -cc | R.Ft | 80.69 | 20 | 1613.8 | 0 | 1613.8 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P1 3BHK Window Sill Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Window Sill Granite Work | Granite Edge Polish (L) | R.Ft | 59.04 | 10 | 590.4 | 0 | 590.4 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Window Sill Granite Work | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P4 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 59.04 | 45 | 2656.8 | 0 | 2656.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 59.04 | 45 | 2656.8 | 0 | 2656.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 206 3BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Window Sill Granite Work | Granite Edge Polish (L) | R.Ft | 59.04 | 10 | 590.4 | 0 | 590.4 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P5 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 202 3BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Window Sill Granite Work | Granite Edge Polish (L) | R.Ft | 59.04 | 10 | 590.4 | 0 | 590.4 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.38 | 460 | 3394.8 | 0 | 3394.8 | 2.5 | 0 | 0 | 0 | 0 | 7.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P5 2BHK Ledge Wall top | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- Flat 208 2BHK WB Counter Fixing Work | Wash Basin Counter-AIE | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P2 3BHK Window Sill Granite | Granite Chamfer Edge Polish -cc | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Customer Changes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 59.04 | 45 | 2656.8 | 0 | 2656.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Window Sill Granite Work | Granite Champher Polish (L) | R.Ft | 59.04 | 20 | 1180.8 | 0 | 1180.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P2 3BHK Ledge Wall top | Chamfer Polish - BCE | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.71 | 460 | 3546.6 | 0 | 3546.6 | 2.5 | 0 | 0 | 0 | 0 | 7.71 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P4 2BHK Window Sill Granite | Granite Champher Polish (L) | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P3 Kitchen Service Ota | Kitchen Otta (L)- BC | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 7.38 | 460 | 3394.8 | 0 | 3394.8 | 2.5 | 0 | 0 | 0 | 0 | 7.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Window Sill Granite Work | Granite Cutting & fixing (L) | R.Ft | 59.04 | 45 | 2656.8 | 0 | 2656.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P5 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P3 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Window Sill Granite Work | Granite Champher Polish (L) | R.Ft | 59.04 | 20 | 1180.8 | 0 | 1180.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P5 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Flat No. P1 Kitchen Main Ota | Kitchen Otta (L) - BRE | R.Ft | 0 | 460 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P3 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P2 3BHK Toilet Ventiltr Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- P1 3BHK Ledge Wall top | Chamfer Polish - BCE | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Window Sill Granite Work | Granite Champher Polish (L) | R.Ft | 59.04 | 20 | 1180.8 | 0 | 1180.8 | 2.5 | 0 | 0 | 0 | 0 | 59.04 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P3 2BHK Toilet Ventiltr Granite | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 208 2BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Toilet Ventilator Granite Work | Granite Cutting & fixing (L) | R.Ft | 22.96 | 45 | 1033.2 | 0 | 1033.2 | 2.5 | 0 | 0 | 0 | 0 | 22.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P2 3BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 209 2BHK Granite Ledge Wall Top | Granite Cutting & fixing (L) | R.Ft | 11.81 | 45 | 531.45 | 0 | 531.45 | 2.5 | 0 | 0 | 0 | 0 | 11.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P5 2BHK Toilet Ventiltr Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Toilet Ventilator Granite Work | Granite Edge Polish (L) | R.Ft | 45.92 | 10 | 459.2 | 0 | 459.2 | 2.5 | 0 | 0 | 0 | 0 | 45.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 204 2BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 8.53 | 45 | 383.85 | 0 | 383.85 | 2.5 | 0 | 0 | 0 | 0 | 8.53 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 203 2BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P4 2BHK Ledge Wall top | Chamfer Polish - BCE | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Granite Ledge Wall Top | Chamfer Polish - BCE | R.Ft | 15.09 | 20 | 301.8 | 0 | 301.8 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P2 3BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 -P5 2BHK Umbra Patti | Granite Cutting & fixing (L) | R.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Window Sill Granite Work | Granite Edge Polish- Mkt. | R.Ft | 80.69 | 10 | 806.9 | 0 | 806.9 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 202 3BHK Window Sill Granite Work | Granite Edge Polish- Mkt. | R.Ft | 80.69 | 10 | 806.9 | 0 | 806.9 | 2.5 | 0 | 0 | 0 | 0 | 80.69 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P5 2BHK Window Sill Granite | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 206 3BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- P1 3BHK Ledge Wall top | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 68.88 | 10 | 688.8 | 0 | 688.8 | 2.5 | 0 | 0 | 0 | 0 | 68.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 201 3BHK Umbra Patti | Granite Edge Polish (L) | R.Ft | 17.06 | 10 | 170.6 | 0 | 170.6 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1-P3 2BHK Ledge Wall top | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 P1 3BHK Toilet Granite Frame | Granite Edge Polish (L) | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 207 3BHK Toilet Granite Frame | Granite Cutting & fixing (L) | R.Ft | 34.44 | 45 | 1549.8 | 0 | 1549.8 | 2.5 | 0 | 0 | 0 | 0 | 34.44 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1 - P1 3BHK Window Sill Granite | Granite Chamfer Edge Polish -cc | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Customer Changes | Cancelled | DUSHANT.GORE | 10 May 2024
GANGA ASMI | 764 | 0 | 08 May 2024 | JUBAIR AHMAD | Wing 1- 205 2BHK Granite Ledge Wall Top | Granite Edge Polish (L) | R.Ft | 15.09 | 10 | 150.9 | 0 | 150.9 | 2.5 | 0 | 0 | 0 | 0 | 15.09 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 102 MS Window Grill | Window Grill (L) | Sq.Ft | 75.58 | 27.5 | 2078.45 | 374.12 | 2452.57 | 2.5 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 101 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 305 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 501 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 404 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 401 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 402 MS Window Grill | Window Grill (L) | Sq.Ft | 75.58 | 27.5 | 2078.45 | 374.12 | 2452.57 | 2.5 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 505 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 304 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 301 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 503 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 504 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 202 MS Window Grill | Window Grill (L) | Sq.Ft | 75.58 | 27.5 | 2078.45 | 374.12 | 2452.57 | 2.5 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 303 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 403 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 205 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 203 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 502 MS Window Grill | Window Grill (L) | Sq.Ft | 75.58 | 27.5 | 2078.45 | 374.12 | 2452.57 | 2.5 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 405 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 302 MS Window Grill | Window Grill (L) | Sq.Ft | 75.58 | 27.5 | 2078.45 | 374.12 | 2452.57 | 2.5 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 204 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 201 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 105 MS Window Grill | Window Grill (L) | Sq.Ft | 43.36 | 27.5 | 1192.4 | 214.64 | 1407.04 | 2.5 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 104 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 765 | 0 | 09 May 2024 | HELIOS | MHADA Wing 1 - 103 MS Window Grill | Window Grill (L) | Sq.Ft | 34.88 | 27.5 | 959.2 | 172.66 | 1131.86 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 104 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 501 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 504 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 101 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 405 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 301 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 303 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 203 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 102 MS Window Grill | Window Grill (M) | Sq.Ft | 75.58 | 82.5 | 6235.35 | 1122.36 | 7357.71 | 0 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 502 MS Window Grill | Window Grill (M) | Sq.Ft | 75.58 | 82.5 | 6235.35 | 1122.36 | 7357.71 | 0 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 105 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 205 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 302 MS Window Grill | Window Grill (M) | Sq.Ft | 75.58 | 82.5 | 6235.35 | 1122.36 | 7357.71 | 0 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 403 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 204 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 505 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 103 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 404 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 402 MS Window Grill | Window Grill (M) | Sq.Ft | 75.58 | 82.5 | 6235.35 | 1122.36 | 7357.71 | 0 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 201 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 503 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 401 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 304 MS Window Grill | Window Grill (M) | Sq.Ft | 34.88 | 82.5 | 2877.6 | 517.96 | 3395.56 | 0 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 202 MS Window Grill | Window Grill (M) | Sq.Ft | 75.58 | 82.5 | 6235.35 | 1122.36 | 7357.71 | 0 | 0 | 0 | 0 | 0 | 75.58 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 766 | 0 | 09 May 2024 | HELIOS (Material) | MHADA Wing 1 - 305 MS Window Grill | Window Grill (M) | Sq.Ft | 43.36 | 82.5 | 3577.2 | 643.9 | 4221.1 | 0 | 0 | 0 | 0 | 0 | 43.36 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 767 | 0 | 09 May 2024 | ATHARVA ENTERPRISES (Swati Ranade) | Non Tower Area Backfilling & Soling | Bobcat Hiring Charges | Hrs | 50 | 800 | 40000 | 7200 | 47200 | 0 | 40 | 32000 | 5760 | 37760 | 10 | 9440 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Jun 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 768 | 0 | 09 May 2024 | DRAUPADA EARTHMOVERS | Non Tower Area Backfilling & Soling | JCB Charges | Hrs | 100 | 900 | 90000 | 16200 | 106200 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 20 May 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 769 | 0 | 09 May 2024 | GOOD OLD DELIGHT | ONLINE / DIGITAL Social / Digital Activity | Retainership for Digital Media - | Month | 12 | 40000 | 480000 | 86400 | 566400 | 0 | 3 | 119999.52 | 21599.94 | 141599.46 | 9 | 424800.54 | MONTHLY MARKETING / MARKETING SOCIAL / DIGITAL MONTHLY RETAINERSHIP CHARGES @ 40,000/-RS + TAX PER MONTH AS ON 01/04/2024 TO 31/03/2025 | 25 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 10 May 2024 |  | MKT. Media | Approved | SWAPNIL JADHAV | 1900-01-01
GANGA ASMI | 770 | 0 | 09 May 2024 | JAISAN | Development Area Material Shifting | Labour Lumsum-DTR | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 May 2024 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 771 | 0 | 09 May 2024 | INFIFLEX TECHNOLOGIES PRIVATE LIMITED | H.O. Admin Cyber Protect Cloud | Installation Charges | No. | 1 | 1200 | 1200 | 216 | 1416 | 0 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 May 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 771 | 0 | 09 May 2024 | INFIFLEX TECHNOLOGIES PRIVATE LIMITED | H.O. Admin Cyber Protect Cloud | Liasioning Charges- BC | No. | 6 | 2500 | 15000 | 2700 | 17700 | 0 | 6 | 15000 | 2700 | 17700 | 0 | 0 | For 1 Year (from- 10/01/2024 to 09/01/2025) | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 May 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 771 | 0 | 09 May 2024 | INFIFLEX TECHNOLOGIES PRIVATE LIMITED | H.O. Admin Cyber Protect Cloud | Cyber Protect Cloud | GB | 1000 | 25 | 25000 | 4500 | 29500 | 0 | 1000 | 25000 | 4500 | 29500 | 0 | 0 | For 1 Year (from- 10/01/2024 to 09/01/2025) | 100 |  | ADITYA.CHOUGULE | it admin | construction open | 16 May 2024 |  | No category | Approved | it admin | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 1.5 TR Split Air Conditioner Mandir Room | AMC Charges | Month | 12 | 400 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1.5 TR Split Air Conditioner - Mandir Room (Qty- 2 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2 TR Split Air conditioner Manager cabin | AMC Charges | Month | 12 | 266.66 | 3199.92 | 575.98 | 3775.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Split Air Conditioner - Manager Cabin (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 1.5 TR Split Air Conditioner Mandir Room | AMC Charges | Month | 12 | 400 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1.5 TR Split Air Conditioner - Mandir Room (Qty- 2 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2 TR Split Air conditioner Manager cabin | AMC Charges | Month | 12 | 266.66 | 3199.92 | 575.98 | 3775.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Split Air Conditioner - Manager Cabin (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2.0 TR Cassett Air Conditioner Play room | AMC Charges | Month | 12 | 266.66 | 3199.92 | 575.98 | 3775.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Cassette Air Conditioner - Play Room (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2.0 TR Split Air Conditioner - Gym Room | AMC Charges | Month | 12 | 2133.33 | 25599.96 | 4608 | 30207.96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Split Air Conditioner - GYM Room (Qty- 8 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2.0 TR Split Air Conditioner Steam Room | AMC Charges | Month | 12 | 533.33 | 6399.96 | 1152 | 7551.96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Split Air Conditioner - Steam Room (Qty- 2 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2.0 TR Split Air Conditioner - Gym Room | AMC Charges | Month | 12 | 2133.33 | 25599.96 | 4608 | 30207.96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Split Air Conditioner - GYM Room (Qty- 8 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2 TR Cassette Air Conditioner Bedroom 7 | AMC Charges | Month | 12 | 266.66 | 3199.92 | 575.98 | 3775.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Cassette Air Conditioner - Bed Room 7 (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 1.5 TR Split Air Conditioner Bedroom 4 | AMC Charges | Month | 12 | 200 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1.5 TR Split Air Conditioner - Bedroom 4 (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 3.0 T Cassette Air conditioner Bedrm 5,6 | AMC Charges | Month | 12 | 800 | 9600 | 1728 | 11328 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 3.0 TR Cassette Air Conditioner - Bed Room 5 & 6 (Qty- 2 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 1.5 TR Split Air Conditioner Bedroom 4 | AMC Charges | Month | 12 | 200 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1.5 TR Split Air Conditioner - Bedroom 4 (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2 TR Cassette Air Conditioner Bedroom 7 | AMC Charges | Month | 12 | 266.66 | 3199.92 | 575.98 | 3775.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Cassette Air Conditioner - Bed Room 7 (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2.0 TR Split Air Conditioner Steam Room | AMC Charges | Month | 12 | 533.33 | 6399.96 | 1152 | 7551.96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Split Air Conditioner - Steam Room (Qty- 2 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 2.0 TR Cassett Air Conditioner Play room | AMC Charges | Month | 12 | 266.66 | 3199.92 | 575.98 | 3775.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2.0 TR Cassette Air Conditioner - Play Room (Qty- 1 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 772 | 0 | 10 May 2024 | ATHARVA AIRCON SYSTEM | 3.0 T Cassette Air conditioner Bedrm 5,6 | AMC Charges | Month | 12 | 800 | 9600 | 1728 | 11328 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 3.0 TR Cassette Air Conditioner - Bed Room 5 & 6 (Qty- 2 Nos.) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 May 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 773 | 0 | 15 May 2024 | SUHANA FABRICATORS | Material required for GH | TABLE | No. | 1 | 3500 | 3500 | 0 | 3500 | 0 | 1 | 3500 | 630 | 4130 | 0 | -630 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 May 2024 |  | MKT. Media | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 774 | 0 | 16 May 2024 | AVNS TECHNOSOFT | H.O. IT Expences | FIREWALL | No. | 1 | 57000 | 57000 | 10260 | 67260 | 0 | 1 | 57000 | 10260 | 67260 | 0 | 0 | Essential Protection Multi Engine sandboxing-Randomware protection,RTDMI Technology,DNS Security,Gateway Antivirus,Anti Spyware,Intrusion Detection & Prevention,Web & URL Filtering,Application Control,Anti spam,Network visibility 24x7 sonicwall support. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 May 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 602.515 | 1 | 602.52 | 108.46 | 710.98 | 2.5 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.583 | 0.5 | 1370.79 | 246.74 | 1617.53 | 2.5 | 0 | 0 | 0 | 0 | 2741.583 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 783.413 | 1 | 783.41 | 141.02 | 924.43 | 2.5 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 783.413 | 1 | 783.41 | 141.02 | 924.43 | 2.5 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 602.515 | 1 | 602.52 | 108.46 | 710.98 | 2.5 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.106 | 1.5 | 1182.16 | 212.78 | 1394.94 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.673 | 1.5 | 899.51 | 161.92 | 1061.43 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 602.267 | 1 | 602.27 | 108.4 | 710.67 | 2.5 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 602.267 | 1 | 602.27 | 108.4 | 710.67 | 2.5 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 819.257 | 1 | 819.26 | 147.46 | 966.72 | 2.5 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 602.267 | 1 | 602.27 | 108.4 | 710.67 | 2.5 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2130.436 | 0.5 | 1065.22 | 191.74 | 1256.96 | 2.5 | 0 | 0 | 0 | 0 | 2130.436 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.673 | 1.5 | 899.51 | 161.92 | 1061.43 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.213 | 1.5 | 1182.32 | 212.82 | 1395.14 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.008 | 1.5 | 901.51 | 162.28 | 1063.79 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 602.267 | 1 | 602.27 | 108.4 | 710.67 | 2.5 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.312 | 0.5 | 1060.66 | 190.92 | 1251.58 | 2.5 | 0 | 0 | 0 | 0 | 2121.312 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.416 | 1.5 | 900.62 | 162.12 | 1062.74 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2130.436 | 0.5 | 1065.22 | 191.74 | 1256.96 | 2.5 | 0 | 0 | 0 | 0 | 2130.436 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 602.515 | 1 | 602.52 | 108.46 | 710.98 | 2.5 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 780.571 | 1.5 | 1170.86 | 210.76 | 1381.62 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.583 | 0.5 | 1370.79 | 246.74 | 1617.53 | 2.5 | 0 | 0 | 0 | 0 | 2741.583 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.312 | 0.5 | 1060.66 | 190.92 | 1251.58 | 2.5 | 0 | 0 | 0 | 0 | 2121.312 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.476 | 0.5 | 1370.74 | 246.74 | 1617.48 | 2.5 | 0 | 0 | 0 | 0 | 2741.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.106 | 1.5 | 1182.16 | 212.78 | 1394.94 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 787.88 | 1.5 | 1181.82 | 212.72 | 1394.54 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.25 | 0.5 | 1370.63 | 246.72 | 1617.35 | 2.5 | 0 | 0 | 0 | 0 | 2741.25 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.658 | 0.5 | 1061.33 | 191.04 | 1252.37 | 2.5 | 0 | 0 | 0 | 0 | 2122.658 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.25 | 0.5 | 1370.63 | 246.72 | 1617.35 | 2.5 | 0 | 0 | 0 | 0 | 2741.25 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.583 | 0.5 | 1370.79 | 246.74 | 1617.53 | 2.5 | 0 | 0 | 0 | 0 | 2741.583 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2072.145 | 0.5 | 1036.07 | 186.5 | 1222.57 | 2.5 | 0 | 0 | 0 | 0 | 2072.145 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.008 | 1.5 | 901.51 | 162.28 | 1063.79 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 602.515 | 1 | 602.52 | 108.46 | 710.98 | 2.5 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.476 | 0.5 | 1370.74 | 246.74 | 1617.48 | 2.5 | 0 | 0 | 0 | 0 | 2741.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.662 | 1.5 | 899.49 | 161.9 | 1061.39 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.583 | 0.5 | 1370.79 | 246.74 | 1617.53 | 2.5 | 0 | 0 | 0 | 0 | 2741.583 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2132.287 | 0.5 | 1066.14 | 191.9 | 1258.04 | 2.5 | 0 | 0 | 0 | 0 | 2132.287 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2069.303 | 0.5 | 1034.65 | 186.24 | 1220.89 | 2.5 | 0 | 0 | 0 | 0 | 2069.303 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.106 | 1.5 | 1182.16 | 212.78 | 1394.94 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 819.257 | 1 | 819.26 | 147.46 | 966.72 | 2.5 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 780.571 | 1.5 | 1170.86 | 210.76 | 1381.62 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.673 | 1.5 | 899.51 | 161.92 | 1061.43 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.673 | 1.5 | 899.51 | 161.92 | 1061.43 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2069.303 | 0.5 | 1034.65 | 186.24 | 1220.89 | 2.5 | 0 | 0 | 0 | 0 | 2069.303 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.106 | 1.5 | 1182.16 | 212.78 | 1394.94 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.416 | 1.5 | 900.62 | 162.12 | 1062.74 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.25 | 0.5 | 1370.63 | 246.72 | 1617.35 | 2.5 | 0 | 0 | 0 | 0 | 2741.25 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.658 | 0.5 | 1061.33 | 191.04 | 1252.37 | 2.5 | 0 | 0 | 0 | 0 | 2122.658 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.833 | 0.5 | 1370.42 | 246.68 | 1617.1 | 2.5 | 0 | 0 | 0 | 0 | 2740.833 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.658 | 0.5 | 1061.33 | 191.04 | 1252.37 | 2.5 | 0 | 0 | 0 | 0 | 2122.658 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.213 | 1.5 | 1182.32 | 212.82 | 1395.14 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 783.413 | 1 | 783.41 | 141.02 | 924.43 | 2.5 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 783.413 | 1 | 783.41 | 141.02 | 924.43 | 2.5 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 819.257 | 1 | 819.26 | 147.46 | 966.72 | 2.5 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 780.571 | 1.5 | 1170.86 | 210.76 | 1381.62 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.213 | 1.5 | 1182.32 | 212.82 | 1395.14 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 787.88 | 1.5 | 1181.82 | 212.72 | 1394.54 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.658 | 0.5 | 1061.33 | 191.04 | 1252.37 | 2.5 | 0 | 0 | 0 | 0 | 2122.658 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.662 | 1.5 | 899.49 | 161.9 | 1061.39 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2130.436 | 0.5 | 1065.22 | 191.74 | 1256.96 | 2.5 | 0 | 0 | 0 | 0 | 2130.436 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2069.303 | 0.5 | 1034.65 | 186.24 | 1220.89 | 2.5 | 0 | 0 | 0 | 0 | 2069.303 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2069.303 | 0.5 | 1034.65 | 186.24 | 1220.89 | 2.5 | 0 | 0 | 0 | 0 | 2069.303 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.25 | 0.5 | 1370.63 | 246.72 | 1617.35 | 2.5 | 0 | 0 | 0 | 0 | 2741.25 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.583 | 0.5 | 1370.79 | 246.74 | 1617.53 | 2.5 | 0 | 0 | 0 | 0 | 2741.583 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.213 | 1.5 | 1182.32 | 212.82 | 1395.14 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.008 | 1.5 | 901.51 | 162.28 | 1063.79 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.008 | 1.5 | 901.51 | 162.28 | 1063.79 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.416 | 1.5 | 900.62 | 162.12 | 1062.74 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.583 | 0.5 | 1370.79 | 246.74 | 1617.53 | 2.5 | 0 | 0 | 0 | 0 | 2741.583 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.673 | 1.5 | 899.51 | 161.92 | 1061.43 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 601 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2737.991 | 0.5 | 1369 | 246.42 | 1615.42 | 2.5 | 0 | 0 | 0 | 0 | 2737.991 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1407. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.25 | 0.5 | 1370.63 | 246.72 | 1617.35 | 2.5 | 0 | 0 | 0 | 0 | 2741.25 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1309 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 505 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2703 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 787.88 | 1.5 | 1181.82 | 212.72 | 1394.54 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 819.257 | 1.5 | 1228.89 | 221.2 | 1450.09 | 2.5 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1103 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 401 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.416 | 1.5 | 900.62 | 162.12 | 1062.74 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.662 | 1.5 | 899.49 | 161.9 | 1061.39 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.213 | 1.5 | 1182.32 | 212.82 | 1395.14 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 602.515 | 1.5 | 903.77 | 162.68 | 1066.45 | 2.5 | 0 | 0 | 0 | 0 | 602.515 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.106 | 1.5 | 1182.16 | 212.78 | 1394.94 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.312 | 0.5 | 1060.66 | 190.92 | 1251.58 | 2.5 | 0 | 0 | 0 | 0 | 2121.312 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2069.303 | 0.5 | 1034.65 | 186.24 | 1220.89 | 2.5 | 0 | 0 | 0 | 0 | 2069.303 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2130.436 | 0.5 | 1065.22 | 191.74 | 1256.96 | 2.5 | 0 | 0 | 0 | 0 | 2130.436 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 801 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2803 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2002. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 503 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1701 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1705 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P3 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2309 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.312 | 0.5 | 1060.66 | 190.92 | 1251.58 | 2.5 | 0 | 0 | 0 | 0 | 2121.312 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2709 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2609 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 819.257 | 1 | 819.26 | 147.46 | 966.72 | 2.5 | 0 | 0 | 0 | 0 | 819.257 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 603 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1703 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2005 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 404 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1209 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.476 | 0.5 | 1370.74 | 246.74 | 1617.48 | 2.5 | 0 | 0 | 0 | 0 | 2741.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.476 | 0.5 | 1370.74 | 246.74 | 1617.48 | 2.5 | 0 | 0 | 0 | 0 | 2741.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2130.476 | 0.5 | 1065.24 | 191.74 | 1256.98 | 2.5 | 0 | 0 | 0 | 0 | 2130.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 202. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.213 | 1.5 | 1182.32 | 212.82 | 1395.14 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.106 | 1.5 | 1182.16 | 212.78 | 1394.94 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2069.303 | 0.5 | 1034.65 | 186.24 | 1220.89 | 2.5 | 0 | 0 | 0 | 0 | 2069.303 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1609 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1909 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1803 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 803 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2302. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1107 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2009 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1804 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 509 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.673 | 1.5 | 899.51 | 161.92 | 1061.43 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 305 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 787.88 | 1.5 | 1181.82 | 212.72 | 1394.54 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 787.88 | 1.5 | 1181.82 | 212.72 | 1394.54 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 108 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2131.082 | 0.5 | 1065.54 | 191.8 | 1257.34 | 2.5 | 0 | 0 | 0 | 0 | 2131.082 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1801 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 780.571 | 1.5 | 1170.86 | 210.76 | 1381.62 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 402. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2203 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.662 | 1.5 | 899.49 | 161.9 | 1061.39 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 903 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1404 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2103 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2307. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2301 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1303 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1905 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 804 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 501 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 787.88 | 1.5 | 1181.82 | 212.72 | 1394.54 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2109 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1805 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2404 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1307. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 908 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2804 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.416 | 1.5 | 900.62 | 162.12 | 1062.74 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P1 - 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 783.413 | 1.5 | 1175.12 | 211.52 | 1386.64 | 2.5 | 0 | 0 | 0 | 0 | 783.413 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2808 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.416 | 1.5 | 900.62 | 162.12 | 1062.74 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.662 | 1.5 | 899.49 | 161.9 | 1061.39 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2001 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2505 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 408 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2405 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2303 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2801 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1506. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1408 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2507. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1207. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2209 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2707. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 508 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1002. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1901 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1301 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1008 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1007. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2101 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 780.571 | 1.5 | 1170.86 | 210.76 | 1381.62 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2704 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 909 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 504 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1308 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2008 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2506. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1807. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1605 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1606 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2403 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 807. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 304 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 805 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1405 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 303 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1709 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 705 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 307. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1806. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1401 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 407. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2406. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2107 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 904 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 207. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1006. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 802. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1702. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2603 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P4 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 602.267 | 1.5 | 903.4 | 162.62 | 1066.02 | 2.5 | 0 | 0 | 0 | 0 | 602.267 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 907. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1903 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.384 | 1 | 600.38 | 108.06 | 708.44 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2070.014 | 0.5 | 1035.01 | 186.3 | 1221.31 | 2.5 | 0 | 0 | 0 | 0 | 2070.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 507. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2502. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2807. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 403 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.008 | 1.5 | 901.51 | 162.28 | 1063.79 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1409 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1507. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1001 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.662 | 1.5 | 899.49 | 161.9 | 1061.39 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 905 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2602. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1004 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2503 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 706. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1205 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1504 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1808 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2605 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.72 | 0.5 | 1371.36 | 246.84 | 1618.2 | 2.5 | 0 | 0 | 0 | 0 | 2742.72 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2742.272 | 0.5 | 1371.14 | 246.8 | 1617.94 | 2.5 | 0 | 0 | 0 | 0 | 2742.272 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2703.664 | 0.5 | 1351.83 | 243.32 | 1595.15 | 2.5 | 0 | 0 | 0 | 0 | 2703.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 109 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2802. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2509 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 901 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1402. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1203 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 308 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 707. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1707. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1708 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 306. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 606 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 309 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1206. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 103 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1902. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1201 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2305 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2401 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2308 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1508 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2809 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1005 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1406. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2408 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1204 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 107 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1802. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2006. 3BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2705 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.582 | 0.5 | 1060.79 | 190.94 | 1251.73 | 2.5 | 0 | 0 | 0 | 0 | 2121.582 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1202. 3BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 806. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2202. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1602. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2201 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 204 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1704 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2207. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 708 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.106 | 1 | 788.11 | 141.86 | 929.97 | 2.5 | 0 | 0 | 0 | 0 | 788.106 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1302. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1503 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2504 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 609 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2130.436 | 0.5 | 1065.22 | 191.74 | 1256.96 | 2.5 | 0 | 0 | 0 | 0 | 2130.436 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 605 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 209 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2740.014 | 0.5 | 1370.01 | 246.6 | 1616.61 | 2.5 | 0 | 0 | 0 | 0 | 2740.014 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 902. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2402. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1208 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 101 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 780.571 | 1 | 780.57 | 140.5 | 921.07 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1904 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2805 . 2BHK Internal Painting Work | 2nd Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 703 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1469.63 | 1.5 | 2204.45 | 396.8 | 2601.25 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2316.664 | 0.5 | 1158.33 | 208.5 | 1366.83 | 2.5 | 0 | 0 | 0 | 0 | 2316.664 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1706. 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2206. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.658 | 0.5 | 1061.33 | 191.04 | 1252.37 | 2.5 | 0 | 0 | 0 | 0 | 2122.658 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 208 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.814 | 1.5 | 901.22 | 162.22 | 1063.44 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1003 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 203 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2409 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1403 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 600.384 | 1.5 | 900.58 | 162.1 | 1062.68 | 2.5 | 0 | 0 | 0 | 0 | 600.384 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2702. 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2204 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 601.062 | 1 | 601.06 | 108.2 | 709.26 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2706. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2003 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1469.63 | 1 | 1469.63 | 264.54 | 1734.17 | 2.5 | 0 | 0 | 0 | 0 | 1469.63 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1809 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 406. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2508 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1907. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 786.644 | 1.5 | 1179.97 | 212.4 | 1392.37 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 206. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2108 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.008 | 1.5 | 901.51 | 162.28 | 1063.79 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 409 . 2BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 607 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.25 | 0.5 | 1370.63 | 246.72 | 1617.35 | 2.5 | 0 | 0 | 0 | 0 | 2741.25 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 502. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1509 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 808 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1106 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 105 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.312 | 0.5 | 1060.66 | 190.92 | 1251.58 | 2.5 | 0 | 0 | 0 | 0 | 2121.312 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2208 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.814 | 1 | 600.81 | 108.14 | 708.95 | 2.5 | 0 | 0 | 0 | 0 | 600.814 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1305 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 205 . 2BHK Internal Painting Work | 1st Coat Ceiling Putty | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 788.213 | 1 | 788.21 | 141.88 | 930.09 | 2.5 | 0 | 0 | 0 | 0 | 788.213 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 405 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.932 | 1 | 599.93 | 107.98 | 707.91 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 701 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P5 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.712 | 0.5 | 1061.36 | 191.04 | 1252.4 | 2.5 | 0 | 0 | 0 | 0 | 2122.712 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1501 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1502. 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 788.902 | 1.5 | 1183.35 | 213 | 1396.35 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2501 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 746.244 | 1.5 | 1119.37 | 201.48 | 1320.85 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1009 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2607 . 3BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 787.88 | 1 | 787.88 | 141.82 | 929.7 | 2.5 | 0 | 0 | 0 | 0 | 787.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.658 | 0.5 | 1061.33 | 191.04 | 1252.37 | 2.5 | 0 | 0 | 0 | 0 | 2122.658 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 0 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 201 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2708 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2122.464 | 0.5 | 1061.23 | 191.02 | 1252.25 | 2.5 | 0 | 0 | 0 | 0 | 2122.464 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1608 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1603 . 2BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 599.673 | 1 | 599.67 | 107.94 | 707.61 | 2.5 | 0 | 0 | 0 | 0 | 599.673 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 602. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.476 | 0.5 | 1370.74 | 246.74 | 1617.48 | 2.5 | 0 | 0 | 0 | 0 | 2741.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 906. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2102. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2741.476 | 0.5 | 1370.74 | 246.74 | 1617.48 | 2.5 | 0 | 0 | 0 | 0 | 2741.476 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 102. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1601 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2606 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1908 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 301 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1957.42 | 1.5 | 2936.13 | 528.5 | 3464.63 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2601 . 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1957.42 | 1 | 1957.42 | 352.34 | 2309.76 | 2.5 | 0 | 0 | 0 | 0 | 1957.42 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2304 . 2BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1530.02 | 1.5 | 2295.03 | 413.1 | 2708.13 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1906. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2106 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1953.37 | 1.5 | 2930.06 | 527.42 | 3457.48 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2806. 3BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 2nd Coat Wall Paint | Sq.Ft | 1521.65 | 1.5 | 2282.48 | 410.84 | 2693.32 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 704 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 709 . 2BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2205 . 2BHK Internal Painting Work | Primer Water Base- Wall | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1109 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 600.416 | 1 | 600.42 | 108.08 | 708.5 | 2.5 | 0 | 0 | 0 | 0 | 600.416 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 506. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2608 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 601.008 | 1 | 601.01 | 108.18 | 709.19 | 2.5 | 0 | 0 | 0 | 0 | 601.008 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1108 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 106 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1607 . 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat P2. 3BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2772.627 | 0.5 | 1386.31 | 249.54 | 1635.85 | 2.5 | 0 | 0 | 0 | 0 | 2772.627 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 702. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2105 . 2BHK Internal Painting Work | Cleaning work.- BRE | Sq.Ft | 2121.312 | 0.5 | 1060.66 | 190.92 | 1251.58 | 2.5 | 0 | 0 | 0 | 0 | 2121.312 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 302. 3BHK Internal Painting Work | 2nd Coat Ceiling Putty | Sq.Ft | 788.902 | 1 | 788.9 | 142 | 930.9 | 2.5 | 0 | 0 | 0 | 0 | 788.902 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 608 . 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1521.65 | 1 | 1521.65 | 273.9 | 1795.55 | 2.5 | 0 | 0 | 0 | 0 | 1521.65 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2701 . 3BHK Internal Painting Work | Primer Water Base- Ceiling | Sq.Ft | 746.244 | 1 | 746.24 | 134.32 | 880.56 | 2.5 | 0 | 0 | 0 | 0 | 746.244 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1306. 3BHK Internal Painting Work | 1st Coat Wall Paint | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2007. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2306. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2004 . 2BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1530.02 | 1 | 1530.02 | 275.4 | 1805.42 | 2.5 | 0 | 0 | 0 | 0 | 1530.02 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1102. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 2407. 3BHK Internal Painting Work | 1st Coat Putty (L) | Sq.Ft | 1953.37 | 1 | 1953.37 | 351.6 | 2304.97 | 2.5 | 0 | 0 | 0 | 0 | 1953.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 809 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 786.644 | 1 | 786.64 | 141.6 | 928.24 | 2.5 | 0 | 0 | 0 | 0 | 786.644 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1101 . 3BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 780.571 | 1.5 | 1170.86 | 210.76 | 1381.62 | 2.5 | 0 | 0 | 0 | 0 | 780.571 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1304 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 601.062 | 1.5 | 901.59 | 162.28 | 1063.87 | 2.5 | 0 | 0 | 0 | 0 | 601.062 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1105 . 2BHK Internal Painting Work | 1st Coat Ceiling Paint | Sq.Ft | 599.662 | 1 | 599.66 | 107.94 | 707.6 | 2.5 | 0 | 0 | 0 | 0 | 599.662 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 775 | 1 | 16 May 2024 | SHAHI ENTERPRISES | Wing 1 Flat 1505 . 2BHK Internal Painting Work | 2nd Coat Ceiling Paint | Sq.Ft | 599.932 | 1.5 | 899.9 | 161.98 | 1061.88 | 2.5 | 0 | 0 | 0 | 0 | 599.932 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | MONALI CHAUDHAR | 21 May 2024
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | MONALI CHAUDHAR | 21 May 2024
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0.1013 | 303.9 | 0 | 303.9 | 0.8987 | 2696.1 |  | 10.13 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0.2957 | 887.1 | 0 | 887.1 | 0.7043 | 2112.9 |  | 29.57 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0.101 | 303 | 0 | 303 | 0.899 | 2697 |  | 10.1 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 776 | 0 | 21 May 2024 | VAISHNAVI MANGESH KADU | Vaishnavi Kadu Travelling Expences | Travelling Allowance | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 777 | 1 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection 200Mbps | Month | 6 | 3333 | 19998 | 3599.64 | 23597.64 | 0 | 6 | 19998 | 3599.66 | 23597.66 | 0 | -0.02 |  | 100 |  | administrator | it admin | construction open | 24 May 2024 |  | No category | Approved | it admin | 1900-01-01
GANGA ASMI | 777 | 1 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection 200Mbps | Month | 0 | 19999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | administrator |  | construction open | 24 May 2024 |  | No category | Cancelled | administrator | 24 May 2024
GANGA ASMI | 777 | 0 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection | Month | 0 | 3333 | 0 | 599.94 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | it admin | construction open | 24 May 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 24 May 2024
GANGA ASMI | 777 | 0 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection | Month | 0 | 3333 | 0 | 599.94 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | it admin | construction open | 24 May 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 24 May 2024
GANGA ASMI | 777 | 0 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection | Month | 0 | 3333 | 0 | 599.94 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | it admin | construction open | 24 May 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 24 May 2024
GANGA ASMI | 777 | 0 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection | Month | 0 | 3333 | 0 | 599.94 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | it admin | construction open | 24 May 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 24 May 2024
GANGA ASMI | 777 | 0 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection | Month | 0 | 3333 | 0 | 599.94 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | it admin | construction open | 24 May 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 24 May 2024
GANGA ASMI | 777 | 0 | 22 May 2024 | TREELINK NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Internet Connection | Month | 0 | 3333 | 0 | 599.94 | 599.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | it admin | construction open | 24 May 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 24 May 2024
GANGA ASMI | 778 | 0 | 24 May 2024 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD. | Pile Integrity Test | Integrity Test | No. | 7 | 600 | 4200 | 756 | 4956 | 0 | 7 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 16 Testing, Analysis & Reports | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 778 | 0 | 24 May 2024 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD. | Pile Integrity Test | Integrity Test | No. | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 16 Testing, Analysis & Reports | Cancelled | ADITYA.CHOUGULE | 30 May 2024
GANGA ASMI | 778 | 0 | 24 May 2024 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD. | Pile Integrity Test | Visiting Charges-AIE | No. | 1 | 2250 | 2250 | 405 | 2655 | 0 | 1 | 2250 | 405 | 2655 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 779 | 0 | 24 May 2024 | S.R.Enterprises | Goel House Pest Control | Snake Treatment | No. | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 May 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 779 | 0 | 24 May 2024 | S.R.Enterprises | Goel House Pest Control | Snake Treatment | No. | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 24 May 2024 |  | S OH Infrastructure | Cancelled | DUSHANT.GORE | 24 May 2024
GANGA ASMI | 780 | 0 | 24 May 2024 | VINAYAKA ASSOCIATE | Wing 1 - Ply Shuttering Material | Shuttering Ply | No. | 42 | 2200 | 92400 | 16632 | 109032 | 0 | 42 | 92400 | 16632 | 109032 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 780 | 0 | 24 May 2024 | VINAYAKA ASSOCIATE | Wing 1 - Ply Shuttering Material | Shuttering Patti | No. | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 1900-01-01 |  | No category | Cancelled | MONALI CHAUDHAR | 24 May 2024
GANGA ASMI | 780 | 0 | 24 May 2024 | VINAYAKA ASSOCIATE | Wing 1 - Ply Shuttering Material | Shuttering Patti | No. | 355 | 115 | 40825 | 7348.5 | 48173.5 | 0 | 355 | 40825 | 7348.5 | 48173.5 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | MS Plate 71 x 72 x 4mm | No. | 71 | 73 | 5183 | 0 | 5183 | 0 | 71 | 5183 | 0 | 5183 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | Hardware Material | No. | 1 | 4850 | 4850 | 873 | 5723 | 0 | 1 | 4850 | 0 | 4850 | 0 | 873 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | MS Plate 132 x 210 x 4mm | No. | 23 | 250 | 5750 | 1035 | 6785 | 0 | 23 | 5750 | 0 | 5750 | 0 | 1035 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | MS Plate 206 x 72 x 4mm | No. | 44 | 175 | 7700 | 1386 | 9086 | 0 | 44 | 7700 | 0 | 7700 | 0 | 1386 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | MS Plate 231 x 76 x 4mm | No. | 26 | 197 | 5122 | 921.96 | 6043.96 | 0 | 26 | 5122 | 0 | 5122 | 0 | 921.96 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | MS Plate 97 x 72 x 4mm | No. | 120 | 87 | 10440 | 1879.2 | 12319.2 | 0 | 120 | 10440 | 0 | 10440 | 0 | 1879.2 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 781 | 0 | 24 May 2024 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | MS Plate 132 x 72 x 4mm | No. | 36 | 120 | 4320 | 777.6 | 5097.6 | 0 | 36 | 4320 | 0 | 4320 | 0 | 777.6 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 782 | 0 | 25 May 2024 | SUNITA ENTERPRISES | Goel House Rennovation Installation of AC System | GI Ducting (M+L) | Sq.Ft | 260 | 100 | 26000 | 0 | 26000 | 2.5 | 0 | 0 | 0 | 0 | 260 | 0 | GI Ducting for AC Outdoor unit Including- Nut Bolt, Gasket, Banding Tar, Transport charges, Callicoon, MS Angle, Chicken Mesh Jali, MS Channel,etc | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 07 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 2881.85 | 0.5 | 1440.93 | 259.36 | 1700.29 | 2.5 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1503.08 | 3.5 | 5260.78 | 946.94 | 6207.72 | 2.5 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1503.08 | 7.5 | 11273.1 | 2029.16 | 13302.26 | 2.5 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 2881.85 | 1.75 | 5043.24 | 907.78 | 5951.02 | 2.5 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 2881.85 | 3.5 | 10086.48 | 1815.56 | 11902.04 | 2.5 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1503.08 | 1.75 | 2630.39 | 473.48 | 3103.87 | 2.5 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 2881.85 | 1.5 | 4322.78 | 778.1 | 5100.88 | 2.5 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1503.08 | 0.5 | 751.54 | 135.28 | 886.82 | 2.5 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1503.08 | 1.5 | 2254.62 | 405.84 | 2660.46 | 2.5 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 2881.85 | 7.5 | 21613.88 | 3890.5 | 25504.38 | 2.5 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 2881.85 | 1 | 2881.85 | 518.74 | 3400.59 | 2.5 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1503.08 | 1 | 1503.08 | 270.56 | 1773.64 | 2.5 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1358.98 | 0.5 | 679.49 | 122.3 | 801.79 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1072.28 | 0.5 | 536.14 | 96.5 | 632.64 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 1099.93 | 0.5 | 549.97 | 99 | 648.97 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.5 | 4679.51 | 842.32 | 5521.83 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.5 | 2038.47 | 366.92 | 2405.39 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.75 | 1924.88 | 346.48 | 2271.36 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 3119.67 | 1.75 | 5459.42 | 982.7 | 6442.12 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.75 | 1876.49 | 337.76 | 2214.25 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (L) | Sq.Ft | 1358.98 | 1.75 | 2378.22 | 428.08 | 2806.3 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | Final Cleaning & Housekeeping work (L) | Sq.Ft | 3119.67 | 0.5 | 1559.84 | 280.78 | 1840.62 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | S OH Conveyance & Transport | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1072.28 | 7.5 | 8042.1 | 1447.58 | 9489.68 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 3119.67 | 7.5 | 23397.53 | 4211.56 | 27609.09 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1358.98 | 7.5 | 10192.35 | 1834.62 | 12026.97 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (L) | Sq.Ft | 1099.93 | 7.5 | 8249.48 | 1484.9 | 9734.38 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1099.93 | 1.5 | 1649.9 | 296.98 | 1946.88 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (L) | Sq.Ft | 1072.28 | 1.5 | 1608.42 | 289.52 | 1897.94 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (L) - | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 3119.67 | 3.5 | 10918.85 | 1965.4 | 12884.25 | 2.5 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1099.93 | 3.5 | 3849.76 | 692.96 | 4542.72 | 2.5 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1358.98 | 3.5 | 4756.43 | 856.16 | 5612.59 | 2.5 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 783 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | Scaffolding work | Sq.Ft | 1072.28 | 3.5 | 3752.98 | 675.54 | 4428.52 | 2.5 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 2881.85 | 2.5 | 7204.63 | 1296.84 | 8501.47 | 0 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1503.08 | 8 | 12024.64 | 2164.44 | 14189.08 | 0 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1503.08 | 1 | 1503.08 | 270.56 | 1773.64 | 0 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 2881.85 | 2.25 | 6484.16 | 1167.14 | 7651.3 | 0 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1503.08 | 2.25 | 3381.93 | 608.74 | 3990.67 | 0 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 10th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Eastside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1072.28 | 1 | 1072.28 | 193.02 | 1265.3 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 2881.85 | 1 | 2881.85 | 518.74 | 3400.59 | 0 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Northside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1358.98 | 1 | 1358.98 | 244.62 | 1603.6 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 1099.93 | 1 | 1099.93 | 197.98 | 1297.91 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1503.08 | 2.5 | 3757.7 | 676.38 | 4434.08 | 0 | 0 | 0 | 0 | 0 | 1503.08 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 2nd Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 23rd Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 12th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 11th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 4th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Northside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1358.98 | 8 | 10871.84 | 1956.94 | 12828.78 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Northside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.5 | 3397.45 | 611.54 | 4008.99 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 9th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 3rd Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 15th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 5th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 1st Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 8th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 16th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 24th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 25th Floor Wing 1 Eastside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.25 | 2412.63 | 434.28 | 2846.91 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 21st Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 7th Floor Wing 1 Eastside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1072.28 | 8 | 8578.24 | 1544.08 | 10122.32 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | 1 Coat Primer (External) (M) | Sq.Ft | 3119.67 | 1 | 3119.67 | 561.54 | 3681.21 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 27th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 28th Floor Wing 1 Westside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.5 | 2749.83 | 494.96 | 3244.79 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Eastside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1072.28 | 2.5 | 2680.7 | 482.52 | 3163.22 | 0 | 0 | 0 | 0 | 0 | 1072.28 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 13th Floor Wing 1 Southside Acrylic Texture Paint | 2nd Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.5 | 7799.18 | 1403.86 | 9203.04 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 26th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 6th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 17th Floor Wing 1 Northside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1358.98 | 2.25 | 3057.71 | 550.38 | 3608.09 | 0 | 0 | 0 | 0 | 0 | 1358.98 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 20th Floor Wing 1 Southside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 3119.67 | 2.25 | 7019.26 | 1263.46 | 8282.72 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 14th Floor Wing 1 Westside Acrylic Texture Paint | 1st Coat Acrylic Paint (M) | Sq.Ft | 1099.93 | 2.25 | 2474.84 | 445.48 | 2920.32 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 10 PAINTING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 22nd Floor Wing 1 Westside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 1099.93 | 8 | 8799.44 | 1583.9 | 10383.34 | 0 | 0 | 0 | 0 | 0 | 1099.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 19th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | 18th Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 3119.67 | 8 | 24957.36 | 4492.32 | 29449.68 | 0 | 0 | 0 | 0 | 0 | 3119.67 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 784 | 0 | 30 May 2024 | ANIL MAHTO ENTERPRISES | Podium Floor Wing 1 Southside Acrylic Texture Paint | Texture Paint- DPo (M) | Sq.Ft | 2881.85 | 8 | 23054.8 | 4149.86 | 27204.66 | 0 | 0 | 0 | 0 | 0 | 2881.85 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Podium | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 103 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 702 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1307 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 906 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2007 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P3 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P4 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2408 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1203 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 109 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 203 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2101 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1007 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1102 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1507 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 808 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2508 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2708 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 501 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P1 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1402 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1903 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1206 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1207 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 603 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1009 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 509 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2307 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2208 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2401 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1404 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1905 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2003 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1607 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1006 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2109 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 106 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 304 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 502 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1005 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2106 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2102 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 403 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1109 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2203 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P6 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2507 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2703 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1406 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1505 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 401 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2001 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 902 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 302 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2705 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2504 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2603 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 408 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1801 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 205 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2801 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2805 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 601 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 908 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1106 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P9 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2405 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2406 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2709 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 608 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1002 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 102 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2804 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1906 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2308 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1405 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1001 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 907 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 309 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2202 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2501 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1205 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1209 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2605 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2601 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1602 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 707 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1509 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1003 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 306 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1403 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 909 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2602 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1208 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 801 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1502 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1202 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 105 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2004 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 802 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1508 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1601 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2509 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1504 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 507 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1407 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 809 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1707 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1302 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2209 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1806 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1706 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1501 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2505 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1702 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 201 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1308 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1401 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1603 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2609 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2802 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 307 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1605 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2105 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 602 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1101 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2304 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1703 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2407 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2706 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1808 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 204 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2806 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 701 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2409 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2404 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 208 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P7 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 303 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 206 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 605 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1909 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1902 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2808 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P8 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1802 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1105 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1204 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 406 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 405 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 905 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2403 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1303 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2707 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2503 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1004 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2702 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 609 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2201 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1305 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1805 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1904 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2302 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1108 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 409 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1103 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2502 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 904 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2309 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2103 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 503 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 505 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2008 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 108 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2009 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 704 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 202 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1408 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2704 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1606 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1301 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 402 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 305 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1804 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2608 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1107 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1304 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1908 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 404 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2306 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 706 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2002 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1901 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2701 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2506 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 703 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 709 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2803 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2107 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1803 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 607 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2807 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1201 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 807 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1708 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1309 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1306 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2305 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1008 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2206 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 209 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1701 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 207 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2205 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1409 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 803 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1705 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 705 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 903 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 301 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1506 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2607 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 805 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2402 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 606 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 101 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1704 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2108 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 407 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 506 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2005 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 901 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 107 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2006 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P2 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1503 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 508 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1608 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 708 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 504 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2204 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2301 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1907 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1609 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 308 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2809 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1709 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1807 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2207 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2303 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 806 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1809 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 804 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P5 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 785 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2606 Toilet Ventilator | Toilet Ventilator (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1206 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 304 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 507 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1403 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1904 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 401 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 708 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2202 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2404 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 302 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2207 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2107 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1706 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 303 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2006 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 206 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P1 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 404 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1402 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1407 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2704 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2205 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2509 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2109 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2508 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1502 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2807 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2009 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2407 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 407 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2806 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2505 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1201 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 501 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 504 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1409 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2803 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1504 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 109 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1209 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1303 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 204 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1905 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 301 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 105 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 406 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2701 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2503 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2108 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2302 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 408 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 505 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 909 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1102 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2208 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1602 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2601 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 701 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1509 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2007 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1103 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 409 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 107 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 207 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 703 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1405 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 305 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1809 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2406 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2204 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2501 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 902 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 906 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2705 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 609 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2004 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1608 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1805 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 707 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1306 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1507 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1506 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 308 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 503 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1203 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2506 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1002 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1108 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 705 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2409 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1708 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1408 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1105 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2307 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 804 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2206 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1101 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 201 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2707 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2709 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 108 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 908 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 904 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 606 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1308 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 901 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2804 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 706 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 605 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2602 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 903 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 205 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1702 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 808 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2605 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2001 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1601 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1008 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 905 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1305 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1909 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1704 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2504 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 805 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1003 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P8 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P5 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2603 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 602 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2703 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2304 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2801 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2402 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1005 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1406 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1004 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1901 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1304 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 702 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1009 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 202 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2105 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1807 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2002 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1006 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 509 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1505 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2608 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2706 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1107 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1501 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 704 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1705 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1309 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1802 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 309 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1202 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 403 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2507 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 405 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2102 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2209 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 803 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1906 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2609 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1707 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2008 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1902 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1907 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1205 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1804 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1609 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2005 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 103 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2401 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1001 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 806 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 106 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 10th Floor Flat No 1007 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 307 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 25th Floor Flat No 2502 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 4th Floor Flat No 402 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1908 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 3rd Floor Flat No 306 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1208 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2301 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 102 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 608 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2101 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 603 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P4 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P3 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2308 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2405 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1703 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 502 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1603 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1302 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 809 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1808 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 601 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1109 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 11th Floor Flat No 1106 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1508 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1803 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1307 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1806 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1606 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 203 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 20th Floor Flat No 2003 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2103 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 506 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2309 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1401 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P6 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 14th Floor Flat No 1404 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2408 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 19th Floor Flat No 1903 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 807 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1701 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 1st Floor Flat No 101 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P2 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 209 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 2nd Floor Flat No 208 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2607 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2303 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2708 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1207 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 5th Floor Flat No 508 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 801 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2805 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 27th Floor Flat No 2702 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 18th Floor Flat No 1801 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2809 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2203 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 17th Floor Flat No 1709 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 22nd Floor Flat No 2201 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1605 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 6th Floor Flat No 607 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 7th Floor Flat No 709 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2808 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 12th Floor Flat No 1204 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P9 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 24th Floor Flat No 2403 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 28th Floor Flat No 2802 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 9th Floor Flat No 907 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 Podium Floor Flat No P7 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 13th Floor Flat No 1301 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2305 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 23rd Floor Flat No 2306 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 21st Floor Flat No 2106 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 16th Floor Flat No 1607 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 26th Floor Flat No 2606 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 15th Floor Flat No 1503 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 786 | 0 | 30 May 2024 | SAI ENGINEERING WORKS | Wing-1 8th Floor Flat No 802 Toilet Ventilator | Toilet Ventilator (M) | No. | 2 | 2700 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 787 | 0 | 01 Jun 2024 | S A CONSTRUCTION | Wing 1-11th Slab (5th Floor) RCC slab,beam,ST,SW | RCC Work - DCH | No. | 1 | 109727 | 109727 | 19750.86 | 129477.86 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Club House | Un-Approved |  | 1900-01-01
GANGA ASMI | 788 | 0 | 01 Jun 2024 | VINAYAKA ASSOCIATE | Wing 1-11th Slab (5th Floor) RCC slab,beam,ST,SW | RCC Work - DCH | No. | 1 | 224324 | 224324 | 40378.32 | 264702.32 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Jun 2024 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 27th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 32nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 33rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 18th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 1 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing 1-11th Slab (5th Floor) RCC slab,beam,ST,SW | RCC Work -Dld | No. | 1 | 1738030 | 1738030 | 312845.4 | 2050875.4 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 34th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | Shifting of shuttering material from last floor to G.F.(L)- | Sorting & Shifting Work | Sq.Ft | 10438.618 | 55.5 | 579343.3 | 104281.8 | 683625.1 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 13th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 19th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 15th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 30th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 24th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 26th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 21st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 111 | 1158686.6 | 208563.58 | 1367250.18 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 27th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 13th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 16th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 34th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 30th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 24th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 19th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 21st Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 28th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 28th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 31st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 14th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 12th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 15th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 17th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 20th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 35th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 31st Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 23rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 16th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 26th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 22nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 18th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 20th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 25th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 14th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 29th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 17th Slab RCC slab,beam,ST,Shear wall | RCC Hand over | Sq.Ft | 10438.618 | 22 | 229649.6 | 41336.92 | 270986.52 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 25th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 10438.618 | 190 | 1983337.42 | 357000.74 | 2340338.16 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 12th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 29th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 789 | 0 | 01 Jun 2024 | KRISHNA CONSTRUCTION (Prop BHISE) | 35th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 10438.618 | 10 | 104386.18 | 18789.52 | 123175.7 | 2.5 | 0 | 0 | 0 | 0 | 10438.618 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Jun 2024 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 790 | 0 | 06 Jun 2024 | IMRAN NISAR ANSARI | Ganga Satellite B1 Bldg. 11th Floor Bedroom painting | Lumpsum work- DCW | No. | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Jun 2024 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Shiv yantra | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Vasturaviraj Pyramid (with crystal) | No. | 225 | 255 | 57375 | 10327.5 | 67702.5 | 0 | 225 | 57375 | 10327.5 | 67702.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Vasturaviraj Pyramid Yellow WB - No. | No. | 12 | 1028.5 | 12342 | 2221.56 | 14563.56 | 0 | 12 | 12342 | 2221.56 | 14563.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Kamakhya Yantra (Large) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Surya (L) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Mandal Remedy | No. | 1 | 135000 | 135000 | 24300 | 159300 | 0 | 1 | 135000 | 351 | 135351 | 0 | 23949 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Vasturaviraj Pyramid Lapiz WB - No. | No. | 8 | 1028.5 | 8228 | 1481.04 | 9709.04 | 0 | 8 | 8228 | 1481.04 | 9709.04 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | PT (Large) | No. | 1 | 1636.25 | 1636.25 | 294.52 | 1930.77 | 0 | 1 | 1636.25 | 294.52 | 1930.77 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 791 | 0 | 14 Jun 2024 | VASTURAVIRAJ VASTU SERVICES PVT LTD | Vastu Remedy Material | Vasturaviraj Pyramid Clear Quartz WB - No. | No. | 12 | 1028.5 | 12342 | 2221.56 | 14563.56 | 0 | 12 | 12342 | 2221.56 | 14563.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 15 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 792 | 0 | 14 Jun 2024 | UMESH SHIVAPPA | Non Tower Area Tractor For Material Shifting | Tractor Trips-BRE | Trips | 159 | 300 | 47700 | 0 | 47700 | 0 | 159 | 47700 | 0 | 47700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jun 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 793 | 0 | 28 Jun 2024 | SAIRAJ CONSTRUCTION | New Labour Camp Bathroom & Toilet PCC Work | Labour Lumsum | No. | 1 | 18000 | 18000 | 3240 | 21240 | 2.5 | 1 | 18000 | 3240 | 21240 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Jul 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 794 | 0 | 28 Jun 2024 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Bondit Application | Bondit | Bucket | 4 | 2800 | 11200 | 2016 | 13216 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Jul 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 795 | 0 | 01 Jul 2024 | GLOBAL GEOTECHNICS | Wing 3 Strata Checking & Certification | Visiting Charges-AIE | No. | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Jul 2024 |  | Admin. Indirect Expenses | Cancelled | DUSHANT.GORE | 11 Jul 2024
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 31.64 | 2 | 63.28 | 0 | 63.28 | 2.5 | 0 | 0 | 0 | 0 | 31.64 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2109 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1808 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 23.5 | 10686.39 | 0 | 10686.39 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1707 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 408 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 19 | 529.72 | 0 | 529.72 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1209 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 1109 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 466.86 | 2 | 933.72 | 0 | 933.72 | 2.5 | 0 | 0 | 0 | 0 | 466.86 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2706 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 807 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1509 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 409 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 19 | 9100.43 | 0 | 9100.43 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 17.5 | 9366.18 | 0 | 9366.18 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1709 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2709 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 28.25 | 4619.16 | 0 | 4619.16 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 408 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 19 | 8640.06 | 0 | 8640.06 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2507 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1306 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 22 | 682 | 0 | 682 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2208 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 25 | 11368.5 | 0 | 11368.5 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 408 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2806 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 27.25 | 12677.25 | 0 | 12677.25 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 307 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 16 | 11378.08 | 0 | 11378.08 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 24.25 | 17244.9 | 0 | 17244.9 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 2108 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 25 | 11368.5 | 0 | 11368.5 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2606 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 15 | 510.15 | 0 | 510.15 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2008 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 25 | 11368.5 | 0 | 11368.5 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 706 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 907 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 607 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1308 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 22 | 10004.28 | 0 | 10004.28 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1108 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.25 | 1636.8 | 0 | 1636.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 21 | 714.21 | 0 | 714.21 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1007 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 808 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2508 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21 | 1520.61 | 0 | 1520.61 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 506 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2806 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2708 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 27.25 | 12391.67 | 0 | 12391.67 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 306 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 20 | 4355.8 | 0 | 4355.8 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 22 | 15644.86 | 0 | 15644.86 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 709 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK) Flat 1106 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 22 | 10234.84 | 0 | 10234.84 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1408 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 807 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1006 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 19 | 13511.47 | 0 | 13511.47 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1206 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 22 | 682 | 0 | 682 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat 2309 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 26 | 4251.26 | 0 | 4251.26 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21 | 1478.4 | 0 | 1478.4 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1909 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1108 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2508 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.25 | 1636.8 | 0 | 1636.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2509 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 28.25 | 4619.16 | 0 | 4619.16 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 506 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 20.5 | 9537.01 | 0 | 9537.01 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1909 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 507 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 21 | 714.21 | 0 | 714.21 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 307 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 15 | 1162.5 | 0 | 1162.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 608 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 20.5 | 9322.17 | 0 | 9322.17 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2608 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 27.25 | 12391.67 | 0 | 12391.67 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2407 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 25 | 11872.75 | 0 | 11872.75 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1207 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2506 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 17.5 | 12444.78 | 0 | 12444.78 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 306 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1006 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1009 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 22 | 10537.34 | 0 | 10537.34 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1207 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 908 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 1108 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1106 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 22 | 682 | 0 | 682 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1308 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19.5 | 1511.25 | 0 | 1511.25 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 24.25 | 17244.9 | 0 | 17244.9 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 609 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 21.5 | 3515.47 | 0 | 3515.47 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.25 | 1683.53 | 0 | 1683.53 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2407 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 25 | 775 | 0 | 775 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 608 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 19 | 10168.99 | 0 | 10168.99 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19.5 | 1511.25 | 0 | 1511.25 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 909 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 807 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 806 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 507 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 22 | 15644.86 | 0 | 15644.86 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2009 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 16.5 | 1194.77 | 0 | 1194.77 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 907 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 20.5 | 9735.66 | 0 | 9735.66 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2107 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 707 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 21.5 | 4682.49 | 0 | 4682.49 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1307 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 909 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2109 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 26 | 4251.26 | 0 | 4251.26 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 707 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 20.5 | 9735.66 | 0 | 9735.66 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 19 | 13511.47 | 0 | 13511.47 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 106 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 20 | 4355.8 | 0 | 4355.8 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 308 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1409 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1206 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2107 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 22 | 15644.86 | 0 | 15644.86 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2506 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 24.25 | 17244.9 | 0 | 17244.9 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 107 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 20 | 4355.8 | 0 | 4355.8 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1106 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 607 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 20.5 | 9735.66 | 0 | 9735.66 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1308 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 17.5 | 12444.78 | 0 | 12444.78 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 706 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 21.5 | 4682.49 | 0 | 4682.49 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 908 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 22 | 15644.86 | 0 | 15644.86 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1009 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 23 | 3760.73 | 0 | 3760.73 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1007 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 19 | 13511.47 | 0 | 13511.47 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 0 | 11818.62 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 16.5 | 561.17 | 0 | 561.17 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 43.59 | 2 | 87.18 | 0 | 87.18 | 2.5 | 0 | 0 | 0 | 0 | 43.59 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1207 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2408 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 25 | 11368.5 | 0 | 11368.5 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK) Flat 1106 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 908 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1208 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 22 | 10004.28 | 0 | 10004.28 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2009 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 26 | 4251.26 | 0 | 4251.26 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 508 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1609 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 24.5 | 4006 | 0 | 4006 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 17.5 | 9401.18 | 0 | 9401.18 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2607 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 108 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1808 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 408 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 20 | 3289.8 | 0 | 3289.8 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 16.5 | 1194.77 | 0 | 1194.77 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1608 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat 2409 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 26 | 4251.26 | 0 | 4251.26 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19.5 | 1511.25 | 0 | 1511.25 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 32.5 | 2 | 65 | 0 | 65 | 2.5 | 0 | 0 | 0 | 0 | 32.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2208 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1306 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1808 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1407 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 509 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2707 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 27.25 | 12941.3 | 0 | 12941.3 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1406 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 22 | 10234.84 | 0 | 10234.84 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2406 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 807 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1409 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 19.5 | 1412 | 0 | 1412 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 43.59 | 2 | 87.18 | 0 | 87.18 | 2.5 | 0 | 0 | 0 | 0 | 43.59 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2706 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 24.25 | 17244.9 | 0 | 17244.9 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2506 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 33.9 | 2 | 67.8 | 0 | 67.8 | 2.5 | 0 | 0 | 0 | 0 | 33.9 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 16 | 11378.08 | 0 | 11378.08 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2209 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 25 | 11974.25 | 0 | 11974.25 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 20.5 | 10971.81 | 0 | 10971.81 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2309 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1309 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 22 | 10537.34 | 0 | 10537.34 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1508 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 15 | 1086.15 | 0 | 1086.15 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2306 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 25 | 11630.5 | 0 | 11630.5 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1008 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 22 | 10004.28 | 0 | 10004.28 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1407 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 23 | 5009.17 | 0 | 5009.17 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1909 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1806 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1807 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1909 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1707 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 607 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2306 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 26 | 5662.54 | 0 | 5662.54 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2509 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 608 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2807 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 19.5 | 1064.9 | 0 | 1064.9 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2408 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 407 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 607 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 16 | 11378.08 | 0 | 11378.08 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1007 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1707 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19.5 | 663.2 | 0 | 663.2 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 508 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1507 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 23.5 | 11160.39 | 0 | 11160.39 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 508 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 17.5 | 9401.18 | 0 | 9401.18 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2008 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 508 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19.5 | 663.2 | 0 | 663.2 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1707 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 19.5 | 1064.9 | 0 | 1064.9 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 809 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 21.5 | 3515.47 | 0 | 3515.47 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 807 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1907 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 23.5 | 11160.39 | 0 | 11160.39 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1706 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 23.5 | 10932.67 | 0 | 10932.67 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 17.5 | 9366.18 | 0 | 9366.18 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2309 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 25 | 11974.25 | 0 | 11974.25 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 16.5 | 561.17 | 0 | 561.17 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No.1007 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 20.5 | 10971.81 | 0 | 10971.81 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 15 | 510.15 | 0 | 510.15 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2508 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1909 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 20.5 | 10971.81 | 0 | 10971.81 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1309 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1708 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 23.5 | 10686.39 | 0 | 10686.39 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 20.5 | 10971.81 | 0 | 10971.81 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2006 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 26 | 5662.54 | 0 | 5662.54 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 15 | 1056 | 0 | 1056 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20.5 | 11012.81 | 0 | 11012.81 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 607 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 17.5 | 12444.78 | 0 | 12444.78 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1607 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2507 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 16.5 | 561.17 | 0 | 561.17 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1707 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2609 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 466.86 | 27.25 | 12721.94 | 0 | 12721.94 | 2.5 | 0 | 0 | 0 | 0 | 466.86 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 409 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2409 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 25 | 11974.25 | 0 | 11974.25 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 908 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1406 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 22 | 682 | 0 | 682 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 1608 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2507 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 27.25 | 12941.3 | 0 | 12941.3 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 1108 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 22 | 10004.28 | 0 | 10004.28 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20.5 | 11012.81 | 0 | 11012.81 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2706 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 27.25 | 12677.25 | 0 | 12677.25 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 607 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 21.5 | 4682.49 | 0 | 4682.49 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1007 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No.1509 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1207 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2009 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 25 | 11974.25 | 0 | 11974.25 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 908 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1909 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 808 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 21.5 | 3536.54 | 0 | 3536.54 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1106 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 20.5 | 11012.81 | 0 | 11012.81 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1207 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 16.5 | 561.17 | 0 | 561.17 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 16 | 8595.36 | 0 | 8595.36 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 907 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 21.5 | 4682.49 | 0 | 4682.49 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1106 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2506 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1506 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2407 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1909 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 107 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2006 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 25 | 11630.5 | 0 | 11630.5 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1507 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 709 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 21.5 | 3515.47 | 0 | 3515.47 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 307 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 506 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 508 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 39.93 | 2 | 79.86 | 0 | 79.86 | 2.5 | 0 | 0 | 0 | 0 | 39.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1007 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 22 | 10448.02 | 0 | 10448.02 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1306 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 38.75 | 2 | 77.5 | 0 | 77.5 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 43.59 | 15 | 653.85 | 0 | 653.85 | 2.5 | 0 | 0 | 0 | 0 | 43.59 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 906 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19.5 | 663.2 | 0 | 663.2 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2506 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2508 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19.5 | 1511.25 | 0 | 1511.25 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No.1809 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2607 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 27.25 | 12941.3 | 0 | 12941.3 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2109 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 706 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2107 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2808 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 28.25 | 4646.84 | 0 | 4646.84 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 16 | 8563.36 | 0 | 8563.36 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 15 | 1086.15 | 0 | 1086.15 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2508 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 28.25 | 4646.84 | 0 | 4646.84 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1708 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 409 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 20 | 3270.2 | 0 | 3270.2 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 407 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 19 | 589 | 0 | 589 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 19 | 10168.99 | 0 | 10168.99 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1606 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 17.5 | 12444.78 | 0 | 12444.78 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 21 | 714.21 | 0 | 714.21 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 606 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1906 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 807 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 20.5 | 9735.66 | 0 | 9735.66 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2107 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2708 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1809 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Common Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 33.9 | 2 | 67.8 | 0 | 67.8 | 2.5 | 0 | 0 | 0 | 0 | 33.9 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1008 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2306 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 508 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 20.5 | 9322.17 | 0 | 9322.17 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 24.25 | 13027.34 | 0 | 13027.34 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 24.25 | 12978.84 | 0 | 12978.84 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 2109 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 466.86 | 2 | 933.72 | 0 | 933.72 | 2.5 | 0 | 0 | 0 | 0 | 466.86 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2806 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 17.5 | 12444.78 | 0 | 12444.78 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21 | 1478.4 | 0 | 1478.4 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1209 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 22 | 10537.34 | 0 | 10537.34 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 21 | 1478.4 | 0 | 1478.4 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2809 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 807 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 307 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 808 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 20.5 | 9322.17 | 0 | 9322.17 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Wing 1 (3BHK)-Flat No. 1006 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1208 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2109 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1007 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19.5 | 1511.25 | 0 | 1511.25 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1107 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1407 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 22 | 10448.02 | 0 | 10448.02 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1206 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 22 | 10234.84 | 0 | 10234.84 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2808 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 27.25 | 12391.67 | 0 | 12391.67 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1306 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat 2408 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25 | 697 | 0 | 697 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1909 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 23.5 | 11255.8 | 0 | 11255.8 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 16 | 8563.36 | 0 | 8563.36 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1908 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 306 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 808 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2207 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 25 | 775 | 0 | 775 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2109 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1606 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 23.5 | 10932.67 | 0 | 10932.67 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 908 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1006 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 22 | 11774.62 | 0 | 11774.62 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1208 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 23 | 3783.27 | 0 | 3783.27 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 906 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No.1007 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 108 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 19 | 8640.06 | 0 | 8640.06 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1208 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 18 | 1303.38 | 0 | 1303.38 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2208 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 0 | 11818.62 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 16.5 | 666.11 | 0 | 666.11 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 307 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 19 | 9023.29 | 0 | 9023.29 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.25 | 1636.8 | 0 | 1636.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1107 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 22 | 682 | 0 | 682 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1007 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 23 | 5009.17 | 0 | 5009.17 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2208 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25 | 697 | 0 | 697 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1207 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 708 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 307 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 20 | 4355.8 | 0 | 4355.8 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 508 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1506 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1106 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 18 | 612.18 | 0 | 612.18 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1308 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 22 | 613.36 | 0 | 613.36 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2308 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 25 | 11368.5 | 0 | 11368.5 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2409 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 307 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2107 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 25 | 11872.75 | 0 | 11872.75 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 706 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2508 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 507 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 20.5 | 9735.66 | 0 | 9735.66 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2206 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 25 | 11630.5 | 0 | 11630.5 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1306 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 908 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1707 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2106 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 25 | 11630.5 | 0 | 11630.5 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2806 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 407 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2007 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 907 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2007 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 25 | 11872.75 | 0 | 11872.75 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 606 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat 2309 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25 | 697 | 0 | 697 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2808 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2508 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 909 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 20.5 | 9818.89 | 0 | 9818.89 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2107 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 25 | 775 | 0 | 775 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1707 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2508 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2409 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 22 | 11774.62 | 0 | 11774.62 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1007 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 106 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2207 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat 2409 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 25 | 697 | 0 | 697 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2207 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 25 | 11872.75 | 0 | 11872.75 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 509 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1306 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2508 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 27.25 | 12391.67 | 0 | 12391.67 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 2109 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 466.86 | 25 | 11671.5 | 0 | 11671.5 | 2.5 | 0 | 0 | 0 | 0 | 466.86 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1207 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 22 | 682 | 0 | 682 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 906 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 20.5 | 9537.01 | 0 | 9537.01 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19.5 | 663.2 | 0 | 663.2 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 806 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1406 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 23 | 5009.17 | 0 | 5009.17 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 15 | 523.2 | 0 | 523.2 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1307 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2506 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2307 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1106 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Master Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 43.59 | 15 | 653.85 | 0 | 653.85 | 2.5 | 0 | 0 | 0 | 0 | 43.59 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 609 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2606 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1706 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19.5 | 663.2 | 0 | 663.2 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 23.25 | 1801.88 | 0 | 1801.88 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1806 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2608 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.25 | 759.73 | 0 | 759.73 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 908 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 20.5 | 9322.17 | 0 | 9322.17 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 17.5 | 12444.78 | 0 | 12444.78 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21 | 1520.61 | 0 | 1520.61 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2507 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 27.25 | 844.75 | 0 | 844.75 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 108 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 16 | 8595.36 | 0 | 8595.36 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2107 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2809 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.25 | 759.73 | 0 | 759.73 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 19.5 | 787.22 | 0 | 787.22 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 21 | 732.48 | 0 | 732.48 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1906 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2708 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 27.25 | 759.73 | 0 | 759.73 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 18 | 1267.2 | 0 | 1267.2 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 19.5 | 663.2 | 0 | 663.2 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 306 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 15 | 819.15 | 0 | 819.15 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 809 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1008 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2608 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 23.25 | 1636.8 | 0 | 1636.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 19.5 | 1064.9 | 0 | 1064.9 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2107 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 21 | 714.21 | 0 | 714.21 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 24.25 | 17244.9 | 0 | 17244.9 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1906 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2109 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 708 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1609 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1908 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1909 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 19 | 13511.47 | 0 | 13511.47 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 0 | 10206.99 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2208 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2708 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1507 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 19 | 13511.47 | 0 | 13511.47 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No.1809 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2108 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 0 | 11818.62 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Master Toilet Flooring | Schedule & Quality | Sq.Ft | 43.59 | 2 | 87.18 | 0 | 87.18 | 2.5 | 0 | 0 | 0 | 0 | 43.59 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 607 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 906 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 606 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2807 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 106 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 16.5 | 575.52 | 0 | 575.52 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1508 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 908 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 16.5 | 1161.6 | 0 | 1161.6 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 19 | 10168.99 | 0 | 10168.99 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 508 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 22 | 15644.86 | 0 | 15644.86 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 16.5 | 1278.75 | 0 | 1278.75 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2506 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 27.25 | 12677.25 | 0 | 12677.25 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 16.5 | 561.17 | 0 | 561.17 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1109 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 19.5 | 1412 | 0 | 1412 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 406 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.25 | 1683.53 | 0 | 1683.53 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2307 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 26 | 5662.54 | 0 | 5662.54 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2708 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 28.25 | 4646.84 | 0 | 4646.84 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2307 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 509 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 16.5 | 1194.77 | 0 | 1194.77 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2707 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 2609 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 28.25 | 4619.16 | 0 | 4619.16 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1008 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 506 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 16.5 | 901.07 | 0 | 901.07 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 16 | 8563.36 | 0 | 8563.36 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat 2308 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 26 | 4276.74 | 0 | 4276.74 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2006 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 22 | 15644.86 | 0 | 15644.86 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2106 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 26 | 5662.54 | 0 | 5662.54 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2807 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 27.25 | 844.75 | 0 | 844.75 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2509 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 27.25 | 13051.93 | 0 | 13051.93 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 309 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 19 | 9100.43 | 0 | 9100.43 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1007 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 18 | 982.98 | 0 | 982.98 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1708 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1206 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 23 | 5009.17 | 0 | 5009.17 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 507 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1707 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 24.5 | 5335.86 | 0 | 5335.86 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1407 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 18 | 1395 | 0 | 1395 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 22 | 11818.62 | 0 | 11818.62 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2309 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1908 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 164.49 | 24.5 | 4030.01 | 0 | 4030.01 | 2.5 | 0 | 0 | 0 | 0 | 164.49 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1908 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1606 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 109 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 466.86 | 19 | 8870.34 | 0 | 8870.34 | 2.5 | 0 | 0 | 0 | 0 | 466.86 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1009 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1906 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 23.5 | 10932.67 | 0 | 10932.67 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1909 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 24.5 | 4006 | 0 | 4006 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 32.5 | 15 | 487.5 | 0 | 487.5 | 2.5 | 0 | 0 | 0 | 0 | 32.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2707 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 18 | 726.66 | 0 | 726.66 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1406 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1807 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 20.5 | 14578.17 | 0 | 14578.17 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2109 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 21 | 1520.61 | 0 | 1520.61 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 608 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1806 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 24.5 | 5335.86 | 0 | 5335.86 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1508 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 23.5 | 10686.39 | 0 | 10686.39 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2408 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2009 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Common Toilet Flooring | Schedule & Quality | Sq.Ft | 33.9 | 2 | 67.8 | 0 | 67.8 | 2.5 | 0 | 0 | 0 | 0 | 33.9 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 20.5 | 10971.81 | 0 | 10971.81 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 24.25 | 17244.9 | 0 | 17244.9 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1209 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)Flat No. 107 Common Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 33.9 | 15 | 508.5 | 0 | 508.5 | 2.5 | 0 | 0 | 0 | 0 | 33.9 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2308 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1607 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1607 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 23.5 | 11160.39 | 0 | 11160.39 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2206 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 21 | 1627.5 | 0 | 1627.5 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1907 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 77.5 | 19.5 | 1511.25 | 0 | 1511.25 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No.1007 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1509 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 507 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 21.5 | 4682.49 | 0 | 4682.49 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK) Flat 1609 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 466.86 | 23.5 | 10971.21 | 0 | 10971.21 | 2.5 | 0 | 0 | 0 | 0 | 466.86 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 707 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 20.5 | 635.5 | 0 | 635.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1308 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1608 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 70.4 | 19.5 | 1372.8 | 0 | 1372.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 308 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 15 | 605.55 | 0 | 605.55 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.25 | 1683.53 | 0 | 1683.53 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1408 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 0 | 10206.99 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 307 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 1806 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 31 | 23.5 | 728.5 | 0 | 728.5 | 2.5 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1908 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 23.5 | 10686.39 | 0 | 10686.39 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 23.25 | 938.6 | 0 | 938.6 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 307 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1208 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 537.21 | 19 | 10206.99 | 0 | 10206.99 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1106 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2707 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 23.25 | 790.73 | 0 | 790.73 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1108 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1809 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 23.5 | 655.18 | 0 | 655.18 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 807 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2406 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 2607 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 28.25 | 6152.57 | 0 | 6152.57 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 408 Flat Flooring | Schedule & Quality | Sq.Ft | 537.21 | 2 | 1074.42 | 0 | 1074.42 | 2.5 | 0 | 0 | 0 | 0 | 537.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2209 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2807 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 535.21 | 19 | 10168.99 | 0 | 10168.99 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 309 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2709 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 19.5 | 1412 | 0 | 1412 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1709 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 708 Toilet Flooring | Schedule & Quality | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1006 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 711.13 | 19 | 13511.47 | 0 | 13511.47 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1707 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 106 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 465.22 | 19 | 8839.18 | 0 | 8839.18 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1306 Toilet Flooring | Schedule & Quality | Sq.Ft | 77.5 | 2 | 155 | 0 | 155 | 2.5 | 0 | 0 | 0 | 0 | 77.5 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1508 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19.5 | 680.16 | 0 | 680.16 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1809 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 478.97 | 23.5 | 11255.8 | 0 | 11255.8 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 107 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 19 | 9023.29 | 0 | 9023.29 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2509 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 72.41 | 23.25 | 1683.53 | 0 | 1683.53 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2106 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No.1509 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 407 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 474.91 | 19 | 9023.29 | 0 | 9023.29 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 607 Balcony Flooring | Schedule & Quality | Sq.Ft | 54.61 | 2 | 109.22 | 0 | 109.22 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2008 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 40.37 | 21 | 847.77 | 0 | 847.77 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1409 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 18 | 627.84 | 0 | 627.84 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2808 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 23.25 | 810.96 | 0 | 810.96 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 409 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 308 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 19 | 8640.06 | 0 | 8640.06 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2506 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2306 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.01 | 21 | 714.21 | 0 | 714.21 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1206 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1309 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 809 Balcony Skirting | Ceramic Skirting - DEn | R.Ft | 27.88 | 20.5 | 571.54 | 0 | 571.54 | 2.5 | 0 | 0 | 0 | 0 | 27.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 909 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat 606 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 217.79 | 21.5 | 4682.49 | 0 | 4682.49 | 2.5 | 0 | 0 | 0 | 0 | 217.79 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2607 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 709 Toilet Flooring | Schedule & Quality | Sq.Ft | 72.41 | 2 | 144.82 | 0 | 144.82 | 2.5 | 0 | 0 | 0 | 0 | 72.41 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1408 Kitchen Toilet Utility WB Counter | Dado Fixing | Sq.Ft | 454.74 | 22 | 10004.28 | 0 | 10004.28 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)Flat No. 109 Master Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 39.93 | 2 | 79.86 | 0 | 79.86 | 2.5 | 0 | 0 | 0 | 0 | 39.93 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1609 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2706 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 23.25 | 1269.68 | 0 | 1269.68 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2507 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 909 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 21.5 | 3515.47 | 0 | 3515.47 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2609 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1907 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2407 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 54.61 | 21 | 1146.81 | 0 | 1146.81 | 2.5 | 0 | 0 | 0 | 0 | 54.61 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2606 Flat Flooring | Schedule & Quality | Sq.Ft | 711.13 | 2 | 1422.26 | 0 | 1422.26 | 2.5 | 0 | 0 | 0 | 0 | 711.13 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 2106 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1507 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 0 | 80.74 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 2006 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 0 | 69.76 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 308 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 1709 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1109 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 23 | 3760.73 | 0 | 3760.73 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1107 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 1506 Utility Flooring | Schedule & Quality | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 2809 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1808 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 70.4 | 2 | 140.8 | 0 | 140.8 | 2.5 | 0 | 0 | 0 | 0 | 70.4 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2209 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 478.97 | 2 | 957.94 | 0 | 957.94 | 2.5 | 0 | 0 | 0 | 0 | 478.97 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat No. 1209 Flat Flooring | Schedule & Quality | Sq.Ft | 535.21 | 2 | 1070.42 | 0 | 1070.42 | 2.5 | 0 | 0 | 0 | 0 | 535.21 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (2BHK)Flat 2308 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 454.74 | 2 | 909.48 | 0 | 909.48 | 2.5 | 0 | 0 | 0 | 0 | 454.74 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 707 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (2BHK)-Flat 1409 Flat Skirting | Vitrified Skirting - BRE | R.Ft | 163.51 | 23 | 3760.73 | 0 | 3760.73 | 2.5 | 0 | 0 | 0 | 0 | 163.51 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 306 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 1606 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 465.22 | 2 | 930.44 | 0 | 930.44 | 2.5 | 0 | 0 | 0 | 0 | 465.22 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing -1 (3BHK)Flat 607 Kitchen Toilet Utility WB Counter | Schedule & Quality | Sq.Ft | 474.91 | 2 | 949.82 | 0 | 949.82 | 2.5 | 0 | 0 | 0 | 0 | 474.91 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 796 | 0 | 04 Jul 2024 | PAPPU BAGELA | Wing 1 (3BHK)-Flat No. 607 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.01 | 2 | 68.02 | 0 | 68.02 | 2.5 | 0 | 0 | 0 | 0 | 34.01 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01